## GoM Daily Work Order data repor
Order | Planner Group | Order Desc. | Plant Section | Plant Section Desc. | ErlStart | LatestFin | WBS Element | Mn.wk.ct | Functional Location | Functional Location Desc. | Order Release | Order Flag | Planning Plant | Order Type | CoCode | SYS.ID | Subnetwork of Opr. | Location | Location Description | ABC Indicator for Technical Object | ABC Indicator Description | Work Order Priority | Scheduled finish date | Order Line ID | OpAc | Item | Material | Material Short Text | Reqmt Date | Shipment Status | Kit Complete | EXEC | TECO | Plant | Sloc | Sloc Desc | Unloading Point | Reservation | Res. Item | Supply Process Code | Supply Process Desc. | IC | FI | Kitt Ind. | Tracking No. | Recipient | Recipt/PrOrigin | Res.Create | Res.Created By | Reqmt Qty | UoM | Wdrawn Qty | Operation Desc. | System Status | Order User Status | Line Status | Original ROS Date | CLSD | Staging Location
60975188 | 508 | XV-12202A-912 Fails to Open | S18 | Water Systems | 2020-02-06 | 2019-10-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.XV-12202A-912 | Filter Backwash On/Off Control Valve | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-02-06 | 119260000000 | 10 | 20 | 7000002603 | 4" 150 1/8 GARLOC IFG-5500 FULL FACE | 2020-02-06 | Received at Worksite |  | 2019-12-28 | 2020-02-10 | U182 | 8201 | Stones Main | ST KB B2 | 11925969 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 1 | USAWJB | 2019-10-04 | USAWJB | 3 | EA | 3 | LOTO System - Confirm Isolation | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU AMW 12/29/19
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 20 | 110 | 7000000068 | DK EXPEDITE FEE (1-2 Weeks Lead Time) mf | 2019-12-08 | Received at Target Location |  | 2020-02-28 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11614811 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI64 | Name 2 | USNSB4 | 2019-11-05 | USSOLE | 1 | EA | 1 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
60548443 | 508 | Hawser reel anchor link arm | S19 | Marine Systems | 2020-04-21 | 2020-09-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.PS.ZZZ-88630 | Hawser Storage Reel | 2019-10-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114265000000 | 10 | 20 | 7000000109 | PACKING CHARGES | 2020-04-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 3/30/20 | 11426455 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2019-10-24 | GW982959 | 1 | EA | 0 | LOTO Hawser reel | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM ZPVS | Approved
60729276 | 508 | O/SI Valve Stuck in Closed Position | S18 | Water Systems | 2020-02-20 | 2019-11-30 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.122-131V | Pump Suction Valve | 2019-05-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-20 | 116320000000 | 10 | 30 | 7000004211 | 5/8-DXST, 5/8" X 3" (2-3/4" FTF) DOX PLT | 2020-02-20 | Received at Worksite |  | 2019-07-13 |  | U182 | 8201 | Stones Main | Issued | 11632019 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 | USNSB4 | 2019-05-13 | USNSB4 | 16 | EA | 16 | Replace Butterfly Valve | REL CNF PRT GMPS PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC |  |  | PU Aaron 07/08/2019
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7500 | 1001201050 | HITCH PIN/WIRE LOCK PIN,WILSNMFG,SWL2600 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1008 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 130 | 7000003196 | Swagelok SS-44F6 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 791 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 15 | EA | 15 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 730 | 7000003463 | 1783-BMS06SA | 2020-03-18 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1064 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-26 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2360 | 7000002591 | Fabreeka Pad 1/4" THK x 12" x 4 3/4" | 2019-04-08 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 258 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011905 | Name 2 | Name 2 | 2019-04-02 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5780 | 1001816265 | GASW,CL300-600,316,GPH,NPS3 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 672 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 32 | EA | 32 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5620 | 7000002629 | Threadolet, 3" x 3/4", 3000#, FS MSS-SP- | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 656 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6720 | 1001646525 | PLUG PIPE TH,AlBRZ,UNC,3/4in | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 883 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 180 | 7000002629 | PLUG, 3/4", SC, HEX HEAD, ASTM A182 GR. | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 31 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 10 | 7000003512 | 2507 3/4" X .065 SMLS | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 779 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 600 | FT | 600 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5300 | 7000002596 | STUD BOLT, 3/4" X 4 1/2" ASTM A193 GRADE | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 591 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 64 | EA | 64 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 580 | 1000708883 | TAPE,ELEC,3M,SCOTCH 35,19x0.178mm,BLUE | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 850 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 10 | EA | 10 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60714079 | 508 | O/SI Steam Trap, Valves, Malfunctioning | S17 | Steam/Hot H2O | 2020-03-11 | 2019-06-15 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.74T | Drain Steam Trap | 2020-02-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-11 | 116148000000 | 20 | 20 | 7000004211 | 20k-25MM Steam trap | 2020-03-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11614810 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-06 | USMNF8 | 2 | EA | 0 | RR Valves 115-394,395, 74T | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60569415 | 508 | O/SI Cargo Valve 241 Hydraulic Leaking | S21 | Oil Treating | 2020-03-24 | 2019-01-31 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-241 | Crude Oil to/from Fwd COTs On/Off Valve | 2019-07-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Complete by 2 Weeks | 2020-04-06 | 114505000000 | 20 | 10 | 7000004212 | HAA-D12 HYD. ROTARY ACTUATOR - (DOUBLE A | 2020-03-24 | Received at Target Location |  | 2019-09-11 |  | U182 | 8201 | Stones Main | ST KB A4 | 11450504 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-02 | USNSB4 | 2 | EA | 2 | Drain 5S Tank To Repair Hydraulic Actuat | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU WPT STKB A4
60720331 | 508 | O/SI Passing Discharge Block Valve | S10 | Chem Injection | 2020-02-11 | 2020-04-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.CI.VABL-128182 | B Pump H1 Discharge Valve | 2020-01-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-11 | 116219000000 | 20 | 10 | 7000000103 | MI BV0108F3710EG3KFSLK BV01 - SINGLE ISO | 2020-02-11 | Received at Worksite |  | 2020-01-27 | 2020-01-27 | U182 | 8201 | Stones Main | ST KB D7 | 11621851 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-06-07 | USNSB4 | 5 | EA | 5 | Replace Discharge Valve VABL-128182 | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU AARON 09/29/2019 CMR
60426272 | 508 | O/SI BSW 198 O-ring seal failure | S22 | Prod Gathering | 2020-06-01 | 2019-04-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.AT-66207-198 | Crude Oil Outlet Water In Oil Analyser | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-01 | 112913000000 | 10 | 20 | 1001816210 | GASW,316/316L,GPH,CL150,NPS3 | 2020-06-01 | Received at Worksite |  | 2019-04-02 |  | U182 | 8201 | Stones Main | ST KB D3 | 11291300 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-01-15 | USNSB4 | 1 | EA | 1 | Perform Isolations To Reinstall Temperat | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU 4/4/2019 CR
61163869 | 508 | MeOH Inj Limit Switch Swap MOC 69266 | S10 | Chem Injection | 2020-04-01 | 2020-03-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.CI.ZZZ-12870 | Turret Methanol Injection System | 2020-01-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-01 | 121427000000 | 10 | 30 | 7000000062 | Topworx K1S-L2ZFNPS | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12142743 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-27 | USNSB4 | 1 | EA | 0 | Install TopWorx Limit Switch MeOH Inject | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 20 | 7000000039 | YMD-8529 HOSE ASSEMBLY X76"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60557093 | 508 | O/SI Passing Valve VABL-661050 | S22 | Prod Gathering | 2020-02-15 | 2019-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.FM.VABL-661050 | Test Fluids Manual Isolation Valve | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-15 | 114365000000 | 20 | 20 | 7000004211 | 2473-3075 3/4 X 5 (4-3/4 FTF) DOX PLTD S | 2020-02-15 | Received at Target Location |  | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Delv 10/03-Wait on GR | 11436470 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-05-29 | USNSB4 | 24 | EA | 24 | Confirm VABL-661050 Replacement | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK RUSH WPOK XGI | TECO
61102085 | 508 | FRC Lifeline discrepancies | S15 | Life Saving | 2020-03-05 | 2020-06-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2020-01-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-05 | 120714000000 | 10 | 50 | 7000004662 | Crimps, lifline | 2020-03-05 | Received at Worksite | 2020-02-17 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 12071420 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-17 | USMNF8 | 3 | EA | 3 | FRC Lifeline discrepancies | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 510 | 7000002591 | 4452K251 Straight Reducer, 3/8 x 1/4 NPT | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 51 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60695904 | 508 | on/off switch is missing | S13 | Fire Protect | 2020-04-01 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.FP.BAT-33120A | Diesel Engine Starting Battery | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-01 | 115942000000 | 10 | 10 | 7000000039 | ASLW20 ILLUMINATED SELECTOR SWITCH | 2020-01-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11594235 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-06-17 | USNSB4 | 5 | EA | 0 | Replace Missing On/Off Switch | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Deleted
61150691 | 508 | 2Y Yokogawa Battery Replacement | S20 | Monitor & Ctrl | 2020-04-15 | 2020-07-14 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.MC.DC | Data Communications | 2020-01-14 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Normal | 2020-04-15 | 121273000000 | 10 | 10 | 1001236860 | BATTERY,NRC,YOKOGAWA,S9129FA,2.4V | 2020-04-15 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | Stones WPT | 12127329 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-01-14 | GW982959 | 20 | EA | 4 | 2Y PLC Battery Replacement | REL ESTC GMPS PRC SETC | EXEC MAXX | EXEC |  |  | ST1A3C 02/08/2020 CMR 4EA
60701397 | 508 | Leaking Globe/Check Valve on Hydrophore | S18 | Water Systems | 2020-04-11 | 2019-10-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.121-20V | Tank Outlet Check Valve | 2020-01-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-11 | 116003000000 | 20 | 40 | 7000004211 | Gasket-10, 5K 40MM GARLOCK GASKET FULL F | 2020-04-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ST1A2C | 11600310 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-05-19 | USNSB4 | 2 | EA | 0 | Drain Hydrophore Tank | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MANX WPOK ZPMM | EXEC |  |  | ST1A2C 02/07/2020 CMR
60911833 | 508 | Hi-Ex Foam VPSV & PSV Replace Order | S13 | Fire Protect | 2020-02-04 | 2019-10-24 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PVV-33170-001 | Foam Tank Pressure Vaccum Relief Valve | 2019-10-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-04 | 118544000000 | 20 | 20 | 7000005901 | 738260 PRESSURE RELIEF VALVE DN40 | 2020-03-19 | Received at Worksite | 2020-01-17 | 2020-02-03 | 2020-02-06 | U182 | 8201 | Stones Main | ST KB A7 | 11854406 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-15 | USNSB4 | 1 | EA | 1 | Replace VPSV & PSV Hi-Expansion Foam | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK RUSH WPOK XGI | TECO |  |  | STKBA7 2/3/20 GG GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5530 | 7000002629 | 2" 150 RFWN Flange Protectors | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 614 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6000 | 7000002629 | Tee, 2" x 2", SW, 400 PSIG WOG, ASME B16 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 698 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 12 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 80 | 1001528226 | COIMC,SWAGELOK,SS81018,1/2x1/2NPT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 786 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 5 | EA | 5 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 750 | 7000003463 | 1585J-M8TGJM-2 | 2020-03-18 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1066 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-26 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6050 | 7000002629 | Elbow, 2", 90, SW, 400 PSIG WOG, ASME B | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 703 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 34 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 660 | 7000003740 | Rosemount In-Line Manifold | 2020-02-21 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 858 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN117 | Name 2 | Name 2 | 2020-01-31 | USLFA4 | 2 | EA | 2 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 200 | 7000003196 | Swagelok 316-S3-PP-8T | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 798 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 40 | EA | 40 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1900 | 7000002629 | PLUG, 1/2", SC, HEX HEAD, ASME B16.11, | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 212 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1220 | 1001581841 | SHT PLT SLD MET,4x8ft,1/2in,A572-50 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 138 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061802 | Name 2 | Name 2 | 2018-12-07 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6790 | 7000002644 | Ball Valve, 3/4", VBT-302MV A | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 890 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60847989 | 508 | MOC GTG5 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-44000 | Gen #5 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 60 | 7000005901 | M20 Locknut | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780944 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI80 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #5 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 120 | 7000002629 | FLANGE, 6", 150#, RF, WN, ASTM A105N, AS | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3910 | 1002047398 | STL SECT MAR,BEAM,8.110in,4.015in,20ft | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 441 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11011902 | Name 4 | Name 4 | 2019-11-01 | USSOLE | 60 | FT | 60 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 90 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2020-03-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E27 | 11477345 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05141901 | Entity 2 | USAWJB | 2019-05-14 | USSOLE | 2 | EA | 2 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
61006507 | 508 | PSV test kits | S21 | Oil Treating | 2020-02-11 | 2020-10-15 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.VE663-00000 | Cargo Oil Pump Systems | 2020-01-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-17 | 119629000000 | 10 | 20 | 7000002596 | 3/4" studs, Teflon coated w nuts | 2020-02-11 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-25 | U182 | 8201 | Stones Main | ST1A3A | 11962883 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 12 | EA | 12 | Install PSV Testt kits | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
61035032 | 508 | LOPC-Tube Failure HOPA L/O Cooler | S21 | Oil Treating | 2020-03-29 | 2020-04-30 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.OT.SS.HAL-66706 | Air Blast Cooler | 2020-02-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-30 | 119955000000 | 10 | 10 | 7000004211 | P/N: DC.26286.13/1: DECA HEAT EXCHANGER | 2020-03-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 11995475 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2020-02-12 | GW982959 | 1 | EA | 0 | lLOTO EQUIPMENT HOPA L/O Cooler | REL ESTC PRC SETC | APPR WP | Deleted
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 100 | 7000002603 | VCS02150 2 150 VCS FLANGE INSULATION KIT | 2020-04-01 | Received at Worksite | 2019-12-19 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 12027172 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-01 | USAWJB | 1 | EA | 1 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 150 | 7000002591 | 2" Flange Protectors | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 2 | EA | 2 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 70 | 7000002591 | 25 Pound White Cotton Rags (Tee Shirt | 2020-02-04 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | DIISTO1927 | Entity 1 | USJRF5 | 2020-01-28 | USLFA4 | 4 | EA | 4 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 30 | 7000004213 | KE35/6 SASAKURA KE35 P/N:6 ELBOW | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
61152001 | 508 | O/SI Leaking Valve on LPU Test Swivel | S22 | Prod Gathering | 2020-02-11 | 2021-01-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.PG.FM.ZZZ-66102 | Oil/Gas/Water Production Swivel | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-15 | 121289000000 | 10 | 10 | 1002381375 | VALVE,NEEDLE,OLIVER,F50S/NA,1/2inNPTF | 2020-02-11 | Not Shipped |  |  | 2020-02-22 | U182 | 8201 | Stones Main | Stock Item - ST1VID2E | 12128927 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Entity 3 |  | 2020-02-09 | USCWJG | 1 | EA | 0 | LOTO System - Confirm Isolation | TECO CNF PRT PRC SETC | XCNF WPOK XGI | TECO
61102085 | 508 | FRC Lifeline discrepancies | S15 | Life Saving | 2020-03-05 | 2020-06-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2020-01-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-05 | 120714000000 | 10 | 40 | 7000004662 | Lifeline float | 2020-03-05 | Received at Worksite | 2020-02-17 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 12071420 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-17 | USMNF8 | 2 | EA | 2 | FRC Lifeline discrepancies | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60921250 | 508 | O/SI Steam Inlet Drain Valve Leaking | S17 | Steam/Hot H2O | 2020-03-11 | 2020-03-02 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.SW.VAGL-115552 | Steam Inlet Drain Valve | 2020-01-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 118651000000 | 30 | 50 | 7000002603 | 2-1/2" FLEX CG 150# SP WND GSKT GRF FLR | 2020-03-11 | Received at Worksite | 2020-01-22 |  |  | U182 | 8201 | Stones Main | ST1A3B | 11865065 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | 4073688 | Name 3 |  | 2020-01-11 | USMNF8 | 5 | EA | 5 | Steam Inlet Drain Valve Leaking | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WP ZPMM | Kit Complete |  |  | ST1A3B 02/3/20 GG
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS2 | 40 | 7000003196 | Swagelok SS-12-SE | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Seawater Eductor | 11545759 | 67 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI59 | Name 2 | Name 2 | 2019-10-23 | USSOLE | 2 | EA | 2 | Shop Order Sheets - I&E Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
60686665 | 508 | O/SI Passing #1 Boiler Drum Vent Valve | S17 | Steam/Hot H2O | 2020-04-01 | 2019-09-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.NAC-11503A | Auxiliary Boiler No. 1 | 2019-12-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-02 | 115837000000 | 30 | 20 | 7000004211 | EP-GVB20X25KM, F-7421 FORGED STEELL GLOB | 2020-05-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11583660 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-04 | USNSB4 | 1 | EA | 0 | Replace Boiler #1 Vent Valve, 20k x 25mm | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6950 | 7000002591 | Fabreeka Pad, 1/4" THK x 8" x 12" | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 943 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2490 | 1001676333 | BLT HEX,A325,UNC,2.1/4in,5/8in | 2019-04-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 271 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04021905 | Name 2 | Name 2 | 2019-04-03 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 20 | 1000720061 | COIMC,SWAGELOK,25071210112,3/4x3/4NPT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 780 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 12 | EA | 12 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6140 | 7000002629 | Adapter Straight, 1/2", SWM x FNPT, 90/1 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 712 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 22 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4880 | 7000002629 | FLANGE, 8" 300 LB RFWN SCH 10S ASME B16. | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 549 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 710 | 7000002591 | Parachute Cord Nylon 7Str 550lb Tested U | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 929 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A395 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 1 | EA | 1 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60665884 | 508 | O/SI Passing Valve SW.115-304V | S17 | Steam/Hot H2O | 2020-03-25 | 2019-09-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.115-304V | PCV Bypass Valve | 2019-11-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-26 | 115603000000 | 30 | 20 | 7000004211 | FLANGE PACK (20K 150A) Flange pack to in | 2020-06-07 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11560290 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-25 | USNSB4 | 1 | EA | 0 | Replace 8" Control Valve SW.115-304V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 730 | 7000002591 | DRILLFORCE HSS Jobber Length 10 PCS,19/6 | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 73 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60859588 | 508 | Replace Offload Station Leak Test Valve | S21 | Oil Treating | 2020-06-02 | 2020-01-20 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.VACH-664001 | Pressure Test Connect Valve | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 117945000000 | 20 | 30 | 1001816211 | GASW,CL150,316,GPH,NPS2 | 2020-06-02 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB A5 | 11794476 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-10 | USNSB4 | 2 | EA | 2 | Replace Offload Station Leak Test Valve | REL ESTC GMPS PRC SETC | APPR EOM MAGN MANX WPOK | Approved |  |  | PU 02/16/20 AMW
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 90 | 1002316824 | GASW,CL150,316/316L,GPH,3in | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 2 | EA | 2 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 50 | 7000003739 | 917806C1 SHAFT,GEARBOX,ACTUATION | 2020-01-19 | Received at Worksite |  | 2020-02-16 | 2020-02-26 | U182 | 8201 | Stones Main | ST KB B2 | 12155706 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-28 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO |  |  | PU 02/16/20 AMW
61076060 | 508 | Install Drink & Ice Cream Machine | S09 | Bldg & Qtrs | 2020-03-17 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GU.BQ.ROOM-213 | Galley | 2019-12-01 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-03-17 | 120415000000 | 10 | 10 | 7000000129 | SOFT SERVE MACHINE | 2019-12-17 | Received at Worksite |  | 2020-02-21 |  | U182 | 8201 | Stones Main | Stones | 12041473 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-02 | USAWJB | 1 | EA | 1 | Install Drink & Ice Cream Machine | REL PRT GMPS PRC SETC | SCHD WPOK | EXEC |  |  | PU ARCHIE MOD22 02/15/2020
61219230 | 508 | GT #3 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-2 | Generator #3 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 10 | 7000003763 | 8MGT-1120-12 POLY CHAIN BELT | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206814 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #3 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 160 | 7000002591 | 1-1/2” ELBOW 90 DEG. THRD SCH 80S ASME B | 2019-10-18 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 40 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN091 | Name 2 | Name 2 | 2019-09-23 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 350 | 1001723500 | WASHER,LOCK,F436,SERMAGAURD,1/2in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 35 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 5 | EA | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60453585 | 508 | Replace Float in Knockout Pot LG-076 | S06 | General | 2020-02-27 | 2019-05-13 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.TU.LG-12901-076 | Turret Util Swivel Flare Gas Level Gauge | 2019-07-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-27 | 113217000000 | 10 | 20 | 7000000065 | Replacement Spring | 2020-02-27 | Not Shipped |  | 2020-02-23 | 2020-03-02 | U182 | 8201 | Stones Main | Issued | 11321739 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 6 |  | 2019-07-14 | USAWJB | 1 | EA | 0 | Replace Float in Knockout Pot LG-076 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 40 | 7000003344 | Pipe, 1 1/2", S/40, ASME B36.10, ASTM A1 | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 20 | EA | 20.25 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 20 | 130 | 7000000068 | DK 1548-30310 End Seal Fitting (RTES) Ne | 2019-12-08 | Received at Target Location |  | 2020-02-28 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11614811 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI64 | Name 2 | USNSB4 | 2019-11-05 | USSOLE | 1 | EA | 1 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 10 | 70 | 7000000068 | DK SEAL 1.60 | 2020-02-07 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | Issued | 11614811 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 7 | USNSB4 | 2019-09-28 | USAWJB | 1 | EA | 1 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
60172773 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-04-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.96T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 110086000000 | 10 | 40 | 7000002603 | Gasket, 40mm, FF, JIS 16K, JIS B2220, No | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008582 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081902 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 6 | EA | 6 | MOC missing steam trap | REL PCNF ESTC GMCO GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3990 | 1001690904 | (PCM-0.23) | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 449 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7630 | 1001665196 | BLT HEX,A325,UNC,2.1/2in,5/8in,SERMAGARD | 2020-02-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 1026 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-23 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4490 | 1002058423 | WASHER,LOCK,F436,SERMAGARD,3/4in | 2019-11-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 501 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141903 | Name 4 | Name 4 | 2019-11-14 | USABCE | 22 | EA | 22 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 370 | 1002300890 | SB2N,B7,2H,UNC,3/4in,4.25in,CTD | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 50 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 810 | 7000002603 | 2" Flange Protectors 2", 150#, RFWN | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose |  | 11179936 | 1047 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-23 | USSOLE | 1 | EA | 1 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5240 | 7000002596 | STUD BOLT, 5/8" X 5 1/2" ASTM A193 GRADE | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 585 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 32 | EA | 32 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60737089 | 508 | VPI test fail COT 5 STBD | S21 | Oil Treating | 2020-02-05 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-544 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-09-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 116406000000 | 20 | 20 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-04-25 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-09 | U182 | 8201 | Stones Main | ST KB B7F | 11640594 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-16 | USNSB4 | 1 | EA | 1 | Repair VPI XV-6635S-544 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3070 | 7000002603 | Gaskets, 2", 300#, RF (for Hydro Only) | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 337 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60989316 | 508 | Compressor Multilin Relay Upgrades | S03 | Elect. Systems | 2020-04-01 | 2020-04-07 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.SGR-44101A12 | Switchgear Section A12 | 2020-01-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-07 | 119417000000 | 10 | 20 | 7000000086 | Grid Automation Services Relay Setting | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11941694 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-24 | USNSB4 | 4 | EA | 0 | LO/TO Perform Isolations MGC-A Multilin | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60172772 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-03-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.95T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 110086000000 | 10 | 40 | 7000002629 | Flange, 40mm, FF, Slip-on, JIS 16K, JIS | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008581 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081901 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 2 | EA | 2 | MOC missing steam trap | REL PCNF ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 90 | 7000005901 | NK Technologies AT2-420-24L-FT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780965 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI77 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 2 | EA | 2 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60699172 | 508 | O/SI Valve XV-1122S-326 over rotating Ba | S19 | Marine Systems | 2020-04-08 | 2019-10-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.BB.XV-1122S-326 | WB Tank No. 1S Water Line Ballast Valve | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-09 | 115978000000 | 50 | 70 | 7000004211 | Hydraulic Actuator Model HAA-D06 | 2020-04-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11597808 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 1 | EA | 0 | Valve over rotating | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 20 | 50 | 7000004211 | SHAFT NUT 145, 20050-035 | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11762536 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 0 | Replace pump cover on Jockey Pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 120 | 7000002662 | 1/2" x 0.049 317L SMLS Uncoated Tubing | 2019-11-26 | Received at Target Location |  |  | 2020-02-14 | U182 | 8201 | Stones Main | Onsite Danos Has | 11882270 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI65 | Name 2 | Name 58 | 2019-11-06 | USSOLE | 40 | FT | 40 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 20 | 1001642069 | BAR FL,1/4in,1.1/2in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 140 | FT | 140 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60911836 | 508 | Light Fixture Out - FWD Machinery Space | S03 | Elect. Systems | 2020-02-22 | 2020-02-25 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.LI.LPP-44105 | Forekpak Normal Lighting Panel | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-22 | 118544000000 | 10 | 10 | 7000002583 | MATERIAL DESCRIPTION: Pauluhn FPS232 | 2020-02-22 | Received at Worksite | 2019-10-16 | 2019-12-04 | 2020-02-26 | U182 | 8201 | Stones Main | ST1A6C | 11854415 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-09 | USABDF | 1 | EA | 1 | Replace Lighting Fixture in Fwd Mach Spa | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO
60739066 | 508 | COT 4 Port vent netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127050 | COT 4 PS Vent Gas Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642942 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 60 | 7000002591 | 4548K381 3/8 NPT, 1" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 60 | 7000002591 | 6" 600# Spectacle Blind, 316SS, 0.88" Th | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 2 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 620 | 7000002591 | 4452K143 Plug with External Hex Drive, | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 62 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60848038 | 508 | Torque Meter Incorrect Reading | S19 | Marine Systems | 2020-02-05 | 2020-07-08 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.MA.PR.VE109-07000 | Main Engine Control System | 2019-07-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-25 | 117810000000 | 10 | 10 | 7000005901 | KFD0-CC-1 CHANNEL CURRENT VOLTAGE CONVER | 2020-02-05 | Received at Worksite | 2019-11-21 | 2020-01-19 |  | U182 | 8201 | Stones Main | Issued | 11781017 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 9 | USNSB4 | 2019-10-15 | USNSB4 | 2 | EA | 1 | Replace Torque Meter Signal Conditioner | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MAKD WPOK | EXEC |  |  | PU AARON W 01/19/2020
61049139 | 508 | HP/LP Piston Failure | S08 | Air Systems | 2020-02-12 | 2020-01-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11804A | Start Air Compressor No. 1 | 2020-02-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-14 | 120119000000 | 10 | 30 | 7000005901 | 3823 CROISSHEAD BEARING 220/240 LP | 2020-02-12 | Received at Worksite | 2020-02-13 | 2020-02-13 |  | U182 | 8201 | Stones Main | ST KB A3 | 12011865 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-13 | USMNF8 | 2 | EA | 2 | Rebuild Start Compressor #1 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAKD MAXX RUSH WPOK | EXEC |  |  | ST1A1C 02/07/2020 CMR
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 260 | 7000002596 | M22" x 2 1/4" A193 B7 Cap Bolt, Xylan | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 26 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 10 | EA | 10 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5700 | 7000002629 | Plug, 3/4", SC Hex Head, ASME B16.11, AS | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 664 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2610 | 7000002629 | FULL FACE BLEED RING, 12", 300#, RF, 1.5 | 2019-04-22 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 283 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04081901 | Name 2 | Name 2 | 2019-04-08 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 350 | 1002240192 | ETHERNET/IP MODULE,ALLENB,1756-EN2TR | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 421 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 3 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4900 | 7000002629 | FLANGE, 1 1/2" 300 LB RF SW ASME B16.5, | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 551 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 20 | 7000004213 | KE35/5 SASAKURA KE35- PN:5 GLOBE VALVE | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7920 | 7000002591 | Weldless End Link, 3/8", Galv., Crosby-L | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1062 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4210 | 7000002596 | 1) 1/8" thick x 3" wide x 1'-4" long Bla | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 471 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 35 | EA | 35 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5550 | 7000002596 | Bolt, 3/4" x 2 1/2" LG, ASTM F3125 Gr. | 2019-12-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 619 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12121901 | Name 4 | Name 4 | 2019-12-13 | USABCE | 36 | EA | 36 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61042037 | 508 | End Stops OOC - Collar Deck - ZZZ-887106 | S40 | Cargo Handling | 2020-02-09 | 2020-06-30 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-11-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-21 | 120026000000 | 10 | 30 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2020-01-18 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | Trolley End Stops | 12002579 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A393 | Name 2 | Name 59 | 2020-02-01 | USSOLE | 96 | EA | 96 | Fabricate End Stops | REL PCNF ESTC GMCO GMPS PPRT PRC SETC | EXEC MAGN MANX WPOK | EXEC
60662381 | 508 | Valve 125-12V Leaking Through Stem | S18 | Water Systems | 2020-04-19 | 2019-09-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.125-12V | FW to M/E Jacket Water Cooler Iso Vlv | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-19 | 115562000000 | 20 | 10 | 7000003464 | 5" BFV, Norriseal 150# lug | 2020-04-19 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11556231 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-19 | USMNF8 | 1 | EA | 0 | Valve leaking through stem- Replace | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60663676 | 508 | Actuator Assembly Malfunction | S06 | General | 2020-05-07 | 2019-09-14 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.HC.TCV-12501-410 | FW Coolers Outlet Temp Control Valve | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-07 | 115578000000 | 20 | 20 | 7000005901 | Pneumatic cylinder, CPA2F80-120 | 2020-05-07 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11557766 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-03 | USMNF8 | 1 | EA | 0 | Replace Actuator Assembly | REL ESTC GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 260 | 1002316829 | GASW,CL300/600,316/316L,GPH,2in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 71 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 6 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 180 | 7000000103 | MTRs | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN112 | Name 2 | Name 2 | 2020-01-21 | USSOLE | 2 | EA | 2 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 260 | 7000002591 | Frictape Netting (5' x 10' Sections) | 2020-06-01 | Not Shipped |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 26 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 5 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 120 | 7000006429 | EMBR18527A.32B | 2020-03-11 | Not Shipped |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 13 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO200017M | Name 3 | USAAN5 | 2020-02-24 | USLFA4 | 1500 | GLL | 0 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 100 | 7000004213 | KE35/13 SASAKURA KE35 P/N 13 LONG NIPPLE | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 820 | 7000002583 | UHMW-PE Strip, 4" x 10" x 12'-4" LG. w/ | 2020-01-12 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 82 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08051901 | Entity 3 | Name 59 | 2019-08-05 | USDKFB | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 270 | 7000002629 | 1 1/2 NIPPLE SCH 80S TBE 4 ASTM A790 GR5 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 54 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A363 | Name 2 | Name 2 | 2019-10-21 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 350 | 1000710732 | COUPLING,HOSE,CAMLOCK,2DSS,2in,SS | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 62 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A364 | Name 2 | Name 2 | 2019-10-23 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
61121269 | 508 | Replace bad purge switch on Meoh P/P C. | S10 | Chem Injection | 2020-02-11 | 2020-06-24 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.CI.LCP-12806C | Methanol Inj Pump C Control Panel | 2020-01-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-11 | 120942000000 | 10 | 10 | 7000005901 | PSCZ-4S 230VAC 316SS CYCLOPS Z PURGE | 2019-11-11 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-14 | U182 | 8201 | Stones Main | ST KB B3 | 12094191 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-01 | USAWJB | 1 | EA | 1 | Replace bad purge switch on Meoh P/P C. | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
60828048 | 508 | Emergency Kits for Lifeboats STONES | S15 | Life Saving | 2020-06-01 |  | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.LS.LB | Lifeboats | 2019-07-04 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 117583000000 | 10 | 40 | 7000002591 | Junojumper Pro Model# JPR180B with/JPRCA | 2020-06-01 | Received at Target Location |  |  | 2020-01-31 | U182 | 8201 | Stones Main | Issued | 11758304 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Entity 5 |  | 2019-07-04 | USDHIE | 5 | EA | 5 | Stage all kits as directed by Leadership | TECO ESTC CSER GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO |  |  | PU 10/31/19 J WELBORN
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 380 | 7000002591 | 4452K434 Tee Connector, 1/2 NPT Female | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 38 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 80 | 7000002591 | Grainger combo locks #5JKW8 | 2020-01-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0005 | Name 8 | USCRFI | 2020-01-13 | USLFA4 | 8 | EA | 8 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 50 | 7000002591 | 10" 300# Spectacle Blind, CS 516 Gr-70, | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 2 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
61200672 | 508 | Stones Small Civil Projects 2020 |  |  | 2020-12-31 |  | P.US.STO.NF.20.009.7240A | GENERIC |  |  | 2020-02-11 | WO | U100 | GEN | US01 | P16 | [5 empty] | 3 Low | 2020-12-31 | 121848000000 | 10 | 60 | 7000002603 | Flange Protector for Weld Neck Backing F | 2020-02-28 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G97 | 12184838 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST02242002 | Name 4 | Name 60 | 2020-02-27 | USSOLE | 1 | EA | 0 | Stones Small Civil Projects 2020 | REL ESTC PRC SETC | APPR | Approved
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 50 | 1000709955 | COIMC,SWAGELOK,SS1210112,3/4x3/4NPT | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 3 | EA | 3 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
61104113 | 508 | EWS55001 Hard Drive #3 failed | S20 | Monitor & Ctrl | 2020-02-08 | 2020-12-08 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.MC.DC.FWD | Firewalls and Devices | 2019-12-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-11 | 120737000000 | 10 | 20 | 7000003852 | Samsung 860 PRO SSD 1TB - 2.5 Inch SATA | 2020-02-08 | Received at Worksite | 2019-12-20 | 2020-01-19 | 2020-02-12 | U182 | 8201 | Stones Main | ST KB B7D | 12073690 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-15 | USMNF8 | 3 | EA | 3 | Configure Hard Drive #3 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60233847 | 508 | N2 Accum 5" Flange Maintenance | S19 | Marine Systems | 2020-05-01 | 2019-07-01 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.PS.ZZZ-87413 | Heave Compensation System Cylinder Mod 1 | 2019-11-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-05-03 | 110780000000 | 10 | 20 | 7000000111 | P/N: BONDED SEAL 5 METRIC CS | 2020-05-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11077989 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2019-11-20 | GW982959 | 2 | EA | 2 | INST SCAFF. Accum 5" Flange Maintenance | REL ESTC GMCO GMPS PRC SETC | APPR EOM MAGN MAOK WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4400 | 7000002596 | Bolt, 5/8" x 1 3/4" LG, ASTM F3125 Gr. A | 2019-11-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 492 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141901 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 36 | EA | 36 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 340 | 1001763848 | SB2N,A193-B7,CTD,UNC,3.25in,5/8in | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 47 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 6 | EA | 6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 530 | 7000002629 | PLUG, 3/4", SC, HEX HEAD, ASTM A182 GR F | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 69 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6090 | 1001574912 | FLG SO,C70600,FF,CL150,3in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 707 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 16 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7830 | 1002316821 | GASW,CL150,316/316L,GPH,1in | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1053 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 13 | EA | 13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2570 | 7000002629 | PLUG, 3/4", SC, HEX HEAD, ASTM A182 GR F | 2019-04-22 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 279 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04081901 | Name 2 | Name 2 | 2019-04-08 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 640 | 7000002629 | SOCK-O-LET, 12" X 1 1/2", 3000#, FS, MS | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 80 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4760 | 1002150255 | SHT PLT SLD MET,4x4ft,3/8in,A572-50 | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 528 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1030 | 1002301610 | SB2N,B8M CL2,8M,UNC,5/8in,3.50in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 119 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 26 | EA | 26 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 250 | 7000002603 | FLAT RING GASKET, 2", 150#, RF, FLEXIBLE | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 38 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 3 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3720 | 1001267672 | BEAM,FLANGE,A-992,4.06in,20ft,0.345in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 402 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3170 | 1001574310 | (PCM-0.23) | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 347 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 110 | 7000003852 | Compact Binoculars 10x42 with Low Light | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
60959173 | 508 | COP1 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-06 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PBE-66301A | Cargo Oil Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-12 | 119077000000 | 10 | 40 | 7000000038 | 3/8" close nipple SS sch 80 | 2020-03-06 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 11907749 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-17 | USRAR6 | 1 | EA | 1 | Add seal flush plan 12 to COP1 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 140 | 7000003196 | MS-MHSUT-O-2507-12-CHM | 2020-12-31 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 14 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 9 | USJRF5 | 2020-01-27 | USAWJB | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61026238 | 508 | MGCB Pipe Support Bracket Installation | S04 | Gas Compress | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DANOS | US.WR508A.GC.GS.VADB-771017 | Inlet Gas Valve | 2019-11-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-01 | 119851000000 | 10 | 20 | 1001676338 | BLT HEX,A325,UNC,3.1/2in,3/4in | 2020-03-27 | Received at Target Location |  | 2019-11-12 |  | U182 | 8201 | Stones Main | SHF9-F65 | 11985064 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111902 | Name 4 |  | 2019-11-12 | USLFA4 | 10 | EA | 10 | Install 4x A325 3/4 x 3-3/4 Bolts | REL PRT GMPS PRC SETC | APPR MAGN MAOK WP ZPMM | EXEC
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 40 | 7000003458 | EMBR18527A.32B | 2021-02-19 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200012A | Name 3 | USAAN5 | 2020-02-05 | USLFA4 | 1500 | GLL | 1500 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60973032 | 508 | MGC-A 3rd Stg Bridle Removal | S04 | Gas Compress | 2020-04-20 | 2020-09-26 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2019-10-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-20 | 119235000000 | 10 | 20 | 7000004753 | 3-COAT PAINT BLIND FLANGES | 2020-03-21 | Received at Target Location | 2019-10-10 | 2019-11-30 |  | U182 | 8201 | Stones Main | ST KB C7 | 11923491 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-02 | USAWJB | 2 | EA | 2 | MGC-A 3rd Stg Bridle Removal MOC78183 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU WPT AMW 11/30/19
60507050 | 508 | STB Vent N2 snuffing system rusting | S06 | General | 2020-03-10 | 2019-02-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.ZZZ-12707 | Cargo Vent Stacks N2 Stuffing System | 2019-06-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-11 | 113805000000 | 20 | 40 | 1002360774 | SB2N,B7,2H,UNC,5/8in,6in,DOXSTEEL | 2020-03-10 | Received at Worksite |  | 2019-06-07 |  | U182 | 8201 | Stones Main | ST KB B3 | 11380546 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-04-19 | USNSB4 | 4 | EA | 4 | Replace Rusted Components Starboard Vent | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MAOK WPOK ZPMM | EXEC
61109055 | 508 | Hilti clip installation engine room | S06 | General | 2020-10-05 | 2020-12-11 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GN.MI.HG | Handrails & Grating | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-10-06 | 120800000000 | 10 | 30 | 7000002583 | 10 BX 377074 Threaded stud X-BT M8-15-6 | 2020-10-05 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12079993 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USMRRO | 2020-02-18 | USMRRO | 10 | EA | 0 | Hilti clip installation engine room | REL PPRT PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 50 | 7000002591 | Grainger MM Wrench set #1WNB8 | 2020-01-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0005 | Name 8 | USCRFI | 2020-01-13 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU ARCHIE 01/29/20 GG
60708311 | 508 | Faulty check valve on FW Gen # 3 | S18 | Water Systems | 2020-04-22 | 2019-10-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.VACH-122504 | Pump Discharge Check Valve | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-22 | 116082000000 | 10 | 40 | 7000005901 | P/N: SWCRIR-0600-P1-G-WB-OA-IB 6" 150# 2 | 2020-04-22 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A1B | 11608239 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-01-30 | GW982959 | 2 | EA | 2 | LOTO- Electric motor FW#3 | REL ESTC GMPS PRC SETC | APPR MAGN WP ZPMM | Approved |  |  | ST1A3C 02/18/2020 CMR
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 50 | 7000003852 | PILOT G2 Premium Refillable & Retractabl | 2020-02-01 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO200006 | Name 10 | USRRIG | 2020-01-19 | USLFA4 | 4 | EA | 0 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | Deleted |  |  | PU DOYLE
60874068 | 508 | FRC inspection deficiencies | S15 | Life Saving | 2020-02-13 | 2020-03-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2019-08-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-03 | 118106000000 | 10 | 20 | 7000004662 | Painter Release Wire | 2020-02-13 | Received at Worksite |  | 2020-02-13 |  | U182 | 8201 | Stones Main | ST KB C7 | 11810577 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-04 | USAWJB | 1 | EA | 1 | FRC inspection deficiencies | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD MAGN WPOK | EXEC |  |  | PU 02/16/20 AMW
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 120 | 1002360862 | SB2N,B7,2H,UNC,7/8in,5.5in,DOXSTEEL | 2021-03-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Gas Riser Pressure Gauge | 11057838 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A176 | Entity 3 | USRRIG | 2018-08-06 | USSOLE | 10 | EA | 10 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved
61211627 | 508 | BGC Motor Purge Controller | S04 | Gas Compress | 2020-04-13 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.PS-77153-112B | Low Purge Drive Motor Press Switch Alarm | 2020-02-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 4 Complete by 4 Weeks | 2020-04-13 | 121979000000 | 10 | 10 | 7000005901 | 2396305 BATTERY FOR ELECTRONIC TIME | 2020-05-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12197911 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-27 | USNSB4 | 6 | EA | 0 | Replace Battery, BGC Motor Purge Control | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60796832 | 508 | DP gauge broke on Air dryer #2 | S08 | Air Systems | 2020-03-03 | 2019-12-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.ZBK-11810A | Control Air Dryer No. 2 | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-03 | 117212000000 | 10 | 20 | 7000005901 | KNAF-31-EL FILTER ELEMENT FOR LINE FILTE | 2020-03-03 | Received at Worksite | 2020-02-05 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB A1 | 11721238 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-15 | USNSB4 | 1 | EA | 1 | Replace Differential Pressure Gauge | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 02/19/20 AMW
60758579 | 508 | UPS Room Door Heavily Corroded | S19 | Marine Systems | 2020-02-18 | 2019-11-17 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.ST.JAJF-007-MIS-0 | Fire Doors | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-19 | 116751000000 | 10 | 10 | 7000004211 | A60 steel double weathertight door | 2020-02-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11675122 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-11-21 | USJDJW | 1 | EA | 0 | REPLACE UPS ROOM DOOR | REL PRT PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60233847 | 508 | N2 Accum 5" Flange Maintenance | S19 | Marine Systems | 2020-05-01 | 2019-07-01 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.PS.ZZZ-87413 | Heave Compensation System Cylinder Mod 1 | 2019-11-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-05-03 | 110780000000 | 10 | 10 | 7000000111 | P/N: M24X160 SHCS GRADE 12.9 PLAIN CARBO | 2020-05-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11077989 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2019-11-20 | GW982959 | 16 | EA | 16 | INST SCAFF. Accum 5" Flange Maintenance | REL ESTC GMCO GMPS PRC SETC | APPR EOM MAGN MAOK WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1370 | 7000002629 | ELBOW, 3", 45 DEG., BW, SCH 10S, ASME B1 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 153 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7330 | 1000727769 | STUD,GRATING,HILTI,377074,SS,15mm | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 991 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 2 | BX | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6680 | 7000002629 | FNPT Boss, 3" x 3/4", 3000#, ASME B16.11 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 879 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 570 | 7000002629 | ELBOW, 8", S/10S (0.148 WT), LR, 45 DEG. | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 73 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7310 | 7000003344 | I6015 SAFE-T-SPAN GRATING, Phenolic w/UV | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 989 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 3 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60959166 | 508 | Replace Ballast Pump #2 Px Gauge | S19 | Marine Systems | 2020-07-06 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.BB.PG-11201B-258 | Ballast Pump No. 2 Suct Pressure Gauge | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-07-06 | 119075000000 | 10 | 10 | 7000000062 | WK 9361103 233.30 4 60PSI 1/2 L Mfr: WI | 2020-07-06 | Received at Target Location | 2019-12-09 |  |  | U182 | 8201 | Stones Main | Stones | 11907502 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-21 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge, Ballast Pump #2 | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD WPOK ZPMM | Kit Complete |  |  | PU AARON W 01/19/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 990 | 7000005901 | 3M Part No. FP301-1 1/2-48"-White-5Pcs | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 959 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI87 | Name 2 | Name 2 | 2020-02-08 | USSOLE | 1 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3090 | 1001267672 | (PCM-0.23) | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 339 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 40 | FT | 40 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 840 | 7000003197 | PL SSW6SB144 SS 6IN D BARRIER STRIP 12FT | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 915 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 4 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 10 | 160 | 1002360784 | SB2N,B7,2H,UNC,5/8in,3.5in,DOXSTEEL | 2019-11-27 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI71 | Name 2 |  | 2019-11-12 | USABCE | 5 | EA | 5 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1420 | 7000002629 | PLUG, 1/2", SC HEX HEAD, ASME B16.11, | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 158 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60352956 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-10 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33320 | No. 1 Starboard Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-11 | 112105000000 | 10 | 70 | 1000717534 | OIL,MTR,30 W,51006,SHELL | 2020-01-19 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11210548 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-02 | USAWJB | 2 | QT | 0 | YR Lifeboat Launch and Run Test | REL GMPS ILAS PRC SETC | APPR MAGN MANX MAXX WPOK ZPMM ZPVS | Deleted
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 40 | 10 | 7000003464 | NPS 2 V150 2052 Size 1 Special Tagging D | 2020-02-18 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8201 | Stones Main | ETA 10-25 | 10754707 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 60 | 2019-03-11 | USNSB4 | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 790 | 7000002591 | LINDAPTER LFF037 M10 BOLT (Hot Dip GalV) | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 79 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 135 | EA | 135 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 140 | 1002058423 | WASHER,LOCK,F436,SERMAGARD,3/4in | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 94 | EA | 94 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 110 | 7000002591 | Key ring, 1/ ½ in, PK25. Item # 1F100, M | 2020-02-15 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20G0139 | Entity 6 | USCRFI | 2020-01-20 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 340 | 7000002603 | Gasket, 2", 150#, FF GRAPH-LOCK 3125TC | 2020-05-13 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G14 | 11581210 | 34 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12091901 | Name 4 | Name 60 | 2019-12-09 | USSOLE | 6 | EA | 6 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60739080 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-03-17 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-242 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-17 | 116430000000 | 10 | 20 | 7000005901 | P.0244110039 AVC 02 CL1 A1 VPI MANIFOLD | 2020-06-05 | Received at Worksite | 2020-01-29 | 2020-02-16 |  | U182 | 8201 | Stones Main | ST KB B7C | 11642976 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 1 | LO/TO Isolate LCP ZZZ-11923 LCP#3 | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 02/16/20 AMW
60902666 | 508 | O/SI MGC-A 3rd Stg Inlet Double Block | S04 | Gas Compress | 2020-06-09 | 2020-08-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VADB-771008 | Inlet Gas Valve | 2019-09-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-06-09 | 118436000000 | 20 | 20 | 7000004211 | INSPECTION & TESTING PACKING & MARKING, | 2021-02-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11843611 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-10-14 | USNSB4 | 1 | EA | 0 | Rigging Services & Assist Replacing DBB | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60989629 | 508 | COPT SW #3 Pump mechanical seal leak | S18 | Water Systems | 2020-04-14 | 2019-12-06 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216C | No. 3 Main/COPT Condenser Cooling Pump | 2019-12-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-14 | 119420000000 | 10 | 60 | 7000004211 | Packing, SVS350M-60A | 2020-04-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11942032 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-13 | USMNF8 | 1 | EA | 0 | COPT SW #3 Pump mechanical seal leak | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 260 | 1001622964 | STL SECT MAR,BEAM,6in,5.990in,20ft | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 726 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231901 | Name 4 | Name 4 | 2019-12-24 | USSOLE | 20 | FT | 20 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4980 | 7000002629 | 90 DEG ELBOW, 4" SCH 10S LR BW CLASS WP- | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 559 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SLB1 | 10 | 7000003862 | Fabricated tie in spools | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Turritella | 11179936 | 198 | 4 | Non-Stock (Purchase Requisition) | N | X |  | 731460TUR | Name 2 | Name 2 | 2019-01-22 | USGBI5 | 3 | EA | 3 | Mechanical Shop Labor | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7880 | 7000002603 | Flange Protectors for Flanges, 1", 150#, | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1058 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 19 | EA | 19 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 270 | 1001816265 | GASW,CL300-600,316,GPH,NPS3 | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 40 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 630 | 7000002662 | PIPE, 12", S/10S (0.180 WT), ASTM A790 U | 2020-02-13 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 817 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST01292001 | Name 4 | Name 4 | 2020-01-30 | USSOLE | 12 | FT | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 620 | 1000716498 | GREASE,LUBT,CR-HINDS,STL8,8oz | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 854 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 3 | EA | 3 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 100 | 7000002629 | FLANGE, 3", 300#, RF, WN, ASTM A182 GR. | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60675075 | 508 | O/SI PV Bulkhead Main Steam Stop | S17 | Steam/Hot H2O | 2020-03-25 | 2019-09-24 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.115-331V | Steam to Separater Isolation Valve | 2019-12-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-26 | 115709000000 | 80 | 10 | 7000004211 | 12-300-CS-GLB-8-HMW | 2020-06-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11570942 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-02 | USNSB4 | 1 | EA | 0 | De-Isolate | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61165411 | 508 | Install Needle Valve on PG-33110-730 | S13 | Fire Protect | 2020-04-01 | 2020-03-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33110-730 | Firewater Lift Pump Inlet Pressure Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-01 | 121447000000 | 10 | 30 | 1000719976 | Stainless Steel Integral Bonnet Needle V | 2020-04-01 | Received at Worksite | 2020-02-24 |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 12144696 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-02-04 | USRAR6 | 2 | EA | 2 | Install Needle Valve on PG-33120-730 | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK WPOK ZPMM | Kit Complete
61006508 | 508 | Replace BGC A position indicator couplin | S04 | Gas Compress | 2020-04-01 | 2020-04-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.ZZZ-77102A | Booster Gas Compressor Package A | 2020-01-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-03 | 119629000000 | 30 | 40 | 7000003464 | HARDWARE 316SS MOUNTING HARDWARE FOR TOP | 2020-04-01 | Received at Worksite | 2020-01-23 |  |  | U182 | 8201 | Stones Main | Stones | 11962884 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-01 | USNSB4 | 4 | EA | 4 | Replace BGC-A Valve Position Indicators | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | ST1B1SIDE 02/07/2020 CMR
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 120 | 7000002646 | HIVDS-44QR 1/2" MNPT x FNPT; 316SS; 6,000P | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 42 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-17 | USSOLE | 9 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
60935784 | 508 | Foam Monitor doesn't Oscillate | S13 | Fire Protect | 2020-02-18 | 2019-11-03 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.M-F3101B | Turret Top Tank Foam Monitor | 2019-11-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 118802000000 | 10 | 10 | 7000004211 | CMU-28/40-A9-1/800-P-40x20 AS GEARBOX S. | 2020-02-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 11880240 | 1 | 4 | Non-Stock (Purchase Requisition) | N | [5 empty] | 2019-11-07 | USJDJW | 1 | EA | 0 | replace gearbox on MOV-33101B401 | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60991727 | 508 | Cooling water pump trips on overload. | S03 | Elect. Systems | 2020-03-02 | 2020-04-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.SGR-44301B14F | Switchgear Sect B14 Feeder to PM-12504B | 2019-11-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-02 | 119442000000 | 10 | 10 | 1002512954 | RELAY,OVERLOAD,ABB,E16DU2.7,690Vac,3P | 2020-03-02 | Not Shipped | 2019-12-03 |  | 2019-11-23 | U182 | 8201 | Stones Main |  | 11944211 | 1 | 1 | Stocked Locally (Reservation) | L | [5 empty] | 2019-11-11 | USMNF8 | 1 | EA | 0 | Replace overload relay no.2 Central fres | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN MAKD WPOK XGI ZPMM | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 810 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 81 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 12 | EA | 12 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 50 | 1002047421 | STL SECT MAR,BEAM,6.380in,6.080in,20ft | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 80 | FT | 80 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 50 | 7000003458 | AFMR19017A.32B | 2021-02-19 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200012A | Name 3 | USRRIG | 2020-02-05 | USLFA4 | 1000 | GLL | 1000 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61170198 | 508 | Faulty Press Trans LACT Skid | S21 | Oil Treating | 2020-04-25 | 2021-01-20 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-25 | 121499000000 | 10 | 40 | 7000002583 | ASHCROFT PN 16T6500SL04LXYWSM 300PSI/BR | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12149917 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-28 | USAWJB | 1 | EA | 0 | MOC 79792 Faulty Press Trans LACT Skid | REL ESTC GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
60908983 | 508 | Corrosion Helideck valve VAGA-331029 | S13 | Fire Protect | 2020-05-14 | 2019-10-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.VAGA-331029 | Helideck FW Pump to Helideck Outlet Vlv | 2019-12-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-05-14 | 118510000000 | 20 | 10 | 7000003464 | 6" 150# RF BROOKSBANK GATE VALVE | 2020-05-14 | Received at Target Location | 2020-02-27 |  |  | U182 | 8201 | Stones Main | STONES | 11851019 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-19 | USMNF8 | 1 | EA | 1 | Remove and replace valve | REL ESTC CSER GMPS PRC SETC | APPR MAGN MAKD RUSH WPOK ZPMM | Kit Complete
61184264 | 508 | broken discharge pulsation damper 12869 | S10 | Chem Injection | 2020-06-20 | 2021-01-26 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CI.MBL-12869 | D Pump Discharge Pulsation Damper | 2020-02-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-06-20 | 121654000000 | 10 | 20 | 7000000103 | HIP HI-Pressure Nipple, HIP 20-21LM6LM6 | 2020-06-20 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 12165420 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-06 | USMNF8 | 2 | EA | 2 | broken discharge pulsation damper 12869 | REL ESTC GMPS PRC SETC | APPR MAGN WP ZPMM | Approved
60749168 | 508 | TFR-44301A leaking cooler fins. | S03 | Elect. Systems | 2020-02-25 | 2019-07-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.TFR-44301A | Essential Transformer | 2019-06-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-05 | 116544000000 | 10 | 10 | 7000003197 | VT19W150C175 RADIATOR DEM'S | 2020-05-25 | Received at Worksite | 2019-11-01 | 2020-02-22 |  | U182 | 8201 | Stones Main | MMR504 | 11654364 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-06-12 | USNBI2 | 5 | EA | 5 | Stage All Materials & Tote Tanks To Main | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 100 | 7000003684 | OIL SAFE STRETCH SPOUT LID, BLACK | 2020-03-28 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-19 | USAWJB | 1 | EA | 1 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 100 | 1002360860 | SB2N,B7,2H,UNC,7/8in,6in,DOXSTEEL | 2021-03-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Gas Riser Pressure Gauge | 11057838 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A176 | Entity 3 | USRRIG | 2018-08-06 | USSOLE | 26 | EA | 26 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved
60884226 | 508 | Lagging missing on boiler iso valves | S17 | Steam/Hot H2O | 2020-02-07 | 2019-10-05 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.VE115 | Vessel Steam/Tank Heating Systems | 2020-01-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-07 | 118224000000 | 20 | 20 | 7000000132 | Fire blankets 49" x 45" | 2020-02-07 | Received at Worksite | 2020-01-13 | 2020-01-24 | 2020-02-10 | U182 | 8201 | Stones Main | ST1ASIDE | 11822352 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-07 | USMNF8 | 2 | EA | 2 | Replace Lagging on boiler iso valves | TECO CNF ESTC GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 2/5/2020 JH GG
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 290 | 7000002596 | 1/4"-20 x 2" 316SS Hex Head Bolts | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 50 | EA | 50 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4960 | 7000002629 | TEE, 8" SCH 10S BW CLASS WP-S SMLS, or W | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 557 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 110 | 1001574265 | FLG BLIND,A105,RF,CL150,3in,W/1/2inTAP | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 24 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1880 | 1000712038 | VNT-2505 | 2019-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 209 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01301901 | Name 2 | Name 2 | 2019-01-31 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5160 | 7000002603 | GASKET, 12" 300LB, 1/8" THICK, RF SPIRAL | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 577 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 7 | EA | 7 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 100 | 7000002603 | Gaskets 12" 300# FR 1/8" THK SPIRAL WOUN | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 636 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7200 | 1000718629 | PIPE,2-3/8,SCH 40,3.65#,BEVEL,0.,2674760 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 978 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 21.1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5720 | 1002316830 | GASW,CL300/600,316/316L,GPH,3in | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 666 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 32 | EA | 32 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4480 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-11-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 500 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141903 | Name 4 | Name 4 | 2019-11-14 | USABCE | 22 | EA | 22 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 480 | 7000002591 | 13/16'' X 2'' DOC, 9200SE 92SE152. Reg | 2020-01-20 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 761 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A383 | Name 2 | Name 2 | 2020-01-18 | USSOLE | 20 | EA | 20 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60847989 | 508 | MOC GTG5 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-44000 | Gen #5 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 50 | 7000005901 | M20 Earth Tag | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780944 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI80 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #5 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 250 | 7000003852 | DEWALT Screwdriver Bit Set, Impact Ready | 2020-12-07 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES11 |  |  | 2019-11-11 | USABCE | 2 | EA | 2 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 20 | 7000003852 | Casio Men's W800H-1AV Classic Sport Watc | 2021-05-26 | Not Shipped |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main | STONES | 11419724 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO19BBSM1 | Name 11 | USKHU3 | 2019-10-15 | USLFA4 | 3 | EA | 0 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO
60344326 | 508 | VABL-777050 Ext Stm Leak | S05 | Gas Dist | 2021-04-30 | 2019-03-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GD.FG.VABL-777050 | Superheater PCV Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2021-04-30 | 112007000000 | 10 | 10 | 1002401852 | SPARE KIT,KIT#232,RMTVALVO | 2021-04-30 | Received at Worksite | 2019-02-21 | 2019-03-06 |  | U182 | 8201 | Stones Main | ST KB D5 | 11200701 | 1 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 | USNSB4 | 2018-10-31 | USFOL2 | 1 | EA | 1 | LO/TO For Repairing Valve VABL-777050 | REL PRT CSER GMPS PRC SETC | EXEC EOM MAKD MAOK WPOK | EXEC |  |  | PU WPT 03/05/2019 AJ
60172772 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-03-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.95T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 110086000000 | 10 | 20 | 7000002629 | Pipe Nipple, 40mm x 12" Lg, S/80, STPG41 | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008581 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081901 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 2 | EA | 2 | MOC missing steam trap | REL PCNF ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60935789 | 508 | COP2 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-10 | 2019-10-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 118809000000 | 10 | 40 | 7000000038 | 3/8” close nipple SS sch 80 | 2020-03-10 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11880945 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-26 | USAWJB | 1 | EA | 1 | Install mechanical seal flush plan 12 | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 80 | 7000003852 | TorcUP Raptor RP-1000 Pneumatic TorqueWr | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | Stones | 12090727 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 11 | USJRF5 | 2020-01-16 | USJRF5 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A4A 02/15/2020 CMR
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 130 | 7000002662 | Pipe, 2", S/80S, ASME B36.19M, ASTM A312 | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 109 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 20 | FT | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1020 | 7000003852 | CRAFTSMAN Ratchet Wrench, 1/2-Inch Drive | 2021-03-31 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 102 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST20CG0146 | MarineForman | USRRIG | 2020-02-20 | USCDP7 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60699172 | 508 | O/SI Valve XV-1122S-326 over rotating Ba | S19 | Marine Systems | 2020-04-08 | 2019-10-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.BB.XV-1122S-326 | WB Tank No. 1S Water Line Ballast Valve | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-09 | 115978000000 | 40 | 50 | 7000004211 | Repair Kit for Hydraulic Actuator HAA-D0 | 2020-04-06 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11597808 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 2 | EA | 0 | Prep tank for entry | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 70 | 7000004213 | KE35/10 SASAKURA KE35/10 TEE | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1260 | 1001664216 | WASHER,LOCK,F436,SERMAGARD,5/8in | 2020-05-07 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G04 | 11581207 | 126 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031901 | Name 4 | Name 59 | 2019-12-04 | USSOLE | 3 | EA | 3 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 230 | 1000727801 | DISC,GRATING,HILTI,247182,1.3/8x1.9/16in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 1 | BX | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118336 | 508 | 2020 Lube Oils / Grease - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 80 | 7000003946 | Shell Corena S4 R 46 | 2020-03-01 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | CPORT | 12090693 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200018R | Entity 6 | JP832018 | 2020-02-27 | USLFA4 | 5 | DR | 5 | 2020 Lube Oils / Grease - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61060939 | 508 | O/SI CAIR3399 CAT2 corrosoin to flange | S08 | Air Systems | 2020-04-01 | 2020-05-19 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.AS.TS118-00000 | Nitrogen Generation & Distribution | 2020-01-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 120244000000 | 20 | 20 | 7000002629 | OA,US,MRC,PIPE,FITTINGS,FLANGES,EA | 2020-04-01 | Received at Worksite | 2020-01-21 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB D3 | 12024358 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-07 | USMNF8 | 1 | EA | 1 | Replace Corroded Flange | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A5A 02/3/20 GG
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 20 | 7000002591 | 3" 600# Hydro/Paddle Blind, CS 516 Gr-70 | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 1 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 180 | 1002058431 | NUT,A563-DH,HEXAGONAL,UNC,1/2,SERMAGARD | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 25 | EA | 25 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60009724 | 508 | MOC Mov-33120-444 does not operator | S13 | Fire Protect | 2020-03-24 | 2019-02-14 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.MOV-33120-444 | FW Pump Outlet to Ring Main Motor Op Vlv | 2018-03-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-26 | 107694000000 | 20 | 30 | 1002407999 | RELAY,ELEC,PHONX,PSR-SCP-24DC/ESP42X11X2 | 2020-03-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 10769362 | 3 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 | USNSB4 | 2020-02-28 | USNSB4 | 4 | EA | 0 | Replace Mov-33120-444 | REL ESTC GMPS PPRT PRC SETC | APPR EOM MANX MAXX WP | Approved
61006512 | 508 | R & R Mechanical seal on COPT 2 | S21 | Oil Treating | 2020-06-02 |  | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2020-02-19 | WO | U100 | 72RE | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 2 Medium | 2020-06-02 | 119629000000 | 10 | 10 | 1002409049 | MECH SEAL,AZT00798SSV01-A+,AESSEAL | 2020-06-02 | Not Shipped |  |  | 2020-02-19 | U182 | 8201 | Stones Main |  | 11962908 | 1 | 1 | Stocked Locally (Reservation) | L | [5 empty] | 2019-10-22 | USMNF8 | 1 | EA | 0 | Mechanical seal Rebuild for COPT pumps | TECO ESTC GMPS PPRT PRC SETC | XCNF MAGN XGI | TECO
60874068 | 508 | FRC inspection deficiencies | S15 | Life Saving | 2020-02-13 | 2020-03-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2019-08-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-03 | 118106000000 | 10 | 30 | 7000004662 | ARMS Lifeboat, Cover, Hydrostatic Interl | 2020-02-13 | Received at Worksite |  | 2020-02-13 |  | U182 | 8201 | Stones Main | ST KB C7 | 11810577 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-04 | USAWJB | 1 | EA | 1 | FRC inspection deficiencies | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD MAGN WPOK | EXEC |  |  | PU 02/16/20 AMW
61021343 | 508 | O/SI Passing Valve VABL-661044 on PST104 | S22 | Prod Gathering | 2020-02-15 | 2020-01-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.FM.VABL-661044 | Pressure Transmitter Isolation Valve | 2019-10-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-16 | 119797000000 | 10 | 20 | 7000002596 | 7/8” X 7 ½” Stud Bolts with 2 Heavy Hex | 2020-01-16 | Received at Target Location |  | 2020-02-11 | 2020-02-20 | U182 | 8270 | Danos - Amelia | VABL-661044 | 11979727 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A386 | Name 2 | Name 59 | 2020-01-28 | USSOLE | 12 | EA | 12 | Replace VABL-661044 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN RUSH WPOK XGI | TECO
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 80 | 7000004211 | ANS200x150x350/PN-25 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 2 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60246898 | 508 | Damaged Hoses on stab plate #2 | S19 | Marine Systems | 2020-03-10 | 2019-07-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89003A | Umb Fluid #2 Upr Stabplate FL Connector | 2019-10-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-03-11 | 110924000000 | 20 | 20 | 7000000101 | #6 FJIC SWIVEL, STRAIGHT, SS FITTINGS BO | 2020-04-29 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | ETA 11/13 | 11092386 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-07 | USNSB4 | 2 | EA | 2 | LO/TO Perform Isolations *2-Man Rule In | REL PRT GMPS PRC SETC | APPR EOM MAGN MAOK WP ZPMM | Approved
60737087 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-03-17 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-240 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-17 | 116406000000 | 20 | 40 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-06-05 | Received at Worksite | 2019-12-10 |  |  | U182 | 8201 | Stones Main | ST1A1B | 11640592 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635S-240 | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 360 | 1002309186 | SB2N,B8M CL2,8M,UNC,3/4in,5.00in | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 49 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 22 | EA | 22 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60696550 | 508 | Spare parts for MGC's | S04 | Gas Compress | 2020-02-09 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GC | Gas Compression | 2020-02-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-02-09 | 115950000000 | 10 | 50 | 7000000033 | Nut D-R Part No: 38A4K10 | 2020-02-09 | Received at Worksite |  |  | 2020-02-10 | U182 | 8201 | Stones Main | ST1A2B | 11595045 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-04-11 | USRAR6 | 64 | EA | 64 | Check in spare compressor parts | TECO ESTC GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO |  |  | PU Marty 06/10/2019 Per Aaron
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7540 | 7000002591 | Weldless End Link, 3/8", Galv., Crosby-L | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1012 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2210 | 1002150255 | SHT PLT SLD MET,4x4ft,3/8in,A572-50 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 243 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4070 | 7000002596 | Bolt, 5/8" x 2 Lg ASTM F3125 Gr. A325 SE | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 457 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 40 | 1002316830 | GASW,CL300/600,316/316L,GPH,3in | 2019-11-29 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | WP 194/ 198 SOLIDS | 11179936 | 535 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 2 | 2019-11-20 | USABCE | 6 | EA | 6 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3770 | 1001676774 | SHT PLT SLD MET,4x4ft,3/4in,A572 GR.50 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 407 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1450 | 1002316830 | GASW,CL300/600,316/316L,GPH,3in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 161 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 13 | EA | 13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4840 | 7000002662 | PIPE 8" SCH 10S B.E., ASME B36.19M, ASTM | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 545 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 80 | FT | 79.17 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6630 | 7000002629 | Elbow, 1/2", 45, SW, 400 PSIG WOG, ASME | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 874 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60562362 | 508 | O/SI Passing Valve 3rd stage PST-330A MG | S04 | Gas Compress | 2020-03-10 | 2019-03-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VAMO-771031 | Pressure Transmitter Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 114424000000 | 20 | 40 | 7000004211 | Doxsteel 2" Fastener pack for 2500 psi c | 2020-03-24 | Received at Worksite |  | 2020-02-07 |  | U182 | 8201 | Stones Main | ST1A4C | 11442408 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-30 | USNSB4 | 1 | EA | 1 | Replace Defective Valve 3rd stage PST-33 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC |  |  | ST1A3C 02/3/20 GG
60989316 | 508 | Compressor Multilin Relay Upgrades | S03 | Elect. Systems | 2020-04-01 | 2020-04-07 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.SGR-44101A12 | Switchgear Section A12 | 2020-01-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-07 | 119417000000 | 20 | 10 | 7000000086 | 869 Motor Protection Relay | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11941694 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-15 | USNSB4 | 4 | EA | 0 | Upgrade MGC-A Multilin Relay To 869 Seri | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61165411 | 508 | Install Needle Valve on PG-33110-730 | S13 | Fire Protect | 2020-04-01 | 2020-03-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33110-730 | Firewater Lift Pump Inlet Pressure Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-01 | 121447000000 | 10 | 20 | 7000003196 | OA,US,SWAGELOK,FITTINGS,EA | 2020-04-01 | Received at Worksite | 2020-02-24 |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 12144696 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-02-04 | USRAR6 | 1 | EA | 1 | Install Needle Valve on PG-33120-730 | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK WPOK ZPMM | Kit Complete
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 460 | 7000002629 | 2" 300# RF Pressure Rated Skillet CS A36 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 91 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 1 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60859588 | 508 | Replace Offload Station Leak Test Valve | S21 | Oil Treating | 2020-06-02 | 2020-01-20 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.VACH-664001 | Pressure Test Connect Valve | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 117945000000 | 10 | 10 | 7000004751 | 2" 150 RF GVI 90 Series Swing Check, 316 | 2020-06-02 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB A5 | 11794476 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-10 | USNSB4 | 1 | EA | 1 | Replace Offload Station Leak Test Valve | REL ESTC GMPS PRC SETC | APPR EOM MAGN MANX WPOK | Approved |  |  | PU 02/16/20 AMW
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 80 | 7000003739 | 917807C1 COUPLING,SPLINED | 2020-01-19 | Received at Worksite |  | 2020-02-16 | 2020-02-26 | U182 | 8201 | Stones Main | ST KB B2 | 12155706 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-28 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO |  |  | PU 02/16/20 AMW
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 70 | 7000004213 | KE35/10 SASAKURA KE35/10 TEE | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 20 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61042035 | 508 | Install Fall protection for IG platform | S06 | General | 2020-02-09 | 2020-01-03 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.IG | Inert Gas/Vent Systems | 2020-01-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-09 | 120026000000 | 20 | 20 | 7000000132 | Swing gate 37" | 2020-02-09 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-09 | U182 | 8201 | Stones Main | WHSE FLOOR | 12002575 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-09 | USMNF8 | 2 | EA | 2 | Install Fall protection for IG platform | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1FLR 01/29/20 GG
60989318 | 508 | O/SI Steam valve VAGL-115688 passing | S17 | Steam/Hot H2O | 2020-04-01 | 2020-04-05 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.VAGL-115688 | Steam Inlet Drain Valve | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 119417000000 | 20 | 10 | 1002407397 | GLOBE VALVE,1GL01-A,NEWAY | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11941696 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-02-05 | USMNF8 | 1 | EA | 0 | Replace steam valve VAGL-115688 | REL ESTC PRC SETC | APPR MAXX WPOK ZPMM | Approved
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 110 | 7000003852 | AK2 Mini PC Intel Celeron J3455,Windows | 2020-04-05 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | AJH021620 | Name 12 | USRRIG | 2020-02-19 | USCDP7 | 1 | EA | 1 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 300 | 7000002629 | 2" Camlock Male Coupling | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 57 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A363 | Name 2 | Name 2 | 2019-10-21 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60994300 | 508 | Passing PSV on lube oil tank | S19 | Marine Systems | 2020-02-25 | 2020-04-10 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.PR.VASC-45103-MIS | Lube Oil Expansion Tank Press Safety Vlv | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-25 | 119475000000 | 10 | 10 | 7000002646 | 10 PSI Relief valve, | 2020-02-25 | Received at Worksite | 2020-01-30 | 2020-02-16 | 2020-03-01 | U182 | 8201 | Stones Main | Issued | 11947514 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 13 |  | 2020-01-19 | USMNF8 | 1 | EA | 1 | Replace relief valve | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO |  |  | PU 02/16/20 AMW
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 60 | 7000003323 | Model# SPFW-32FC32SS3-32MC32SS3-480 | 2019-09-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN082 | Name 2 | Name 2 | 2019-08-19 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 690 | 7000002591 | 4452K239 3/4 NPT | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 69 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 20 | 7000003343 | Flat Bar, 1/4" x 3", ASTM A36 | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 20 | FT | 20 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
60701397 | 508 | Leaking Globe/Check Valve on Hydrophore | S18 | Water Systems | 2020-04-11 | 2019-10-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.121-20V | Tank Outlet Check Valve | 2020-01-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-11 | 116003000000 | 10 | 70 | 1001209957 | BLT+N,A193-B7,CTD,UNC,3.1/4,5/8 | 2020-02-11 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A1B | 11600310 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-28 | USAWJB | 10 | EA | 10 | LO/TO Perform Isolations To Repair Globe | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MANX WPOK ZPMM | EXEC |  |  | ST1A2C 02/18/2020 CMR
61049139 | 508 | HP/LP Piston Failure | S08 | Air Systems | 2020-02-12 | 2020-01-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11804A | Start Air Compressor No. 1 | 2020-02-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-14 | 120119000000 | 10 | 40 | 7000005901 | 3824 CROSSHEAD BEARING 220/240 HP | 2020-02-12 | Received at Worksite | 2020-02-13 | 2020-02-13 |  | U182 | 8201 | Stones Main | ST KB A3 | 12011865 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-13 | USMNF8 | 1 | EA | 1 | Rebuild Start Compressor #1 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAKD MAXX RUSH WPOK | EXEC |  |  | ST1A1C 02/07/2020 CMR
60985336 | 508 | PBE-10907A High vibration at 6X | S19 | Marine Systems | 2020-06-01 | 2020-03-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.PR.PBE-10907A | Steering Gear No. 1 Pump | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-04 | 119372000000 | 10 | 10 | 7000005901 | Mitsubishi Hydraulic pump,3V-FH2B.MK | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11937182 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 1 | EA | 0 | LOTO- PBE-10907A | REL ESTC PRC SETC | APPR MAGN RUSH WP | Approved
61175103 | 508 | Barrier Fluid HPU Sample Mod | S24 | Subsea Systems | 2020-03-03 | 2020-03-19 | O.US.STO.STO.002.724FP | 508ACR | US.WR508A.SE.OH.ZZZ-12865 | Barrier Fluid Hydraulic Power Unit | 2020-01-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-03 | 121557000000 | 10 | 40 | 7000003196 | 2507-600-C Cap | 2020-03-03 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7A | 12155741 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-29 | USNSB4 | 4 | EA | 4 | Install Needle Valves & Fabricate Tubing | REL GMPS PRC SETC | SCHD EOM MAGN MAOK WPOK | EXEC |  |  | PU A WISTRAND 02/24/2020
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 130 | 7000004213 | Customs IMPORT DUTIES/TAX/CUSTOMS BROKER | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 13 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7900 | 7000002591 | Cold Shut, 3/16" Forged Steel | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1060 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 760 | 7000002629 | BLIND FLANGE, 12", 300#, RF, ASTM A182 G | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 92 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6380 | 7000002603 | Gasket, 4", 150#, FF, 1/8" THK., ASME B1 | 2020-01-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 757 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01142001 | Name 4 | Name 4 | 2020-01-14 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 470 | 1002132222 | CABLE TIE,PANDUIT,MLTFC4H,14.3x0.31 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 839 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 1000 | EA | 1000 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
61155211 | 508 | No.2 SA Compressor LO emulsified | S08 | Air Systems | 2020-02-18 | 2020-01-30 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11804B | Start Air Compressor No. 2 | 2020-01-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 3 Complete by 2 Weeks | 2020-02-18 | 121329000000 | 10 | 10 | 1002150072 | OIL FILTER,3722,SPERRE | 2020-02-18 | Not Shipped |  |  | 2020-02-04 | U182 | 8201 | Stones Main | Stones | 12132885 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-01-18 | USAWJB | 1 | EA | 0 | Change oil/filter & T/S #2 SA Compressor | TECO CNF ESTC PRC SETC | XCNF MAXX WPOK XGI ZPMM | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7840 | 1002309182 | SB2N,B8M CL2,8M,UNC,1/2in,2.75in | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1054 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 50 | EA | 50 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 490 | 7000002591 | 17100 rotaloc pilot | 2020-01-20 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 762 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A383 | Name 2 | Name 2 | 2020-01-18 | USSOLE | 20 | EA | 20 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7260 | 7000003344 | Plate, .375" x 24" x 24",ASTM A572 GR 50 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 984 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1140 | 1001645366 | WASHER,FLAT,SS316,5/8in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 130 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 56 | EA | 56 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5260 | 7000002596 | STUD BOLT, 5/8" X 3 1/2" ASTM A193 GRADE | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 587 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 64 | EA | 64 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60756604 | 508 | Vacuum Condenser Heat Exchanger | S17 | Steam/Hot H2O | 2020-04-01 | 2019-06-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.HBG-11508 | COPT Vacuum Condenser Heat Exchanger | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 116627000000 | 10 | 60 | 7000002596 | SNB7 M22 X 140MM: STUDS AND NUTS. B7 tef | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A2C | 11662728 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-01-16 | GW982959 | 80 | EA | 80 | Main condenser tubes leaking | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WP ZPMM ZPVS | Approved |  |  | ST1A3B 02/18/2020 CMR
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 160 | 7000002629 | Flange, 8", 600#, RFWN, S/60 Bore, ASME | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 112 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 80 | 7000006192 | H266M | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 38 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-17 | USSOLE | 29 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 60 | 1002316830 | GASW,CL300/600,316/316L,GPH,3in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 51 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 8 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 20 | 7000000052 | 2nd Stage MGC Suction Scrubber Vessel | 2020-01-17 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones Job No: 2301 | 11340898 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN007 | Name 2 | Name 2 | 2019-08-02 | USGBI5 | 2 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
61219231 | 508 | GT #1 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113 | Generator #1 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 60 | 7000003763 | 14325 3/8 X 12 SQ KEYSTOCK | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206815 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #1 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1210 | 7000002629 | Pipe Nipple, 2" x S/40 x 12" LG, (2.375 | 2020-05-07 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G04 | 11581207 | 121 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031901 | Name 4 | Name 59 | 2019-12-04 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60786904 | 508 | O/SI Gas Swivel Leaking Fitting | S19 | Marine Systems | 2020-04-07 | 2020-05-31 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89930 | Gas Swivel Local Pressurization Unit | 2019-12-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-07 | 117067000000 | 10 | 10 | 1000719975 | CONN,SWAGELOK,SS-600-1-8,3/8x1/2in | 2020-04-07 | Received at Worksite | 2020-01-07 | 2020-01-20 |  | U182 | 8201 | Stones Main | ST KB B7C | 11706746 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-27 | USAWJB | 1 | EA | 1 | O/SI Gas Swivel Leaking Fitting | REL PRT GMPS PRC SETC | EXEC MAKD MAOK WPOK | EXEC |  |  | PU Aaron 01/19/2020
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 420 | 7000002591 | Gauge, 6IN 0-25000 PSI | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 73 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 3 | EA | 3 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
60453594 | 508 | 26-PL664001- Install permanent Pipe Supp | S21 | Oil Treating | 2020-02-18 | 2019-11-10 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-18 | 113218000000 | 10 | 40 | 7000002596 | U-Bolt, 3" (Shell Standard) | 2020-01-22 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | JOB: SHF9-F92 | 11321849 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221902 | Name 4 |  | 2019-11-22 | USLFA4 | 5 | EA | 5 | 26-PL664001- Install permanent Pipe Supp | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60815109 | 508 | SWLift Hypochlorite Analyzer not working | S18 | Water Systems | 2020-03-03 | 2019-12-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZZZ-12204 | Chlorine Analyser Assembly | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-04 | 117437000000 | 20 | 10 | 7000005901 | W3T158828 CARD SENSOR CPL MICRO 2000 PT1 | 2020-06-01 | Received at Worksite | 2019-12-16 | 2020-01-20 |  | U182 | 8201 | Stones Main | MOD 22 FLOOR | 11743718 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-21 | USNSB4 | 1 | EA | 1 | Replace Hypochlorite Meter | REL PRT GMCO GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 80 | 1001267401 | CHANNEL,4in,5.4lb/ft,20ft | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 60 | FT | 60 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 330 | 1002360785 | SB2N,B7,2H,UNC,5/8in,3.25in,DOXSTEEL | 2020-05-13 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G14 | 11581210 | 33 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12091901 | Name 4 | Name 60 | 2019-12-09 | USSOLE | 14 | EA | 14 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 660 | 7000002591 | 4452K236 Cap, 1/4 NPT | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 66 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 420 | 7000002591 | 4452K165 Bushing Adapter, 1/2 Male x 1/4 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 42 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61165413 | 508 | Install Needle Valve on PG-33120-733 | S13 | Fire Protect | 2020-03-10 | 2020-03-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33120-733 | SW Booster Pump Outlet Pressure Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-10 | 121447000000 | 10 | 20 | 7000003196 | OA,US,SWAGELOK,FITTINGS,EA | 2020-03-10 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144698 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 1 | EA | 1 | Install Needle Valve on PG-33120-733 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60871423 | 508 | Drive End Bearing Leaking Oil - BGCA | S04 | Gas Compress | 2020-03-03 | 2020-01-28 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-20000 | Booster Gas Compression System Train A | 2019-11-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-08 | 118080000000 | 10 | 30 | 7000000039 | 200731584 GAP SEAL | 2020-03-03 | Received at Worksite | 2019-11-24 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B8 | 11807987 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-05 | USJDJW | 4 | EA | 4 | Erect Scaffold | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU Aaron 01/19/2020
61102257 | 508 | P.Crane radiator fan shroud corroded | S40 | Cargo Handling | 2020-05-10 | 2020-06-10 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-10 | 120716000000 | 10 | 50 | 7000006081 | Channel Guard mount 21826 | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12071582 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 2 | EA | 0 | P.Crane radiator fan shroud corroded | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
60154514 | 508 | O/SI Passing cargo valves - COT 3S | S21 | Oil Treating | 2022-01-01 | 2018-07-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6633S-268 | Crude Oil to/from COT 3 SB Valve | 2018-06-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2022-01-02 | 109837000000 | 10 | 10 | 7000000105 | REPAIR KIT 8" NAKAKITA VALVE (10K-000A, | 2022-01-01 | Received at Worksite |  | 2018-06-30 |  | U182 | 8201 | Stones Main | ST KB D5 | 10983742 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-06-13 | USNSB4 | 1 | EA | 1 | Replace Soft Goods XV-6633SP-268 Butterf | REL PRT CSER GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU Aaron 10/03/2018
60246898 | 508 | Damaged Hoses on stab plate #2 | S19 | Marine Systems | 2020-03-10 | 2019-07-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89003A | Umb Fluid #2 Upr Stabplate FL Connector | 2019-10-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-03-11 | 110924000000 | 20 | 10 | 7000000101 | #6 FJIC SWIVEL, STRAIGHT, SS FITTINGS BO | 2020-04-29 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ETA 11/13 | 11092386 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-07 | USNSB4 | 2 | EA | 2 | LO/TO Perform Isolations *2-Man Rule In | REL PRT GMPS PRC SETC | APPR EOM MAGN MAOK WP ZPMM | Approved
60840919 | 508 | Relocate PORT CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-02-25 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-25 | 117729000000 | 10 | 10 | 7000000103 | 1" Stainless Steel Ball Valve | 2020-02-25 | Received at Worksite | 2019-11-27 | 2020-01-20 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772907 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 5 | EA | 5 | Relocate Crane Slew G-box Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD MAOK NCMP WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60840919 | 508 | Relocate PORT CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-02-25 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-25 | 117729000000 | 10 | 40 | 7000000101 | 1" Stainless Steel 304 Street L 90 Degre | 2020-02-25 | Received at Worksite | 2019-11-27 | 2020-01-20 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772907 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 5 | EA | 5 | Relocate Crane Slew G-box Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD MAOK NCMP WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60696550 | 508 | Spare parts for MGC's | S04 | Gas Compress | 2020-02-09 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GC | Gas Compression | 2020-02-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-02-09 | 115950000000 | 10 | 20 | 7000000033 | Gasket Pkg Case: D-R Part No: X1498T29U | 2020-02-09 | Received at Worksite |  |  | 2020-02-10 | U182 | 8201 | Stones Main | CR Request 6/4 | 11595045 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-04-11 | USRAR6 | 5 | EA | 5 | Check in spare compressor parts | TECO ESTC GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO |  |  | PU Bubba 08/29/2019 CMR
60562362 | 508 | O/SI Passing Valve 3rd stage PST-330A MG | S04 | Gas Compress | 2020-03-10 | 2019-03-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VAMO-771031 | Pressure Transmitter Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 114424000000 | 10 | 60 | 7000002603 | R26 STEEL OVAL RTJ GSKT API | 2020-03-10 | Received at Worksite |  | 2020-02-07 |  | U182 | 8201 | Stones Main | ST1A4B | 11442408 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-30 | USAWJB | 3 | EA | 3 | LO/TO Perform Isolations To Replace Defe | REL PRT GMPS PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC |  |  | ST1A3C 02/3/20 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1940 | 7000002603 | GASKET, 4", 150#, FF, 1/8" THK, GARLOCK | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 216 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5580 | 7000002662 | Pipe, 3", S/10S, ASME B36.19M, ASTM A790 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 652 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 80 | FT | 87 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2470 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-04-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 269 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04021905 | Name 2 | Name 2 | 2019-04-03 | USSOLE | 16 | EA | 16 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 20 | 30 | 7000003852 | LockNLube Grease Coupler locks onto Zerk | 2020-01-28 | Received at Worksite |  | 2020-01-19 |  | U182 | 8201 | Stones Main | Issued | 11783572 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-03 | USMNF8 | 1 | EA | 1 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC |  |  | PU AARON W
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 680 | 7000002591 | 1/4'' THK X 5 1/2'' x 28 5/8'' Fabreeka | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 925 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A394 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 550 | 7000002596 | 1/2'' x 2-1/4'' HHMB All Thread Sermagar | 2020-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 772 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A389 | Name 2 | Name 2 | 2020-01-27 | USSOLE | 220 | EA | 220 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 320 | 7000003852 | GearLight LED Tactical Flashlight S1000 | 2020-12-07 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 32 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES11 |  |  | 2019-11-11 | USABCE | 2 | EA | 2 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
61134552 | 508 | Helideck foam monitor upgrade MOC 80280 | S13 | Fire Protect | 2020-05-27 | 2020-07-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF331-12100 | FiFi Helideck Foam System | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-27 | 121087000000 | 10 | 90 | 7000002603 | Flange Protectors 6", 150#, FF | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H04 | 12108694 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST03022001 | Name 4 | Name 60 | 2020-03-03 | USSOLE | 2 | EA | 0 | Helideck foam monitor upgrade MOC 80280 | REL ESTC PRC SETC | APPR MAGN MANX WP | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 150 | 7000003196 | MS-MHSUT-O-12FK-M | 2020-12-31 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 15 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 9 | USJRF5 | 2020-01-27 | USAWJB | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 250 | 7000002596 | Stud, 1/2” x 3” LG, ASTM A320 Gr. L7 w/( | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 6 | EA | 6 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60921250 | 508 | O/SI Steam Inlet Drain Valve Leaking | S17 | Steam/Hot H2O | 2020-03-11 | 2020-03-02 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.SW.VAGL-115552 | Steam Inlet Drain Valve | 2020-01-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 118651000000 | 30 | 40 | 7000002603 | 1 FLEX CG 150# SP WND GSKT GRF FLR 304 | 2020-03-11 | Received at Worksite | 2020-01-22 |  |  | U182 | 8201 | Stones Main | ST1A3B | 11865065 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | 4073688 | Name 3 |  | 2020-01-11 | USMNF8 | 10 | EA | 10 | Steam Inlet Drain Valve Leaking | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WP ZPMM | Kit Complete |  |  | ST1A3B 02/3/20 GG
60717786 | 508 | #3 latching dog cylinder bolts are broke | S19 | Marine Systems | 2020-02-18 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-21 | 116191000000 | 10 | 40 | 7000003852 | Chicago Latrobe 550 Series Cobalt Steel | 2020-02-18 | Received at Worksite |  | 2019-10-27 | 2020-02-07 | U182 | 8201 | Stones Main | Issued | 11619069 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 14 |  | 2019-05-20 | USMNF8 | 1 | EA | 1 | Gather tools and equipment | TECO PRT GMCO GMPS PRC SETC | XCNF MAGN MAOK NCMP WPOK XGI | TECO |  |  | PU Aaron 06/11/2019 CMR
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 240 | 7000002603 | 2” Class 150 RF 1/8” Thick Spiral Wound | 2019-10-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | STONES | 11545759 | 50 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 15 | Name 15 | 2019-10-18 | USABCE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1180 | 7000002591 | 2"" x 27' U-Hook Ratchet Strap | 2020-04-15 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F64 | 11581207 | 118 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111901 | Name 4 | Name 59 | 2019-11-12 | USSOLE | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 30 | 7000002603 | Gasket, 1/8” Neoprene, Cut to Match API | 2019-05-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E35 | 11545759 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05291902 | Name 2 | Name 2 | 2019-05-29 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
61048407 | 508 | Secure Lifeboat Lifejacket Boxes | S15 | Life Saving | 2020-02-04 | 2020-11-07 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.PP-AW | Air & Water Survival Personal Prot Equip | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-05 | 120100000000 | 10 | 10 | 7000000111 | 3/8 x 1 1/2" bolts for life jacket boxes | 2020-02-04 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7B | 12010041 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-12 | USAMH7 | 16 | EA | 16 | Secure Lifeboat Lifejacket Boxes | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 200 | 7000002591 | 100 ft Steel/SAE/Metric Double Duty Oil | 2020-02-28 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20C0143 | Entity 7 | USCRFI | 2020-02-05 | USLFA4 | 3 | EA | 3 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU CARGO 2/24/2020 GG
61102257 | 508 | P.Crane radiator fan shroud corroded | S40 | Cargo Handling | 2020-05-10 | 2020-06-10 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-10 | 120716000000 | 10 | 40 | 7000006081 | Screen guard 21831 | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12071582 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 2 | EA | 0 | P.Crane radiator fan shroud corroded | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
60172773 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-04-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.96T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 110086000000 | 10 | 80 | 7000004211 | 16k Steam Trap flange both ends | 2020-04-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11008582 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-12 | USMNF8 | 2 | EA | 0 | MOC missing steam trap | REL PCNF ESTC GMCO GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 60 | 1001628126 | FLG BLIND,A105,RTJ,CL1500,2in,W/1/2inTAP | 2021-03-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Gas Riser Pressure Gauge | 11057838 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A176 | Entity 3 | USRRIG | 2018-08-06 | USSOLE | 1 | EA | 1 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved
60959163 | 508 | COP #2 Disch Px Gauge | S21 | Oil Treating | 2020-02-04 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PG-66301B-342B | Discharge Pressure Gauge | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-04 | 119075000000 | 10 | 20 | 7000005901 | WK TAG Mfr: WIKA INSTRUMENT CORP Mfr | 2020-05-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11907499 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-10-23 | USNSB4 | 1 | EA | 0 | LO/TO Perform Isolations | REL ESTC CSER GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Deleted |  |  | PU AARON W 01/19/2020
60840919 | 508 | Relocate PORT CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-02-25 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-25 | 117729000000 | 10 | 60 | 7000000101 | 3/4" x 1" MNPT x 1" FNPT 304 Stainless S | 2020-02-25 | Received at Worksite | 2019-11-27 | 2020-01-20 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772907 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 5 | EA | 5 | Relocate Crane Slew G-box Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD MAOK NCMP WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60233847 | 508 | N2 Accum 5" Flange Maintenance | S19 | Marine Systems | 2020-05-01 | 2019-07-01 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.PS.ZZZ-87413 | Heave Compensation System Cylinder Mod 1 | 2019-11-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-05-03 | 110780000000 | 10 | 40 | 7000000111 | P/N: M24 PLAIN CARBON STEEL | 2020-05-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11077989 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2019-11-20 | GW982959 | 16 | EA | 16 | INST SCAFF. Accum 5" Flange Maintenance | REL ESTC GMCO GMPS PRC SETC | APPR EOM MAGN MAOK WPOK ZPMM | Approved
60701549 | 508 | PCV internals in poor condition | S13 | Fire Protect | 2020-04-25 | 2020-02-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PCV-33151B-456 | Seawater Pump Outlet Press Control Valve | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-25 | 116003000000 | 20 | 20 | 7000002646 | Part No: VM7922502F | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | WR.508A Stones | 11600323 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USFOL2 | 2019-09-30 | USFOL2 | 1 | EA | 0 | Replace PCV 456 | REL GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4780 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 530 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 164 | EA | 164 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 10 | 30 | 7000003852 | LockNLube Grease Coupler locks onto Zerk | 2020-05-16 | Ready for Shipment after Kitting |  | 2020-01-19 |  | U182 | 8201 | Stones Main | Issued | 11783572 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 14 | USNSB4 | 2019-08-10 | USMNF8 | 1 | EA | 1 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC |  |  | PU KIM C
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 450 | 7000002591 | 10" Ziptipes, qty. | 2020-01-20 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 754 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A373 | Name 2 | Name 2 | 2020-01-14 | USSOLE | 3000 | EA | 3000 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2630 | 7000002629 | ELBOW, 12, S/10S (0.180 WT), LR, 90 DEG. | 2019-04-23 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 285 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04091901 | Name 2 | Name 2 | 2019-04-10 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 720 | 7000002629 | FLANGE, 2", 300#, RF, WN, ASTM A182 GR. | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 88 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3590 | 1001267393 | ANGL MTL,EQ,STL,20ft,L3x3x3/8in | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Stones Solids Tie-in | 11179936 | 389 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161902 | Name 4 | Name 4 | 2019-10-17 | USGBI5 | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1080 | 1001759231 | SB2N,A193B8MCL2,UNC,4in,3/4in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 124 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2060 | 7000002629 | THREAD-O-LET, 8" X 1/2", 3000#, FS, MSS- | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 228 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4280 | 1001768231 | ELB BW,WPB,45DEG,LR,40,NPS4 | 2019-11-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 480 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11121901 | Name 4 | Name 4 | 2019-11-12 | USLFA4 | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 50 | 7000003852 | HON Filing Cabinet - 400 Series Four-Dra | 2021-05-26 | Ready for Shipment after Kitting |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main | STONES | 11419724 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19BBSM1 | Name 11 | USKHU3 | 2019-10-15 | USLFA4 | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU J. WELBOURN 11/21/19
60517728 | 508 | Tilting Skillet Repair | S03 | Elect. Systems | 2020-02-04 | 2019-06-11 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.PDP-44310 | Galley Distribution Panel | 2019-03-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 113927000000 | 20 | 40 | 7000005901 | 3754077 TRANSFORMER CB9140AE2+ FUTURA | 2020-02-24 | Not Shipped |  |  | 2020-02-09 | U182 | 8201 | Stones Main | STONES | 11392705 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 1 | EA | 0 | Repair Tilting Skillet | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN WPOK XGI | TECO
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 70 | 7000005903 | 317L 1/2" X .035 SMLS 317L OUTSOURCED TU | 2020-02-24 | Received at Worksite |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | Onboard/Staged @ TEG | 11516913 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-09 | USNSB4 | 100 | FT | 100 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 260 | 7000002591 | ½” drive torque wrench 50-250 ft-lb. Par | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 26 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0140 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60739070 | 508 | COT 3 S IG Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127058 | COT 3 SB IG Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116430000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642966 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61076060 | 508 | Install Drink & Ice Cream Machine | S09 | Bldg & Qtrs | 2020-03-17 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GU.BQ.ROOM-213 | Galley | 2019-12-01 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-03-17 | 120415000000 | 10 | 30 | 7000000129 | WORK TABLE, CABINET BASE HINGED DOORS | 2019-12-17 | Received at Worksite |  | 2020-02-21 |  | U182 | 8201 | Stones Main | Stones | 12041473 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-02 | USAWJB | 1 | EA | 1 | Install Drink & Ice Cream Machine | REL PRT GMPS PRC SETC | SCHD WPOK | EXEC |  |  | STLD17 0215/2020 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 200 | 1001207659 | PIPE,API 5L-B/X42,BLACK,80/XH,6in,SRL | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 20 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 21 | FT | 18 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118336 | 508 | 2020 Lube Oils / Grease - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000003946 | 55 gal. drums of ( Shell Turbo T-46 oil) | 2021-01-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | CPORT | 12090693 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0001 | Name 17 | JP832018 | 2020-01-06 | USLFA4 | 2 | DR | 2 | 2020 Lube Oils / Grease - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 40 | 7000000036 | Wilden Diaphragm Pump | 2019-07-17 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia |  | 11545759 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN073 |  |  | 2019-06-17 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 920 | 7000003344 | Plate, 1/4" x 24" x 24", ASTM A36 (PCM-0 | 2020-02-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F13 | 11581207 | 92 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09191901 | Entity 3 | Name 59 | 2019-09-19 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 310 | 7000002591 | Rust-Oleum 7543838 Professional High Per | 2020-02-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 31 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 6 | EA | 6 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 110 | 7000000039 | 6801-16-16-NW0-SS STR. THREAD ELBOW | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 6 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 640 | 7000002591 | 4452K145 Plug with External Hex Drive, 3 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 64 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60847988 | 508 | MOC GTG4 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-34000 | Gen #4 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 70 | 7000005901 | MLTFC4H-LP316 50 PER PACK | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780943 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI79 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 1 | EA | 1 | SAEP LO/TO Isolate GTG #4 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
61184264 | 508 | broken discharge pulsation damper 12869 | S10 | Chem Injection | 2020-06-20 | 2021-01-26 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CI.MBL-12869 | D Pump Discharge Pulsation Damper | 2020-02-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-06-20 | 121654000000 | 10 | 10 | 7000000103 | HIP HI-Pressure valve, HIP 20-12LF6 | 2020-06-20 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A1B | 12165420 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-06 | USMNF8 | 2 | EA | 2 | broken discharge pulsation damper 12869 | REL ESTC GMPS PRC SETC | APPR MAGN WP ZPMM | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 50 | 1000408623 | SUPPORT KIT,TUBE,1,304S3PP16T,SWAGELOK | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 15 | KIT | 15 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 100 | 1000709994 | UNIC,SWAGELOK,SS12106,3/4in | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 8 | EA | 8 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 120 | 7000000133 | RKI ES-037RRM-h2S Sensor hydrogen sulfid | 2020-02-28 | Received at Target Location |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG144 | Entity 7 | USKHU3 | 2020-02-05 | USLFA4 | 1 | EA | 1 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2700 | 7000002662 | Pipe, 3", S/40S, ASME B36.19M, ASTM A790 | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 294 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 680 | FT | 687.3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 730 | 1001816266 | HOT ORDER | 2020-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Flushing | 11179936 | 961 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A392 | Name 2 | Name 2 | 2020-02-10 | USSOLE | 8 | EA | 8 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3920 | 7000002596 | Bolt, 1/2" x 1 1/2" LG, ASTM F3125 Gr. A | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 442 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11011902 | Name 4 | Name 4 | 2019-11-01 | USSOLE | 232 | EA | 232 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6270 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 725 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 20 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4990 | 7000002629 | 90 DEG ELBOW, 8" SCH 10S LR BW CLASS WP- | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 560 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3220 | 7000002596 | BLT HEX,A325,UNC,4.50in,3/4in,HDG | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 352 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 680 | 7000003197 | PL SSTW04HCC SS 4IN W CHNL WRAP AROUND C | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 899 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 45 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5410 | 7000002603 | GASKET, 2" 300LB, RF (Hydro Only) | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 602 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 9 | EA | 9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 300 | 7000003197 | TRIM LOK INC Mfr # 1350B2X1/4-25 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 822 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 3 | EA | 3 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
61219229 | 508 | GT #4 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-3 | Generator #4 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-21 | 122068000000 | 10 | 50 | 7000003763 | 2012 1-7/16 BUSHING | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206813 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #4 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
60935789 | 508 | COP2 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-10 | 2019-10-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 118809000000 | 10 | 60 | 7000000038 | 2-1/2” lower mount gauge 0-300 psi 1/4” | 2020-03-10 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11880945 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-26 | USAWJB | 2 | EA | 2 | Install mechanical seal flush plan 12 | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 570 | 7000000134 | Emerson AMS TREX Communicator | 2020-03-01 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 57 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOA15SJS | Name 18 | USJRF5 | 2020-02-16 | USLFA4 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 10 | 7000000052 | ,,1st Stage MGC Suction Scrubber Vessel | 2020-01-17 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones Job No: 2301 | 11340898 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN007 | Name 2 | Name 2 | 2019-08-02 | USGBI5 | 2 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 400 | 7000002591 | Steel Drawer Bin Cabinet, 33-3/4"W x 17- | 2020-02-28 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 40 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WHSE26JAN2 | Name 19 | USHBE9 | 2020-02-04 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 02/18/2020 ST1FLR1
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 60 | 7000002583 | ALUMINUM DOMED HEAD SOLID RIVETS 3/16 | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 4 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 120 | 7000003852 | MSA (Mine Safety Appliances) 10127422 MS | 2021-03-01 | Received at Target Location |  | 2020-02-03 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOACR02BA | Name 18 | USJRF5 | 2020-02-21 | USCDP7 | 1 | EA | 1 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 410 | 7000002591 | 1500 Bar 3M Hose ASSY, Blue, w/ Couplers | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 72 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
60935788 | 508 | O/SI Passing Loading Valve COT 3P | S21 | Oil Treating | 2020-02-11 | 2020-08-24 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-663UD-297 | Crude Oil O/O to COT 3 PS Valve | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-11 | 118802000000 | 20 | 30 | 1002400497 | GASKET,DWG:IFC-1 402-123-01/10,ISLIP-FC | 2020-02-11 | Not Shipped |  | 2020-01-15 |  | U182 | 8201 | Stones Main | ST KB D5 | 11880243 | 3 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-01-08 | USNSB4 | 1 | EA | 0 | Rebuild Loading Valve | REL PRT PRC SETC | EXEC RUSH WPOK | Deleted
60453594 | 508 | 26-PL664001- Install permanent Pipe Supp | S21 | Oil Treating | 2020-02-18 | 2019-11-10 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-18 | 113218000000 | 10 | 70 | 7000002596 | Flat Washer, 5/8", ASTM F436 (Sermaguard | 2020-01-22 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | JOB: SHF9-F92 | 11321849 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221902 | Name 4 |  | 2019-11-22 | USLFA4 | 5 | EA | 5 | 26-PL664001- Install permanent Pipe Supp | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 160 | 1001676309 | BLT HEX,A325,2in,1/2in | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 5 | EA | 5 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61102257 | 508 | P.Crane radiator fan shroud corroded | S40 | Cargo Handling | 2020-05-10 | 2020-06-10 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-10 | 120716000000 | 10 | 30 | 7000006081 | Right hand guard mount 21820 | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12071582 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 2 | EA | 0 | P.Crane radiator fan shroud corroded | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 70 | 7000003852 | Black n' Red Casebound Soft Cover Journa | 2020-02-01 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 10 | USRRIG | 2020-01-19 | USLFA4 | 10 | EA | 0 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | Deleted |  |  | PU DOYLE
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 20 | 7000006081 | P45-304-050 ELBOW 45 DEGREE FTG.S/S | 2020-03-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-13 | USAWJB | 4 | EA | 0 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
60737050 | 508 | A/C Compressor Excessive Corrosion | S09 | Bldg & Qtrs | 2020-03-24 | 2019-06-29 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.BQ.ROOM-124 | Battery Room | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Complete by 2 Weeks | 2020-03-25 | 116406000000 | 20 | 10 | 7000000086 | AC Condensing Unit | 2020-03-24 | Received at Worksite | 2020-01-16 |  |  | U182 | 8201 | Stones Main | Warehouse floor | 11640555 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-13 | USNSB4 | 1 | EA | 1 | Assist Replacing Badly Rusting A/C Compr | REL PCNF ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WP | Kit Complete |  |  | ST1FLR 01/30/2020 GG
60909046 | 508 | REPLACE DAMAGED AIR OIL REGULATOR | S08 | Air Systems | 2020-02-20 | 2020-08-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.VE118-30000 | Service Air System | 2020-01-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-20 | 118510000000 | 10 | 30 | 7000000034 | QUIKCLAMP & MOUNTING BRACKET MI 4314-52 | 2020-02-20 | Received at Worksite | 2020-01-27 | 2020-02-07 | 2020-02-21 | U182 | 8201 | Stones Main | Issued | 11851043 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 20 | USNSB4 | 2020-01-03 | USNSB4 | 1 | EA | 1 | Replace Air/Oil Regulator | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A1B 02/07/2020 CMR
60739047 | 508 | Repair Welding Rod Oven | S06 | General | 2020-02-11 | 2019-10-31 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GN | General | 2019-06-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-11 | 116427000000 | 10 | 20 | 7000005901 | PHX1200200 OVEN ELECTRODE STABILISATION | 2020-02-11 | Received at Worksite | 2020-01-16 | 2020-02-03 | 2020-02-14 | U182 | 8201 | Stones Main | ST KB B3 | 11642663 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-16 | USNSB4 | 1 | EA | 1 | Replace Welding Rod Oven. Assemble & Fu | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
60729276 | 508 | O/SI Valve Stuck in Closed Position | S18 | Water Systems | 2020-02-20 | 2019-11-30 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.122-131V | Pump Suction Valve | 2019-05-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-20 | 116320000000 | 10 | 10 | 7000004211 | XWS-FLT-DF-01-125, 125MM 10K DOUBLE FLAN | 2020-02-20 | Received at Worksite |  | 2019-07-13 |  | U182 | 8201 | Stones Main | Issued | 11632019 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 | USNSB4 | 2019-05-13 | USNSB4 | 1 | EA | 1 | Replace Butterfly Valve | REL CNF PRT GMPS PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC |  |  | PU Aaron 07/08/2019
61118362 | 508 | 2020 Onshore Lab Analysis Services | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 20 | 7000000133 | HYDRO TEST ONLY OF 4500PSI SCOTT SCBA BO | 2021-02-20 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090699 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | HSESTO003 | Name 21 | USKHU3 | 2020-01-21 | USLFA4 | 2 | EA | 2 | 2020 Onshore Lab Analysis Services | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU CARLOS A. 02/07/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 10 | 7000002596 | M20 Nuts AISI 316 | 2019-11-15 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Skids | 11179936 | 474 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSW551A367 | Name 2 | Name 2 | 2019-11-11 | USLFA4 | 200 | EA | 200 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2370 | 7000002591 | Fabreeka Pad 1/4" THK x 12" x 7" | 2019-04-08 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 259 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011905 | Name 2 | Name 2 | 2019-04-02 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 180 | 7000003196 | Swagelok 316-S3-PP-12T | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 796 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 180 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 50 | 7000003196 | 3/4" 2507-1213-1 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 783 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 20 | EA | 20 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 10 | 7000003852 | McGill Utility #300 Series Heavy Duty 1/ | 2020-03-19 | Not Shipped |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 18 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST20CG0151 | Marine Sup | USKHU3 | 2020-02-26 | USCDP7 | 4 | EA | 0 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 940 | 1001816209 | GASW,CL150,316,GPH,NPS4 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 110 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4220 | 7000002596 | Two Part Epoxy (Two Part Epoxy Shall Be | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 472 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5230 | 7000002603 | GASKET, 4" 150LB, 1/8" THICK, RF SPIRAL | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 584 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 11 | EA | 11 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 250 | 7000003196 | Swagelok SS-TBP8 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 803 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 100 | EA | 100 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60739081 | 508 | VPI test fail COT 5 STBD | S21 | Oil Treating | 2020-02-05 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-243 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-09-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 116430000000 | 20 | 20 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-04-25 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-09 | U182 | 8201 | Stones Main | ST KB B7F | 11642977 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-18 | USNSB4 | 1 | EA | 1 | Repair VPI XV-6635S-243 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU Aaron ST1A1B 01/19/2020 C
60859588 | 508 | Replace Offload Station Leak Test Valve | S21 | Oil Treating | 2020-06-02 | 2020-01-20 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.VACH-664001 | Pressure Test Connect Valve | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 117945000000 | 10 | 20 | 7000004753 | 3-COAT PAINT FIRE SYSTEEM RED | 2020-06-02 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | ST KB A5 | 11794476 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-10 | USNSB4 | 1 | EA | 1 | Replace Offload Station Leak Test Valve | REL ESTC GMPS PRC SETC | APPR EOM MAGN MANX WPOK | Approved |  |  | PU 02/16/20 AMW
60970408 | 508 | CRN Boom Tip Platform Grating Deficiency | S06 | General | 2020-02-20 | 2020-03-26 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GN.MI.HG | Handrails & Grating | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-21 | 119205000000 | 10 | 40 | 1002217987 | TOEBOARD,INTREPID,T5-J | 2019-12-20 | Received at Target Location |  |  | 2020-02-13 | U182 | 8270 | Danos - Amelia | Boom Rest Grating | 11920544 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A374 | Name 2 | USMCS1 | 2019-12-10 | USSOLE | 200 | EA | 200 | CRN Boom Tip Platform Grating Deficiency | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WP XGI | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 100 | 1002150255 | SHT PLT SLD MET,4x4ft,3/8in,A572-50 | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 70 | 7000005811 | MODEL 630 AFFF FOAM WHEEL UNIT | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 6 | EA | 0 | Send In/Replace Fire Ext Due Hydro | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
61006512 | 508 | R & R Mechanical seal on COPT 2 | S21 | Oil Treating | 2020-06-02 |  | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2020-02-19 | WO | U100 | 72RE | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 2 Medium | 2020-06-02 | 119629000000 | 10 | 20 | 7000000035 | 140 MM Mechanical seal, Z3110-AZT798SSV0 | 2020-06-02 | Received at Worksite |  |  | 2020-02-19 | U182 | 8201 | Stones Main | STONES | 11962908 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-09 | USMNF8 | 1 | EA | 1 | Mechanical seal Rebuild for COPT pumps | TECO ESTC GMPS PPRT PRC SETC | XCNF MAGN XGI | TECO
60920252 | 508 | Ballast Pump 1 Bellows Leaking | S19 | Marine Systems | 2020-02-16 | 2019-10-27 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-17 | 118636000000 | 10 | 40 | 7000000038 | FULL SET OF BOLTS ON ATTACHED | 2020-02-02 | Received at Worksite | 2020-01-07 | 2020-01-20 | 2020-02-25 | U182 | 8201 | Stones Main | GRN MILE MOD 22 | 11863639 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-03 | USAWJB | 2 | EA | 2 | Replace Ballast Pump 1 Bellows | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD RUSH WPOK XGI | TECO |  |  | PU Aaron GRN MILE MOD 22
61035030 | 508 | TDR Corroded bolts on Sea riser clamps | S06 | General | 2020-04-01 | 2020-05-03 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GN.MI.RI | Risers | 2019-12-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-01 | 119955000000 | 20 | 10 | 7000003852 | Neoprene Rubber Sheet, Rolls, Strips 1/8 | 2020-04-01 | Received at Worksite | 2020-02-03 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST1A3A | 11995472 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-02 | USMNF8 | 3 | EA | 3 | Replace Riser clamp bolts | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60989629 | 508 | COPT SW #3 Pump mechanical seal leak | S18 | Water Systems | 2020-04-14 | 2019-12-06 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216C | No. 3 Main/COPT Condenser Cooling Pump | 2019-12-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-14 | 119420000000 | 10 | 20 | 7000004211 | Packing, PN: 31 | 2020-04-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11942032 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-13 | USMNF8 | 1 | EA | 0 | COPT SW #3 Pump mechanical seal leak | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 920 | 1001816127 | GASW,CL300-600,316,GPH,NPS2 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 108 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1010 | 7000002596 | STUD BOLTS, 7/8" DIA. X 5 1/2" LONG, AS | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 117 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 53 | EA | 53 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 640 | 7000002644 | Apollo 3/4" NPT Deadman Valve | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 856 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN116 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2250 | 1001666793 | PIPE MET,X52,STD,4in | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 247 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 231 | FT | 244.45 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60562362 | 508 | O/SI Passing Valve 3rd stage PST-330A MG | S04 | Gas Compress | 2020-03-10 | 2019-03-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VAMO-771031 | Pressure Transmitter Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 114424000000 | 10 | 50 | 7000002596 | 1 X 13 A194/194 TEFLON BLUE W/ PAINTED | 2020-03-10 | Received at Worksite |  | 2020-02-07 |  | U182 | 8201 | Stones Main | ST1A3C | 11442408 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-30 | USAWJB | 8 | EA | 8 | LO/TO Perform Isolations To Replace Defe | REL PRT GMPS PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC |  |  | ST1A3C 02/3/20 GG
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 10 | 60 | 7000003852 | Insignia - 6' 4K UltraHD HDMI Cable (2-p | 2020-05-16 | Not Shipped |  | 2020-01-19 |  | U182 | 8201 | Stones Main | STONES | 11783572 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 22 | USNSB4 | 2019-08-10 | USMNF8 | 1 | EA | 0 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 590 | 1000708882 | TAPE,ELEC,3M,SCOTCH 35,19x0.178mm,WHITE | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 851 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 10 | EA | 10 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 150 | 7000003852 | Anker PowerCore 10000, One of The Smalle | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
60756604 | 508 | Vacuum Condenser Heat Exchanger | S17 | Steam/Hot H2O | 2020-04-01 | 2019-06-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.HBG-11508 | COPT Vacuum Condenser Heat Exchanger | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 116627000000 | 10 | 40 | 7000000101 | p/n: Gasket, non-Asbestos, 1.5t , Item | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 11662728 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2019-10-14 | GW982959 | 4 | EA | 0 | Main condenser tubes leaking | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WP ZPMM ZPVS | Approved
61165404 | 508 | Install Needle Valve on PG-33110-731 | S13 | Fire Protect | 2020-03-05 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33110-731 | Firewater Lift Pump Outlet Press Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-05 | 121447000000 | 10 | 10 | 1000719976 | COIMC,SWAGELOK,SS60016,3/8x3/8NPT | 2020-03-05 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144688 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 2 | EA | 2 | Install Needle Valve on PG-33110-731 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60975189 | 508 | XV-12202B-924 Fails to Open | S18 | Water Systems | 2020-02-07 | 2019-10-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.XV-12202B-924 | Filter Backwash On/Off Control Valve | 2019-10-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-02-07 | 119260000000 | 10 | 20 | 7000002603 | 4" 150 1/8 GARLOC IFG-5500 FULL FACE | 2020-02-07 | Received at Worksite |  | 2020-01-20 | 2020-02-14 | U182 | 8201 | Stones Main | ST KB D5 | 11925970 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-10-04 | USAWJB | 3 | EA | 3 | LOTO System - Confirm Isolation | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 80 | 7000002629 | Flange, 1/2", 150#, RFWN, ASME B16.5, AS | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 1 | EA | 1 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
60747148 | 508 | COT 3 P HC Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127014 | COT 3 PS HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651960 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60739064 | 508 | 6P Vent netherlock not locking | S06 | General | 2020-05-21 | 2019-11-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127040 | COT 6 PS Vent Main Isolation Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642940 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-17 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 440 | 7000002629 | 2" 600# RF Blind 1/2" NPT, ASTM A182 GR F3 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 89 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 2 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60352955 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-09 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33310 | No. 1 Port Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-10 | 112105000000 | 10 | 70 | 1002312330 | SEALANT,GE,SCS1001,10.1 fl.oz | 2020-02-09 | Received at Worksite |  | 2020-01-19 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210547 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-02 | USAWJB | 1 | EA | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 90 | 7000003852 | MSA 10106722 Combustible Gas and Methane | 2021-03-01 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOACR02BA | Name 18 | USJRF5 | 2020-02-21 | USCDP7 | 3 | EA | 3 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 880 | 7000002591 | DEWALT Wire Brush, Knotted, 1-Inch (DW49 | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 88 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 6 | EA | 6 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 10 | 10 | 7000004211 | Pump Cover, Inner, 35664325 | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A2B | 11762536 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 1 | LOTO/ISO Jockey pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved |  |  | ST1A2B 02/18/2020 CMR
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1040 | 7000003852 | GEARWRENCH 24mm 12 Point Ratcheting ... | 2021-03-31 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 104 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST20CG0146 | MarineForman | USRRIG | 2020-02-20 | USCDP7 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61219230 | 508 | GT #3 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-2 | Generator #3 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 20 | 7000003763 | 8MX-31S-12 1210 GT2SPKT | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206814 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #3 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 550 | 7000002591 | 4452K257 Straight Reducer, 3/4 x 3/8 NPT | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 55 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60747152 | 508 | COT 2 STBD IG Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127055 | COT 2 SB IG Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651964 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 20 | 7000000133 | 35 Custom Orientation Wheels | 2019-06-28 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Stones | 11545759 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN071 | Name 23 | Name 23 | 2019-06-13 | USGBI5 | 1 | EA | 1 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 90 | 7000000039 | 32SFO SPLIT FLANGE KIT 2" CODE 61 | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 4 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 130 | 7000003946 | Mineral Spirits | 2020-03-06 | Not Shipped |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 14 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST200019AA | Name 3 | USRRIG | 2020-03-02 | USLFA4 | 2 | DR | 0 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 520 | 7000002591 | 4452K253 Straight Reducer, 1/2 x 1/4 NPT | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 52 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
29504908 | 508 | XV-66702-655 Hot Oil Valve Passing | S21 | Oil Treating | 2020-03-31 | 2019-02-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-66702-655 | Heater/Cooler Actuated Inlet Valve | 2019-11-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-02 | 107451000000 | 30 | 10 | 7000004751 | 4" 150 RF Full Port WKM 370D6, 24-PWF-23 | 2020-07-21 | Received at Worksite | 2020-02-12 | 2020-02-24 |  | U182 | 8201 | Stones Main | Staged | 10745081 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-13 | USNSB4 | 1 | EA | 1 | Replace XV-66702-655 Valve, Actuator, & | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | ST LAYDOWN 02/24/2020
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 450 | 7000002591 | 4452K169 Bushing Adapter, 3/4 Male x 3/ | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 45 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 100 | 7000002591 | Black n' Red Casebound Soft Cover Journa | 2020-02-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200006 | Name 10 | USRRIG | 2020-01-21 | USLFA4 | 10 | EA | 10 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60848029 | 508 | OSI N2 HMI DEGRADING | S08 | Air Systems | 2020-05-06 | 2019-09-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.AT-11820-600 | Oxygen Analyser | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-05-06 | 117810000000 | 10 | 10 | 7000003740 | eO2 sensor; t90-=12 sec.; electrochemica | 2020-05-06 | Ready for Shipment after Kitting |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST KB D3 | 11781007 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 24 | USNSB4 | 2019-08-23 | USNSB4 | 1 | EA | 1 | Replace Front Screen/Keypad, N2 Analyzer | REL PCNF PRT GMPS PRC SETC | EXEC EOM MAGN WPOK | EXEC |  |  | PU 02/16/20 AMW
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 10 | 7000004211 | ANS200x150x350/PN-7 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 2 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60747150 | 508 | COT 3 P HC Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127026 | COT 3 PS HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651962 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61019646 | 508 | MGCA Pipe Support Bracket Installation | S04 | Gas Compress | 2020-04-01 | 2020-10-18 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VADB-771008 | Inlet Gas Valve | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-01 | 119776000000 | 10 | 10 | 7000000111 | 3/4 X 3-3/4 A325 STRUCTURAL BOLTS | 2020-04-01 | Received at Worksite | 2020-02-03 | 2020-02-03 |  | U182 | 8201 | Stones Main | STONES | 11977627 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-13 | USAMH7 | 10 | EA | 10 | Install 4x A325 3/4 x 3-3/4 Bolts | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | STKBB3 2/3/20 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 340 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 734 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231901 | Name 4 | Name 4 | 2019-12-24 | USSOLE | 37 | EA | 37 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 960 | 7000005901 | 3M Part No. FP301-1/8-100'-Clear-Spool | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 956 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI87 | Name 2 | Name 2 | 2020-02-08 | USSOLE | 5 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 60 | 7000000101 | 3/4" x 1" MNPT x 1" FNPT 304 Stainless S | 2020-04-29 | Received at Worksite | 2019-11-27 | 2020-01-29 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772908 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 5 | EA | 5 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO |  |  | ST1A1C 01/22/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7730 | 1002316829 | GASW,CL300/600,316/316L,GPH,2in | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1036 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 5 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 170 | 7000002629 | REDUCING TEE, 6" X 3", S/10S (0.134 WT) | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 30 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2720 | 7000002629 | Elbow, 3", LR 90, S/40S, BW, ASME B16.9 | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 296 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5380 | 7000002603 | GASKET, 12" 300LB, RF (Hydro Only) | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 599 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 7 | EA | 7 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 110 | 7000002644 | 3/4" 2-way PBM Floating Ball Valve | 2019-02-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN038 | Name 2 | Name 2 | 2018-11-28 | USSOLE | 4 | EA | 4 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6960 | 7000002591 | Fabreeka #700 Epoxy Adhesive Kit with 50 | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 944 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6160 | 1001566527 | PLUG PIPE TH,AlBRZ,MNPT,1/2in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 714 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3700 | 7000002603 | 3" Flange Protectors for Flange, 3", 150 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 400 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61098380 | 508 | Biocide Chemical Inj for Cargos & Drains | S21 | Oil Treating | 2020-09-28 | 2020-11-27 | C.US.STO.FI.19.012.1230A | 508CI&E | US.WR508A.OT.SS.VE663-70000 | Cargo Tank Systems | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-09-28 | 120671000000 | 10 | 30 | 7000000052 | SWAGELOK SS-65TF12-JL | 2020-09-28 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 12067106 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI76 | Name 2 | Name 61 | 2019-12-23 | USSOLE | 14 | EA | 0 | Biocide Chemical Inj for Cargos & Drains | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 180 | 1002309185 | SB2N,B8M CL2,8M,UNC,3/4in,4.25in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 63 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 64 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 200 | 7000002591 | Item # 5WE25 (std machinery key kit) | 2020-02-21 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0008 | Name 17 | USHBE9 | 2020-01-30 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A6C 02/18/2020 CMR
60737100 | 508 | VPI & actuator test fail Slop Port | S21 | Oil Treating | 2020-02-10 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SW.XV-663SP-678 | Produced Water/Slop Tank Decant Line Vlv | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-10 | 116406000000 | 20 | 10 | 7000005901 | P.0244110037 AVC 02 CL1 A1 VPI MANIFOLD | 2020-04-30 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7F | 11640605 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-16 | USNSB4 | 1 | EA | 1 | Repair VPI XV-663SP-678 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1070 | 7000002591 | 13/16'' Hogan Bits REG mag drill bits | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 107 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 6 | EA | 6 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 220 | 7000002591 | CF Hand Chain Hoist, 1T CF010 | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 1 | EA | 1 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60629364 | 508 | GT-5 Replace air inlet button plugs | S03 | Elect. Systems | 2020-03-15 | 2020-02-21 | O.US.STO.STO.005.724FP | GGTSSLTB | US.WR508A.ES.PG.LAN-11150 | Gas Turbine Power Generation Package 5 | 2019-07-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-15 | 115191000000 | 10 | 40 | 7000003739 | Conduit Plug PN 1739552 | 2020-03-15 | Received at Worksite |  | 2020-01-20 |  | U182 | 8201 | Stones Main | ST KB B7B | 11519120 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-24 | USAWJB | 2 | EA | 2 | GT-5 Replace air inlet button plugs | REL PRT GMPS PRC SETC | EXEC MAGN MAOK WPOK | EXEC |  |  | PU Aaron 01/19/2020
60445278 | 508 | Corrosion blisters on HP flare lines | S03 | Elect. Systems | 2020-02-18 | 2019-11-10 | O.US.STO.STO.005.724FP | MI_PAINT | US.WR508A.ES.PG.TS111-25100 | Gen #3 Gas Turbine Fuel Gas System | 2018-11-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-18 | 113123000000 | 10 | 10 | 1000721634 | U-BOLT,GALV,3/8x1in,ARMORCOAT,W/4NUT | 2020-02-18 | Received at Worksite |  | 2019-10-09 |  | U182 | 8201 | Stones Main | 5 of 23 ST1A2C | 11312272 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2019-10-09 | USAWJB | 23 | EA | 23 | Corrosion blisters on HP flare lines | REL PRT GMPS PRC SETC | EXEC MAOK WPOK | EXEC |  |  | ST 1A2C 5EA 10/18/2019 CMR
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 220 | 7000004211 | VIS-DN-500-L/HDA - Lug Type Butterfly Va | 2020-06-01 | Not Shipped |  | 2019-12-03 |  | U182 | 8201 | Stones Main | Stones | 11739629 | 22 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | Name 59 | 2019-09-12 | USRAR6 | 1 | EA | 0 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60739055 | 508 | COT 5 P HC netherlock fails to lock | S06 | General | 2020-04-01 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127008 | COT 5 PS HC Main Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642931 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 110 | 7000002591 | Gasket, 20", 5K, Garlock 500, 1/8" thick | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 7 | EA | 7 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 310 | 1000671260 | SUPER METAL,POLYMER,BELZONA,1111,Gry,1kg | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 31 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 12 | KG | 12 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60960149 | 508 | SDV-938A Passing on MGC-A | S04 | Gas Compress | 2020-07-10 | 2020-09-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.SDV-77135A-938 | Gas Outlet Start Up Line Shutdown Valve | 2019-11-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-07-10 | 119089000000 | 20 | 20 | 7000004211 | 2-RJ GSK 2" BX RING GASKETS | 2020-10-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11908867 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-05 | USNSB4 | 2 | EA | 0 | Replace Defective Valve SDV-77135A-938A | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61193289 | 508 | #2 Start Air Comp Oil Emulsified | S08 | Air Systems | 2020-03-10 | 2020-04-03 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11804B | Start Air Compressor No. 2 | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 121764000000 | 10 | 10 | 1002150072 | OIL FILTER,3722,SPERRE | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12176387 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 5 | EA | 0 | #2 Start Air Comp Oil Emulsified | REL PRC SETC | APPR MAXX WPOK ZPMM | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 60 | 7000002629 | 2” # 150 Flange ASME B16.5 RF A182 F53 D | 2019-11-27 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI67 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 2 | EA | 2 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
60989629 | 508 | COPT SW #3 Pump mechanical seal leak | S18 | Water Systems | 2020-04-14 | 2019-12-06 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216C | No. 3 Main/COPT Condenser Cooling Pump | 2019-12-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-14 | 119420000000 | 10 | 30 | 7000004211 | Mouth ring, SVS250M-38 | 2020-04-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11942032 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-13 | USMNF8 | 2 | EA | 0 | COPT SW #3 Pump mechanical seal leak | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
60888532 | 508 | Radiator cap needs to be replaced | S15 | Life Saving | 2020-02-08 | 2020-02-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.LS.ZZZ-33310 | No. 1 Port Side Lifeboat | 2019-09-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-08 | 118274000000 | 10 | 10 | 7000004662 | Radiator Cap for Lifeboat Engine | 2020-02-08 | Received at Worksite | 2020-02-03 | 2019-09-04 | 2020-02-12 | U182 | 8201 | Stones Main | Stones | 11827404 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-04 | USABDF | 1 | EA | 1 | Radiator cap needs to be replaced | TECO CNF ESTC GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1070 | 7000002596 | STUD BOLTS, 1 1/8" DIA. X 7" LONG, W/ | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 123 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 246 | EA | 246 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 690 | 1000709901 | FLG_PIPE,BLIND,RF,8",150#,CS,ASTM A-105 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 85 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61219229 | 508 | GT #4 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-3 | Generator #4 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-21 | 122068000000 | 10 | 20 | 7000003763 | 8MX-31S-12 1210 GT2SPKT | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206813 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #4 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 690 | 7000002591 | DRILLFORCE HSS Jobber Length 10 PCS,7/64 | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 69 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 430 | 7000002603 | 2" 300# RF Blind 1/2" NPT, ASTM A182 GR F5 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 88 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 4 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61114758 | 508 | O/SI SDV-77163A-904A Passing By | S04 | Gas Compress | 2020-02-15 | 2020-06-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.SDV-77163A-904 | 2nd Stg Compressor Out Gas Shutdown Vlv | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-15 | 120863000000 | 10 | 20 | 7000004753 | 3-COAT PAINT RAL-1023 STONES YELLOW,,,,, | 2020-02-15 | Received at Worksite | 2020-01-23 | 2020-02-07 | 2020-02-18 | U182 | 8201 | Stones Main | GKA002/STBD laydown | 12086293 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 59 | 2019-12-27 | USAWJB | 1 | EA | 1 | Replace SDV-77163A-904A | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO
60909926 | 508 | Purifier 2 By-Pass valve not functioning | S06 | General | 2020-06-15 | 2020-08-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.LO.117-48V | Lube Oil Purifier Supply Pump #2 Valve | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-06-15 | 118521000000 | 10 | 30 | 7000004211 | gasket-10 25MM 5K GARLOCK GASKETS 1/16" | 2020-06-15 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11852103 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-10 | USNSB4 | 2 | EA | 0 | Replace By-Pass Gate Valve 117-48V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 80 | 7000002629 | Flange, 2", 150#, S/80, RFWN, ASME B16.5 | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 2 | EA | 2 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60352956 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-10 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33320 | No. 1 Starboard Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-11 | 112105000000 | 10 | 80 | 1002312330 | SEALANT,GE,SCS1001,10.1 fl.oz | 2020-02-10 | Received at Target Location |  | 2020-01-19 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210548 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-02 | USAWJB | 1 | EA | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
60959173 | 508 | COP1 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-06 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PBE-66301A | Cargo Oil Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-12 | 119077000000 | 10 | 20 | 7000000038 | 3/8" mnpt x 3/8" tube SS fitting | 2020-03-06 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 11907749 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-17 | USRAR6 | 4 | EA | 4 | Add seal flush plan 12 to COP1 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60675080 | 508 | Cracked motor frame on Ejector pump #3 | S18 | Water Systems | 2020-12-24 | 2019-09-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PBE-12204C | No. 3 FW Generator Ejector Pump | 2019-12-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-12-24 | 115709000000 | 10 | 20 | 7000000037 | ITEM 37 BELONGS TO A GASKET KIT -- ARTIC | 2020-12-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11570947 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-20 | USNSB4 | 2 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 230 | 7000002603 | 1 ½” Class 150 RF 1/8” Thick Spiral Woun | 2019-10-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | STONES | 11545759 | 49 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 15 | Name 15 | 2019-10-18 | USABCE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 110 | 1001645341 | BLT HEX,A325,UNC,2in,3/4in,SERMAGARD | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 24 | EA | 24 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 190 | 1001723501 | WASHER,FLAT,F436,SERMAGAURD,1/2in | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 15 | EA | 15 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 130 | 1000712143 | VALVE,NEEDLE,1/2in,SS,H1RDS4Q,ANDRS-GR | 2019-10-18 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 36 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN091 | Name 2 | Name 2 | 2019-09-23 | USGBI5 | 1 | EA | 1 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60544614 | 508 | Mechanical seal is leaking | S18 | Water Systems | 2020-06-02 | 2019-07-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216A | No. 1 Main/COPT Condenser Cooling Pump | 2019-12-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 114224000000 | 10 | 10 | 7000004211 | SVS350M-22A SLEEVE | 2020-06-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11422404 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-15 | USMNF8 | 1 | EA | 0 | Mechanical seal is leaking | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
61219225 | 508 | GT #5 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-4 | Generator #5 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 60 | 7000003763 | 14325 3/8 X 12 SQ KEYSTOCK | 2020-04-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206809 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #5 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 50 | 7000000133 | 637167 Nike DriFit Vertical Mesh Polo in | 2019-12-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Turritella TDR Improvemen | 11545759 | 84 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO1127191 | Name 2 | Name 2 | 2019-12-03 | USSOLE | 154 | EA | 154 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 100 | 7000000039 | 6400-16-16-O-SS STR. THREAD O-RING CONNE | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 4 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 10 | 7000000039 | AMD-2421 HYDRAULIC OIL COOLER ASSEMBLY | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 430 | 1001768456 | ELB BW,WPB,90DEG,LR,80,NPS2 | 2019-11-20 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 43 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06141901 | Name 2 | Name 59 | 2019-06-17 | USDKFB | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 10 | 7000000066 | Yokogawa Differential Pressure Transmitt | 2020-02-04 | Received at Worksite |  |  | 2020-02-14 | U182 | 8201 | Stones Main | ST KB B8 | 11882270 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 58 | 2019-10-24 | USNSB4 | 1 | EA | 1 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO |  |  | STKBD5 02/3/20 GG
61046320 | 508 | Overhaul helideck standby pump cartridge | S13 | Fire Protect | 2020-04-21 | 2020-05-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33132 | Helideck Firewater Pump | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 120075000000 | 10 | 10 | 7000004211 | Pump Impeller C05BX, 69692-001D2 | 2020-04-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12007515 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-20 | USMNF8 | 2 | EA | 0 | Overhaul helideck standby pump cartridge | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 130 | 1000720094 | PLIC,SWAGELOK,SS1210P,3/4in | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 5 | EA | 5 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60806311 | 508 | Door Latch Broken And Door Gasket | S21 | Oil Treating | 2020-03-03 | 2019-12-18 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.OT.SS.ZZZ-66601 | Laboratory Package | 2019-07-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-03 | 117323000000 | 10 | 10 | 7000005901 | ASSA abloy 565 SIMPLE BOLT LOCK, 50MM | 2020-03-03 | Received at Worksite |  | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B6 | 11732256 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-15 | USMNF8 | 2 | EA | 2 | Door Latch Broken And Door Gasket | REL CNF PRT GMPS PRC SETC | SCHD MAGN MAOK WPOK | EXEC
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 120 | 7000003196 | Swagelok SS-12-HN | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 5 | EA | 5 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 240 | 7000003852 | MRCOOL Bedside Lamp with Bluetooth Speak | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 24 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 840 | 7000002591 | 17100 rotaloc pi | 2020-03-03 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia |  | 11179936 | 1074 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-28 | USLFA4 | 20 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1250 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 141 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061802 | Name 2 | Name 2 | 2018-12-07 | USSOLE | 156 | EA | 156 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60871576 | 508 | Replace water eductor on No.1 FWG | S18 | Water Systems | 2020-04-22 | 2020-01-26 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-22 | 118081000000 | 30 | 10 | 7000004213 | WE014-9478 Water Ejector FOR: DISTILLING | 2020-08-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11808149 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-09 | USNSB4 | 1 | EA | 0 | Replace Water Eductor On No.1 Fresh Wate | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 450 | 1000947595 | BLOCK,TERMINAL,ALLENB,1756-TBCH,36 PIN | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 431 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 6 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 30 | 7000000101 | 1" Nipple Stainless Steel 304x Close | 2020-04-29 | Received at Worksite | 2019-11-27 | 2020-01-29 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772908 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 10 | EA | 10 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO |  |  | ST1A1C 01/22/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5900 | 1001676781 | SHT PLT SLD MET,4x4ft,1/2in,A572 GR.50 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 684 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 130 | 7000000103 | 3" Duplex Remington Floating Ball Valve | 2019-01-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN031 | Name 2 | Name 2 | 2018-12-03 | USGBI5 | 3 | EA | 3 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1830 | 7000002603 | GASKET, 8", 300#, RF, 1/8" THK., SPIRAL | 2019-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 201 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01241901 | Name 2 | Name 2 | 2019-01-24 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4800 | 1002058423 | WASHER,LOCK,F436,SERMAGARD,3/4in | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 532 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 82 | EA | 82 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 960 | 1001816266 | GASW,CL300-600,316,GPH,NPS1.1/2 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 112 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 880 | 1001816208 | GASW,CL150,316,GPH,NPS6 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 104 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 10 | 7000002662 | PIPE, 14", S/80 (0.750 WT), ASTM A106 GR | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 2 | FT | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6850 | 7000000098 | 1/4" x 50 ft SS Braid hose w/ SS MNPT E/ | 2020-02-05 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 11179936 | 932 | 4 | Non-Stock (Purchase Requisition) | N | X |  | 204202001 | Name 25 | Name 25 | 2020-02-04 | USLFA4 | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 210 | 7000003197 | Brady Part No. M21-187-C-342 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 2 | EA | 2 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 60 | 7000002603 | Gasket, 500mm, JIS 5K, JIS B2220, Non-As | 2020-03-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E27 | 11477345 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05141901 | Entity 2 | USAWJB | 2019-05-14 | USSOLE | 2 | EA | 2 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3150 | 1001581841 | (PCM-0.23) | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 345 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4290 | 1001816209 | GASW,CL150,316,GPH,NPS4 | 2019-11-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 481 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11121901 | Name 4 | Name 4 | 2019-11-12 | USLFA4 | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61151919 | 508 | P.Crane swing gearbox sight glass cloudy | S40 | Cargo Handling | 2020-10-31 | 2021-01-07 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-10-31 | 121288000000 | 10 | 20 | 7000006081 | Copper washer, 423000300,, | 2020-10-31 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12128844 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-06 | USMNF8 | 6 | EA | 0 | Replace port crane gearbox sight glass | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 280 | 7000000103 | 3" SDV Assembly | 2020-03-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 412 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN098 | Name 2 | Name 2 | 2019-10-21 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3790 | 7000002596 | Bolt, 3/4" x 4 3/8" Lg., ASTM A325 GALV | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 409 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4920 | 7000002629 | FLANGE, 1" 300 LB RF SW ASME B16.5, AST | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 553 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1010 | 7000003852 | Estwing Gooseneck Wrecking Bar PRO - 36" | 2021-03-31 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 101 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST20CG0146 | MarineForman | USCRFI | 2020-02-20 | USCDP7 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 70 | 7000002629 | Flange, 3", 150#, S/10S, RFWN, ASME B16. | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 70 | 1002316829 | GASW,CL300/600,316/316L,GPH,2in | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 103 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 5 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61089244 | 508 | Aft FW Pump FT-431 failure | S13 | Fire Protect | 2020-03-15 | 2019-12-29 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.FT-33110-431 | Firewater Pump FCV Flow Transmitter | 2019-12-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-03-16 | 120564000000 | 10 | 10 | 7000000064 | Model No: TF8-F801GP-A101SM2-HANNAN-NNN- | 2020-06-23 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12056371 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-19 | USNSB4 | 1 | EA | 0 | LO/TO Isolate Power To FT-431 Aft FW Pum | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60699172 | 508 | O/SI Valve XV-1122S-326 over rotating Ba | S19 | Marine Systems | 2020-04-08 | 2019-10-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.BB.XV-1122S-326 | WB Tank No. 1S Water Line Ballast Valve | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-09 | 115978000000 | 40 | 40 | 7000004211 | Repair Kit for Hydraulic Actuator Model | 2020-04-06 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11597808 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 2 | EA | 0 | Prep tank for entry | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60557093 | 508 | O/SI Passing Valve VABL-661050 | S22 | Prod Gathering | 2020-02-15 | 2019-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.FM.VABL-661050 | Test Fluids Manual Isolation Valve | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-15 | 114365000000 | 10 | 70 | 7000002596 | 1 3/8” X 12” Stud Bolts with 2 Heavy Hex | 2020-01-07 | Received at Target Location |  | 2020-02-11 | 2020-02-20 | U182 | 8270 | Danos - Amelia | VABL-661055 Valve Change | 11436470 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A387 | Name 2 | Name 59 | 2020-01-29 | USSOLE | 26 | EA | 26 | Replace VABL-661050 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK RUSH WPOK XGI | TECO
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 100 | 7000002591 | 8" 300# Spectacle Blind, CS 516 Gr-70, . | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 2 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
61221684 | 508 | Steam Expansion Bellows critical spare | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-22 | P.US.STO.NF.20.015.7240A | 508ERENG | US.WR508A.GU.SW.VE115-32000 | Boiler System Steam Distribution | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-06-02 | 122096000000 | 10 | 70 | 7000003323 | Expansion Joint EJ-540587-A | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12209639 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAMH7 | 2020-03-02 | USRAR6 | 1 | EA | 0 | Shut down steam system | CRTD PRC | INIT RUSH WP | Approved
60796835 | 508 | No. 2 F.W. Gen Ejector P/P Gauge leaking | S18 | Water Systems | 2020-02-08 | 2019-08-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PBE-12204B | No. 2 FW Generator Ejector Pump | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-08 | 117212000000 | 10 | 20 | 7000000066 | ADAPTER REDUCING PIPE 1/2 FEMALE ADAPTER | 2020-03-09 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7A | 11721241 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-22 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge FPBE-12204B | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 2/5/2020 JH GG
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 70 | 7000003196 | Swagelok SS-TBP16 | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 50 | EA | 50 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60739059 | 508 | 6S HC Netherlock Not Locking Open/Closed | S06 | General | 2020-04-01 | 2019-11-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127017 | COT 6 SB HC Main Isolation Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642935 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 330 | 7000002591 | Belzona Applicators | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 33 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 16 | EA | 16 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 670 | 7000002629 | WELD-O-LET, 12" X 2" (2" S/40S (0.154 WT | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 83 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 750 | 7000002629 | FLANGE, 12", 150#, RF, WN, ASTM A350 GR | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 91 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2090 | 7000002629 | PLUG, 1/2", SC, HEX HEAD, ASTM A182 GR F | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 231 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 20 | 7000003196 | SS-45F8 BALL VALVE | 2020-02-05 | Received at Worksite |  |  | 2020-02-17 | U182 | 8201 | Stones Main | ST KB A3 | 11882563 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-29 | USNSB4 | 4 | EA | 4 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7860 | 1001210773 | EYE ROD,U-BOLT,3/8x1,INODO1 | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1056 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 13 | EA | 13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7340 | 1001167726 | CARTRIDGE,HILTI,412689,BROWN,M10 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 992 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 2 | BX | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 120 | 1001210571 | VALVE,BALL,QUADRANT,S6FSSPFSLMT075,3/4in | 2019-02-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN038 | Name 2 | Name 2 | 2018-11-28 | USSOLE | 4 | EA | 4 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4270 | 1001210571 | VALVE,BALL,QUADRANT,S6FSSPFSLMT075,3/4in | 2019-11-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 479 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11121901 | Name 4 | Name 4 | 2019-11-12 | USLFA4 | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6330 | 7000002603 | Flange Protectors 10", 150#, RFWN | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 741 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12271901 | Name 4 | Name 4 | 2019-12-26 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 230 | 1002301610 | SB2N,B8M CL2,8M,UNC,5/8in,3.50in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 68 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 18 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61134552 | 508 | Helideck foam monitor upgrade MOC 80280 | S13 | Fire Protect | 2020-05-27 | 2020-07-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF331-12100 | FiFi Helideck Foam System | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-27 | 121087000000 | 10 | 20 | 7000002629 | Flange, 3", 150#, FF, WN, Min Wall .095, | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H04 | 12108694 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST03022001 | Name 4 | Name 60 | 2020-03-03 | USSOLE | 2 | EA | 0 | Helideck foam monitor upgrade MOC 80280 | REL ESTC PRC SETC | APPR MAGN MANX WP | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 60 | 7000002591 | Grainger Pliers set #10N539 | 2020-01-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0005 | Name 8 | USCRFI | 2020-01-13 | USLFA4 | 1 | EA | 1 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 970 | 7000002662 | Pipe 3.500 OD 0.438 WT, ASTM A53 Gr. B ( | 2020-03-10 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 97 | 4 | Non-Stock (Purchase Requisition) | N | X |  | PE10041901 | Name 4 | Name 59 | 2019-10-07 | USSOLE | 20 | FT | 22.05 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 100 | 7000002591 | Steel Drum Truck, Drum Capacity: 55 gal. | 2020-02-15 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20G0139 | Entity 6 | USCRFI | 2020-01-20 | USLFA4 | 3 | EA | 3 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU ARCHIE S 02/07/2020
61048407 | 508 | Secure Lifeboat Lifejacket Boxes | S15 | Life Saving | 2020-02-04 | 2020-11-07 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.PP-AW | Air & Water Survival Personal Prot Equip | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-05 | 120100000000 | 10 | 30 | 7000000111 | 3/8" lock nuts for life jacket boxes | 2020-02-04 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7B | 12010041 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-12 | USAMH7 | 16 | EA | 16 | Secure Lifeboat Lifejacket Boxes | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60739069 | 508 | COT 5 P IG netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127053 | COT 5 PS IG Vent Line Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116430000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642965 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60909046 | 508 | REPLACE DAMAGED AIR OIL REGULATOR | S08 | Air Systems | 2020-02-20 | 2020-08-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.VE118-30000 | Service Air System | 2020-01-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-20 | 118510000000 | 10 | 10 | 7000000034 | FILTER REG. 3/4 10 BAR | 2020-02-20 | Received at Worksite | 2020-01-27 | 2020-02-07 | 2020-02-21 | U182 | 8201 | Stones Main | Issued | 11851043 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 20 | USNSB4 | 2020-01-03 | USNSB4 | 1 | EA | 1 | Replace Air/Oil Regulator | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A1B 02/07/2020 CMR
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 50 | 7000002603 | Gasket, 500mm, JIS 5K, JIS B2220, Non-As | 2020-03-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E27 | 11477345 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05141901 | Entity 2 | USAWJB | 2019-05-14 | USSOLE | 1 | EA | 1 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 100 | 7000002591 | Cap Bolt, M22 x 3 1/2", Gr. B7 w/ASTM A1 | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 50 | EA | 50 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4200 | 7000002596 | Black Acetal Pad, 1/4" thick x 8" x 8" ( | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 470 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60796830 | 508 | BI Broken psi gauge on hydac filter skid | S06 | General | 2020-04-01 | 2020-06-08 | O.US.STO.STO.005.724FP | 508OPER | US.WR508A.GU.PR.PG-66211-985 | Slip Sampling Filter Pressure Gauge | 2019-06-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-01 | 117212000000 | 10 | 10 | 1002407250 | PRESSURE GAUGE,0TO16bar,47395292,WIKA | 2019-08-01 | Received at Worksite |  | 2019-09-16 |  | U182 | 8201 | Stones Main | ST KB B7 | 11721236 | 1 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 |  | 2019-06-17 | USAWJB | 1 | EA | 1 | BI Broken psi gauge on hydac filter skid | REL ESTC CSER GMPS PPRT PRC SETC | EXEC MAOK WPOK | EXEC |  |  | PU AARON 09/29/2019 CMR
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 750 | 7000002591 | DRILLFORCE (5Pcs) 21/64 in. x 4-5/8 in. | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 75 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 3 | EA | 3 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 940 | 7000002591 | ECO-FLO Products PUP62 Water Transfer Dr | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 94 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60739064 | 508 | 6P Vent netherlock not locking | S06 | General | 2020-05-21 | 2019-11-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127040 | COT 6 PS Vent Main Isolation Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642940 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-17 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 90 | 7000003740 | Rosemount Integral Manifold | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN110 | Name 2 | Name 2 | 2019-12-18 | USLFA4 | 4 | EA | 4 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60921249 | 508 | O/SI Isolation Valve Packing Leak | S17 | Steam/Hot H2O | 2020-04-02 | 2020-03-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGA-115514 | Stbd Steam to COT 6 Isolation Valve | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-03 | 118650000000 | 60 | 10 | 7000004211 | 4-150-CSGOSY-G, 4" 150 C/S GATE VALVE OS | 2020-04-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11864984 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-16 | USNSB4 | 1 | EA | 0 | Replace Valve VAGA-115514 | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60935789 | 508 | COP2 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-10 | 2019-10-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 118809000000 | 10 | 80 | 7000000038 | 3/8” fnpt SS wye strainer | 2020-03-10 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11880945 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-26 | USAWJB | 1 | EA | 1 | Install mechanical seal flush plan 12 | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 10 | 7000004213 | KE35/1-4-SET | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
61221684 | 508 | Steam Expansion Bellows critical spare | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-22 | P.US.STO.NF.20.015.7240A | 508ERENG | US.WR508A.GU.SW.VE115-32000 | Boiler System Steam Distribution | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-06-02 | 122096000000 | 10 | 40 | 7000003323 | Expansion Joint EJ-540584-A | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12209639 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAMH7 | 2020-03-02 | USRAR6 | 1 | EA | 0 | Shut down steam system | CRTD PRC | INIT RUSH WP | Approved
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 110 | 7000005811 | Hydro test 33 Gallon FFFP Wheel units | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 12 | EA | 0 | Send In/Replace Fire Ext Due Hydro | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60739061 | 508 | COT 4 S HC Netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127021 | COT 4 SB HC Main Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642937 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 100 | 1001664310 | BLT HEX,A325,UNC,2.1/2in,3/4in,SERMAGARD | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 10 | EA | 10 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60970408 | 508 | CRN Boom Tip Platform Grating Deficiency | S06 | General | 2020-02-20 | 2020-03-26 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GN.MI.HG | Handrails & Grating | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-21 | 119205000000 | 10 | 10 | 1000856876 | GRATING,SERRATED,3/16X1.1/2X3ftX20ft | 2019-10-04 | Received at Target Location |  |  | 2020-02-13 | U182 | 8256 | Danos - Larose | SHF9-F21 | 11920544 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09301902 | Name 4 | USMCS1 | 2019-10-01 | USSOLE | 2 | EA | 2 | CRN Boom Tip Platform Grating Deficiency | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WP XGI | TECO
60507050 | 508 | STB Vent N2 snuffing system rusting | S06 | General | 2020-03-10 | 2019-02-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.ZZZ-12707 | Cargo Vent Stacks N2 Stuffing System | 2019-06-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-11 | 113805000000 | 20 | 50 | 1002360784 | SB2N,B7,2H,UNC,5/8in,3.5in,DOXSTEEL | 2020-03-10 | Received at Worksite |  | 2019-06-07 |  | U182 | 8201 | Stones Main | ST KB B3 | 11380546 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-04-19 | USNSB4 | 4 | EA | 4 | Replace Rusted Components Starboard Vent | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MAOK WPOK ZPMM | EXEC
60628814 | 508 | Pitstop Damaged/Leaking Bulkhead fitting | S19 | Marine Systems | 2020-02-24 | 2019-04-24 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-89007A | Stabplate #4 Up Signal/Optical Connector | 2019-07-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-24 | 115186000000 | 10 | 10 | 7000003196 | 3/4" MEDIUM PRESSURE BULKHEAD | 2020-02-24 | Received at Worksite |  | 2019-07-22 |  | U182 | 8201 | Stones Main | ST KB B7A | 11518591 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-04-22 | USJDJW | 1 | EA | 1 | Replace Bulkhead Fitting | REL ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MAOK RUSH WPOK | EXEC |  |  | PU 6/16/19 AARON W.
60688041 | 508 | Subsea HPU hose with twisted assembly | S24 | Subsea Systems | 2020-02-18 | 2019-09-25 | O.US.STO.STO.002.724FP | 508MECH | US.WR508A.SE.OH.MS554-10000 | Subsea Hydraulic System | 2020-01-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 115853000000 | 10 | 10 | 7000000098 | 1" X 12.40" Hose FEMALE JIC EACH END | 2020-02-18 | Received at Worksite | 2020-01-16 | 2020-02-08 | 2020-02-28 | U182 | 8201 | Stones Main | ST1A2C | 11585327 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-09 | USMNF8 | 1 | EA | 1 | Replace kinked Hose SBMT0397 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A2C 01/30/2020 GG
60847988 | 508 | MOC GTG4 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-34000 | Gen #4 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 10 | 7000005903 | Amercable Part Number 37-102-308 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780943 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI79 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 120 | FT | 120 | SAEP LO/TO Isolate GTG #4 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60874068 | 508 | FRC inspection deficiencies | S15 | Life Saving | 2020-02-13 | 2020-03-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2019-08-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-03 | 118106000000 | 10 | 60 | 7000004662 | ARMS Lifeboat, Oil Level Sight Glass, | 2020-02-13 | Received at Worksite |  | 2020-02-13 |  | U182 | 8201 | Stones Main | ST KB C7 | 11810577 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-04 | USAWJB | 1 | EA | 1 | FRC inspection deficiencies | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD MAGN WPOK | EXEC |  |  | PU 02/16/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2160 | 1001267672 | HOT ORDER | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 238 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60973122 | 508 | MGC-B 3rd Stg Bridle Removal | S04 | Gas Compress | 2020-04-18 | 2020-09-25 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-10000 | Main Gas Compression System Train B | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-19 | 119235000000 | 10 | 50 | 7000002596 | BLT+N,A193-B7,CTD,UNC,9,7/8 | 2020-02-11 | Received at Target Location | 2020-01-06 | 2020-01-06 |  | U182 | 8270 | Danos - Amelia | 3RD Stage Suction | 11923512 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A361 | Name 2 | Name 59 | 2019-10-21 | USSOLE | 34 | EA | 34 | MGC-B 3rd Stg Bridle Removal MOC78183 | REL PRT GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU WPT AMW 11/30/19
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3870 | 1002301610 | SB2N,B8M CL2,8M,UNC,5/8in,3.50in | 2019-11-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 437 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10311902 | Name 2 | Name 2 | 2019-10-31 | USSOLE | 45 | EA | 45 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4050 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 455 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 50 | EA | 50 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3130 | 1001271538 | (PCM-0.23) | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 343 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6610 | 7000002629 | Elbow, 2", 90, SW, 400 PSIG WOG, ASME B | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 872 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 38 | EA | 38 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60737084 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-02-08 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-219 | Crude Oil to/from Fwd COT'S On/Off Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-08 | 116406000000 | 10 | 30 | 7000005901 | P.0244110029 AVC 02 CL1 A1 VPI MANIFOLD | 2020-04-28 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-10 | U182 | 8201 | Stones Main | ST KB B6 | 11640589 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635S-219 | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 40 | 7000002591 | 3" Gas sampling accumulator bulb for col | 2020-01-30 | Received at Worksite |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20G0138 | Name 26 | USKHU3 | 2020-01-14 | USLFA4 | 3 | EA | 3 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7800 | 7000002629 | Elbow, 1", 3000#, 45, SW, ASME B16.11, | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1050 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4580 | 1002316829 | GASW,CL300/600,316/316L,GPH,2in | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 510 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1270 | 7000002603 | 2" FLG PROTECTOR (FLANGE, 2", 300#, RF | 2019-12-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 143 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12101801 | Name 2 | Name 2 | 2018-12-11 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 620 | 7000002662 | PIPE, 8", S/40S (0.322 WT), ASTM A790 UN | 2020-02-13 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 816 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST01292001 | Name 4 | Name 4 | 2020-01-30 | USSOLE | 12 | FT | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 590 | 7000006110 | SLING,WEB,TUFFY,EEF2901P-04,2PLY,1inx4ft | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 776 | 4 | Non-Stock (Purchase Requisition) | N |  |  | SWR551A388 | Name 2 | Name 2 | 2020-01-27 | USSOLE | 8 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2220 | 1001676781 | Plate, 1/2" x 96" x 96", ASTM A572 Gr. 5 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 244 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7350 | 1001665196 | BLT HEX,A325,UNC,2.1/2in,5/8in,SERMAGARD | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 993 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-15 | USSOLE | 50 | EA | 35 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3810 | 1001708541 | WASHER,LOCK,F436,GALV,3/4in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 411 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 28 | EA | 28 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118371 | 508 | 2020 Lab Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 50 | 7000003852 | Acer KA220HQ bi 22" (21.5” viewable) Ful | 2021-03-11 | Received at Target Location |  | 2020-01-11 |  | U182 | 8201 | Stones Main | STONES | 12090728 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20OP001 | Name 27 | USRRIG | 2020-02-27 | USCDP7 | 1 | EA | 1 | 2020 Lab Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 30 | 7000003196 | SS-810-6 UNION | 2020-02-24 | Received at Worksite |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-09 | USNSB4 | 5 | EA | 5 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 30 | 7000003197 | HWKE DIRECT ITEM HAWKE M20 NYLON WASHER | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11780965 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | Name 58 | 2019-10-29 | USNSB4 | 4 | EA | 0 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC PRC SETC | APPR EOM MAGN WP ZPMM | Deleted
61212182 | 508 | FRC radio hand & head set | S15 | Life Saving | 2020-12-06 | 2021-02-14 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.GU.LS.CMRV-33331 | Rescue Boat VHF Radio | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-12-06 | 121986000000 | 10 | 10 | 7000003852 | Icom M424g21 Ic-m424 Vhf Marine Transcei | 2020-03-06 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12198570 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-25 | USAWJB | 1 | EA | 0 | Install New Radio in FRC | REL ESTC PRC SETC | APPR MAGN | Approved
60440621 | 508 | Replace Laydown Timber - MODs 15, 17, 19 | S40 | Cargo Handling | 2020-03-10 | 2020-06-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.LS | Loading Stations | 2019-08-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 113072000000 | 10 | 40 | 7000002583 | Carbon Steel Wood Drilling Bit, Spade St | 2020-03-10 | Received at Worksite |  | 2019-09-11 |  | U182 | 8201 | Stones Main | ST KB A1 | 11307214 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-06 | USAWJB | 5 | EA | 5 | Replace Laydown Timbers - MOD 15 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAOK RUSH WPOK | EXEC |  |  | PU KB A1
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 20 | 100 | 7000004211 | SEALING RING 42736124 151<(>,<)> 20071-3 | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11762536 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 1 | Replace pump cover on Jockey Pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved |  |  | ST1A2B 02/18/2020 CMR
60717786 | 508 | #3 latching dog cylinder bolts are broke | S19 | Marine Systems | 2020-02-18 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-21 | 116191000000 | 40 | 70 | 7000002596 | M24-3.0 PITCH X 65MM, SOCKET HEAD CAPSCR | 2020-02-18 | Received at Worksite |  | 2019-10-27 | 2020-02-07 | U182 | 8201 | Stones Main | Issued | 11619069 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 14 |  | 2019-05-21 | USMNF8 | 8 | EA | 8 | Replace broken bolts in the cylinder #3 | TECO PRT GMCO GMPS PRC SETC | XCNF MAGN MAOK NCMP WPOK XGI | TECO
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 410 | 7000002591 | 4452K163 Bushing Adapter, 3/8 Male x 1/ | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 41 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60891772 | 508 | Hiller Deficiencies | S13 | Fire Protect | 2020-03-21 | 2020-02-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2019-08-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-21 | 118312000000 | 10 | 10 | 7000000108 | AMEREX 23cuft N2 Cylinder (3817) | 2020-03-04 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | Issued | 11831177 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19CG112 | Cargo |  | 2019-08-19 | USABCE | 16 | EA | 16 | Hiller Deficiiencies | REL PRT GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1320 | 1001837029 | CAP PIPE SW,A105,CL3K,NPS1 | 2019-12-27 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 132 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A381 | Name 2 | Name 59 | 2019-12-24 | USSOLE | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 880 | 7000002591 | PS Doors Model LSG-24-PCY | 2020-02-02 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 88 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08261903 | Entity 3 | Name 59 | 2019-08-27 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 20 | 140 | 7000000068 | DK BOOT-2 Double Leg Shrink Boot Kit Cus | 2019-12-08 | Received at Target Location |  | 2020-02-28 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11614811 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI64 | Name 2 | USNSB4 | 2019-11-05 | USSOLE | 2 | EA | 2 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 40 | 7000004211 | ANS200x150x350/PN-13 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 2 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118149 | 508 | SC1 Shear pin limit switch ZS-88501-08 | S19 | Marine Systems | 2020-02-25 | 2020-06-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-88501 | Structural Connector No. 1 | 2020-02-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-25 | 120905000000 | 10 | 10 | 7000005901 | FIC-M12F4 CONNECTOR 4 PIN FEMALE | 2020-02-25 | Received at Target Location |  | 2020-02-16 |  | U182 | 8201 | Stones Main | Issued | 12090507 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 28 |  | 2019-12-23 | USAWJB | 10 | EA | 10 | SC1 Shear pin limit switch ZS-88501-08 | REL CNF ESTC PRC SETC | EXEC MAGN WPOK | EXEC
60975189 | 508 | XV-12202B-924 Fails to Open | S18 | Water Systems | 2020-02-07 | 2019-10-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.XV-12202B-924 | Filter Backwash On/Off Control Valve | 2019-10-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-02-07 | 119260000000 | 10 | 10 | 7000003464 | 4-150-BA02B SHIPHAM 4-150-BA02B 4" 150# | 2020-02-07 | Received at Worksite |  | 2020-01-20 | 2020-02-14 | U182 | 8201 | Stones Main | STAGED | 11925970 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-10-04 | USAWJB | 1 | EA | 1 | LOTO System - Confirm Isolation | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 500 | 7000000052 | Hex SDSS DBB Injection Quill | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 539 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN105 | Name 2 | Name 2 | 2019-11-22 | USLFA4 | 4 | EA | 4 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5080 | 7000002629 | BLEED RING, 2" , FULL FACE 150LB w/ (2) | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 569 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2130 | 1001816127 | GASW,CL300-600,316,GPH,NPS2 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 235 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 9 | EA | 9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 630 | 7000000052 | Det-Tronics Gas Detector | 2020-02-26 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 770 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN114 | Name 2 | Name 2 | 2020-01-23 | USSOLE | 4 | EA | 4 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5650 | 7000002629 | Elbow, 3", 45, S/10S, BW, ASME B16.9, A | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 659 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 17 | EA | 17 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 170 | 7000000133 | PMI Report of all balls, seats, stems, e | 2019-01-17 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 188 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN031 | Name 2 | Name 2 | 2019-01-16 | USGBI5 | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 530 | 7000002646 | 4" 150# RF FP WKM Floating Ball | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 542 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN104 | Name 2 | Name 2 | 2019-11-22 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6040 | 7000002629 | Elbow, 3", 45, BW, Class 700, ASME B16. | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 702 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 830 | 7000002591 | 13/16'' Hogan Bits REG mag drill bits | 2020-03-03 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia |  | 11179936 | 1073 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-28 | USLFA4 | 20 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60177919 | 508 | Mod 6 - vlv long bolts Diss metals | S04 | Gas Compress | 2020-06-01 | 2019-06-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VABL-771251 | Cooler Press Diff Transmitter Iso Valve | 2019-08-26 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-06-01 | 110146000000 | 10 | 10 | 7000002596 | 5/8-11 X 3-3/4 STUD BOLT A193 B8M SS | 2020-06-01 | Ready for Shipment after Kitting | 2019-10-29 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB D3 | 11014637 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-26 | USNSB4 | 4 | EA | 4 | LO/TO Shutdown Down Process Train, De-In | REL ESTC CSER GMPS PRC SETC | EXEC EOM MAGN MAKD MANX WPOK | EXEC |  |  | PU WPT 11-25-19
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 270 | 1001566525 | TUBING,SQUARE,A500-B,4x4x1/4in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 727 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231901 | Name 4 | Name 4 | 2019-12-24 | USSOLE | 20 | FT | 20 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7810 | 1001566530 | ELB SW,A182,90DEG,CL3000,1in | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1051 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 12 | EA | 12 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3300 | 7000002646 | Ball Valve, 1/2", VBT-1502D (See Attache | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 360 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161903 | Name 4 | Name 4 | 2019-10-16 | USLFA4 | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60352955 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-09 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33310 | No. 1 Port Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-10 | 112105000000 | 10 | 10 | 1001618989 | OIL FILTER,359-BUKH0202,ALXR-RYN | 2020-02-09 | Received at Worksite |  | 2019-10-20 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210547 | 1 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 | USAWJB | 2019-07-17 | USRAR6 | 1 | EA | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
61112406 | 508 | 2nd Stg Sep PST upgrade | S22 | Prod Gathering | 2020-04-11 | 2020-06-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.PST-66202-178 | 2nd Stg Separator Press Sfty Transmitter | 2019-12-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-11 | 120837000000 | 20 | 100 | 7000002583 | Service charge to tap holes in blind fla | 2020-04-11 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 12083677 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-12 | USMNF8 | 2 | EA | 2 | Upgrade PST-66202-178 To Rosemount Trans | REL ESTC GMPS PPRT PRC SETC | APPR EOM MAGN MAOK RUSH WPOK ZPMM | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 290 | 7000003852 | AstroAI ATG150 2 Pack Digital Tire Press | 2020-12-07 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES11 |  |  | 2019-11-11 | USABCE | 2 | EA | 2 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 640 | 7000003852 | GROZ Soft Face 14lb Sledge Hammer with 3 | 2020-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 64 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0011 | Name 29 | USRRIG | 2020-02-18 | USLFA4 | 4 | EA | 4 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61020713 | 508 | Stripping Pump lubricator broken | S21 | Oil Treating | 2020-02-11 | 2019-12-18 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.VE663-22000 | Cargo Stripping Pump System | 2019-11-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-11 | 119790000000 | 10 | 10 | 7000000038 | P/N 170 AUTOMATIC LUBRICATOR | 2020-02-11 | Received at Worksite | 2020-01-02 | 2020-01-20 | 2020-02-14 | U182 | 8201 | Stones Main | ST KB A3 | 11979035 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-06 | USAWJB | 1 | EA | 1 | Replace Stripping Pump Lubricator | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 2/5/2020 JH GG
60871421 | 508 | O/SI TEG Reboiler Stripping Gas PCV-001 | S39 | Gas Treating | 2020-03-10 | 2020-01-29 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.PCV-77211-001 | TEG Reboiler Pressure Control Valve | 2019-09-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-10 | 118080000000 | 20 | 10 | 1001816267 | GASW,CL300-600,316,GPH,NPS1 | 2020-03-10 | Received at Worksite |  | 2019-12-28 |  | U182 | 8201 | Stones Main | ST KB D1 | 11807985 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-23 | USNSB4 | 8 | EA | 8 | Replace 1" Fisher Valve TEG Reboiler Str | REL PRT GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU AMW 12/29/19
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 620 | 7000003852 | Wilton 11111 B.A.S.H Mechanics Hammer Ki | 2020-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 62 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0011 | Name 29 | USRRIG | 2020-02-18 | USLFA4 | 6 | EA | 6 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61155246 | 508 | Install Barring Device on MGCA | S04 | Gas Compress | 2020-03-03 | 2020-07-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-03 | 121329000000 | 10 | 70 | 7000003514 | 91104A033 (lock washers) | 2019-11-01 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST1A6C | 12132852 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0006 | Name 17 | JP832018 | 2020-01-27 | USLFA4 | 1 | BX | 1 | Install Barring Device on MGCA | REL PCNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC |  |  | ST1A6C 02/16/20 AMW
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 850 | 7000002591 | DRILLFORCE (5 Pcs) 1/2 in. x 6 in. HSS T | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 85 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 3 | EA | 3 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60717786 | 508 | #3 latching dog cylinder bolts are broke | S19 | Marine Systems | 2020-02-18 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-21 | 116191000000 | 50 | 50 | 7000003684 | QTY: 1 Master palm industrial low profil | 2020-02-18 | Received at Worksite |  | 2019-10-27 | 2020-02-07 | U182 | 8201 | Stones Main | ST1A2B | 11619069 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-05-20 | USMNF8 | 1 | EA | 1 | Replace broken bolts in the cylinder #3 | TECO PRT GMCO GMPS PRC SETC | XCNF MAGN MAOK NCMP WPOK XGI | TECO |  |  | PU Patrick G. 07/14/2019 CMR
60989319 | 508 | O/SI condensate return valve VAGA-115526 | S17 | Steam/Hot H2O | 2020-04-01 | 2020-04-05 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.VAGA-115526 | Stbd Condensate from COT 4 Iso Valve | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-02 | 119417000000 | 20 | 10 | 7000000104 | 2-1/2 Neway gate valve | 2020-04-01 | Received at Worksite | 2020-02-13 |  |  | U182 | 8201 | Stones Main | ST1A5B | 11941697 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-04 | USMNF8 | 1 | EA | 1 | Shut down steam system | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | ST1A5B AMW
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 180 | 1002316823 | GASW,CL150,316/316L,GPH,2in | 2019-11-26 | Received at Target Location |  |  | 2020-02-14 | U182 | 8270 | Danos - Amelia | Onsite Danos Has | 11882270 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI70 | Name 2 |  | 2019-11-12 | USABCE | 1 | EA | 1 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 100 | 7000003323 | Part# 200-B-SS | 2019-09-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 33 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN082 | Name 2 | Name 2 | 2019-08-19 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 40 | 7000002591 | 4548K136 1/4 NPT, 4" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 700 | 1001645341 | BLT HEX,A325,UNC,2in,3/4in,SERMAGARD | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 70 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 5 | EA | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 80 | 7000002591 | Acetone https://www.grainger.com/product | 2020-02-26 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOELEC020 | Name 30 | Name 30 | 2019-08-15 | USLFA4 | 1 | EA | 1 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU SHAWN 10/01/2019 CMR
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 90 | 7000002591 | 4548K156 3/8 NPT, 4" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60760710 | 508 | A/C Compressor Excessive Corrosion | S14 | HVAC | 2020-03-24 | 2019-11-19 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.DAL-10811 | Nav Bridge Dk Ba Air Handling Unit | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-26 | 116775000000 | 10 | 10 | 7000000086 | Nav/Bridge Deck Battery Room AC Unit (TA | 2020-03-24 | Received at Worksite | 2020-01-16 |  |  | U182 | 8201 | Stones Main | Warehouse floor | 11677535 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-14 | USNSB4 | 1 | EA | 1 | LO/TO & Hot Work Permit | REL PCNF ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPVS | Kit Complete |  |  | ST1FLR 01/30/2020 GG
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 20 | 100 | 7000000068 | DK 2256-27AC9 (1) 1/4" OD X .035" WALL T | 2019-12-08 | Received at Target Location |  | 2020-02-28 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11614811 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI64 | Name 2 | USNSB4 | 2019-11-05 | USSOLE | 100 | EA | 100 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
61163855 | 508 | PG369A analog gauge in need of replacmen | S04 | Gas Compress | 2020-03-10 | 2021-01-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.PG-77100A-369A | DE Lube Oil Supply Pressure Gauge | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 121428000000 | 10 | 10 | 7000000066 | 232.30 4 300PSI 1/2 L | 2020-03-10 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B7E | 12142828 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-23 | USAWJB | 1 | EA | 1 | PG369A analog gauge in need of replacmt | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6550 | 7000002629 | Tee, 3" x 3", .095 Min Wall, BW, ASME B1 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 866 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60840919 | 508 | Relocate PORT CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-02-25 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-25 | 117729000000 | 10 | 50 | 7000000101 | 1" Pipe Plug Stainless Steel 304 | 2020-02-25 | Received at Worksite | 2019-11-27 | 2020-01-20 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772907 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 5 | EA | 5 | Relocate Crane Slew G-box Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD MAOK NCMP WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5500 | 7000002629 | 1 1/2" 300 RFWN Flange Protectors | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 611 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 80 | 7000003197 | ¾” NPT Hawke 153AX/3/4”NPT | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 6 | EA | 6 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 950 | 7000005901 | Yellow / Green Heat Shrink 1/2" | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 955 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI87 | Name 2 | Name 2 | 2020-02-08 | USSOLE | 1 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 400 | 1000709154 | DIGITAL INPUT MODULE,ALLENB,1756-IB16D | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 426 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 6 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 70 | 7000004213 | KE35/10 SASAKURA KE35/10 TEE | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 820 | 7000003197 | SSW12VFC72 SS COV. 12W VFC STR 6FT | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 913 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 12 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 260 | 7000003852 | YETI Rambler 14 oz Stainless Steel Vacuu | 2020-12-07 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 26 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES11 |  |  | 2019-11-11 | USABCE | 2 | EA | 2 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 30 | 7000004213 | KE35/6 SASAKURA KE35 P/N:6 ELBOW | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7770 | 1001816127 | GASW,CL300-600,316,GPH,NPS2 | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1040 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 1000 | 7000005901 | M9F11220 | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 960 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI87 | Name 2 | Name 2 | 2020-02-08 | USSOLE | 1 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 10 | 7000002629 | Pipe, 500mm x 600mm LG., S/20, ASME B36. | 2020-03-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E27 | 11477345 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05141901 | Entity 2 | USAWJB | 2019-05-14 | USSOLE | 1 | EA | 1 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 410 | 1000712038 | VALVE,NEEDLE,1/2in,SS,H1RDS44Q,ANDRS-GR | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 54 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7000 | 1001210748 | U-BOLT,HDG,ARMORCOAT,3x1/2in,W/4NUT | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 948 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052001 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 13 | EA | 13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 40 | 7000003197 | MCT Frame, Roxtec EXBR00001002121 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 1 | EA | 1 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 70 | 7000002596 | Studs, M22 x 50mm LG., ASTM A193 Gr. B7 | 2020-03-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E27 | 11477345 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05141901 | Entity 2 | USAWJB | 2019-05-14 | USSOLE | 9 | EA | 9 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
60665886 | 508 | GS #1 Pump Discharge Valves Passing | S19 | Marine Systems | 2020-03-24 | 2019-09-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.BB.PBE-12301A | Bilge/Ballast/General Service Pump No. 1 | 2019-11-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-26 | 115603000000 | 10 | 10 | 7000004211 | 10K200AWC-AGNR-HW F-7472, Cast steel Scr | 2020-06-06 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11560292 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-22 | USNSB4 | 2 | EA | 0 | Rigging Services & Assist Replacement 8" | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6190 | 1001574896 | GSKT FLR,FF,CL150,1/8in,SF3300,2in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 717 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 36 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 530 | 1002360707 | SB2N,B7,2H,UNC,3/4in,4.5in,DOXSTEEL | 2020-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 767 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A382 | Name 2 | Name 2 | 2020-01-20 | USSOLE | 18 | EA | 18 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
61165414 | 508 | Install Needle Valve on PG-33120-731 | S13 | Fire Protect | 2020-03-10 | 2020-03-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33120-731 | FW Lift Pump Outlet Pressure Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-10 | 121447000000 | 10 | 10 | 1000719976 | COIMC,SWAGELOK,SS60016,3/8x3/8NPT | 2020-03-10 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144699 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 2 | EA | 2 | Install Needle Valve on PG-33120-731 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 20 | 100 | 7000005901 | AT2-420-24L-FT AC CURRENT TRANSDUCER | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11780965 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-11-04 | USNSB4 | 2 | EA | 0 | Install GTG #2 Vent Fan FANS MOC-71695 | REL ESTC PRC SETC | APPR EOM MAGN WP ZPMM | Deleted
60367921 | 508 | CARGO-Dummy Spade Replace COT 5S IG Line | S06 | General | 2020-03-20 | 2018-11-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127046 | COT 5 SB IG Main Manual Valve | 2019-05-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-22 | 112273000000 | 10 | 30 | 7000002596 | 5/16-18 1105/1280 SERMAGARD NUTS | 2020-03-20 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | Warehouse floor | 11227253 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-05-15 | USNSB4 | 56 | EA | 56 | CARGO-Dummy Spade Replace COT 5S IG Line | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | ST1FLR 2/3/20 GG
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1030 | 7000003852 | T.W Evans Cordage 27-302 1/4-Inch by 500 | 2021-03-31 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 103 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST20CG0146 | MarineForman | USRRIG | 2020-02-20 | USCDP7 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 20 | 70 | 7000004211 | Ball Bearing, 43216118 143 | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A2B | 11762536 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 1 | Replace pump cover on Jockey Pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved |  |  | ST1A2B 02/18/2020 CMR
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 220 | 7000002591 | 4548K223 1 NPT, 2" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60526908 | 508 | TG-77130A-311A BROKEN | S04 | Gas Compress | 2020-05-05 | 2019-12-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.TG-77130A-311A | CM Inlet Temperature Gauge | 2019-05-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-05-05 | 114027000000 | 10 | 20 | 7000005901 | TG-77130A-311A THI-100-A+AMX TEMPERATURE | 2020-05-05 | Not Shipped | 2020-02-21 |  |  | U182 | 8201 | Stones Main | STONES | 11402692 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 0 | Replace Produced Water Temperature Gauge | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD WPOK ZPMM | Kit Complete
60557093 | 508 | O/SI Passing Valve VABL-661050 | S22 | Prod Gathering | 2020-02-15 | 2019-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.FM.VABL-661050 | Test Fluids Manual Isolation Valve | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-15 | 114365000000 | 20 | 30 | 7000004211 | R45304OCT R45 OCT 304 SS API RING 6' 3-6 | 2020-02-15 | Not Shipped |  | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Delv 10/03-Wait on GR | 11436470 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-05-29 | USNSB4 | 2 | EA | 0 | Confirm VABL-661050 Replacement | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK RUSH WPOK XGI | TECO
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 280 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2020-04-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F90 | 11581210 | 28 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11201901 | Name 4 | Name 60 | 2019-11-20 | USABCE | 3 | EA | 3 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 170 | 7000002591 | 4548K193 3/4 NPT, 2" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1160 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2020-04-15 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F64 | 11581207 | 116 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111901 | Name 4 | Name 59 | 2019-11-12 | USSOLE | 38 | EA | 38 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61076060 | 508 | Install Drink & Ice Cream Machine | S09 | Bldg & Qtrs | 2020-03-17 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GU.BQ.ROOM-213 | Galley | 2019-12-01 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-03-17 | 120415000000 | 10 | 40 | 7000003852 | Panasonic 1700W Digital Commercial Micro | 2019-12-15 | Received at Worksite |  | 2020-02-21 |  | U182 | 8201 | Stones Main | Issued | 12041473 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Camp Boss |  | 2019-12-05 | USMNF8 | 1 | EA | 1 | Install Drink & Ice Cream Machine | REL PRT GMPS PRC SETC | SCHD WPOK | EXEC |  |  | DLVD GALLEY 12/27/19 GG
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 120 | 7000002591 | 2" x 27' U-Hook Ratchet Strap (including | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 2 | EA | 2 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
60661354 | 508 | O/SI Steam Inlet is Passing | S17 | Steam/Hot H2O | 2020-03-10 | 2019-09-07 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-337V | Steam to No. 2 COPT Isolation Valve | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 115550000000 | 30 | 30 | 7000004211 | ham-hand-150 HAMMER HANDWHEEL | 2020-05-09 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11555034 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-21 | USNSB4 | 1 | EA | 0 | Replace Valve 115-337V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 110 | 7000002591 | Neoprene Rubber, 1/8" x 4" wide x 12' lo | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 1 | EA | 1 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 120 | 7000002629 | 4" 150 # ASME B16.5 ASTM A105 CARBON EQU | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 638 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
61083783 | 508 | Swing Gates STBD CRN Interior Pedistal | S40 | Cargo Handling | 2020-03-16 | 2020-01-24 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-12-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-17 | 120503000000 | 10 | 20 | 7000000111 | Carriage bolts for crane swing gates | 2020-03-16 | Received at Target Location | 2020-01-09 |  |  | U182 | 8201 | Stones Main | STONES | 12050316 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-09 | USAMH7 | 9 | EA | 9 | Install Gates STBD CRN Pedistal Interior | REL PCNF PRT GMPS PRC SETC | APPR MAGN MAKD MAOK WPOK ZPMM | Kit Complete
60935864 | 508 | SWOS-Certify Offload Hose Tethers | S21 | Oil Treating | 2020-02-18 | 2019-11-01 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.ZZZ-66410 | Offloading Hose Reel | 2019-10-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 118810000000 | 20 | 20 | 7000000041 | proof load rope add 26mm polyester cover | 2020-02-18 | Not Shipped |  | 2019-10-18 | 2020-02-13 | U182 | 8201 | Stones Main | Stones/Turitella | 11881041 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-10-18 | USMNF8 | 2 | EA | 0 | Reinstall Offload Hose Tethers | TECO ESTC PRC SETC | XCNF MAGN NCMP WPOK XGI ZPMM | TECO
61219229 | 508 | GT #4 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-3 | Generator #4 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-21 | 122068000000 | 10 | 40 | 7000003763 | 8MX-80S-12 SPKT | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206813 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #4 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7220 | 1001566524 | TUBING,SQUARE,A500-B,3x3x1/4in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 980 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3260 | 1001708541 | WASHER,LOCK,F436,GALV,3/4in | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 356 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 160 | EA | 160 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2820 | 7000002662 | Pipe, 3", S/10S, ASME B36.19M, ASTM A790 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 312 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 300 | FT | 299.54 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 800 | 1001210571 | VBT-1502SS | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose |  | 11179936 | 1046 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-23 | USSOLE | 1 | EA | 1 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4830 | 7000002662 | PIPE 4" SCH 10S B.E., ASME B36.19M, ASTM | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 544 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60989629 | 508 | COPT SW #3 Pump mechanical seal leak | S18 | Water Systems | 2020-04-14 | 2019-12-06 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216C | No. 3 Main/COPT Condenser Cooling Pump | 2019-12-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-14 | 119420000000 | 10 | 10 | 7000004211 | Sleeve, SVS350M-22a | 2020-04-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11942032 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-13 | USMNF8 | 1 | EA | 0 | COPT SW #3 Pump mechanical seal leak | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7910 | 7000002591 | Safety Snap Hook, 7/16", Galv., Crosby-L | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1061 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60739068 | 508 | COT 5S IG netherlock fail to lock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127052 | COT 5 SB IG Vent Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642944 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4700 | 1002047398 | STL SECT MAR,BEAM,8.110in,4.015in,20ft | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 522 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 40 | FT | 40 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1470 | 1002309218 | SB2N,B7,2H,UNC,7/8in,5.00in,CTD | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 163 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 26 | EA | 26 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 70 | 7000005901 | MLTFC4H-LP316 50 PER PACK | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780965 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI77 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 1 | EA | 1 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 130 | 7000002596 | 0005 5601-XXXX 00000 1/4" BEAM CLAMPS | 2020-02-24 | Received at Target Location |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-15 | USNSB4 | 25 | EA | 25 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 50 | 7000002596 | M12 X 150 MM FULL THREAD STUDS WITH 2 NU | 2020-04-01 | Received at Worksite | 2019-12-19 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 12027172 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-01 | USAWJB | 2 | EA | 2 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 60 | 7000002629 | Eccentric Reducer, 3" x 2", S/80, ASME B | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60440621 | 508 | Replace Laydown Timber - MODs 15, 17, 19 | S40 | Cargo Handling | 2020-03-10 | 2020-06-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.LS | Loading Stations | 2019-08-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 113072000000 | 10 | 70 | 7000002583 | Black Sealant, Silicone, 10.3 oz. Cartri | 2020-03-10 | Received at Worksite |  | 2019-09-11 |  | U182 | 8201 | Stones Main | ST KB A1 | 11307214 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-06 | USAWJB | 4 | EA | 4 | Replace Laydown Timbers - MOD 15 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAOK RUSH WPOK | EXEC |  |  | PU KB A1
60737082 | 508 | O/SI Actuator Seal Test Failed 4 STBD | S21 | Oil Treating | 2020-03-24 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6634S-546 | Crude Oil to/from COT 4 SB Valve | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-24 | 116406000000 | 20 | 10 | 7000004212 | HAA-D10-RK HYD. ROTARY ACTUATOR - (DOUBL | 2020-03-24 | Received at Worksite | 2019-11-11 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB B8 | 11640587 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-03 | USNSB4 | 2 | EA | 2 | Repair Actuator XV-6634A-546 COT 4S | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 20 | 110 | 7000004211 | O-RING 42030536 3, 20070-039 | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A2B | 11762536 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 1 | Replace pump cover on Jockey Pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved |  |  | ST1A2B 02/18/2020 CMR
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 20 | 1001566524 | TUBING,SQUARE,A500-B,3x3x1/4in | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 40 | FT | 40 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 100 | 1001210571 | VBT-1502 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 55 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 1 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 190 | 7000003739 | COS102 Freight-Overnight Delivery | 2020-02-24 | Received at Target Location |  |  | 2020-02-26 | U182 | 8201 | Stones Main | STONES | 12155706 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 190 | 1002360784 | SB2N,B7,2H,UNC,5/8in,3.5in,DOXSTEEL | 2019-11-26 | Received at Target Location |  |  | 2020-02-14 | U182 | 8270 | Danos - Amelia | Onsite Danos Has | 11882270 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI70 | Name 2 |  | 2019-11-12 | USABCE | 5 | EA | 5 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 270 | 1002316829 | GASW,CL300/600,316/316L,GPH,2in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 72 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 3 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 460 | 7000002591 | 4452K171 Bushing Adapter, 3/4 Male x 1/2 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 46 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60557093 | 508 | O/SI Passing Valve VABL-661050 | S22 | Prod Gathering | 2020-02-15 | 2019-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.FM.VABL-661050 | Test Fluids Manual Isolation Valve | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-15 | 114365000000 | 30 | 10 | 7000004211 | 6" x 4" ANSI CLASS 1500 REDUCED PORT BAL | 2020-03-16 | Received at Worksite |  | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Delv 10/03-Wait on GR | 11436470 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 59 | 2019-05-29 | USNSB4 | 1 | EA | 1 | Replace Passing Valve VABL-661050 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK RUSH WPOK XGI | TECO |  |  | PU MIKE N 2/12/2020
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 70 | 7000004211 | ANS200x150x350/PN-24 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 2 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 130 | 7000003852 | HP 962 ¦ 4 Ink Cartridges¦ Black, Cyan, | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main |  | 12090697 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  |  | USRRIG | 2020-01-30 | USAWJB | 1 | EA | 1 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU AARON
60720325 | 508 | O/SI Steam Drain Valve Leaking | S17 | Steam/Hot H2O | 2020-03-10 | 2019-06-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGA-115586 | LP Steam at FR 68 Drain Valve | 2019-12-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-10 | 116218000000 | 20 | 10 | 7000004211 | BONNEY L1-12-LE 1, GATE 1 150# A105 RF F | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11621843 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-19 | USNSB4 | 1 | EA | 0 | Remove & Replace Steam Valve VAGA-11558 | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61218667 | 508 | Replace Lifeboat Rations & Water | S15 | Life Saving | 2020-12-10 | 2021-02-17 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.LB | Lifeboats | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-12-11 | 122061000000 | 10 | 10 | 7000004662 | Datrex Emergency Food Ration, 2400kcal | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12206109 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-25 | USAWJB | 80 | EA | 0 | Replace Lifeboat Rations & Water | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 30 | 1000709994 | UNIC,SWAGELOK,SS12106,3/4in | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 6 | EA | 6 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5060 | 7000002629 | SWAGE, CONC, 2" X 1" BLE X PSE SCH 40S, | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 567 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3140 | 1001271537 | (PCM-0.23) | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 344 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2730 | 7000002629 | Elbow, 3", 45, S/40S, BW, ASME B16.9, A | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 297 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 29 | EA | 29 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7930 | 7000003343 | Angle, L3 X 2 X .375, ASTM A36 | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1063 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-26 | USSOLE | 100 | FT | 100 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118789 | 508 | Hand Held Radio Order | S11 | Communications | 2020-04-22 |  | O.US.STO.STO.005.71300 | 508ET | US.WR508A.GU.CO.RAD | Radio and Satellite System | 2019-12-24 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-04-22 | 120912000000 | 10 | 10 | 7000003742 | MOTOROLA MOTO TURBO HANDHELD RADIO (AAH5 | 2020-04-22 | Received at Worksite | 2020-01-15 | 2020-01-24 | 2020-01-25 | U182 | 8201 | Stones Main | ET Office | 12091239 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 31 |  | 2019-12-24 | USAWJB | 6 | EA | 6 | Collect Hand Held Radio Order | TECO CNF ESTC GMPS PRC SETC | XCNF MAKD WPOK XGI | TECO |  |  | PU AARON W 01/24/20 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 990 | 1002309190 | SB2N,B8M CL2,8M,UNC,7/8in,5.50in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 115 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 158 | EA | 158 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2840 | 7000002629 | Tee, 3" x 3", S/10S, BW, ASME B16.9, AST | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 314 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4610 | 7000002629 | 2" Flange Protectors for Flange, 3", 300 | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 513 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1640 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 180 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 12 | EA | 12 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3600 | 1001663703 | BAR RND MTL,CS,1in | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Stones Solids Tie-in | 11179936 | 390 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161902 | Name 4 | Name 4 | 2019-10-17 | USGBI5 | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6620 | 7000002629 | Elbow, 2", 45, SW, 400 PSIG WOG, ASME B | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 873 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 12 | EA | 12 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7870 | 1001816213 | GASW,CL150,316,GPH,NPS1 | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1057 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 13 | EA | 13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3110 | 1001566525 | (PCM-0.23) | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 341 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 100 | FT | 100 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6080 | 1001627870 | FLG SO,C70600,FF,CL150,6in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 706 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
61175887 | 508 | LACT -Drain Valves Severely Corroded | S21 | Oil Treating | 2020-03-14 | 2020-03-25 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-24 | 121566000000 | 50 | 20 | 7000004751 | 1/2" X 3" Dox Steel Studs w/ Nuts | 2020-03-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12156642 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-25 | USNSB4 | 152 | EA | 0 | Replace Defective Valves On LACT Skid | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60839934 | 508 | Replace Broken Lamp Cover in ER | S03 | Elect. Systems | 2020-04-25 | 2020-07-06 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES | Electrical Systems | 2019-07-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-25 | 117719000000 | 10 | 10 | 7000002591 | 00000 PAULUHN # FP232L Replacement Cover | 2020-04-25 | Received at Worksite | 2019-11-13 | 2019-12-04 |  | U182 | 8201 | Stones Main | ST1A6C | 11771872 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-05 | USRAR6 | 1 | EA | 1 | Replace Broken Lamp Cover in ER | REL ESTC CSER GMPS PPRT PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60717786 | 508 | #3 latching dog cylinder bolts are broke | S19 | Marine Systems | 2020-02-18 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-21 | 116191000000 | 50 | 80 | 7000002596 | M24-3.0 PITCH X 75MM, SOCKET HEAD CAPSCR | 2020-02-18 | Received at Worksite |  | 2019-10-27 | 2020-02-07 | U182 | 8201 | Stones Main | Issued | 11619069 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 14 |  | 2019-05-21 | USMNF8 | 8 | EA | 8 | Replace broken bolts in the cylinder #3 | TECO PRT GMCO GMPS PRC SETC | XCNF MAGN MAOK NCMP WPOK XGI | TECO |  |  | PU Aaron 06/11/2019 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 610 | 1000718629 | PIPE,2-3/8,SCH 40,3.65#,BEVEL,0.,2674760 | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 61 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 21 | FT | 22.4 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60891772 | 508 | Hiller Deficiencies | S13 | Fire Protect | 2020-03-21 | 2020-02-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2019-08-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-21 | 118312000000 | 10 | 60 | 7000000108 | Ansul Odorizer (42278) | 2020-03-04 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | Installed | 11831177 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19CG112 | Name 32 |  | 2019-08-19 | USABCE | 1 | EA | 1 | Hiller Deficiiencies | REL PRT GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved |  |  | PU AMW 12/29/19
61195386 | 508 | CAT 3 CAIR3625 dissimilar metal contact | S10 | Chem Injection | 2020-03-30 | 2021-02-02 | O.US.STO.STO.005.724FP | 508DANOS | US.WR508A.GU.CI.TS128-11000 | Biocide Injection System | 2020-02-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-30 | 121785000000 | 10 | 10 | 7000003852 | Neoprene Rubber Sheet, Rolls, Strips 1/8 | 2020-03-30 | Received at Worksite | 2020-02-12 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B6 | 12178538 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-09 | USMNF8 | 1 | EA | 1 | CAT 3 CAIR3625 dissimilar metal contact | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 80 | 7000004213 | KE35/11 SASAKURA KE35 P/N 11 GLOBE VALVE | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 21 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 500 | 7000003852 | Fluke TLK289 Industrial Master Test Lead | 2021-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 50 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN012620A | Name 3 | USRRIG | 2020-02-12 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 170 | 1002064535 | BLT HEX,A325,UNC,1/2in,1.1/4in,SERMAGARD | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 10 | EA | 10 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60749169 | 508 | TFR-44301B cooling fin leaks. | S03 | Elect. Systems | 2020-05-01 | 2019-07-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.TFR-44301B | Essential Transformer | 2019-10-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-05-08 | 116544000000 | 10 | 20 | 7000003945 | 550 Gallon Empty Tote Tank | 2020-05-01 | Not Shipped |  | 2020-02-22 |  | U182 | 8201 | Stones Main | Stones | 11654425 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAWJB | 2020-02-19 | USRAR6 | 1 | EA | 0 | Stage All Materials & Tote Tanks To Main | REL PCNF PRT PRC SETC | APPR MAGN RUSH WP | EXEC
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 60 | 7000004211 | ANS200x150x350/PN-23 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 2 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 190 | 7000002591 | 4548K196 3/4 NPT, 4" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61219225 | 508 | GT #5 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-4 | Generator #5 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 50 | 7000003763 | 2012 1-7/16 BUSHING | 2020-04-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206809 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #5 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 80 | 7000006081 | P45-304-050 ELBOW 45 DEGREE FTG.S/S | 2020-04-29 | Received at Target Location | 2020-02-13 |  | 2020-02-22 | U182 | 8201 | Stones Main | STONES | 11772908 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-13 | USAWJB | 4 | EA | 4 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 70 | 7000003852 | Extreme Max 3006.6611 BoatTector Stainle | 2020-01-15 | Received at Worksite |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO2CG0137 | Name 26 | USCRFI | 2020-01-14 | USLFA4 | 5 | EA | 5 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU CAPT. TIM
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7620 | 1001267393 | ANGL MTL,EQ,STL,20ft,L3x3x3/8in | 2020-02-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1025 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-21 | USLFA4 | 80 | FT | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2780 | 1001759324 | SB2N,A193B8MCL2,UNC,4.5in,3/4in | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 302 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 432 | EA | 432 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6670 | 7000002629 | Blind Flange, 4", 150#, FF, ASME B16.5, | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 878 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 540 | 1001704804 | LUG,COMPRESSION,FCIBRNDY,YA28L4BOX,3/8in | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 846 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 50 | EA | 50 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 630 | 7000002629 | THREAD-O-LET, 8" X 1/2", 6000#, FS, MSS- | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 79 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4360 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-11-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 488 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11131902 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 156 | EA | 156 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 90 | 7000006081 | BV-SS-FP 050 1/2 BALL VALVE 2000 PSI S/S | 2020-04-29 | Received at Target Location | 2020-02-13 |  | 2020-02-22 | U182 | 8201 | Stones Main | STONES | 11772908 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-13 | USAWJB | 4 | EA | 4 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 160 | 7000002603 | Gaskets 3" 300# FR 1/8" THK SPIRAL WOUND | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 642 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 6 | EA | 6 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5640 | 7000002629 | Elbow, 2", LR 90, S/40S, BW, ASME B16.9 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 658 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 420 | 1001736206 | CONNECTOR,CABLE,APPLETON,TMC2-075075A,Al | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 834 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 4 | EA | 4 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60806311 | 508 | Door Latch Broken And Door Gasket | S21 | Oil Treating | 2020-03-03 | 2019-12-18 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.OT.SS.ZZZ-66601 | Laboratory Package | 2019-07-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-03 | 117323000000 | 10 | 20 | 7000003852 | Weather Stripping Door/Window Seal Strip | 2020-03-03 | Received at Worksite |  | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B6 | 11732256 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-15 | USMNF8 | 2 | EA | 2 | Door Latch Broken And Door Gasket | REL CNF PRT GMPS PRC SETC | SCHD MAGN MAOK WPOK | EXEC |  |  | ST1A1B 02/16/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6030 | 7000002629 | Elbow, 3", LR 90, BW, Class 700, ASME B | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 701 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 7 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 80 | 7000003852 | SCIONE Fidget Spinner Metal 5 Pack Stain | 2021-05-26 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main | STONES | 11419724 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19BBSM1 | Name 11 | USKHU3 | 2019-10-15 | USLFA4 | 10 | EA | 10 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/01/19 J WELBOURN
60959167 | 508 | Ballast Pump #1 Suction Px Gauge | S19 | Marine Systems | 2020-02-04 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.BB.PG-11201A-246 | Ballast Pump No. 1 Suct Pressure Gauge | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-04 | 119075000000 | 20 | 10 | 7000000062 | WK 9361103 Mfr: WIKA INSTRUMENT CORP M | 2020-02-04 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7D | 11907503 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 33 | USNSB4 | 2019-10-21 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge, Ballast Pump #1 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD WPOK XGI | TECO |  |  | PU AARON W 01/19/2020
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 120 | 7000002603 | 1/2" Flange Protector for 1/2", 150#, RF | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 1 | EA | 1 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 70 | 7000006192 | SSH2-63Y 1/4" FNPT; 316SS 5,000PSI; Nippl | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 37 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-17 | USSOLE | 29 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
61015475 | 508 | MGC B-TT-77100B-374B need to be replaced | S04 | Gas Compress | 2020-04-07 | 2020-04-21 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.TT-77100B-374B | NDE Lube Oil Return Temp Transmitter | 2019-11-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-07 | 119725000000 | 20 | 10 | 1002407400 | TRTE,YOKOGAWA,YTA610-JA1C-4DJ/N4/SU2 | 2020-04-07 | Not Shipped | 2020-02-04 |  |  | U182 | 8201 | Stones Main | Stones | 11972503 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 | USNSB4 | 2019-11-18 | USNSB4 | 1 | EA | 0 | Replace Yokogawa Transmitter & Temperatu | REL GMPS PRC SETC | APPR EOM MAGN MAKD MAOK RUSH WPOK ZPMM | Kit Complete
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 180 | 7000000039 | One(1) Det-tronics Q1201C 1001 X-Series | 2020-02-28 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20ACR00 | Name 9 | USCRFI | 2020-01-28 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 10 | 1000710324 | FTG_PIPE,PLUG,3/4",316 SS | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 46 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 3 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 340 | 7000002591 | 22mm 1/2” drive crowfoot socket. Part nu | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 34 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0140 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 900 | 7000002591 | AMES 1160200 60 in. Wedge-Point Crowbar, | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 90 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 50 | 7000006192 | HLS3DBB8M8FMGP4FNC 1/2" MNPT x 1/2" FNPT (3 | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 35 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-17 | USSOLE | 9 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
60958245 | 508 | Slew Drive Mounting Bolts- STBD CRN | S40 | Cargo Handling | 2020-02-25 | 2020-09-17 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2020-02-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-25 | 119064000000 | 20 | 20 | 1002386497 | OIL,LUBT,SHELL,OMALA S2 G 150,5gal | 2020-02-25 | Received at Target Location | 2020-02-22 | 2020-02-22 | 2020-02-22 | U182 | 8201 | Stones Main | MOD 22 GRN Mile | 11906448 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-12 | USAMH7 | 6 | PAI | 6 | CAN USA Assist Relocate Crane Slew Gearb | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF EOM MAGN MAKD MAOK RUSH WPOK XGI | TECO
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 550 | 7000003852 | EDjr-5T EDjunior Dillon Dynamometer with | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | Stones | 12090727 | 55 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Entity 3 | USRRIG | 2020-02-13 | USJRF5 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61175082 | 508 | N2 Comp. A low pres. and output | S19 | Marine Systems | 2020-03-13 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87409A | Turret Centralised HPU N2 Intensifer A | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-15 | 121557000000 | 10 | 10 | 7000000047 | N2 Intensifier Piston Ring Kit | 2020-03-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12155720 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAWJB | 2020-01-28 | USRAR6 | 1 | EA | 0 | N2 Comp. A low pres. and output | REL ESTC PRC SETC | APPR MAGN WP | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 50 | 1001627957 | PIPE MET,A106 GR-B,STD,3/4in | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 20 | FT | 21 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 80 | 7000000039 | YMD-8524 HOSE ASSEMBLY X27"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2420 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2019-04-08 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 264 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011905 | Name 2 | Name 2 | 2019-04-02 | USSOLE | 124 | EA | 124 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 530 | 7000003198 | #4/0 Green / Yellow Insulated Ground Wi | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 845 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 150 | FT | 150 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2380 | 7000002591 | Fabreeka Pad 1/4" THK x 5 1/2" x 28 5/8 | 2019-04-08 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 260 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011905 | Name 2 | Name 2 | 2019-04-02 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 30 | 7000000133 | 12ga. 316 SS 20"x18"x5" T-Card Box | 2020-02-15 | Not Shipped |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  | HSESTO002 | Name 21 | USKHU3 | 2020-01-09 | USLFA4 | 2 | EA | 0 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2450 | 1001645341 | BLT HEX,A325,UNC,2in,3/4in,SERMAGARD | 2019-04-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 267 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04021905 | Name 2 | Name 2 | 2019-04-03 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 830 | 7000003197 | PL SSW6VIB9024 SS BARRIER 6IND TRAY IV-9 | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 914 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 2 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 20 | 7000002591 | Locker- Red Flame-Resistant Resin and Sh | 2021-02-28 | Received at Worksite |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | HSESTO001 | Name 21 | USCRFI | 2020-01-08 | USLFA4 | 1 | EA | 1 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU M. WILSON 02/25/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 900 | 1001816207 | GASW,CL150,316,GPH,NPS8 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 106 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 200 | 7000002596 | Beam Clamps 1/4"-20 Tap Holes TNB 510 | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 50 | EA | 50 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
61098380 | 508 | Biocide Chemical Inj for Cargos & Drains | S21 | Oil Treating | 2020-09-28 | 2020-11-27 | C.US.STO.FI.19.012.1230A | 508CI&E | US.WR508A.OT.SS.VE663-70000 | Cargo Tank Systems | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-09-28 | 120671000000 | 10 | 60 | 7000000052 | CUSTOM GASKET 20-1/4"OD X 12-1/2"ID,ON A | 2020-04-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 12067106 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI76 | Name 2 | Name 61 | 2020-02-06 | USSOLE | 12 | EA | 10 | Biocide Chemical Inj for Cargos & Drains | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 60 | 7000003852 | Sojourner 9PCS Seamless Bandanas Face Ma | 2021-05-26 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main | STONES | 11419724 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19BBSM1 | Name 11 | USKHU3 | 2019-10-15 | USLFA4 | 5 | EA | 5 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/01/19 J WELBOURN
61104116 | 508 | Rm 418 PAGA speaker not working | S11 | Communications | 2020-02-18 | 2020-12-08 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.GU.CO.CMPI-565AC50-3 | Loudspeaker Safe Area C Dk Cabin 418 | 2019-12-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-18 | 120737000000 | 10 | 10 | 1002408830 | LOUDSPEAKER,DNH,SAFE-561T,6W,100V | 2020-02-18 | Received at Worksite |  | 2020-02-06 | 2020-02-23 | U182 | 8201 | Stones Main | ST1A7 | 12073693 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  |  |  | 2020-02-06 | USMNF8 | 1 | EA | 1 | Tblshoot Rm 418 PAGA speaker A | TECO CNF PRT GMPS PRC SETC | XCNF MAOK SFIX XGI | TECO |  |  | ST1A1C 02/07/2020 CMR
61188789 | 508 | TSE Turret CPE missing Backup Regulator | S20 | Monitor & Ctrl | 2020-02-11 | 2020-04-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MC.SH.CPE-55310 | Collar Deck Fusible Loop Panel | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-12 | 121714000000 | 10 | 10 | 1001577311 | REGULATOR,FLTR,NORGREN,B38-444-A1LA | 2020-02-11 | Received at Worksite |  | 2020-02-05 | 2020-02-14 | U182 | 8201 | Stones Main |  | 12171381 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  |  |  | 2020-02-05 | USMNF8 | 1 | EA | 1 | Install Backup Regulator PCV-55310-002 | TECO CNF PRT GMPS PRC SETC | XCNF MAOK WPOK XGI | TECO |  |  | ST1A1C 02/07/2020 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1290 | 1001676333 | BLT HEX,A325,UNC,2.1/4in,5/8in | 2020-05-14 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | Crane Access Platform | 11581207 | 129 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A372 | Name 2 | Name 59 | 2019-12-09 | USSOLE | 20 | EA | 20 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 280 | 7000002603 | 2" Flange Protector 2", 150#, RF | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 28 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1030 | 7000002591 | 13/16'' X 2'' DOC, 9200SE 92SE152. Reg | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 103 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 6 | EA | 6 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 990 | 7000003852 | Louisville Ladder 4-Foot Fiberglass Step | 2021-03-31 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 99 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST20CG0146 | MarineForman | USRRIG | 2020-02-20 | USCDP7 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 300 | 7000002603 | Flange Protectors 2", 600#, RF | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 126 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60847991 | 508 | MOC GTG1 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-04000 | Gen #1 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117810000000 | 10 | 30 | 7000005901 | M20 Nylon Washer | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780966 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI76 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #1 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 520 | 7000003852 | Fluke-289/FVF FlukeView Forms Combo Kit | 2021-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 52 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN012620A | Name 3 | USRRIG | 2020-02-12 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60975381 | 508 | Passing Valve on MGC B VAMO-771092 | S04 | Gas Compress | 2020-07-22 | 2020-09-26 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VAMO-771092 | Pressure Transmitter Isolation Valve | 2019-12-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-07-22 | 119261000000 | 20 | 10 | 7000004211 | 2MO12-F (2" #1500) MSB4 Monoflange-Sliml | 2020-08-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11926125 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-02 | USNSB4 | 1 | EA | 0 | Replace VAMO-771092 on MGC-B. 2nd Level | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 230 | 7000002591 | 3/4" G-2130 Shackle, 4 3/4T 1019515 | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 1 | EA | 1 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 220 | 7000003852 | CyeeLife 15 Packs-Soft tip Darts 18 Gram | 2020-03-16 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN020720A | Name 3 | USCRFI | 2020-02-09 | USLFA4 | 4 | EA | 4 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | DLVD OIM 02/20/2020 GG
60701397 | 508 | Leaking Globe/Check Valve on Hydrophore | S18 | Water Systems | 2020-04-11 | 2019-10-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.121-20V | Tank Outlet Check Valve | 2020-01-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-11 | 116003000000 | 10 | 60 | 7000004211 | Gasket-10, 5K 40MM GARLOCK GASKET FULL F | 2020-02-11 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | Stones | 11600310 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-28 | USAWJB | 2 | EA | 2 | LO/TO Perform Isolations To Repair Globe | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MANX WPOK ZPMM | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 40 | 7000002591 | Grainger SAE Wrench set #1WNB7 | 2020-01-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0005 | Name 8 | USCRFI | 2020-01-13 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU ARCHIE 01/29/20 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7890 | 7000003515 | Chain, 3/16" Proof Coil, Galv. | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1059 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60696550 | 508 | Spare parts for MGC's | S04 | Gas Compress | 2020-02-09 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GC | Gas Compression | 2020-02-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-02-09 | 115950000000 | 10 | 10 | 7000000033 | Ring Set Renewal: D-R Part No: 100019535 | 2020-02-09 | Received at Worksite |  |  | 2020-02-10 | U182 | 8201 | Stones Main | ST1A2B | 11595045 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-04-11 | USRAR6 | 5 | EA | 5 | Check in spare compressor parts | TECO ESTC GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO |  |  | PU Marty 06/10/2019 Per Aaron
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5760 | 7000002644 | Ball Valve, 3/4", VBT-1502D (See attache | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 670 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 930 | 1001816205 | GASW,CL150,316,GPH,NPS12 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 109 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 30 | 7000003196 | Swagelok SS-1610-3 | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 3 | EA | 3 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60744548 | 508 | LER port side doors leaking water | S09 | Bldg & Qtrs | 2020-03-21 | 2020-05-03 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.BQ | Buildings/Quarters | 2019-11-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-21 | 116489000000 | 10 | 20 | 7000004211 | D2.1 Class H120, STL. WEATHER & GAS TIGH | 2020-03-21 | Received at Target Location | 2020-02-03 |  |  | U182 | 8201 | Stones Main | Stones | 11648860 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-08 | USAWJB | 1 | EA | 1 | Replace LER doors | REL ESTC GMCO GMPS PPRT PRC SETC | APPR MAGN MAKD MAOK RUSH WP | Kit Complete
61155246 | 508 | Install Barring Device on MGCA | S04 | Gas Compress | 2020-03-03 | 2020-07-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-03 | 121329000000 | 10 | 20 | 7000002591 | 2636A32 (1/2" NC taper thread tap) | 2019-11-01 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST1A6C | 12132852 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0006 | Name 17 | JP832018 | 2020-01-27 | USLFA4 | 2 | EA | 2 | Install Barring Device on MGCA | REL PCNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC |  |  | ST1A6C 02/16/20 AMW
61208363 | 508 | Latching Dog Tubing to Hose Replacement | S19 | Marine Systems | 2020-04-02 | 2020-04-11 | P.US.STO.NF.20.010.7240A | 508ACR | US.WR508A.MA.PS.ZZZ-87412A | BTM Bouy Stinger Bell | 2020-02-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-04-02 | 121937000000 | 50 | 20 | 7000000098 | 12MJ X 12MB SS Stainless Steel Adapter | 2020-04-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12193721 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-20 | USNSB4 | 12 | EA | 0 | Replace Tubing Lines With Hose, Latching | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 150 | 7000002591 | 1-1/2” ASME CLASS 150 FLANGE RF THRD SCH | 2019-10-18 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 39 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN091 | Name 2 | Name 2 | 2019-09-23 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60367921 | 508 | CARGO-Dummy Spade Replace COT 5S IG Line | S06 | General | 2020-03-20 | 2018-11-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127046 | COT 5 SB IG Main Manual Valve | 2019-05-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-22 | 112273000000 | 10 | 20 | 7000002596 | 5/16-18 X 1" 1105/1280 SERMAGARD BOLTS | 2020-03-20 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | Warehouse floor | 11227253 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-05-15 | USNSB4 | 32 | EA | 32 | CARGO-Dummy Spade Replace COT 5S IG Line | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | ST1FLR 2/3/20 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1120 | 1001663819 | SHT PLT SLD MET,4x4ft,1/8in | 2020-04-15 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F64 | 11581207 | 112 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111901 | Name 4 | Name 59 | 2019-11-12 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60507050 | 508 | STB Vent N2 snuffing system rusting | S06 | General | 2020-03-10 | 2019-02-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.ZZZ-12707 | Cargo Vent Stacks N2 Stuffing System | 2019-06-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-11 | 113805000000 | 10 | 20 | 7000000039 | 5203871 NON-RETURN VALVE AC FOR T-VALVE | 2020-06-08 | Received at Worksite |  | 2019-06-07 |  | U182 | 8201 | Stones Main | 1 in ST KB B3 | 11380546 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-04-09 | USNSB4 | 8 | EA | 8 | Replace Rusted Components Starboard Vent | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MAOK WPOK ZPMM | EXEC
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 40 | 7000003852 | StarTech.com USB 3.0 to Gigabit Ethernet | 2020-03-31 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | CAOA021320 | Name 12 | USRRIG | 2020-02-19 | USLFA4 | 4 | EA | 4 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1060 | 7000003852 | RIDGID 31100 Model 818 Aluminum Straight | 2021-03-31 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 106 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST20CG0146 | MarineForman | USRRIG | 2020-02-20 | USCDP7 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 400 | 7000002591 | 4452K436 Tee Connector, 1 NPT Female | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 40 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61218667 | 508 | Replace Lifeboat Rations & Water | S15 | Life Saving | 2020-12-10 | 2021-02-17 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.LB | Lifeboats | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-12-11 | 122061000000 | 10 | 20 | 7000004662 | Datrex Water, DX1000W<(>,<)> 4oz (125ml) | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12206109 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-25 | USAWJB | 1920 | EA | 0 | Replace Lifeboat Rations & Water | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 50 | 7000002591 | 4548K137 1/4 NPT, 5" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 320 | 7000002591 | Rust-Oleum 7564838 Professional High Per | 2020-02-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 32 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 6 | EA | 6 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60172773 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-04-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.96T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 110086000000 | 10 | 60 | 7000002591 | 40mm Flange Protectors | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008582 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081902 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 6 | EA | 6 | MOC missing steam trap | REL PCNF ESTC GMCO GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 100 | 7000002591 | 4548K157 3/8 NPT, 5" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 230 | 7000002591 | ROD, BRASS 360 ¾ DIA x 3 Ft L,, | 2020-03-16 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO115EREN | Name 33 | USCRFI | 2020-02-09 | USLFA4 | 3 | EA | 3 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4930 | 7000002629 | FLANGE, 4" 150 LB RFWN SCH 40 ASTM A105 | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 554 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 21 | EA | 21 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7180 | 1001991793 | PIPE MET,API 5L-X42,BARE,40,1.1/2in,SRL | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 976 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 220 | FT | 222.9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60562362 | 508 | O/SI Passing Valve 3rd stage PST-330A MG | S04 | Gas Compress | 2020-03-10 | 2019-03-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VAMO-771031 | Pressure Transmitter Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 114424000000 | 20 | 10 | 1002360812 | SB2N,B7,2H,UNC,1in,13in,DOXSTEEL | 2020-03-10 | Not Shipped |  | 2020-02-07 |  | U182 | 8201 | Stones Main | ST1A3C | 11442408 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-01-21 | USNSB4 | 8 | EA | 0 | Replace Defective Valve 3rd stage PST-33 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 360 | 1002059414 | CBL ELEC ARM FIRE,600V,3,12AWG | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 828 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 160 | FT | 160 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2560 | 7000002629 | PLUG, 1/2", SC, HEX HEAD, ASTM A182 GR F | 2019-04-22 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 278 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04081901 | Name 2 | Name 2 | 2019-04-08 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 140 | 7000002629 | WELD-O-LET, 14" X 2" (2" S/XXS (0.436 WT | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 27 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 510 | 7000000052 | Documentation | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 540 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN105 | Name 2 | Name 2 | 2019-11-22 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6450 | 1000716158 | GSKT,SPW,316L,GRAPH,CG,CS,2in,300# | 2020-02-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 809 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01282001 | Name 4 | Name 4 | 2020-01-29 | USDKFB | 9 | EA | 9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 420 | 7000002591 | 27 x 40 Polypropylene Bag, Wht Rice Sack | 2020-01-20 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 751 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A373 | Name 2 | Name 2 | 2020-01-14 | USSOLE | 48 | EA | 48 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 540 | 7000000052 | Solids Handling Control Panel w/o Panel | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 616 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN106 | Entity 4 | Entity 4 | 2019-11-26 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 100 | 7000002646 | 1/2" Anderson Greenwood Duplex Needle Valv | 2019-02-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN038 | Name 2 | Name 2 | 2018-11-28 | USSOLE | 4 | EA | 4 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 90 | 1000712038 | VNT-2505 | 2019-02-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN038 | Name 2 | Name 2 | 2018-11-28 | USSOLE | 10 | EA | 10 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
61035030 | 508 | TDR Corroded bolts on Sea riser clamps | S06 | General | 2020-04-01 | 2020-05-03 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GN.MI.RI | Risers | 2019-12-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-01 | 119955000000 | 10 | 10 | 7000002596 | M30-3.5 X 230MM GR 8.8 HEX BOLT | 2020-04-01 | Received at Worksite | 2020-01-17 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST1A3A | 11995472 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-11 | USMNF8 | 24 | EA | 24 | Replace Riser clamp bolts | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A3B 02/3/20 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4190 | 7000002596 | Square U-Bolt (Galv.) w/(4) Nuts (Galv.) | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 469 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 15 | EA | 15 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2870 | 7000002629 | Threadolet, 2" x 1/2", 3000#, FS MSS-SP- | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 317 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60884538 | 508 | 12pack N2 bottles rack 3600psi | S08 | Air Systems | 2020-02-18 | 2020-02-05 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.TS118 | Topsides Air & Nitrogen Systems | 2019-09-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-18 | 118225000000 | 10 | 20 | 7000000122 | Rental fee for item 0010 for 6 months | 2020-02-18 | Received at Target Location | 2020-01-08 | 2020-01-24 | 2020-01-26 | U182 | 8201 | Stones Main | Stones | 11822473 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-10 | USABDF | 184 | EA | 184 | 12pack N2 bottles rack 3600psi | TECO CNF ESTC GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 40 | 7000002591 | Stud, 7/8" x 5", ASTM A193 Gr. B7 w/ASTM | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 66 | EA | 66 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 30 | 7000005901 | M20 Nylon Washer | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780965 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI77 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 140 | 1001210745 | PIPE MET,SA106 GR.B,XH,1.1/2in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 21 | FT | 21 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1090 | 7000003852 | GEARWRENCH 49 Pc. 1/2" Drive 6 Point 120 | 2021-03-31 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 109 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST20CG0146 | MarineForman | USCRFI | 2020-02-20 | USCDP7 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 50 | 7000000052 | Norgren Filter / Regulator | 2019-07-17 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia |  | 11545759 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN073 |  |  | 2019-06-17 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 30 | 7000004213 | KE35/6 SASAKURA KE35 P/N:6 ELBOW | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 16 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 90 | 7000002596 | Stud, 1" x 7.5" LG., ASTM A193 Gr. B8M C | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 105 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 54 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 440 | 7000000098 | 1" RENEGADE BLUE EACH 1" X 12FT CHEMICAL | 2020-03-16 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 44 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOET00120 | Name 3 | USCRFI | 2020-02-09 | USLFA4 | 3 | EA | 3 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1 FLR 2/24/2020 GG
61074272 | 508 | Centralized HPU Motor A bad relay. | S19 | Marine Systems | 2020-04-22 | 2020-05-27 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.MA.PS.PBE-89021A | Turret Centralized HPU Pump 1/A | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-22 | 120397000000 | 10 | 20 | 7000005901 | AW101651 FUSE M 4A | 2020-04-22 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12039690 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-20 | USAWJB | 10 | EA | 0 | Centralized HPU Motor A bad relay. | REL ESTC CSER GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 390 | 7000002591 | Steel Drawer Bin Cabinet, 33-3/4"W x 11- | 2020-02-28 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 39 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WHSE26JAN2 | Name 19 | USHBE9 | 2020-02-04 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 02/18/2020 ST1FLR1
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1170 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2020-04-15 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F64 | 11581207 | 117 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111901 | Name 4 | Name 59 | 2019-11-12 | USSOLE | 38 | EA | 38 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 90 | 1002301612 | SB2N,B8M CL2,8M,UNC,3/4in,3.50in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 54 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 4 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 30 | 7000002591 | Evapo-Rust Original Super Safe Rust Remo | 2020-02-04 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | DIISTO1927 | Entity 1 | USJRF5 | 2020-01-28 | USLFA4 | 1 | EA | 2 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 40 | 7000000039 | YMD-8529 HOSE ASSEMBLY X33"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60959162 | 508 | COP #3 Disch Px Gauge | S21 | Oil Treating | 2020-02-04 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PG-66301C-342C | Cargo Oil Pump #1 Disch Pressure Gauge | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-04 | 119075000000 | 20 | 20 | 7000000062 | WK TAG SS TAG, Mfr: WIKA INSTRUMENT COR | 2020-02-04 | Received at Target Location |  |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB A5 | 11907498 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 33 | USNSB4 | 2019-10-21 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge PG-342C, COP #3 D | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN WPOK XGI | TECO
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 100 | 1000720169 | COIMC,SWAGELOK,SS121018,3/4x1/2NPT | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 3 | EA | 3 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 390 | 7000002591 | 4452K435 Tee Connector, 3/4 NPT Female | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 39 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 10 | 7000000104 | P/N: ARMSTRONG AIR VET MODEL 22-AV,3/4” | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8201 | Stones Main | ST KB A5 | 11978555 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 58 | 2019-11-21 | GW982959 | 2 | EA | 2 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
60739062 | 508 | COT 4 P HC line Netherlock | S06 | General | 2020-04-01 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127022 | COT 4 PS HC Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642938 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60544614 | 508 | Mechanical seal is leaking | S18 | Water Systems | 2020-06-02 | 2019-07-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216A | No. 1 Main/COPT Condenser Cooling Pump | 2019-12-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 114224000000 | 10 | 50 | 7000004211 | Packing pn:54-3, SVS350M-54-3 | 2020-06-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11422404 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-15 | USMNF8 | 1 | EA | 0 | Mechanical seal is leaking | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3980 | 1001566525 | (PCM-0.23) | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 448 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 180 | FT | 180 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6900 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 938 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60655411 | 508 | Discharge check valve passing | S08 | Air Systems | 2020-02-27 | 2019-09-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11805 | Top Up Start Air Compressor | 2019-11-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-27 | 115485000000 | 10 | 60 | 7000000034 | Packing Cost | 2020-04-12 | Received at Worksite |  | 2020-02-16 | 2020-03-01 | U182 | 8201 | Stones Main | Issued | 11548488 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 13 | USNSB4 | 2019-11-26 | USNSB4 | 1 | EA | 1 | LO/TO Compressor #1, Single Isolation | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 02/16/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6580 | 7000002629 | Reducing Tee, 4" x 3", .109 x .095 Min W | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 869 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1560 | 1001566524 | TUBING,SQUARE,A500-B,3x3x1/4in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 172 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 300 | 1002309220 | SB2N,B7,2H,UNC,1in,5.50in,CTD | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 43 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 10 | 7000004211 | Butter Fly Valve - VIS-DN-500-GRP01 Quot | 2020-06-01 | Not Shipped |  | 2019-12-03 |  | U182 | 8201 | Stones Main | Stones | 11739629 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | Name 59 | 2019-08-12 | USRAR6 | 1 | EA | 0 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 40 | 7000004213 | KE35/7 SASAKURA KE35 P/N 7 NIPPLE | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60737049 | 508 | Drive End Bearing Leaking Oil - BGCB | S04 | Gas Compress | 2020-03-25 | 2019-06-29 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.CM-77102B | HV Electric Mtr Booster Gas Compressor B | 2019-06-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-27 | 116406000000 | 10 | 10 | 7000000039 | 200757101 FLOAT LAB SEAL | 2020-03-25 | Received at Worksite |  | 2019-07-04 |  | U182 | 8201 | Stones Main | ST KB A4 | 11640554 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-06-07 | USJDJW | 4 | EA | 4 | LOTO- BGC B and lube oil pump | REL GMPS PRC SETC | EXEC EOM MAGN MAOK RUSH WPOK | EXEC |  |  | PU Aaron 07/08/2019
60797069 | 508 | Tgen #4 backup battery failure | S03 | Elect. Systems | 2020-04-02 | 2020-06-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PG.BAT-11140 | Generator Package 4 Battery | 2019-11-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-04 | 117215000000 | 60 | 10 | 7000000086 | 125Vdc battery sized as specified. The 9 | 2020-07-31 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11721504 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | VERTIV | USNSB4 | 2019-11-08 | USNSB4 | 1 | EA | 0 | VERTIV - Lead Crew - Remove & Replace Ba | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM ZPVS | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5390 | 7000002603 | GASKET, 8" 300LB, RF (Hydro Only) | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 600 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 13 | EA | 13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60889480 | 508 | TG-66702-133 Replace Temp Indicator | S21 | Oil Treating | 2020-05-29 | 2020-08-05 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.RL.DP-MD-16-DB14 | Module 16 HBG-66702 | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-05-29 | 118286000000 | 10 | 10 | 7000000067 | Model No: MMM03511F49-3H-SS-BBPHV-SG-BTS | 2020-05-29 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B6 | 11828586 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-16 | USNSB4 | 1 | EA | 1 | Replace Temp Indicator TG-66702-133 | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK RUSH WPOK | EXEC
60739080 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-03-17 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-242 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-17 | 116430000000 | 10 | 10 | 7000000070 | BiFold FP02/S0A/C3/43/SC/S/RK-04 Repair | 2020-03-17 | Received at Worksite | 2020-01-29 | 2020-02-16 |  | U182 | 8201 | Stones Main | ST KB B7C | 11642976 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-27 | USNSB4 | 1 | EA | 1 | LO/TO Isolate LCP ZZZ-11923 LCP#3 | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 02/16/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1060 | 7000002596 | STUD BOLTS, 1 1/8" DIA. X 8 1/2" LONG, | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 122 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 36 | EA | 36 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7110 | 7000003343 | Beam, W16 X 57, ASTM A992 (4 @ 40' LG, 1 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 969 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 180 | FT | 180 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 600 | 1000708893 | TAPE,ELEC,3M,SCOTCH 35,19x0.178mm,GREEN | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 852 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 10 | EA | 10 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3670 | 1001759242 | SB2N,A193B8MCL2,UNC,4in,5/8in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 397 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 54 | EA | 54 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61155246 | 508 | Install Barring Device on MGCA | S04 | Gas Compress | 2020-03-03 | 2020-07-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-03 | 121329000000 | 10 | 30 | 7000002591 | 2636A72 (1/2" NC taper thread tap) | 2019-11-01 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST1A6C | 12132852 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0006 | Name 17 | JP832018 | 2020-01-27 | USLFA4 | 2 | EA | 2 | Install Barring Device on MGCA | REL PCNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC |  |  | ST1A6C 02/16/20 AMW
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 10 | 7000005903 | Amercable Part Number 37-102-308 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780965 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI77 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 120 | FT | 120 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 210 | 7000002591 | Item # 494P35 (hand siphon pump) | 2020-02-21 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0008 | Name 17 | USHBE9 | 2020-01-30 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A6C 02/18/2020 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1060 | 7000002591 | 1-1/16'' # Rotaloc Cutter. Pilot M407140 | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 106 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 6 | EA | 6 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61221684 | 508 | Steam Expansion Bellows critical spare | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-22 | P.US.STO.NF.20.015.7240A | 508ERENG | US.WR508A.GU.SW.VE115-32000 | Boiler System Steam Distribution | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-06-02 | 122096000000 | 10 | 50 | 7000003323 | Expansion Joint EJ-540585-A | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12209639 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAMH7 | 2020-03-02 | USRAR6 | 1 | EA | 0 | Shut down steam system | CRTD PRC | INIT RUSH WP | Approved
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 140 | 7000003852 | XANAD Hard Case for Logitech Spotlight . | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | Stones | 12090697 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 34 |  | 2020-02-10 | USJRF5 | 1 | EA | 1 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60959162 | 508 | COP #3 Disch Px Gauge | S21 | Oil Treating | 2020-02-04 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PG-66301C-342C | Cargo Oil Pump #1 Disch Pressure Gauge | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-04 | 119075000000 | 20 | 10 | 7000000062 | WK MISC Mfr: WIKA INSTRUMENT CORP Mfr | 2020-02-04 | Received at Worksite |  |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB A5 | 11907498 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 33 | USNSB4 | 2019-10-21 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge PG-342C, COP #3 D | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN WPOK XGI | TECO
60453585 | 508 | Replace Float in Knockout Pot LG-076 | S06 | General | 2020-02-27 | 2019-05-13 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.TU.LG-12901-076 | Turret Util Swivel Flare Gas Level Gauge | 2019-07-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-27 | 113217000000 | 10 | 10 | 7000000065 | Replacement Float | 2020-02-27 | Received at Worksite |  | 2020-02-23 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B3 | 11321739 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-07-14 | USAWJB | 1 | EA | 1 | Replace Float in Knockout Pot LG-076 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | ST1A3C 02/15/2020 CMR
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 240 | 7000002591 | 4548K226 1 NPT, 4" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 24 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4390 | 1002047398 | STL SECT MAR,BEAM,8.110in,4.015in,20ft | 2019-11-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 491 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141901 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60989313 | 508 | Erratic Speed Reading Steam Turbine #3 | S21 | Oil Treating | 2020-02-11 | 2020-04-04 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.OT.SS.CPI-66301C | Steam Turbine Control Panel | 2019-10-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-11 | 119417000000 | 20 | 10 | 7000005903 | 37-102-611 2pr 16awg CABLE. | 2020-02-11 | Received at Worksite | 2019-11-21 | 2020-01-19 | 2020-02-19 | U182 | 8201 | Stones Main | ST1A5B | 11941691 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | 3.54 | 2019-10-24 | USNSB4 | 60 | FT | 60 | Replace Existing Cable With Shielded Cab | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD WPOK XGI | TECO |  |  | PU AMW ST1A5B
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3500 | 1002360782 | SB2N,B7,2H,UNC,5/8in,4in,DOXSTEEL | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 380 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 62 | EA | 62 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5660 | 7000002629 | Flange, 3", 300#, RFWN, S/10S Bore, ASME | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 660 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 30 | EA | 30 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 390 | 7000003198 | Okonite570-99-1184 / BELDEN # 7953A | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 831 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 1000 | FT | 1000 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5870 | 7000002591 | Neoprene Strips, 1/8" thick x 3 1/2" wid | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 681 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4020 | 1001581841 | (PCM-0.23) | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 452 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5350 | 7000002644 | BALL VALVE, 1/2" FULL PORT 3705 PSI MNPT | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 596 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60737087 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-03-17 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-240 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-17 | 116406000000 | 20 | 20 | 7000000070 | BiFold FP03/S0A/C3/43/SC/S/RK-04 Repair | 2020-06-05 | Received at Worksite | 2019-12-10 |  |  | U182 | 8201 | Stones Main | ETA 10/31 | 11640592 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-27 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635S-240 | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | PU 01/19/2020 AMW
60737049 | 508 | Drive End Bearing Leaking Oil - BGCB | S04 | Gas Compress | 2020-03-25 | 2019-06-29 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.CM-77102B | HV Electric Mtr Booster Gas Compressor B | 2019-06-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-27 | 116406000000 | 10 | 60 | 7000003684 | ELRING CURIL T LIQUID GASKET NON-HARDENI | 2020-03-25 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB A4 | 11640554 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-30 | USAWJB | 2 | EA | 2 | LOTO- BGC B and lube oil pump | REL GMPS PRC SETC | EXEC EOM MAGN MAOK RUSH WPOK | EXEC |  |  | STKBA4 2/3/20 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 560 | 7000002629 | ELBOW, 8", S/10S (0.148 WT), LR, 90 DEG. | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 72 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 17 | EA | 17 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7690 | 7000002629 | Elbowlet, 2" x 3/4", 3000#, FS SCRD, MSS | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1032 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60837065 | 508 | Bad Pressure Gauge Inst air Dryer #2 | S08 | Air Systems | 2020-02-25 | 2020-07-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.ZBK-11810A | Control Air Dryer No. 2 | 2019-07-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 117686000000 | 10 | 20 | 7000000062 | WK 52858420 | 2020-02-25 | Received at Worksite |  | 2020-02-16 | 2020-02-29 | U182 | 8201 | Stones Main | ST KB A7 | 11768556 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-17 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge Instrument Air Dr | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | ST1A1C 02/18/2020 CMR
60909926 | 508 | Purifier 2 By-Pass valve not functioning | S06 | General | 2020-06-15 | 2020-08-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.LO.117-48V | Lube Oil Purifier Supply Pump #2 Valve | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-06-15 | 118521000000 | 10 | 20 | 7000004211 | doxsteel-1 DOXSTEEL FASTENER FLANGE PACK | 2020-06-15 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11852103 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-10 | USNSB4 | 1 | EA | 0 | Replace By-Pass Gate Valve 117-48V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 110 | 7000003684 | WHITE SILICONE O-RING SILICONE GREASE | 2020-04-01 | Received at Worksite | 2019-12-19 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 12027172 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-01 | USAWJB | 1 | EA | 1 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 20 | 1002409140 | FLTR ELEMENT SET,13A213/3/1015+,MAHLEIND | 2019-12-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12027172 | 2 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 | STANDARD | 2019-11-24 | USAWJB | 1 | EA | 0 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | APPR MAGN WPOK ZPMM | Deleted
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1350 | 7000002596 | BLT HEX,A325,UNC,5/8in,7in,SERMAGARD | 2019-12-27 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | Crane Access Platform | 11581207 | 135 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A380 | Name 2 | Name 59 | 2019-12-24 | USSOLE | 36 | EA | 36 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60686663 | 508 | O/SI #1 Boiler Steam to 16K Hdr Valve | S17 | Steam/Hot H2O | 2020-04-11 | 2019-09-30 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-200A | Steam to 16K Steam Header Valve | 2019-12-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-12 | 115837000000 | 30 | 30 | 7000004211 | Forge steel globe valve EP-GVB20X25KM | 2020-04-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11583658 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-18 | USMNF8 | 1 | EA | 0 | Replace passing valve 115-200A | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60352955 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-09 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33310 | No. 1 Port Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-10 | 112105000000 | 10 | 40 | 1002386512 | OIL,COOLANT,SHELL,ZONE 50/5 0AF,1gal | 2020-02-09 | Received at Target Location |  | 2019-10-20 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210547 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-07-17 | USRAR6 | 1 | GLL | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 100 | 7000003684 | BLADES FOR LIGHT DUTY AIR-POWERED | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 250 | 7000003740 | Rosemount Product Drawing | 2020-03-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 25 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN118 | Name 2 | Name 2 | 2020-01-31 | USLFA4 | 8 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 110 | 7000003740 | Rosemount Documentation, Certifications | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN110 | Name 2 | Name 2 | 2019-12-18 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60737085 | 508 | VPI test fail COT 5 STBD | S21 | Oil Treating | 2020-02-08 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-222 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-09-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-08 | 116406000000 | 20 | 10 | 7000005901 | P.0244110037 AVC 02 CL1 A1 VPI MANIFOLD | 2020-04-28 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-10 | U182 | 8201 | Stones Main | ST KB B7F | 11640590 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-16 | USNSB4 | 1 | EA | 1 | Repair VPI XV-6635S-222 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60985334 | 508 | O/SI VABF-122008 passing | S18 | Water Systems | 2020-03-10 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VABF-122008 | Filter Backwash Water Outlet Valve | 2019-10-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-10 | 119372000000 | 20 | 10 | 7000004211 | 4IN150-CBFV-ISLIP | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937180 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-10-29 | USNSB4 | 1 | EA | 0 | Replace VABF-122008 Butterfly Valve MAJ- | REL ESTC GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60847988 | 508 | MOC GTG4 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-34000 | Gen #4 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 40 | 7000005901 | M20 Serrated Washer | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780943 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI79 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #4 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60085018 | 508 | O/SI XV-6636P-215 6 COT-#3 Cargo Line | S21 | Oil Treating | 2020-03-12 | 2018-06-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6636P-215 | Crude Oil to/from COT 6 On/Off PS Valve | 2018-05-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-13 | 108964000000 | 10 | 30 | 1002400773 | GASKET,427 AC002-26"-10,ISLIP-FC | 2020-03-12 | Received at Worksite |  | 2018-05-14 |  | U182 | 8201 | Stones Main | ST KB B4 | 10896408 | 3 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 |  | 2018-05-08 | USNSB4 | 2 | EA | 2 | Replace Soft Goods XV-6636P-215 | REL ESTC GMPS PRC SETC | EXEC EOM MAOK WPOK | EXEC |  |  | PU AARON 6/11/2018
60747152 | 508 | COT 2 STBD IG Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127055 | COT 2 SB IG Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651964 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60085018 | 508 | O/SI XV-6636P-215 6 COT-#3 Cargo Line | S21 | Oil Treating | 2020-03-12 | 2018-06-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6636P-215 | Crude Oil to/from COT 6 On/Off PS Valve | 2018-05-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-13 | 108964000000 | 10 | 10 | 1002400775 | SEAT,427 AC002-26"-3,ISLIP-FC | 2020-03-12 | Received at Worksite |  | 2018-05-14 |  | U182 | 8201 | Stones Main | ST KB B4 | 10896408 | 1 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 |  | 2018-05-08 | USNSB4 | 1 | EA | 1 | Replace Soft Goods XV-6636P-215 | REL ESTC GMPS PRC SETC | EXEC EOM MAOK WPOK | EXEC |  |  | PU AARON 6/11/2018
60847988 | 508 | MOC GTG4 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-34000 | Gen #4 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 90 | 7000005901 | NK Technologies AT2-420-24L-FT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780943 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI79 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 2 | EA | 2 | SAEP LO/TO Isolate GTG #4 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 110 | 7000002591 | Approved Drawings for above items | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 10 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 690 | 7000002591 | 1/4" x 600' (box) Manila Rope | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 927 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A395 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 1 | EA | 1 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5920 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 686 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 26 | EA | 26 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 470 | 7000000086 | Sampler Panel | 2020-03-06 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 433 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN102 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4120 | 7000002596 | Bolt, 3/4" x 2 1/2 Lg ASTM F3125 GrA325 | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 462 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 62 | EA | 62 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 210 | 7000000133 | Crating for the 8” and 12” Valves | 2019-01-17 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 286 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN031 | Name 2 | Name 2 | 2019-04-23 | USGBI5 | 1 | EA | 0 | Engineered Equipment | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6010 | 7000002629 | Tee, 1/2" x 1/2", SW, 400 PSIG WOG, ASME | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 699 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1920 | 7000002603 | GASKET, 8", 150#, FF, 1/8" THK, GARLOCK | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 214 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 350 | 7000002591 | 30 x 40 Polypro Bag, White Rice Sack | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 35 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 36 | EA | 36 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7710 | 7000002629 | Flange, 2", 300#, RFWN, S/40S Bore, ASME | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1034 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60959163 | 508 | COP #2 Disch Px Gauge | S21 | Oil Treating | 2020-02-04 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PG-66301B-342B | Discharge Pressure Gauge | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-04 | 119075000000 | 20 | 40 | 7000000066 | WK TAG Mfr: WIKA INSTRUMENT CORP Mfr | 2020-02-04 | Received at Target Location |  |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB A5 | 11907499 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 33 | USNSB4 | 2019-10-29 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge PG-342B, COP #2 D | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN WPOK XGI | TECO
60739059 | 508 | 6S HC Netherlock Not Locking Open/Closed | S06 | General | 2020-04-01 | 2019-11-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127017 | COT 6 SB HC Main Isolation Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642935 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61179023 | 508 | Remove TSE loops from non hydrocarbon MO | S20 | Monitor & Ctrl | 2020-03-19 | 2020-03-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MC.SH.TSE | TSE/Fusible Plug Loops | 2020-02-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-19 | 121603000000 | 10 | 10 | 1000720172 | CAIC,SWAGELOK,SS600C,3/8in | 2020-03-19 | Received at Worksite |  | 2020-02-06 |  | U182 | 8201 | Stones Main | ST KB B7E | 12160285 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  |  |  | 2020-02-06 | USAMH7 | 8 | EA | 8 | Remove unneeded TSE loops. | REL PRT GMPS PRC SETC | EXEC MAOK WPOK | EXEC |  |  | ST1A1C 02/12/2020 CMR
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 10 | 90 | 7000005901 | 39A530 M42x2" HEX PLUG CARBON STEEL | 2020-05-16 | Received at Worksite |  | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB B5 | 11783572 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-21 | USNSB4 | 22 | EA | 22 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC |  |  | PU AARON W
60797145 | 508 | Faulty Defrost component Galley Upright | S09 | Bldg & Qtrs | 2020-03-24 | 2019-12-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.BQ.ROOM-213 | Galley | 2019-08-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-24 | 117216000000 | 10 | 10 | 7000000086 | Galley Freezer Unit (Frigidaire Electrol | 2020-03-24 | Received at Worksite | 2020-01-16 |  |  | U182 | 8201 | Stones Main | Wesley Howard | 11721560 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-15 | USNSB4 | 1 | EA | 1 | Replace Faulty Components Galley Upright | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM ZPVS | Kit Complete |  |  | ST1FLR 01/30/2020 GG
61155246 | 508 | Install Barring Device on MGCA | S04 | Gas Compress | 2020-03-03 | 2020-07-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-03 | 121329000000 | 10 | 90 | 7000003517 | 92620A716 (1/2" x 1-1/2" grade 8 bolts) | 2019-11-01 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST1A6C | 12132852 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0006 | Name 17 | JP832018 | 2020-01-27 | USLFA4 | 1 | PK | 1 | Install Barring Device on MGCA | REL PCNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC |  |  | ST1A6C 02/16/20 AMW
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 200 | 1002128203 | NUT,SPRING,COOP-BLI,N224SS6,1/4in,316 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 100 | EA | 100 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 170 | 7000003852 | Hallmark Holiday Reversible Wrapping Pap | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 110 | 7000002603 | 0003 2511-XXXX 00000 3/4" 150# SPIRAL | 2020-02-24 | Received at Target Location |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-15 | USNSB4 | 2 | EA | 2 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
60739067 | 508 | COT 4 Port IG netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127051 | COT 4 PS IG Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642943 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60985335 | 508 | VABF-122009 Passing By | S18 | Water Systems | 2020-03-03 | 2019-11-30 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.VABF-122009 | Filter Backwash Water Outlet Valve | 2019-10-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-03 | 119372000000 | 20 | 30 | 7000002596 | 5/8-11 X 4-1/4" 316 SS BOLTS W/1 FLAT WA | 2020-03-03 | Received at Worksite | 2019-11-13 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB D1 | 11937181 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 1 | USNSB4 | 2019-10-29 | USNSB4 | 16 | EA | 16 | Replace VABF-122009 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD WPOK | EXEC
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 140 | 7000003739 | 909106C1 BEARING,CYLINDRICAL ROLLER | 2020-02-24 | Received at Target Location |  |  | 2020-02-26 | U182 | 8201 | Stones Main | STONES | 12155706 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 830 | 7000002583 | UHMW-PE Strip, 4" x 8" x 6'-4" LG. w/ (1 | 2020-01-12 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 83 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08051901 | Entity 3 | Name 59 | 2019-08-05 | USDKFB | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60958935 | 508 | MGC A 2nd Stage Gas Outlet DBB Passing | S04 | Gas Compress | 2021-04-01 | 2020-03-10 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VADB-771003 | Heat Exchanger Isolation Valve | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2021-04-02 | 119075000000 | 10 | 10 | 7000000039 | 6'' 600 RF W/ 1/2'' BLEED NB00 /BODY A18 | 2021-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 11907487 | 1 | 4 | Non-Stock (Purchase Requisition) | N | [5 empty] | 2020-02-11 | USJDJW | 1 | EA | 0 | hang rigging MGC A 2nd Stage Gas Outlet | REL CSER PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61221684 | 508 | Steam Expansion Bellows critical spare | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-22 | P.US.STO.NF.20.015.7240A | 508ERENG | US.WR508A.GU.SW.VE115-32000 | Boiler System Steam Distribution | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-06-02 | 122096000000 | 10 | 10 | 7000003323 | Expansion Joint EJ-540581-A | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12209639 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAMH7 | 2020-03-02 | USRAR6 | 1 | EA | 0 | Shut down steam system | CRTD PRC | INIT RUSH WP | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 570 | 7000002591 | 4452K261 Straight Reducer, 1 x 1/4 NPT F | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 57 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61006512 | 508 | R & R Mechanical seal on COPT 2 | S21 | Oil Treating | 2020-06-02 |  | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2020-02-19 | WO | U100 | 72RE | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 2 Medium | 2020-06-02 | 119629000000 | 10 | 30 | 7000000035 | 100 MM Mechanical seal, Z3110-AZT0099SSV | 2020-06-02 | Ready for Shipment after Kitting |  |  | 2020-02-19 | U182 | 8201 | Stones Main | STONES | 11962908 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-09 | USMNF8 | 1 | EA | 1 | Mechanical seal Rebuild for COPT pumps | TECO ESTC GMPS PPRT PRC SETC | XCNF MAGN XGI | TECO |  |  | PU CRIS TO STOCK LOC.ST1H3C
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 240 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 24 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 4 | EA | 4 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61137356 | 508 | Aft FireWater Pump Panel Lights Out | S13 | Fire Protect | 2020-03-03 | 2020-12-28 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.FP.ZZZ-33110 | Aft Firewater Pump Package | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-03 | 121118000000 | 10 | 10 | 7000005901 | 2FMK6 4.0W T3-1/4 BA9S LAMP | 2020-03-03 | Received at Worksite | 2020-02-04 | 2020-02-19 |  | U182 | 8201 | Stones Main | ST KB B7E | 12111791 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-06 | USNSB4 | 20 | EA | 20 | Replace Defective Aft FireWater Pump Pan | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 02/19/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2040 | 7000002629 | WELD-O-LET, 8" X 2" (2" S/40S (0.154 WT) | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 226 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3680 | 1001645366 | WASHER,FLAT,SS316,5/8in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 398 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 108 | EA | 108 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6360 | 1001807386 | FLWN,A105,CL150,80,NPS2 | 2019-01-08 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 744 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01032001 | Name 4 | Name 4 | 2020-01-03 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5930 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 687 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 26 | EA | 26 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1000 | 7000002596 | STUD BOLTS, 7/8" DIA. X 7 1/2" LONG, AS | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 116 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2000 | 1001665195 | HOT ORDER | 2019-02-15 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 222 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02121901 | Name 2 | Name 2 | 2019-02-13 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 480 | 1000708922 | TIE_CABLE,TYRAP,5",.270",TY27MX,THOMASBE | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 840 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 1500 | EA | 1500 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 360 | 7000002591 | 2''x4'x2Ply Nylon Straps | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 745 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A384 | Name 2 | Name 2 | 2020-01-11 | USSOLE | 6 | EA | 6 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 820 | 7000002591 | 13/16'' X 2'' DOC, 9200SE 92SE152. Reg | 2020-03-03 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia |  | 11179936 | 1072 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-28 | USLFA4 | 20 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 150 | 7000002591 | 0007 5601-XXXX 00000 TY27MX-14 BLACK TY | 2020-02-24 | Received at Target Location |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-15 | USNSB4 | 100 | EA | 100 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 70 | 7000003197 | PAN MLTFC4H-LP316 MLTTIE FULLYCOATED 31 | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11780965 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | Name 58 | 2019-10-29 | USNSB4 | 150 | EA | 0 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC PRC SETC | APPR EOM MAGN WP ZPMM | Deleted
60973032 | 508 | MGC-A 3rd Stg Bridle Removal | S04 | Gas Compress | 2020-04-20 | 2020-09-26 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2019-10-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-20 | 119235000000 | 10 | 22 | 7000004751 | 2" 1500 RTL ASMWE B16.5 Blind Flanges Si | 2020-04-20 | Received at Worksite | 2019-10-10 | 2019-11-30 |  | U182 | 8201 | Stones Main | ST KB C7 | 11923491 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-02 | USAWJB | 2 | EA | 2 | MGC-A 3rd Stg Bridle Removal MOC78183 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU WPT AMW 11/30/19
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 260 | 7000002596 | Flat Washers, 1/2”, 316 SS (Xylar + Xyla | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 26 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 12 | EA | 12 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 40 | 7000002629 | Flange, 10", 300#, RFWN, S/40S Bore, ASM | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 100 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1230 | 1001768461 | ELB BW,WPB,90DEG,LR,40,NPS1.1/2 | 2020-05-07 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G04 | 11581207 | 123 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031901 | Name 4 | Name 59 | 2019-12-04 | USSOLE | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 10 | 7000002591 | 10 FT LENGTH 2X2 ALUMINUM ANGLE IRON | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 6 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 180 | 7000002629 | Flange, 2", 150#, S/80, RFWN, ASME B16.5 | 2019-09-08 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04221901 | Entity 2 | Name 60 | 2019-04-22 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
61021143 | 508 | Replace Dryer filters 1B Acom HVAC comp | S14 | HVAC | 2020-04-07 | 2020-04-22 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.HV.VE108-00000 | Accommodation HVAC | 2020-01-30 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-07 | 119795000000 | 20 | 10 | 7000000047 | Dryer filter, Mahle P12015 Screw on filt | 2020-04-07 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11979462 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-30 | USMNF8 | 2 | EA | 0 | Replace Dryer filters 1B Acom HVAC unit | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60847991 | 508 | MOC GTG1 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-04000 | Gen #1 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117810000000 | 10 | 100 | 7000005901 | NK Technologies AT2-420-24L-FT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780966 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI76 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 2 | EA | 2 | SAEP LO/TO Isolate GTG #1 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
61165412 | 508 | Install Needle Valve on PG-33110-732 | S13 | Fire Protect | 2020-03-07 | 2020-03-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33110-732 | Seawater Booster Pump Inlet Press Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-07 | 121447000000 | 10 | 20 | 7000003196 | OA,US,SWAGELOK,FITTINGS,EA | 2020-03-07 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144697 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 1 | EA | 1 | Install Needle Valve on PG-33110-732 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 140 | 7000002629 | 1 1/2" Flange Blind 600# RF ASME B16.5, | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 59 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 1 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61213997 | 508 | Oil Emulsified Start air compressor #2 | S08 | Air Systems | 2020-04-08 | 2020-04-17 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.AS.CAE-11804B | Start Air Compressor No. 2 | 2020-02-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-08 | 122006000000 | 10 | 10 | 1002150072 | OIL FILTER,3722,SPERRE | 2020-04-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12200631 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-02-23 | USAWJB | 1 | EA | 0 | Change Oil/Filter Start Air Comp.#2 | REL ESTC PRC SETC | APPR MAXX WPOK ZPMM | Approved
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 20 | 7000000039 | YMD-8529 HOSE ASSEMBLY X76"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61102257 | 508 | P.Crane radiator fan shroud corroded | S40 | Cargo Handling | 2020-05-10 | 2020-06-10 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-10 | 120716000000 | 10 | 80 | 7000006081 | Guard sheet 21829 | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12071582 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 2 | EA | 0 | P.Crane radiator fan shroud corroded | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6200 | 1001625314 | BLT+N,AL-651,UNC,4in,3/4in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 718 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 18 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4000 | 7000002662 | Pipe, 3 1/2", S/40, API 5L Grade X52 | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 450 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 21 | FT | 22.4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 140 | 7000000133 | RKI 91-0019RK Cylinder, isobutane 10% | 2020-02-28 | Received at Target Location |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG144 | Entity 7 | USKHU3 | 2020-02-05 | USLFA4 | 1 | EA | 1 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5000 | 7000002629 | 90 DEG ELBOW, 12" SCH 10S LR BW CLASS WP | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 561 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 60 | 7000002644 | 8" 150# RF FP WKM Trunnion Ball Valve | 2019-02-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN038 | Name 2 | Name 2 | 2018-11-28 | USSOLE | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60739062 | 508 | COT 4 P HC line Netherlock | S06 | General | 2020-04-01 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127022 | COT 4 PS HC Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642938 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1390 | 7000002629 | FLANGE, 3" 300, RFWN, SCH 10, ASME B16.5 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 155 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5770 | 7000002646 | Needle Valve, 1/2", VNT-2505D (See attac | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 671 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 7 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5420 | 7000002603 | GASKET, 1 1/2" 300LB, RF (Hydro Only) | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 603 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2300 | 1001645338 | BLT HEX,A325,UNC,2.1/4in,3/4in | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 252 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 70 | EA | 144 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5710 | 7000002629 | Plug, 1/2", SC Hex Head, ASME B16.11, AS | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 665 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 8 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 620 | 7000002629 | THREAD-O-LET, 8" X 3/4", 6000#, FS, MSS- | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 78 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 940 | 7000005901 | Yellow / Green Heat Shrink 3/4" | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 954 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI87 | Name 2 | Name 2 | 2020-02-08 | USSOLE | 1 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1580 | 1001676781 | SHT PLT SLD MET,4x4ft,1/2in,A572 GR.50 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 174 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 720 | 7000003197 | SSTF06HBC9012SS 6INW CHNL TRAY H90 12INR | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 903 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 3 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6060 | 7000002629 | Elbow, 2", 45, SW, 400 PSIG WOG, ASME B | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 704 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 10 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 70 | 7000002596 | 1 X 10-1/2 W/ 3 NUTS A194 B7/194 2H | 2020-04-01 | Received at Worksite | 2019-12-19 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 12027172 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-01 | USAWJB | 24 | EA | 24 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
60935789 | 508 | COP2 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-10 | 2019-10-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 118809000000 | 10 | 20 | 7000000038 | 3/8” mnpt x 3/8” tube SS fitting | 2020-03-10 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11880945 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-26 | USAWJB | 4 | EA | 4 | Install mechanical seal flush plan 12 | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
60655412 | 508 | Jockey Pump B Motor Fan Failed | S13 | Fire Protect | 2020-02-06 | 2020-02-28 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.FP.PM-33151B | Seawater Jockey Pump Motor | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-06 | 115485000000 | 20 | 10 | 7000005901 | 3GZF304128-1 FAN M3BP/GP/HP 280SM | 2020-04-06 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB A3 | 11548489 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 1 | Replace Cooling Fan, Jockey Pump B Motor | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 2/5/2020 JH GG
61175887 | 508 | LACT -Drain Valves Severely Corroded | S21 | Oil Treating | 2020-03-14 | 2020-03-25 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-24 | 121566000000 | 50 | 10 | 7000004751 | 1" 150 RF Full Port, Quadrant Ball Valve | 2020-03-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12156642 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-25 | USNSB4 | 19 | EA | 0 | Replace Defective Valves On LACT Skid | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60592977 | 508 | MeOH A Pump passing valve VADB-128103 | S10 | Chem Injection | 2020-03-10 | 2020-01-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.CI.VADB-128103 | A Pump Discharge Isolation Valve | 2019-07-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 114773000000 | 30 | 20 | 1002404538 | BALL VALVE,BV1516FMP06FMP3710EV9+,BIFOLD | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 02/11 | 11477341 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-11-07 | USMNF8 | 1 | EA | 0 | Replace Valve VADB-128103 MeOh "A" | REL ESTC GMPS PPRT PRC SETC | APPR EOM MANX WPOK ZPMM | Approved
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 100 | 1002292485 | SB2N,B7,2H,UNC,1/2in,2.50in,CTD | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 5 | EA | 5 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 20 | 7000003519 | TSR Blend Thinner 55 gallon drum | 2020-02-04 | Received at Target Location |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | DIISTO1927 | Entity 1 | USJRF5 | 2020-01-28 | USLFA4 | 2 | DR | 2 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 150 | 7000006429 | AFMR19017A.32B | 2020-03-18 | Not Shipped |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 16 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO20020AA | Name 3 | USRRIG | 2020-03-03 | USLFA4 | 500 | GLL | 0 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60985337 | 508 | Pear Link on Hawser Chain | S19 | Marine Systems | 2020-04-21 | 2020-09-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.PS.VE886-00000 | Mooring Hawser Equipment | 2019-12-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-04-22 | 119372000000 | 10 | 10 | 7000002596 | MATERIAL DESCRIPTION: M20-2.5 PITCH X 13 | 2020-04-21 | Received at Worksite | 2019-12-02 | 2019-12-02 |  | U182 | 8201 | Stones Main | ST KB B7B | 11937183 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 35 |  | 2019-10-09 | USMNF8 | 10 | EA | 10 | Replace hawser link bolts | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU WPT AMW 11/30/19
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 20 | 7000002591 | 4548K133 1/4 NPT, 2" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61060939 | 508 | O/SI CAIR3399 CAT2 corrosoin to flange | S08 | Air Systems | 2020-04-01 | 2020-05-19 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.AS.TS118-00000 | Nitrogen Generation & Distribution | 2020-01-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 120244000000 | 20 | 30 | 7000002596 | 1/2 X 3 (2-3/4 FTF) DOX PLTD STUD BOLT | 2020-04-01 | Received at Worksite | 2020-01-21 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB D3 | 12024358 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-07 | USMNF8 | 4 | EA | 4 | Replace Corroded Flange | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A5A 02/3/20 GG
60453594 | 508 | 26-PL664001- Install permanent Pipe Supp | S21 | Oil Treating | 2020-02-18 | 2019-11-10 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-18 | 113218000000 | 10 | 60 | 7000002596 | Nut, 5/8", ASTM A194 Gr. 2H (Sermaguard | 2020-01-22 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | JOB: SHF9-F92 | 11321849 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221902 | Name 4 |  | 2019-11-22 | USLFA4 | 5 | EA | 5 | 26-PL664001- Install permanent Pipe Supp | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 90 | 7000002591 | 10" 150# Spectacle Blind, Duplex Stainle | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 2 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
60507050 | 508 | STB Vent N2 snuffing system rusting | S06 | General | 2020-03-10 | 2019-02-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.ZZZ-12707 | Cargo Vent Stacks N2 Stuffing System | 2019-06-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-11 | 113805000000 | 10 | 10 | 7000000039 | REGULATOR 520 AC PRESSURE 0-1.5 BAR FOR | 2020-06-08 | Received at Worksite |  | 2019-06-07 |  | U182 | 8201 | Stones Main | WHS Floor | 11380546 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-04-09 | USNSB4 | 8 | EA | 8 | Replace Rusted Components Starboard Vent | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MAOK WPOK ZPMM | EXEC
60958039 | 508 | Slew Drive Mounting Bolts- PORT CRN | S40 | Cargo Handling | 2020-02-25 | 2020-09-17 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-09-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-26 | 119064000000 | 20 | 20 | 1002386497 | OIL,LUBT,SHELL,OMALA S2 G 150,5gal | 2020-02-25 | Received at Target Location | 2020-01-12 | 2020-02-01 | 2020-02-22 | U182 | 8201 | Stones Main | MOD 22 GRN Mile | 11906378 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-12 | USAMH7 | 6 | PAI | 6 | CAN USA Assist Relocate Crane Slew Gearb | TECO ESTC GMPS PPRT PRC SETC | XCNF EOM MAGN MAKD NCMP RUSH WPOK XGI | TECO
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 270 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2020-04-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F90 | 11581210 | 27 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11201901 | Name 4 | Name 60 | 2019-11-20 | USABCE | 3 | EA | 3 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60879616 | 508 | 16000 HR service due #3 Air Compressor | S08 | Air Systems | 2020-02-04 | 2019-09-03 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11801C | No. 3 Air Compressor | 2019-09-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 4 Complete by 4 Weeks | 2020-02-04 | 118173000000 | 10 | 10 | 7000000083 | Service Kit # 3001500640 | 2020-02-04 | Ready for Shipment after Kitting | 2019-10-29 | 2019-11-25 | 2020-02-13 | U182 | 8201 | Stones Main | Issued | 11817298 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 36 | USAWJB | 2019-09-05 | USRAR6 | 1 | EA | 1 | 16000 HR service due #3 Air Compressor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO |  |  | PU WPT 11-25-19
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7320 | 1000727801 | DISC,GRATING,HILTI,247182,1.3/8x1.9/16in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 990 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 2 | BX | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5320 | 7000002596 | STUD BOLT, 1 1/8" X 7" ASTM A182 GRADE F | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 593 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 96 | EA | 96 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 10 | 1000709396 | NPHT,SWAGELOK,SS-8-HLN-2.00,1/2in,NPTM | 2021-03-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB C7 | 11057838 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO182KDC | Name 37 | USRRIG | 2018-07-24 | USLFA4 | 4 | EA | 4 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved |  |  | PU MOD22 1st FLR 09/04/2018 MP
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 810 | 7000003197 | SSW06VFC72 SS COV. 6W VFC STR 6FT | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 912 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 6 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3310 | 1001207642 | PIPE,API 5L-B/X42,BLACK,STD,12in,SRL | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 361 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 20 | FT | 20.76 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 310 | 1002300893 | SB2N,B7,2H,UNC,3/4in,7.00in,CTD | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 44 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4170 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 467 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 238 | EA | 238 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60936974 | 508 | GT5 Gas Fuel Valve Bolts Recalled | S03 | Elect. Systems | 2020-04-01 | 2020-03-07 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.FCV-11150-130 | Generator #5 Fuel Gas Flow Control Valve | 2020-01-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 118822000000 | 10 | 10 | 7000003739 | 601722C1 KIT,HDWR,PECC VALVE | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11882244 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | STANDARD | 2020-01-21 | USAWJB | 1 | EA | 0 | GT1 Gas Fuel Valve Bolts Recalled | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118371 | 508 | 2020 Lab Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000002591 | 330mm, NIST Standards Hydrometer for API | 2020-02-16 | Received at Worksite |  | 2020-01-11 |  | U182 | 8201 | Stones Main | STONES | 12090728 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO2CG0145 | Name 3 | USRRIG | 2020-02-16 | USLFA4 | 2 | EA | 2 | 2020 Lab Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 70 | 1002316823 | GASW,CL150,316/316L,GPH,2in | 2019-11-27 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI67 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 3 | EA | 3 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
60739085 | 508 | 663UD-XV-299 Actuator & VPI test fail | S21 | Oil Treating | 2020-03-26 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-663UD-299 | Crude Oil O/O to COT 2 PS Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-29 | 116430000000 | 111 | 30 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-06-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642981 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 0 | Repair Hydraulic Actuator Cargo Valve XV | REL GMPS PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60958182 | 508 | Bad high pressure filter housing | S03 | Elect. Systems | 2020-03-18 | 2020-03-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.TS111-16000 | Gen #2 Gas Turbine Lube Oil System | 2020-01-30 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119063000000 | 10 | 10 | 7000003739 | 186278-1 FILTER,LIQUID FUEL,SIMPLEX | 2020-03-18 | Received at Worksite | 2020-02-12 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB C3 | 11906295 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-30 | USJDJW | 1 | EA | 1 | Replace high pressure filter housing | REL GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 300 | 1001665195 | BLT HEX,A325,UNC,1.3/4in,5/8in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 30 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 46 | EA | 46 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60578049 | 508 | Replace Produced Water HX Inlet TG-117 | S26 | Water Treating | 2020-04-10 | 2020-01-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.WT.CL.TG-12402-117 | Produced Water Inlet Temperature Gauge | 2019-07-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 114607000000 | 10 | 10 | 7000005901 | TG-12402-117 THI-100-A+AMX TEMPERATURE 1 | 2020-04-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11460730 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-07-18 | USNSB4 | 1 | EA | 0 | Replace Produced Water HX Inlet TG-117 | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61118336 | 508 | 2020 Lube Oils / Grease - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 60 | 7000003946 | 55 gal drums of Shell Tellus S2 VX 100 h | 2020-12-31 | Not Shipped |  | 2020-01-08 |  | U182 | 8201 | Stones Main | CPORT | 12090693 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOMEC0013 | Name 17 | JP832018 | 2020-02-24 | USLFA4 | 4 | DR | 0 | 2020 Lube Oils / Grease - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 630 | 7000003852 | Genius Tools 590364 Drilling Hammer 4 Lb | 2020-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 63 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOMEC0011 | Name 29 | USRRIG | 2020-02-18 | USLFA4 | 10 | EA | 9 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 170 | 7000002591 | 2x1-1/2” NIPPLE CONC. SWAGE SCH 80S TBE | 2019-10-18 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 41 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN091 | Name 2 | Name 2 | 2019-09-23 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60312673 | 508 | Spring Packs for Fuel Valves | S19 | Marine Systems | 2020-04-28 | 2018-10-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PR.VE109-03000 | Main Engine Fuel System | 2018-08-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-05-02 | 111650000000 | 10 | 10 | 1002399965 | DISTANCE PIPE,90101-0117-222,MANDT | 2020-04-02 | Received at Worksite |  | 2019-03-26 |  | U182 | 8201 | Stones Main | ST KB D5 | 11164973 | 1 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 |  | 2018-08-31 | USAWJB | 22 | EA | 22 | Replace Fuel Valves Spring Packs | REL ESTC GMPS PPRT PRC SETC | APPR EOM MAXX WP | EXEC |  |  | PU 21pc 3/26/19 AARON
60839939 | 508 | Replace Auto Drain on #4 IAC | S08 | Air Systems | 2020-02-11 | 2020-01-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.CAE-11801D | No. 4 Air Compressor | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-11 | 117719000000 | 10 | 10 | 7000000034 | HN TRAP 505 (6001789) Trap 505 | 2020-02-11 | Received at Worksite | 2020-01-20 | 2020-02-03 | 2020-02-14 | U182 | 8201 | Stones Main | ST KB B3 | 11771877 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-06 | USNSB4 | 1 | EA | 1 | Replace Auto Drain on #4 IAC | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 2/5/2020 JH GG
61151919 | 508 | P.Crane swing gearbox sight glass cloudy | S40 | Cargo Handling | 2020-10-31 | 2021-01-07 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-10-31 | 121288000000 | 10 | 10 | 7000006081 | Sight glass plug,419201000,, | 2020-10-31 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12128844 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-06 | USMNF8 | 6 | EA | 0 | Replace port crane gearbox sight glass | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61179017 | 508 | FRC Trim Tabs Fail to Operate | S15 | Life Saving | 2020-02-11 | 2020-04-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2020-01-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-10 | 121603000000 | 10 | 10 | 7000003852 | Lenco 10222-211D Trim Tab Switch Kit, Do | 2020-02-11 | Received at Worksite | 2020-02-14 |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 12160254 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  |  |  | 2020-02-11 | USMNF8 | 1 | EA | 1 | Replace FRC trim buttons | REL PCNF ESTC GMPS PPRT PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61083783 | 508 | Swing Gates STBD CRN Interior Pedistal | S40 | Cargo Handling | 2020-03-16 | 2020-01-24 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-12-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-17 | 120503000000 | 10 | 10 | 7000002583 | 37" Intrepid Universal Gravity-Closing S | 2020-01-07 | Received at Worksite | 2019-12-19 | 2019-12-31 |  | U182 | 8201 | Stones Main | ST1A6A | 12050316 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-04 | USAWJB | 3 | EA | 3 | Install Gates STBD CRN Pedistal Interior | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4600 | 7000002629 | 3" Flange Protectors for Flange, 3", 300 | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 512 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 11 | EA | 11 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 100 | 7000006081 | PB-304-100-050 1''X 1/2 BUSHINGS S/S | 2020-04-29 | Received at Target Location | 2020-02-13 |  | 2020-02-22 | U182 | 8201 | Stones Main | STONES | 11772908 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-13 | USAWJB | 4 | EA | 4 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2710 | 7000002629 | Lateral 45, 3" x 3", S/40S, BW, ASTM A8 | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 295 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1360 | 7000002629 | ELBOW, 3", LR 90, BW, SCH 10S, ASME B16. | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 152 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1740 | 1002292484 | SB2N,B7,2H,UNC,1/2in,3.00in,CTD | 2019-01-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 191 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01171901 | Name 2 | Name 2 | 2019-01-18 | USDSVB | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2110 | 7000002629 | BLIND FLANGE, 2", 300#, RF, ASTM A182 GR | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 233 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1800 | 7000002596 | STUD BOLTS, 1 1/8" DIA. X 7" LONG, W/ | 2019-01-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 197 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01171902 | Name 2 | Name 2 | 2019-01-18 | USDSVB | 32 | EA | 32 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60756604 | 508 | Vacuum Condenser Heat Exchanger | S17 | Steam/Hot H2O | 2020-04-01 | 2019-06-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.HBG-11508 | COPT Vacuum Condenser Heat Exchanger | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 116627000000 | 10 | 30 | 7000000101 | p/n: Baffle Plate ss400: 14t, Item 8. | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 11662728 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2019-10-14 | GW982959 | 2 | EA | 0 | Main condenser tubes leaking | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WP ZPMM ZPVS | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7980 | 1000709864 | FLG_PIPE,BLIND,FF,2",150#,6",CU/NI,Q | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 1083 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-28 | USSOLE | 6 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5560 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-12-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 630 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12121901 | Name 4 | Name 4 | 2019-12-13 | USABCE | 36 | EA | 36 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2800 | 7000002603 | 3" Flange Protectors for Flange, 3", 300 | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 304 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 90 | EA | 90 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60315609 | 508 | Replace SC8 LVDT2 Sensor | S19 | Marine Systems | 2020-06-12 | 2019-02-27 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-88508 | Structural Connector No. 8 | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-12 | 111682000000 | 20 | 10 | 7000005901 | 011317340983-M LINEAR VARIABLE DIFFERENT | 2020-12-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11168231 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-10-14 | USNSB4 | 1 | EA | 0 | Replace SC#8 LVDT Sensor | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7950 | 7000002629 | Elbow, 1/2", 45, SW, 400 PSIG WOG, ASME | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 1080 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-28 | USSOLE | 6 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 120 | 1000711628 | VALVE,BALL,SWAGELOK,SS-45F8,1/2in,S316 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 790 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 3 | EA | 3 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60839364 | 508 | Check Valve VACH-331020 Passing by | S13 | Fire Protect | 2020-06-01 | 2020-01-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.VACH-331020 | SW Jockey Pump to Helideck Check Valve | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-01 | 117712000000 | 10 | 40 | 7000004212 | 5/8"-11 Silica Bronze Nuts | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11771154 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-15 | USNSB4 | 16 | EA | 0 | Replace Check Valve VACH-331020 | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61219229 | 508 | GT #4 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-3 | Generator #4 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-21 | 122068000000 | 10 | 30 | 7000003763 | 1210 28MM TL BUSHING 119588 | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206813 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #4 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 210 | 7000003852 | Harley-Davidson Embossed B&S Stainless S | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2480 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-04-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 270 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04021905 | Name 2 | Name 2 | 2019-04-03 | USSOLE | 16 | EA | 16 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 20 | 90 | 7000004211 | SEALING RING, 20071-312 | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11762536 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 0 | Replace pump cover on Jockey Pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
61006509 | 508 | SDTA Missing PG-77401-107 on Buoy | S39 | Gas Treating | 2021-12-31 | 2020-04-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.PG-77401-107 | Gas Export Pipeline Press Gauge | 2019-12-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2022-01-01 | 119629000000 | 20 | 10 | 7000000062 | 0-20,000 psi Sub Sea Gauge will ship loo | 2022-03-31 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 3/1/20 | 11962905 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-04 | USNSB4 | 1 | EA | 0 | Replace PG-77401-107 on KAA77402 | REL CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 150 | 1001769788 | ELB BW,316L,90DEG,LR,80S,NPS2 | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 111 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1100 | 7000003852 | Estwing Gooseneck Wrecking Bar PRO - 24" | 2021-03-31 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 110 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST20CG0146 | MarineForman | USRRIG | 2020-02-20 | USCDP7 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 220 | 7000002596 | Stud, 1 1/8" x 8 3/4" LG., ASTM A193 Gr. | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 118 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 40 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60507050 | 508 | STB Vent N2 snuffing system rusting | S06 | General | 2020-03-10 | 2019-02-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.ZZZ-12707 | Cargo Vent Stacks N2 Stuffing System | 2019-06-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-11 | 113805000000 | 20 | 70 | 1001772402 | GARJ,SS316,OCTAL,R15 | 2020-03-10 | Received at Worksite |  | 2019-06-07 |  | U182 | 8201 | Stones Main | ST KB B3 | 11380546 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-04-19 | USNSB4 | 2 | EA | 2 | Replace Rusted Components Starboard Vent | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MAOK WPOK ZPMM | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 990 | 7000002591 | McMaster Carr Part No. 98480A640 - 18-8 | 2020-03-15 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 99 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081903 | Name 4 | Name 59 | 2019-10-08 | USSOLE | 14 | EA | 14 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118369 | 508 | 2020 BBSM / Awards / Recognition | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000000133 | Order Number: 0265387 SALESORDER_0019320 | 2020-02-28 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090726 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | O20ACR002S | Entity 5 | USJRF5 | 2020-02-13 | USLFA4 | 1 | EA | 1 | 2020 BBSM / Awards / Recognition | REL ESTC PRC SETC | EXEC STDG | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 360 | 1002058431 | NUT,A563-DH,HEXAGONAL,UNC,1/2,SERMAGARD | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 36 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 5 | EA | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 400 | 1001210745 | PIPE MET,SA106 GR.B,XH,1.1/2in | 2019-11-20 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 40 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06141901 | Name 2 | Name 59 | 2019-06-17 | USDKFB | 21 | FT | 21 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60315607 | 508 | Replace SC3 LVDT2 Sensor | S19 | Marine Systems | 2020-06-12 | 2019-02-26 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-88503 | Structural Connector No. 3 | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-12 | 111682000000 | 20 | 10 | 7000005901 | 011317340983-M LINEAR VARIABLE DIFFERENT | 2020-12-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11168151 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-10-14 | USNSB4 | 2 | EA | 0 | Replace SC#3 LVDT Sensor | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61035031 | 508 | Abandon Winch HMI ESD Plunger OOS | S19 | Marine Systems | 2020-03-29 | 2020-05-01 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.MA.PS.LCP-89002 | Abandonment Winch Hydraulic Control Pnl | 2020-01-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-29 | 119955000000 | 10 | 10 | 7000005901 | 8003/111-001 UL PUSHBUTTON NO-NC | 2020-03-29 | Received at Target Location | 2020-02-11 |  |  | U182 | 8201 | Stones Main | MMR758 2-19-2020 | 11995474 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-27 | USNSB4 | 2 | EA | 1 | Replace ESD Plunger, Abandon Winch HMI | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD WPOK ZPMM | Kit Complete
60233847 | 508 | N2 Accum 5" Flange Maintenance | S19 | Marine Systems | 2020-05-01 | 2019-07-01 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.PS.ZZZ-87413 | Heave Compensation System Cylinder Mod 1 | 2019-11-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-05-03 | 110780000000 | 10 | 30 | 7000000111 | P/N: RETAIN RING 5.00 METRIC AISI 302 | 2020-05-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11077989 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2019-11-20 | GW982959 | 2 | EA | 2 | INST SCAFF. Accum 5" Flange Maintenance | REL ESTC GMCO GMPS PRC SETC | APPR EOM MAGN MAOK WPOK ZPMM | Approved
61165608 | 508 | PMS RIO Control cabinet fan not working | S03 | Elect. Systems | 2020-02-18 | 2021-01-13 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.ES.PM.RIO-45102 | Power Mgmt System Remote I/O Panel | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-18 | 121456000000 | 10 | 10 | 7000003852 | ebmpapst Fan DV4650-470 230VAC 50HZ 110M | 2020-02-18 | Received at Worksite |  | 2020-02-08 | 2020-02-25 | U182 | 8201 | Stones Main | ST KB A3 | 12145572 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-23 | USAWJB | 2 | EA | 2 | PMS RIO Control cabinet fan not working | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | ST1A2C 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2790 | 1001816265 | GASW,CL300-600,316,GPH,NPS3 | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 303 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 49 | EA | 49 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 900 | 7000003197 | TB SSW6VSP SS VERTICAL ADJUSTABLE 6IND | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 921 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 10 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6570 | 7000002629 | Tee, 1/2" x 1/2", SW, 400 PSIG WOG, ASME | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 868 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4500 | 7000002629 | Threadolet, 2" x 1/2", 3000#, FS MSS-SP- | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 502 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 760 | 7000003197 | SSTF06SHB9012SS 6INW CHNL TRAY H90 12INR | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 907 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 5 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 40 | 7000002629 | Sockolet, 1/2", CL 3000, ASME B16.11, AS | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 1 | EA | 1 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 390 | 7000002644 | BALL VALVE, 3", VBF-302 FP | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 52 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60055275 | 508 | O/SI Incorrect material on gauge LG-7715 | S04 | Gas Compress | 2020-04-11 | 2019-03-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.LG-77151A-231A | 1st Stage Suction Scrubber Level Gauge | 2019-02-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-11 | 108488000000 | 10 | 40 | 7000002603 | 00000 VCS03150 3" 150# VCS FLANGE INSULA | 2020-04-11 | Ready for Shipment after Kitting | 2019-02-25 | 2019-03-27 |  | U182 | 8201 | Stones Main | ST KB C7 | 10848765 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-02-12 | USJDJW | 2 | EA | 2 | LG-7715 change bolting/gaskets | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
60756604 | 508 | Vacuum Condenser Heat Exchanger | S17 | Steam/Hot H2O | 2020-04-01 | 2019-06-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.HBG-11508 | COPT Vacuum Condenser Heat Exchanger | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 116627000000 | 10 | 10 | 7000000101 | REVERSING COVER:QTY 1, item 5 | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 11662728 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2019-10-14 | GW982959 | 1 | EA | 0 | Main condenser tubes leaking | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WP ZPMM ZPVS | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1310 | 7000002603 | 1 1/2" FLG PROTECTOR (FLG,1.1/2",300 RF | 2019-12-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 147 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12101801 | Name 2 | Name 2 | 2018-12-11 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60739070 | 508 | COT 3 S IG Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127058 | COT 3 SB IG Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116430000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642966 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 590 | 7000003852 | Genius Tools 590216 Ball Peen Hammer 1 L | 2020-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 59 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0011 | Name 29 | USRRIG | 2020-02-18 | USLFA4 | 10 | EA | 10 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 710 | 7000002591 | DRILLFORCE HSS Jobber Length 10 PCS,17/6 | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 71 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 2 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60675080 | 508 | Cracked motor frame on Ejector pump #3 | S18 | Water Systems | 2020-12-24 | 2019-09-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PBE-12204C | No. 3 FW Generator Ejector Pump | 2019-12-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-12-24 | 115709000000 | 10 | 30 | 7000000037 | ITEM 60 FORMED WIRE SPRING -- ARTICLE NU | 2020-12-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11570947 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-20 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 40 | 7000003768 | 1”x 6’ CEE2-91, 2 ply E & E nylon | 2020-01-25 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0002 | Name 17 | USJRF5 | 2020-01-08 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU ST1A4B 01/22/2020 CMR
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 860 | 7000002591 | Harris Welding Helmet/Hood Clear Lens Co | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 86 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 3 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60367921 | 508 | CARGO-Dummy Spade Replace COT 5S IG Line | S06 | General | 2020-03-20 | 2018-11-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127046 | COT 5 SB IG Main Manual Valve | 2019-05-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-22 | 112273000000 | 10 | 40 | 7000002596 | 5/16 1105/1280 SERMAGARD FLAT WASHERS | 2020-03-20 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | Warehouse floor | 11227253 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-05-15 | USNSB4 | 64 | EA | 64 | CARGO-Dummy Spade Replace COT 5S IG Line | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | ST1FLR 2/3/20 GG
60440621 | 508 | Replace Laydown Timber - MODs 15, 17, 19 | S40 | Cargo Handling | 2020-03-10 | 2020-06-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.LS | Loading Stations | 2019-08-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 113072000000 | 10 | 30 | 7000002583 | M22x39.00mm O.D., Flat Washer, Stainless | 2020-03-10 | Received at Worksite |  | 2019-09-11 |  | U182 | 8201 | Stones Main | ST KB A1 | 11307214 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-05 | USAWJB | 30 | EA | 30 | Replace Laydown Timbers - MOD 15 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAOK RUSH WPOK | EXEC |  |  | PU KB A1
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 870 | 7000003343 | Beam, W10 X 30, ASTM A992 (1 @ 40' LG) | 2020-01-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 87 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08201901 | Entity 3 | Name 59 | 2019-08-20 | USSOLE | 40 | FT | 40 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 630 | 7000002591 | 4452K144 Plug with External Hex Drive, 1 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 63 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 110 | 1000720080 | TEE,UNION,SWAGELOK,SS-1210-3,3/4in | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 9 | EA | 9 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
61102257 | 508 | P.Crane radiator fan shroud corroded | S40 | Cargo Handling | 2020-05-10 | 2020-06-10 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-10 | 120716000000 | 10 | 70 | 7000006081 | Guard sheet 21828 | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12071582 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 2 | EA | 0 | P.Crane radiator fan shroud corroded | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
60911833 | 508 | Hi-Ex Foam VPSV & PSV Replace Order | S13 | Fire Protect | 2020-02-04 | 2019-10-24 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PVV-33170-001 | Foam Tank Pressure Vaccum Relief Valve | 2019-10-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-04 | 118544000000 | 20 | 10 | 7000005901 | 546531 PRESSURE/VACUUM RELIEF | 2020-03-19 | Received at Worksite | 2020-01-17 | 2020-02-03 | 2020-02-06 | U182 | 8201 | Stones Main | ST KB A7 | 11854406 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-15 | USNSB4 | 1 | EA | 1 | Replace VPSV & PSV Hi-Expansion Foam | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK RUSH WPOK XGI | TECO |  |  | ST1A5C 01/29/20 GG
60847987 | 508 | MOC GTG3 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-24000 | Gen #3 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 70 | 7000005901 | NK Technologies AT2-420-24L-FT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780940 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI78 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 2 | EA | 2 | SAEP LO/TO Isolate GTG #3 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60079802 | 508 | O/SI XV-6636P-210, 6P Str. Suction 8" | S21 | Oil Treating | 2020-03-12 | 2018-06-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6636P-210 | Crude Oil to/from COT 6 On/Off PS Valve | 2018-05-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-13 | 108901000000 | 10 | 10 | 7000000105 | REPAIR KIT 8" NAKAKITA VALVE (10K-000A, | 2020-03-12 | Received at Worksite |  | 2018-10-17 |  | U182 | 8201 | Stones Main | ST KB D5 | 10890124 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-05-29 | USNSB4 | 1 | EA | 1 | Replace Soft Goods XV-6636P-210 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU Aaron 10/03/2018
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 320 | 1001690134 | NUT IMP,SS316,UNC,1/4in,W/NYLON INSERT | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 32 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 200 | EA | 200 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3400 | 1001768449 | ELB BW,WPB,90DEG,LR,40,NPS4 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 370 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 11 | EA | 11 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60665884 | 508 | O/SI Passing Valve SW.115-304V | S17 | Steam/Hot H2O | 2020-03-25 | 2019-09-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.115-304V | PCV Bypass Valve | 2019-11-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-26 | 115603000000 | 30 | 10 | 7000004211 | 20K150AWC-GT-HW, F-7313, Cast steel Glob | 2020-06-07 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11560290 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-25 | USNSB4 | 1 | EA | 0 | Replace 8" Control Valve SW.115-304V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 70 | 7000006081 | 304-050X3 PIPE NIPPLE 1/2 X 3'' LG.S/S | 2020-04-29 | Received at Target Location | 2020-02-13 |  | 2020-02-22 | U182 | 8201 | Stones Main | STONES | 11772908 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-13 | USAWJB | 4 | EA | 4 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4890 | 7000002629 | FLANGE, 4" 300 LB RFWN SCH 10S ASME B16. | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 550 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 90 | 7000002629 | 12" 300 # ASME B16.5 ASTM A182 GR F53 TA | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 635 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4570 | 1002316830 | GASW,CL300/600,316/316L,GPH,3in | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 509 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 12 | EA | 12 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3730 | 1001566525 | TUBING,SQUARE,A500-B,4x4x1/4in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 403 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 60 | 7000004213 | KE35/9 SASAKURA KE35 P/N 9 ORIFICE | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 210 | 7000002629 | TEE, 6" X 3", S/160 (0.719 WT) X S/XXS ( | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 34 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61134552 | 508 | Helideck foam monitor upgrade MOC 80280 | S13 | Fire Protect | 2020-05-27 | 2020-07-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF331-12100 | FiFi Helideck Foam System | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-27 | 121087000000 | 10 | 50 | 1001646145 | GASKET,GARLOCK,37010-7106,CL150,6in | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H04 | 12108694 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST03022001 | Name 4 | Name 60 | 2020-03-03 | USSOLE | 5 | EA | 0 | Helideck foam monitor upgrade MOC 80280 | REL ESTC PRC SETC | APPR MAGN MANX WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6440 | 1000716217 | GASW,316L,GPH,CL300,3in | 2020-02-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 808 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01282001 | Name 4 | Name 4 | 2020-01-29 | USDKFB | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 710 | 7000000052 | BRACKET,HEAVY DUTY,METAL,20# | 2020-03-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1016 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-16 | USSOLE | 4 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 280 | 7000002603 | PIKOTEK INSULATING FLANGE KIT, 3", 300#, | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 41 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5570 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-12-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 631 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12121901 | Name 4 | Name 4 | 2019-12-13 | USABCE | 36 | EA | 36 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60313098 | 508 | O/SI VADB-857032 on HP1 Valve | S24 | Subsea Systems | 2020-03-18 | 2019-08-24 | O.US.STO.STO.002.724FP | 508ACR | US.WR508A.SE.OH.ZZZ-55401 | Subsea Valves Hydraulic Power Unit | 2019-03-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-03-18 | 111656000000 | 10 | 10 | 1002509014 | VALVE,DBB,SWAGELOK,DB16M4M2V15,1in | 2020-03-18 | Received at Worksite |  | 2019-05-20 |  | U182 | 8201 | Stones Main | Issued | 11165575 | 1 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 38 |  | 2019-03-26 | USNSB4 | 1 | EA | 1 | LO/TO Perform Isolations To Replace Defe | REL PRT GMPS PRC SETC | EXEC EOM MAOK WPOK | EXEC |  |  | PUST1A1B 5/17/19 MJP
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 370 | 1001621891 | CBL,AMER-CBL,37102613BS,16AWG,4PAIR | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 829 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 887 | FT | 887 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4910 | 7000002629 | FLANGE, 2" 300 LB RFWN SCH 40S ASME B16. | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 552 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118371 | 508 | 2020 Lab Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 40 | 7000003852 | Cateck Bus-Powered USB 3.0 3-Port Alumin | 2021-03-11 | Received at Target Location |  | 2020-01-11 |  | U182 | 8201 | Stones Main | STONES | 12090728 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20OP001 | Name 27 | USRRIG | 2020-02-27 | USCDP7 | 1 | EA | 1 | 2020 Lab Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60847991 | 508 | MOC GTG1 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-04000 | Gen #1 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117810000000 | 10 | 20 | 7000005901 | Hawke Part Number 121 / A / M20 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780966 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI76 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #1 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
61098380 | 508 | Biocide Chemical Inj for Cargos & Drains | S21 | Oil Treating | 2020-09-28 | 2020-11-27 | C.US.STO.FI.19.012.1230A | 508CI&E | US.WR508A.OT.SS.VE663-70000 | Cargo Tank Systems | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-09-28 | 120671000000 | 10 | 20 | 7000000052 | S6FSSPFSLTT100 - stock subject to prior | 2020-09-28 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 12067106 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI76 | Name 2 | Name 61 | 2019-12-23 | USSOLE | 7 | EA | 0 | Biocide Chemical Inj for Cargos & Drains | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60352955 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-09 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33310 | No. 1 Port Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-10 | 112105000000 | 10 | 80 | 1000717534 | OIL,MTR,30 W,51006,SHELL | 2020-02-09 | Received at Worksite |  | 2020-01-19 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210547 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-02 | USAWJB | 2 | QT | 12 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 100 | 7000003196 | 1/2" x 1/2" MNPT Straight Fitting (Swagelok | 2019-11-19 | Received at Target Location |  |  | 2020-02-14 | U182 | 8270 | Danos - Amelia | Onsite Danos Has | 11882270 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI66 | Name 15 | Name 58 | 2019-11-06 | USABCE | 6 | EA | 6 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60975393 | 508 | O/SI BGCB Discharge Valve Passing | S04 | Gas Compress | 2020-02-15 | 2021-12-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VABL-771293 | Outlet Gas SDV Isolation Valve | 2019-12-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 8 User defined period | 2020-02-15 | 119261000000 | 10 | 30 | 7000004751 | 7/8" X 5-1/2" Teflon Coated Studs w/ Nut | 2020-02-15 | Received at Worksite | 2020-01-13 | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Stones | 11926135 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-24 | USAWJB | 24 | EA | 24 | Replace VABL-771293 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 80 | 7000003323 | Part# 200-A-SS | 2019-09-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 31 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN082 | Name 2 | Name 2 | 2019-08-19 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
61219231 | 508 | GT #1 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113 | Generator #1 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 30 | 7000003763 | 1210 28MM TL BUSHING 119588 | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206815 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #1 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61118336 | 508 | 2020 Lube Oils / Grease - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 30 | 7000003946 | Citgo Compressor-Gard PAG-220 oil 55 gal | 2020-02-10 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | CPORT | 12090693 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0007 | Name 17 | JP832018 | 2020-01-28 | USLFA4 | 4 | DR | 4 | 2020 Lube Oils / Grease - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60585840 | 508 | Latch Mech Hydr Vlvs-Incorrect Material | S19 | Marine Systems | 2020-03-25 | 2019-03-27 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-25 | 114695000000 | 10 | 10 | 7000000106 | RPIC-LNN/AP AISI316 pressure relief valv | 2020-03-25 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | ETA 10/31 | 11469454 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-02-19 | USAWJB | 6 | EA | 6 | Replace Latch Mech Hydr Valves | REL ESTC GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 30 | 7000000039 | YMD-8529 HOSE ASSEMBLY X45"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60747150 | 508 | COT 3 P HC Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127026 | COT 3 PS HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651962 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60840919 | 508 | Relocate PORT CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-02-25 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-25 | 117729000000 | 10 | 30 | 7000000101 | 1" Nipple Stainless Steel 304 x Close | 2020-02-25 | Received at Worksite | 2019-11-27 | 2020-01-20 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772907 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 10 | EA | 10 | Relocate Crane Slew G-box Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD MAOK NCMP WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60884227 | 508 | Lagging for new 16 K Bellows | S17 | Steam/Hot H2O | 2020-03-03 | 2019-10-05 | O.US.STO.STO.005.724FP | GISNCANI | US.WR508A.GU.SW.VE115-41000 | 16K Steam System in Engine Room | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-03 | 118224000000 | 20 | 20 | 7000000132 | Lagging, 26" x 27" | 2020-03-03 | Received at Worksite | 2020-02-11 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1ASIDE | 11822353 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-11 | USMNF8 | 1 | EA | 1 | Install Pipe insulation on flange | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
61104543 | 508 | Rebuild MPV on #4 Inst Air Comp | S08 | Air Systems | 2020-02-27 | 2020-06-11 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11801D | No. 4 Air Compressor | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-28 | 120737000000 | 20 | 20 | 1002404354 | PRESSURE VALVE,2906 0959 00,ATLAS-CO | 2020-02-27 | Received at Worksite | 2020-02-11 | 2020-02-11 | 2020-02-14 | U182 | 8201 | Stones Main |  | 12073700 | 2 | 1 | Stocked Locally (Reservation) | L | X |  |  |  |  | 2020-02-04 | USMNF8 | 1 | EA | 1 | Rebuild MPV on #4 Inst Air Comp | TECO CNF GMPS PPRT PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI ZPMM | TECO |  |  | ST1A2C 02/12/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1730 | 1001759241 | SB2N,A193B8MCL2,UNC,4.5in,5/8in | 2019-01-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 190 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01171901 | Name 2 | Name 2 | 2019-01-18 | USDSVB | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4520 | 7000002629 | Elbow, 3", LR 90, S/10S, BW, ASME B16.9 | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 504 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 170 | 1000719976 | COIMC,SWAGELOK,SS60016,3/8x3/8NPT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 795 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 30 | EA | 30 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6600 | 7000002629 | Elbow, 3", LR 90, BW, .095 Min Wall, AS | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 871 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 7 | EA | 7 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 520 | 7000002629 | PLUG, 1/2", SC, HEX HEAD, ASTM A182 GR F | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 68 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3080 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 338 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2530 | 7000002629 | FLANGE, 12", 300#, RF, WN, SCH 10S, ASTM | 2019-04-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 275 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04021905 | Name 2 | Name 2 | 2019-04-03 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 90 | 7000003852 | Hallmark Reversible Christmas Wrapping P | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2320 | 1001645341 | BLT HEX,A325,UNC,2in,3/4in,SERMAGARD | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 254 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 28 | EA | 28 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60663676 | 508 | Actuator Assembly Malfunction | S06 | General | 2020-05-07 | 2019-09-14 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.HC.TCV-12501-410 | FW Coolers Outlet Temp Control Valve | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-07 | 115578000000 | 20 | 10 | 7000003852 | YUFUTOL Carbide Burrs Set 10pcs Double C | 2020-05-07 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main |  | 11557766 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  |  |  | 2020-01-05 | USMNF8 | 1 | EA | 1 | Replace Actuator Assembly | REL ESTC GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1840 | 7000002596 | STUD BOLTS, 7/8" DIA. X 5 1/2" LONG, AST | 2019-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 202 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01241901 | Name 2 | Name 2 | 2019-01-24 | USSOLE | 28 | EA | 28 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60562362 | 508 | O/SI Passing Valve 3rd stage PST-330A MG | S04 | Gas Compress | 2020-03-10 | 2019-03-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VAMO-771031 | Pressure Transmitter Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 114424000000 | 20 | 30 | 7000004211 | 2-250 BX-152 | 2020-03-24 | Received at Worksite |  | 2020-02-07 |  | U182 | 8201 | Stones Main | ST1A4C | 11442408 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-30 | USNSB4 | 2 | EA | 2 | Replace Defective Valve 3rd stage PST-33 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC |  |  | ST1A4C 01/29/20 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1990 | 7000002596 | 8" SQUARE U-BOLT W/ DOUBLE NUTS (SEE ATT | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 221 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 60 | 7000006192 | HPBWB12M12F 3/4" MNPT x 3/4" FNPT; 316SS; 6, | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 36 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-17 | USSOLE | 17 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 770 | 7000002591 | DRILLFORCE (5 Pcs) 23/64 in. x 4-7/8 in. | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 77 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 3 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60661316 | 508 | Seals M.E. Exhaust Valves 4,5,6 leaking | S19 | Marine Systems | 2020-04-28 | 2019-09-12 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.PR.XXX-109-MIS-00 | Main Engine Cylinder No. 4 | 2020-02-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-03 | 115550000000 | 30 | 20 | 7000000030 | Packing | 2020-04-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 11555015 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  |  | USNSB4 | 2020-02-12 | USNSB4 | 1 | EA | 0 | MAN - Rpl Seals on Exhaust Valves 4,5,6 | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM ZPVS | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 580 | 7000003852 | Wilton 90412 4-pound Head, 12 B.A.S.H B | 2020-03-06 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 58 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOMEC0011 | Name 29 | USRRIG | 2020-02-18 | USLFA4 | 4 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60739064 | 508 | 6P Vent netherlock not locking | S06 | General | 2020-05-21 | 2019-11-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127040 | COT 6 PS Vent Main Isolation Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642940 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-17 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 110 | 7000003739 | 947027C1 SHAFT,ACCY DRIVE | 2020-02-24 | Received at Target Location |  |  | 2020-02-26 | U182 | 8201 | Stones Main | STONES | 12155706 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO
60470624 | 508 | Turret Gantry Crane Out of Service | S40 | Cargo Handling | 2020-06-01 | 2019-11-19 | O.US.STO.STO.005.724FP | GHEMSPAR | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-06-01 | 113409000000 | 10 | 50 | 7000000040 | Parking Chain Stainless Steel | 2020-06-01 | Received at Worksite |  | 2019-07-17 | 2020-01-02 | U182 | 8201 | Stones Main | ST KB B2 | 11340935 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-02-15 | USRAR6 | 38 | EA | 38 | Turret Gantry Crane Out of Service | TECO PCNF ESTC GMPS PPRT PRC SETC | XCNF NCMP WPOK XGI ZPVS | TECO |  |  | PU Marty S 05/07/2019 CR
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 420 | 7000000098 | 1" RENEGADE BLUE EACH 1" X 4FT CHEMICAL | 2020-03-16 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 42 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOET00120 | Name 3 | USCRFI | 2020-02-09 | USLFA4 | 3 | EA | 3 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1 FLR 2/24/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 330 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 33 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 70 | EA | 70 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61219231 | 508 | GT #1 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113 | Generator #1 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 10 | 7000003763 | 8MGT-1120-12 POLY CHAIN BELT | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206815 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #1 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 30 | 7000006081 | BV-SS-FP 050 1/2 BALL VALVE 2000 PSI S/S | 2020-03-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-13 | USAWJB | 4 | EA | 0 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
60973122 | 508 | MGC-B 3rd Stg Bridle Removal | S04 | Gas Compress | 2020-04-18 | 2020-09-25 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-10000 | Main Gas Compression System Train B | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-19 | 119235000000 | 10 | 30 | 7000004751 | 2" 1500 RTJ Ring Gaskets | 2020-03-19 | Received at Worksite | 2020-01-06 | 2020-01-06 |  | U182 | 8201 | Stones Main | ST KB C7 | 11923512 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 59 | 2019-10-02 | USAWJB | 4 | EA | 4 | MGC-B 3rd Stg Bridle Removal MOC78183 | REL PRT GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU WPT AMW 11/30/19
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7270 | 7000003344 | Plate, .5" x 96" x 120", ASTM A572 GR 50 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 985 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 600 | 7000006110 | SLING,WEB,TUFFY,EEF2901P-06,2PLY,1inx6ft | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 777 | 4 | Non-Stock (Purchase Requisition) | N |  |  | SWR551A388 | Name 2 | Name 2 | 2020-01-27 | USSOLE | 8 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3710 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 401 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4160 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 466 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 238 | EA | 238 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 80 | 1002360784 | SB2N,B7,2H,UNC,5/8in,3.5in,DOXSTEEL | 2019-11-27 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI67 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 5 | EA | 5 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 50 | 7000002629 | FLANGE, 14", 150#, RF, WN, ASTM A105N, A | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 860 | 7000002591 | 6'' Saw-Zaw Blades (Milwaukee Torch Bime | 2020-03-03 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia |  | 11179936 | 1076 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-28 | USLFA4 | 100 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2650 | 7000002629 | TEE, 12" X 12", S/10S (0.180 WT) X S/10S | 2019-05-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 288 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04301901 | Name 2 | Name 2 | 2019-05-01 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 40 | 7000002596 | Studs, M22 x 270mm LG., ASTM A193 Gr. B7 | 2020-03-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E27 | 11477345 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05141901 | Entity 2 | USAWJB | 2019-05-14 | USSOLE | 18 | EA | 18 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
60911821 | 508 | Replace starting solenoid on Gen# 3 | S03 | Elect. Systems | 2020-04-28 | 2019-10-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.ES.PG.ZZZ-11101C | Essential Generator No. 3 Engine | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-28 | 118543000000 | 20 | 20 | 7000005901 | 51314-01D SOLENOID VALVE 3/2 N/C | 2020-04-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11854297 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-18 | USMNF8 | 1 | EA | 0 | Replace starting solenoid | REL ESTC GMPS PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7790 | 7000002629 | Tee, 1" x 1", 3000#, SW, ASME B16.11, AS | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1049 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1440 | 7000002603 | GASKET, 12" 150, SPIRALWOUND, 1/8" THK C | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 160 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 9 | EA | 9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2080 | 7000002629 | FULL FACE BLEED RING, 8", 300#, RF, 1.5" | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 230 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6530 | 7000002662 | Pipe, 2", .083 Min Wall, ASTM B466, 90/1 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 864 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 180 | FT | 180 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60725219 | 508 | Replace Suction and Discharge Gauges | S18 | Water Systems | 2020-02-09 | 2020-04-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PG-12110A-102 | Pump Suction Pressure Gauge | 2019-12-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-09 | 116277000000 | 10 | 40 | 7000000062 | WK TAG SS TAG Mfr: WIKA INSTRUMENT CORP | 2020-02-09 | Received at Worksite | 2020-01-13 | 2020-01-29 |  | U182 | 8201 | Stones Main | ST KB A6 | 11627685 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 2 | Replace Suction and Discharge Gauges | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 2/5/2020 JH GG
60825651 | 508 | ECR Console Cooling Fan Failing | S19 | Marine Systems | 2020-02-05 | 2020-06-24 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.MA.PR.ZZZ-10901 | Main Engine Ctrl System Control Panel | 2019-10-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-05 | 117556000000 | 10 | 10 | 7000005901 | DP200A-2123-XBT-R 220VAC FAN | 2020-02-05 | Received at Worksite | 2019-11-20 | 2020-01-20 | 2020-02-09 | U182 | 8201 | Stones Main | ST KB A3 | 11755555 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-15 | USNSB4 | 4 | EA | 4 | Replace ECR Console Cooling Fan | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK RUSH WPOK XGI | TECO |  |  | PU Aaron ST1A1B 01/19/2020 C
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 70 | 7000003684 | AIR-POWERED HAMMER KIT FOR SOLID RIVETS< | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 370 | 7000002603 | 10", 300#, Flex Gasket 316 spiral wound, | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 82 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 3 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60847991 | 508 | MOC GTG1 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-04000 | Gen #1 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117810000000 | 10 | 60 | 7000005901 | M20 Locknut | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780966 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI76 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #1 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1110 | 7000002591 | Pilot for mag drill bit | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 111 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 18 | EA | 18 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 290 | 1001664216 | WASHER,LOCK,F436,SERMAGARD,5/8in | 2020-04-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F90 | 11581210 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11201901 | Name 4 | Name 60 | 2019-11-20 | USABCE | 3 | EA | 3 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60739066 | 508 | COT 4 Port vent netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127050 | COT 4 PS Vent Gas Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642942 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 710 | 1001645338 | BLT HEX,A325,UNC,2.1/4in,3/4in | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 71 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 68 | EA | 68 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 240 | 7000002596 | M22" x 2 3/4" A193 B7 Cap Bolt, Xylan | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 24 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 10 | EA | 10 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60739068 | 508 | COT 5S IG netherlock fail to lock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127052 | COT 5 SB IG Vent Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642944 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 70 | 7000002591 | Gasket, 20", 5K, Garlock Graph-Lock Styl | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 9 | EA | 9 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6390 | 7000002603 | Gasket, 4", 150#, FF, 1/8" THK. W/Spacer | 2020-01-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 758 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01142001 | Name 4 | Name 4 | 2020-01-14 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 380 | 7000002591 | 2''x8'x2Ply Nylon Straps | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 747 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A384 | Name 2 | Name 2 | 2020-01-11 | USSOLE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 540 | 1001816265 | GASW,CL300-600,316,GPH,NPS3 | 2020-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 768 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A382 | Name 2 | Name 2 | 2020-01-20 | USSOLE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6740 | 7000002603 | GASKET,GARLOCK,37010-7104,CL150,4in | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 885 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 7 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 280 | 7000003852 | AmazonBasics Large Travel Luggage Duffel | 2020-12-07 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 28 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES11 |  |  | 2019-11-11 | USABCE | 2 | EA | 2 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 80 | 7000002603 | 20" Flange Protector | 2020-03-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E27 | 11477345 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05141901 | Entity 2 | USAWJB | 2019-05-14 | USSOLE | 2 | EA | 2 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3850 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2019-11-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 435 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10311902 | Name 2 | Name 2 | 2019-10-31 | USSOLE | 140 | EA | 140 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1570 | 1001271538 | ANGL MTL,EQ,CS,20ft,L4x4x1/4in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 173 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61019557 | 508 | N2 Generation Membrane Filter E Repair | S08 | Air Systems | 2020-03-01 | 2019-12-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.MAK-11827E | E Membrane Filter | 2019-10-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-01 | 119776000000 | 10 | 20 | 7000002596 | 1/2 X 3 (2-3/4 FTF) DOX PLTD STUD BOLT | 2020-03-01 | Received at Worksite | 2019-11-06 | 2020-02-16 | 2020-03-02 | U182 | 8201 | Stones Main | STA1 Side | 11977557 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USAWJB | 8 | EA | 8 | N2 Generation Membrane Filter E Repair | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 310 | 7000002591 | ¾” drive 50mm impact socket Part number | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 31 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0140 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60352956 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-10 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33320 | No. 1 Starboard Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-11 | 112105000000 | 10 | 30 | 1002386483 | OIL,LUBT,SHELL,ROTELLA T4 TP 15W 40,1gal | 2020-02-10 | Received at Worksite |  | 2019-10-20 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210548 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-07-17 | USRAR6 | 2 | GLL | 2 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 40 | 7000004754 | 3/4" x 0.065 317L SMLS Coated Tubing | 2020-03-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 30 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI86 | Name 2 | Name 2 | 2020-02-07 | USSOLE | 140 | FT | 0 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 10 | 7000002662 | Pipe, 10", S/40S, ASME B36.19M, ASTM A79 | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 97 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 20 | FT | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60985323 | 508 | Port crane leaking exhaust pipe | S40 | Cargo Handling | 2020-03-24 | 2020-06-30 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZBE-87401 | Port Side Pedestal Crane Engine | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-27 | 119372000000 | 30 | 20 | 7000006081 | Exhaust clamp with Nuts/Bolts,, | 2020-03-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11937169 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-10 | USMNF8 | 1 | EA | 0 | Replace Port crane exhaust Pipe | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
61149205 | 508 | Overboard Oil in Water Analyzer PC Failu | S26 | Water Treating | 2020-02-11 | 2020-03-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.WT.FL.AT-12403-121 | Produced Water to Slop Tank Oil Analyser | 2020-01-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-11 | 121253000000 | 10 | 10 | 7000000093 | Overboard oil in water analyzer PC | 2020-02-11 | Received at Worksite | 2020-01-28 | 2020-02-07 | 2020-02-17 | U182 | 8201 | Stones Main | ST1A1C | 12125307 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 39 |  | 2020-01-15 | USAMH7 | 1 | EA | 1 | Replace PC, Test, & Calibrate | TECO CNF ESTC GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU Wayne P 02/11/2020
61179024 | 508 | Pad eyes on hose reel | S21 | Oil Treating | 2020-03-17 | 2020-03-25 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.ZZZ-66410 | Offloading Hose Reel | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-19 | 121603000000 | 10 | 10 | 7000002596 | 3/4-10 X 4 HVY HEX BOLT A193 B7 W/ 1 HV | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12160286 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-26 | USAWJB | 30 | EA | 0 | Install Pad Eyes Hose Reel Drum | REL PCNF PPRT PRC SETC | APPR MAGN WP | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 500 | 1001724723 | BEAM,WIDE,A992-50,8x24 | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 50 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 20 | FT | 20 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 110 | 7000004213 | KE35/14 SASAKURA KE35 P/N 14 GLOBE VALVE | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
60739059 | 508 | 6S HC Netherlock Not Locking Open/Closed | S06 | General | 2020-04-01 | 2019-11-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127017 | COT 6 SB HC Main Isolation Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642935 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 210 | 7000002629 | 3/4" Flange ASME B16.5 CL300 RF Thread fla | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 5 | EA | 5 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
61200672 | 508 | Stones Small Civil Projects 2020 |  |  | 2020-12-31 |  | P.US.STO.NF.20.009.7240A | GENERIC |  |  | 2020-02-11 | WO | U100 | GEN | US01 | P16 | [5 empty] | 3 Low | 2020-12-31 | 121848000000 | 10 | 50 | 7000002603 | Flange Protector for Weld Neck Backing F | 2020-02-28 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G97 | 12184838 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST02242002 | Name 4 | Name 60 | 2020-02-27 | USSOLE | 1 | EA | 0 | Stones Small Civil Projects 2020 | REL ESTC PRC SETC | APPR | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 80 | 1000711269 | VALVE,BALL,SWAGELOK,SS-65TF12,3/4in | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 6 | EA | 6 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 90 | 1000709977 | ADAPTOR,TUBE,SWAGELOK,SS12TA18,3/4x1/2in | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 3 | EA | 3 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6730 | 1001566527 | PLUG PIPE TH,AlBRZ,MNPT,1/2in | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 884 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60737084 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-02-08 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-219 | Crude Oil to/from Fwd COT'S On/Off Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-08 | 116406000000 | 10 | 10 | 7000000070 | BiFold MI FP03/S0A/C3/43/SC/S/RK-04 Repa | 2020-04-28 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-10 | U182 | 8201 | Stones Main | ST KB B6 | 11640589 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-27 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635S-219 | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 80 | 7000000133 | RKI 73-0622 RX-8700 Gas meter | 2020-02-28 | Received at Target Location |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG144 | Entity 7 | USKHU3 | 2020-02-05 | USLFA4 | 1 | EA | 1 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6290 | 7000002629 | Weldolet, 10" x 2", S/40 x S/80, MSS-SP- | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 737 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12271901 | Name 4 | Name 4 | 2019-12-26 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 50 | 7000003852 | Stainless Steel Shoulder Eye Bolts - Typ | 2020-01-15 | Received at Worksite |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO2CG0137 | Name 26 | USCRFI | 2020-01-14 | USLFA4 | 5 | EA | 5 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU CAPT. TIM
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3560 | 1001622964 | STL SECT MAR,BEAM,6in,5.990in,20ft | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Stones Solids Tie-in | 11179936 | 386 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161902 | Name 4 | Name 4 | 2019-10-17 | USGBI5 | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7250 | 1001676778 | SHT PLT SLD MET,4x8ft,1/4in,A572 GR.50 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 983 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 720 | 7000000052 | CABINET,FIRE EXT,FIBERGLASS,36 1/4" X 19 | 2020-03-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1017 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-16 | USSOLE | 4 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 20 | 7000002629 | Pipe Nipple, 1/2" x 4", S/160, PE x BE, | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 1 | EA | 1 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1760 | 7000002662 | PIPE, 12", S/10S (0.180 WT), ASTM A790 U | 2019-01-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 193 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01171902 | Name 2 | Name 2 | 2019-01-18 | USDSVB | 21 | FT | 19.8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60714079 | 508 | O/SI Steam Trap, Valves, Malfunctioning | S17 | Steam/Hot H2O | 2020-03-11 | 2019-06-15 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.74T | Drain Steam Trap | 2020-02-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-11 | 116148000000 | 20 | 10 | 7000004211 | 20k-25MM Globe Valve | 2020-03-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11614810 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-06 | USMNF8 | 2 | EA | 0 | RR Valves 115-394,395, 74T | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 60 | 7000000052 | Orion Level Instrument | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2301 | 11340898 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN103 | ORION | ORION | 2019-11-19 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 190 | 7000002629 | Reducing Tee, 3" x 1 1/2", S/10S x S/80, | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 170 | 7000002629 | Flange, 3", 600#, RFWN, S/80S Bore, ASME | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 113 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60970408 | 508 | CRN Boom Tip Platform Grating Deficiency | S06 | General | 2020-02-20 | 2020-03-26 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GN.MI.HG | Handrails & Grating | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-21 | 119205000000 | 10 | 50 | 7000002591 | T5J Intrepid Toe board links with mounti | 2020-01-27 | Received at Target Location |  |  | 2020-02-13 | U182 | 8270 | Danos - Amelia | Toe Boards | 11920544 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A390 | Name 2 | USMCS1 | 2020-01-25 | USLFA4 | 200 | EA | 200 | CRN Boom Tip Platform Grating Deficiency | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WP XGI | TECO
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 100 | 1002301613 | SB2N,B8M CL2,8M,UNC,5/8in,5.00in | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 106 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 9 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 320 | 1001763647 | SB2N,A193-B7,CTD,8UN,10.75in,1.1/4in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 77 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 14 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 120 | 7000003684 | BLACK-OXIDE HIGH-SPEED STEEL DRILL BIT | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 12 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60352956 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-10 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33320 | No. 1 Starboard Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-11 | 112105000000 | 10 | 40 | 1002386512 | OIL,COOLANT,SHELL,ZONE 50/5 0AF,1gal | 2020-02-10 | Received at Target Location |  | 2019-10-20 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210548 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-07-17 | USRAR6 | 1 | GLL | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 30 | 7000003739 | 246120-1 CLUTCH,SPRAG | 2020-01-19 | Received at Worksite |  | 2020-02-16 | 2020-02-26 | U182 | 8201 | Stones Main | ST KB B2 | 12155706 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-28 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO |  |  | PU 02/16/20 AMW
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 20 | 7000003458 | AFMR19017A.32B | 2021-01-22 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO190001A | Name 3 | USRRIG | 2020-01-06 | USLFA4 | 500 | GLL | 500 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 500 | 7000002591 | 4452K176 Bushing Adapter, 1 Male x 3/4 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 50 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60739065 | 508 | COT 4S Vent netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127049 | IG Vent COT 4 SB Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642941 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60847988 | 508 | MOC GTG4 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-34000 | Gen #4 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 60 | 7000005901 | M20 Locknut | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780943 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI79 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #4 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 60 | 7000002591 | Cap Bolt, 7/8" x 2" (Teflon Coated) | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 10 | EA | 10 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60874068 | 508 | FRC inspection deficiencies | S15 | Life Saving | 2020-02-13 | 2020-03-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2019-08-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-03 | 118106000000 | 10 | 50 | 7000004662 | ARMS Lifeboat, Oil Filter, Steyr SE256 | 2020-02-13 | Received at Worksite |  | 2020-02-13 |  | U182 | 8201 | Stones Main | Put in Stock | 11810577 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-04 | USAWJB | 1 | EA | 1 | FRC inspection deficiencies | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD MAGN WPOK | EXEC |  |  | PU 02/16/20 AMW
60737049 | 508 | Drive End Bearing Leaking Oil - BGCB | S04 | Gas Compress | 2020-03-25 | 2019-06-29 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.CM-77102B | HV Electric Mtr Booster Gas Compressor B | 2019-06-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-27 | 116406000000 | 10 | 20 | 7000000039 | 200350021 FLOAT LAB SEAL | 2020-03-25 | Received at Worksite |  | 2019-07-04 |  | U182 | 8201 | Stones Main | ST KB A4 | 11640554 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-06-07 | USJDJW | 4 | EA | 4 | LOTO- BGC B and lube oil pump | REL GMPS PRC SETC | EXEC EOM MAGN MAOK RUSH WPOK | EXEC |  |  | PU Aaron 07/08/2019
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 170 | 7000003852 | MSA 10106722 Combustible Gas and Methane | 2020-12-31 | Not Shipped |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 17 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | IT Dep. | USCRFI | 2020-02-14 | USJRF5 | 10 | EA | 0 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1200 | 1001678667 | CHNL,2.034,0.314,20ft | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 136 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061802 | Name 2 | Name 2 | 2018-12-07 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 660 | 7000003197 | PL SSF612LVO9012 SS 12INW 6IND OV-90 12I | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 897 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 2 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
61118331 | 508 | 2020 Chemical Order - Engine Room | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 20 | 7000003458 | AFMR19017A.32B | 2020-01-29 | Received at Worksite |  | 2020-01-10 |  | U182 | 8201 | Stones Main | CPORT | 12090688 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200004A | Name 40 | USRRIG | 2020-01-16 | USLFA4 | 1000 | GLL | 1000 | 2020 Chemical Order - Engine Room | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6650 | 7000002629 | Flange, 3", SO, 150#, FF, Min Wall .095, | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 876 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60739060 | 508 | COT 5 P HC netherlock fails to lock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.IG.VABF-127020 | COT 5 PS HC Main Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-21 | Not Shipped |  |  | 2020-02-13 | U182 | 8201 | Stones Main | Stones | 11642936 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-20 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | TECO ESTC CSER PRC SETC | XCNF MAGN NCMP WPOK XGI | TECO
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 110 | 7000003196 | Swagelok SS-810-3 | 2019-11-20 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI68 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 2 | EA | 2 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6830 | 7000002603 | Flange Protectors 2", SW, 150#, FF | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 894 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 35 | EA | 35 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 20 | 20 | 7000003852 | Apache 98108515 3/4" x 14" Farm Fuel Tra | 2020-01-28 | Received at Target Location |  | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB B5 | 11783572 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-03 | USMNF8 | 1 | EA | 1 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC |  |  | PU AARON W 01/19/2020
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 410 | 7000002591 | Additional Drawer Dividers For Above 18 | 2020-02-28 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 41 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WHSE26JAN2 | Name 19 | USJRF5 | 2020-02-04 | USLFA4 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 20 | 40 | 7000004211 | ROLLER BEARING, CYLINDRICAL 43563071, 20 | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A2B | 11762536 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 1 | Replace pump cover on Jockey Pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved |  |  | ST1A2B 02/18/2020 CMR
60936972 | 508 | GT3 Gas Fuel Valve Bolts Recalled | S03 | Elect. Systems | 2020-04-01 | 2020-03-07 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.FCV-11130-130 | Generator #3 Fuel Gas Flow Control Valve | 2020-01-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 118822000000 | 10 | 10 | 7000003739 | 601722C1 KIT,HDWR,PECC VALVE | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11882242 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | STANDARD | 2020-01-21 | USAWJB | 1 | EA | 0 | GT1 Gas Fuel Valve Bolts Recalled | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
29504908 | 508 | XV-66702-655 Hot Oil Valve Passing | S21 | Oil Treating | 2020-03-31 | 2019-02-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-66702-655 | Heater/Cooler Actuated Inlet Valve | 2019-11-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-02 | 107451000000 | 30 | 30 | 7000004751 | 5/8" X 3-1/2" DOX COATED STUDS W/ NUTS | 2020-03-31 | Received at Worksite | 2020-02-12 | 2020-02-24 |  | U182 | 8201 | Stones Main | Staged | 10745081 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-13 | USNSB4 | 16 | EA | 16 | Replace XV-66702-655 Valve, Actuator, & | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | ST LAYDOWN 02/24/2020
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 110 | 7000004213 | KE35/14 SASAKURA KE35 P/N 14 GLOBE VALVE | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 24 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61141209 | 508 | OPS cabinet needs latches | S19 | Marine Systems | 2020-12-13 | 2020-12-30 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-89901 | Turret Oil Pressurization System HPU | 2020-01-30 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-12-13 | 121161000000 | 10 | 20 | 7000002583 | Cam Latch, Keyed, Polished Chrome | 2020-04-13 | Not Shipped | 2020-02-26 |  |  | U182 | 8201 | Stones Main | STONES | 12116064 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-26 | USAWJB | 2 | EA | 0 | OPS cabinet needs latches | REL PCNF ESTC GMPS PPRT PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 290 | 7000002591 | Rust-Oleum 7579838-6 PK Professional 757 | 2020-02-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 960 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2020-02-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F13 | 11581207 | 96 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09191901 | Entity 3 | Name 59 | 2019-09-19 | USSOLE | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 300 | 7000002591 | Rust-Oleum 7592838 - 6 PK Professional H | 2020-02-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 30 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 130 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 94 | EA | 94 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 90 | 1001663814 | SHT PLT SLD MET,4x4ft,1/4in,A572-50 | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60891772 | 508 | Hiller Deficiencies | S13 | Fire Protect | 2020-03-21 | 2020-02-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2019-08-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-21 | 118312000000 | 10 | 20 | 7000000108 | AMEREX 2.5 ABC Fire Ext (B417T) | 2020-03-04 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | Issued | 11831177 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19CG112 | Cargo |  | 2019-08-19 | USABCE | 8 | EA | 8 | Hiller Deficiiencies | REL PRT GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
60544614 | 508 | Mechanical seal is leaking | S18 | Water Systems | 2020-06-02 | 2019-07-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216A | No. 1 Main/COPT Condenser Cooling Pump | 2019-12-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 114224000000 | 10 | 30 | 7000004211 | SVS350M-38, MOUTH RING | 2020-06-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11422404 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-15 | USMNF8 | 2 | EA | 0 | Mechanical seal is leaking | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
60935788 | 508 | O/SI Passing Loading Valve COT 3P | S21 | Oil Treating | 2020-02-11 | 2020-08-24 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-663UD-297 | Crude Oil O/O to COT 3 PS Valve | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-11 | 118802000000 | 20 | 20 | 1002400498 | PACKING,DWG:IFC-1 402-123-01/13,ISLIP-FC | 2020-02-11 | Not Shipped |  | 2020-01-15 |  | U182 | 8201 | Stones Main | ST KB D5 | 11880243 | 2 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-01-08 | USNSB4 | 1 | EA | 0 | Rebuild Loading Valve | REL PRT PRC SETC | EXEC RUSH WPOK | Deleted
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 50 | 7000002629 | Flange, 1 1/2", S/40 Bore, 150#, RFWN, A | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 4 | EA | 4 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 20 | 7000002591 | Pipe, 20", S/20, BE, ASME B36.10M, ASTM | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 20 | EA | 20.25 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 340 | 7000002591 | Belzona Mixing Boards | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 34 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 16 | EA | 16 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 30 | 1001931007 | ELB BW,WPB,90DEG,LR,STD,NPS12 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 2 | EA | 2 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 430 | 7000002591 | Fire Retardant Tarp, Grn Canvas 10'x 10' | 2020-01-20 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 752 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A373 | Name 2 | Name 2 | 2020-01-14 | USSOLE | 12 | EA | 12 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 380 | 7000003198 | Amercable 37-102-601-BS | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 830 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 110 | FT | 110 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 340 | 1001656154 | CONTROLLER,WAINBEE,1756-L73,8MB,2.5W | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 420 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
61151919 | 508 | P.Crane swing gearbox sight glass cloudy | S40 | Cargo Handling | 2020-10-31 | 2021-01-07 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-10-31 | 121288000000 | 10 | 30 | 7000006081 | Breather Valve, 419020700,, | 2020-10-31 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12128844 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-06 | USMNF8 | 3 | EA | 0 | Replace port crane gearbox sight glass | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 780 | 7000003463 | PC-KK9D3YV01M | 2020-03-18 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1069 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-26 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6880 | 7000002596 | Bolt, 3/4" x 3 1/2" LG., HH, ASTM A325T, | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 936 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 40 | 7000003852 | Zippo Brushed Chrome Pocket Lighter | 2021-05-26 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main | STONES | 11419724 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19BBSM1 | Name 11 | USKHU3 | 2019-10-15 | USLFA4 | 20 | EA | 20 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/01/19 J WELBOURN
61172407 | 508 | 6M Electric Motor Greasing | S06 | General | 2020-04-28 | 2020-06-25 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GN.MI.EM | Electric Motors | 2020-01-26 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Production Critical | 2020-05-11 | 121527000000 | 10 | 10 | 1001509600 | GREASE,SHELL,TACTICEMVGADUS S5T1002,TUBE | 2020-04-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12152697 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-27 | USRAR6 | 12 | TU | 0 | 6M Electric Motor Greasing | REL PRC SETC | APPR MANX WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7380 | 7000002596 | BLT HEX,A325,UNC,1.3/4in,3/4in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 996 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 44 | EA | 44 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1460 | 1001764048 | SB2N,A193-B7,CTD,UNC,6in,7/8in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 162 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 26 | EA | 26 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 80 | 7000002644 | 3" 150# RF FP Trunnion Ball Valve | 2019-02-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN038 | Name 2 | Name 2 | 2018-11-28 | USSOLE | 2 | EA | 2 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5330 | 7000002596 | STUD BOLT, 3/4" X 4" ASTM A182 GRADE F55 | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 594 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7150 | 1001642016 | CHNL,C8x11.5,2.260in,0.220in,0.390in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 973 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 780 | 7000003197 | SSW606HCC STAINLESS STELL ACCESSORIES | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 909 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 40 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60756604 | 508 | Vacuum Condenser Heat Exchanger | S17 | Steam/Hot H2O | 2020-04-01 | 2019-06-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.HBG-11508 | COPT Vacuum Condenser Heat Exchanger | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 116627000000 | 10 | 90 | 7000002596 | 5FT X 5 FT X 1/8” GARLOCK 3000: | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | Staged | 11662728 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-01-16 | GW982959 | 6 | EA | 6 | Main condenser tubes leaking | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WP ZPMM ZPVS | Approved |  |  | STLD17 02/18/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 850 | 7000002591 | Pilot for mag drill bit | 2020-03-03 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia |  | 11179936 | 1075 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-28 | USLFA4 | 20 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2100 | 7000002629 | FLANGE, 2", 300#, RF, WN, ASTM A182 GR. | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 232 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 600 | 7000003740 | Agency Approval Certificates | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 692 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN109 | Name 2 | Name 2 | 2019-12-17 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 210 | 7000003196 | 316-S3-WPE | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 799 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 40 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 80 | 7000003197 | BRA M21-187-C-342 110924 CART M21 B342 . | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11780965 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | Name 58 | 2019-10-30 | USNSB4 | 1 | EA | 0 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC PRC SETC | APPR EOM MAGN WP ZPMM | Deleted
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000002591 | OZ Lifting Quick Adjust Trolley 1 Ton Ca | 2021-01-28 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0003 | Name 17 | USJRF5 | 2020-01-08 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU K CASE 01/29/20 GG
60725219 | 508 | Replace Suction and Discharge Gauges | S18 | Water Systems | 2020-02-09 | 2020-04-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PG-12110A-102 | Pump Suction Pressure Gauge | 2019-12-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-09 | 116277000000 | 10 | 30 | 7000000062 | WK 52900722 233.54 2.5 -1/5BAR/PSI 1/4 L | 2020-02-09 | Received at Worksite | 2020-01-13 | 2020-01-29 |  | U182 | 8201 | Stones Main | ST KB A6 | 11627685 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 2 | Replace Suction and Discharge Gauges | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 2/5/2020 JH GG
60175730 | 508 | PCV-77703-966A Passing Through | S05 | Gas Dist | 2020-03-25 | 2018-12-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GD.FG.PCV-77703-966A | Buyback Gas to HP Scrubber Pres Ctrl Vlv | 2018-11-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-27 | 110121000000 | 20 | 20 | 7000000111 | FLANGE PACK, Flange Pack for 2" 2500 SAM | 2020-03-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 11/28 | 11012083 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2018-11-06 | USNSB4 | 1 | EA | 0 | Set Up Rigging & Assist Replacement Of P | REL PRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60426272 | 508 | O/SI BSW 198 O-ring seal failure | S22 | Prod Gathering | 2020-06-01 | 2019-04-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.AT-66207-198 | Crude Oil Outlet Water In Oil Analyser | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-01 | 112913000000 | 10 | 10 | 1002360782 | SB2N,B7,2H,UNC,5/8in,4in,DOXSTEEL | 2020-06-01 | Received at Worksite |  | 2019-04-02 |  | U182 | 8201 | Stones Main | ST KB D3 | 11291300 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-01-15 | USNSB4 | 4 | EA | 4 | Perform Isolations To Reinstall Temperat | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU 4/4/2019 CR
60935789 | 508 | COP2 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-10 | 2019-10-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 118809000000 | 10 | 50 | 7000000038 | 3/8” tube x 3/8” tube x 1/4” fnpt SS tee | 2020-03-10 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11880945 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-26 | USAWJB | 2 | EA | 2 | Install mechanical seal flush plan 12 | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 20 | 7000003768 | 1”x 3’ CEE2-91, 2 ply E & E nylon | 2020-01-25 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0002 | Name 17 | USJRF5 | 2020-01-08 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU ST1A4B 01/22/2020 CMR
61118371 | 508 | 2020 Lab Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 20 | 7000003852 | SanDisk 64GB Extreme PRO SDXC UHS-I Card | 2021-03-11 | Received at Target Location |  | 2020-01-11 |  | U182 | 8201 | Stones Main | STONES | 12090728 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20OP001 | Name 27 | USRRIG | 2020-02-27 | USCDP7 | 2 | EA | 2 | 2020 Lab Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61155254 | 508 | Production Swivel Bearing Flush | S19 | Marine Systems | 2020-03-03 | 2020-03-11 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.MS895 | Production Swivel Stack | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-03 | 121329000000 | 20 | 20 | 7000003945 | Shell Morlina S4 B 68 | 2020-03-03 | Received at Worksite | 2020-02-17 | 2020-02-24 |  | U182 | 8201 | Stones Main | Warehouse Oil Locker | 12132861 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-11 | USMNF8 | 10 | EA | 10 | Production Swivel Bearing Flush | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAXX WPOK | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 30 | 1000717281 | BAR FL,A36,1/4,2in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 20 | FT | 20 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 740 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 74 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 125 | EA | 125 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 540 | 1000717268 | BAR FL,A36,3/8in,4in,20ft | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 54 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 40 | FT | 40 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61170198 | 508 | Faulty Press Trans LACT Skid | S21 | Oil Treating | 2020-04-25 | 2021-01-20 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-25 | 121499000000 | 10 | 30 | 1000720068 | FTG_TUBE,CAP,1/2",316 S,SS-8-CP,SWAGELOK | 2020-04-25 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 12149917 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-26 | USAWJB | 1 | EA | 1 | MOC 79792 Faulty Press Trans LACT Skid | REL ESTC GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
60507050 | 508 | STB Vent N2 snuffing system rusting | S06 | General | 2020-03-10 | 2019-02-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.ZZZ-12707 | Cargo Vent Stacks N2 Stuffing System | 2019-06-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-11 | 113805000000 | 20 | 80 | 7000005901 | 5262.0012-15 BAR_G-H64H79H03H01-3.1 API | 2020-03-10 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11380546 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-15 | USNSB4 | 1 | EA | 1 | Replace Rusted Components Starboard Vent | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
60737083 | 508 | Solenoid & VPI test fail 5P | S21 | Oil Treating | 2020-02-10 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635P-217 | Crude Oil to/from COT 5 On/Off PS Valve | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-10 | 116406000000 | 20 | 10 | 7000000070 | BiFold FP02/S0A/C3/43/SC/S/RK-04 Repair | 2020-04-30 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B6 | 11640588 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-27 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635P-217 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 440 | 7000002591 | Tee Block | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 75 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
60699172 | 508 | O/SI Valve XV-1122S-326 over rotating Ba | S19 | Marine Systems | 2020-04-08 | 2019-10-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.BB.XV-1122S-326 | WB Tank No. 1S Water Line Ballast Valve | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-09 | 115978000000 | 40 | 30 | 7000004211 | Repair Kit for Hydraulic Actuator HAA-D1 | 2020-04-06 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11597808 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 2 | EA | 0 | Prep tank for entry | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60557093 | 508 | O/SI Passing Valve VABL-661050 | S22 | Prod Gathering | 2020-02-15 | 2019-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.FM.VABL-661050 | Test Fluids Manual Isolation Valve | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-15 | 114365000000 | 30 | 50 | 7000002596 | 1-3/8 X 12 Studs (11-3/4 FTF) TEFLON CTD | 2020-02-15 | Received at Worksite |  | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | ST1A5C | 11436470 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 59 | 2019-11-19 | USMNF8 | 24 | EA | 24 | Replace Passing Valve VABL-661050 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK RUSH WPOK XGI | TECO |  |  | ST 1A5C 12/13/19
61091319 | 508 | IGFU recycle pump B produced H20 leak | S26 | Water Treating | 2020-04-03 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405B | Flotation Cell Recycle Pump B | 2019-12-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-03 | 120587000000 | 20 | 10 | 7000004418 | 70.0 MM Mechanical seal | 2020-04-03 | Received at Worksite | 2020-01-20 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST1A2A | 12058721 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-19 | USAWJB | 1 | EA | 1 | Replace IGFU recycle pump B Mech Seal | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A2A 01/30/2020 GG
60172773 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-04-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.96T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 110086000000 | 10 | 70 | 7000002591 | 2"" x 27' U-Hook Ratchet Strap | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008582 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081902 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 2 | EA | 2 | MOC missing steam trap | REL PCNF ESTC GMCO GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61102257 | 508 | P.Crane radiator fan shroud corroded | S40 | Cargo Handling | 2020-05-10 | 2020-06-10 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-10 | 120716000000 | 10 | 20 | 7000006081 | Left hand guard mount 21819 | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12071582 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 2 | EA | 0 | P.Crane radiator fan shroud corroded | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 230 | 7000000052 | AB Power Supply | 2019-10-09 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 307 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN092 | Name 23 | Name 23 | 2019-09-27 | USGBI5 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2960 | 7000002629 | Plug, 1/2", SC, Hex head, ASME B16.11, A | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 326 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 320 | 1002196116 | CBL ELEC ARM,0.6/1kV,16pr,16AWG,BRZ,Blk | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 824 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 154 | FT | 154 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
61193291 | 508 | AxTech Study - Bell Latching Mechanism | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.010.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-02-07 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 121764000000 | 10 | 20 | 7000000098 | 12MJ X 12MB SS | 2020-12-31 | Not Shipped |  | 2020-02-07 |  | U182 | 8201 | Stones Main | Stones | 12176389 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAMH7 | 2020-02-11 | USRAR6 | 24 | EA | 0 | AxTech Study - Bell Latching Mechanism | REL ESTC PRC SETC | EXEC | EXEC
60850126 | 508 | Hydraulic oil leak on supply line | S19 | Marine Systems | 2020-04-03 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-88501 | Structural Connector No. 1 | 2019-10-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-04-03 | 117836000000 | 10 | 10 | 7000002591 | 0.89MTRS OVERALL LENGTH OF 3/4 575X-12 H | 2020-04-03 | Received at Worksite | 2019-12-03 | 2019-12-21 |  | U182 | 8201 | Stones Main | Issued | 11783574 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 28 |  | 2019-10-08 | USJDJW | 1 | EA | 1 | Iso Hydraulic suppply line | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK RUSH WPOK | EXEC |  |  | PU MUHAMED
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 140 | 7000000052 | HK32247D31C33 10.75" Injection | 2019-01-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 58 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN039 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 2 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60815108 | 508 | ER S/W Hypochlorite Analyzer Malfunction | S18 | Water Systems | 2020-03-03 | 2019-12-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZZZ-12214 | Chlorine Analyser Assembly | 2019-10-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-04 | 117437000000 | 20 | 20 | 7000005901 | W3T331891 MICRO/DEOX 2000 230VAC C/W WET | 2020-06-01 | Received at Worksite | 2019-12-05 | 2020-01-20 |  | U182 | 8201 | Stones Main | ST1A6B | 11743717 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-15 | USNSB4 | 1 | EA | 1 | Replace Hypochlorite Meter | REL PRT GMCO GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU AARON W 01/19/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5810 | 7000002603 | 2" Flange Protectors for Flange, 2", 300 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 675 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4080 | 7000002596 | Bolt, 5/8" x 2-1/4 Lg ASTM F3125 GrA325 | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 458 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 6 | EA | 6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60847989 | 508 | MOC GTG5 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-44000 | Gen #5 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 20 | 7000005901 | Hawke Part Number 121 / A / M20 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780944 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI80 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #5 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6500 | 7000000126 | Racks of Nitrogen | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 11179936 | 815 | 4 | Non-Stock (Purchase Requisition) | N | X |  | 129202001 | Name 3 | Name 3 | 2020-01-29 | USLFA4 | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4440 | 7000002629 | Plug, 3/4", SC, Hex Head, ASTM A182 Gr. F5 | 2019-11-22 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 496 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141902 | Name 2 | Name 2 | 2019-11-14 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 440 | 7000002591 | BLACK ACETAL PAD, 1/4" X 11" X 7 7/8" FR | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 57 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60996511 | 508 | Hyd. level low in tank | S13 | Fire Protect | 2020-02-18 | 2020-10-09 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.ZZZ-33110 | Aft Firewater Pump Package | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-18 | 119501000000 | 10 | 10 | 7000000118 | Tellus 46, 55 gal drum | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | WR.508A Stones | 11950146 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-16 | USFOL2 | 1 | EA | 1 | Hyd. level low in tank | REL ESTC GMPS PRC SETC | APPR MAGN MAOK RUSH WPOK ZPMM | Approved
60847991 | 508 | MOC GTG1 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-04000 | Gen #1 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117810000000 | 10 | 80 | 7000005901 | Brady Part No. M21-187-C-342 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780966 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI76 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 1 | EA | 1 | SAEP LO/TO Isolate GTG #1 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60172772 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-03-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.95T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 110086000000 | 10 | 30 | 7000002629 | Elbow, 40mm, LR 90°BW, JIS B2312, PS410 | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008581 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081901 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 1 | EA | 1 | MOC missing steam trap | REL PCNF ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60699172 | 508 | O/SI Valve XV-1122S-326 over rotating Ba | S19 | Marine Systems | 2020-04-08 | 2019-10-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.BB.XV-1122S-326 | WB Tank No. 1S Water Line Ballast Valve | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-09 | 115978000000 | 50 | 60 | 7000004211 | Hydraulic Actuator Model HAA-D05 | 2020-04-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11597808 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 1 | EA | 0 | Valve over rotating | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60881246 | 508 | Containment plugs on stern | S06 | General | 2020-02-04 | 2020-01-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.HB.PC | Process Containment Hardware Barriers | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-04 | 118192000000 | 10 | 40 | 7000003852 | SeaSense Drain Plug 1-1/4-Inch Snap, Bra | 2020-02-04 | Received at Worksite |  |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B6 | 11819160 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-01 | USAWJB | 11 | EA | 11 | Containment plugs on stern | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60699172 | 508 | O/SI Valve XV-1122S-326 over rotating Ba | S19 | Marine Systems | 2020-04-08 | 2019-10-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.BB.XV-1122S-326 | WB Tank No. 1S Water Line Ballast Valve | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-09 | 115978000000 | 50 | 90 | 7000004211 | Hydraulic Actuator Model HAA-D10 | 2020-04-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11597808 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 1 | EA | 0 | Valve over rotating | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 280 | 1001664298 | BLT HEX,A325,UNC,1.1/2in,1/2in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 28 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 5 | EA | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 670 | 1002058433 | NUT,A563-DH,HEXAGONAL,UNC,1,SERMAGARD | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 67 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 14 | EA | 14 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60739058 | 508 | COT 3 Stbd HC Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127013 | COT 3 SB HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642934 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60975189 | 508 | XV-12202B-924 Fails to Open | S18 | Water Systems | 2020-02-07 | 2019-10-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.XV-12202B-924 | Filter Backwash On/Off Control Valve | 2019-10-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-02-07 | 119260000000 | 10 | 40 | 7000000104 | Set of drawings for valve | 2020-02-07 | Not Shipped |  | 2020-01-20 | 2020-02-14 | U182 | 8201 | Stones Main | Not needed to change vlv | 11925970 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAWJB | 2019-10-31 | USRAR6 | 1 | EA | 0 | LOTO System - Confirm Isolation | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7990 | 1001646136 | GASKET,GARLOCK,36010-0006,CL150,2in | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 1084 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-28 | USSOLE | 14 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60739060 | 508 | COT 5 P HC netherlock fails to lock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.IG.VABF-127020 | COT 5 PS HC Main Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-21 | Not Shipped |  |  | 2020-02-13 | U182 | 8201 | Stones Main | Stones | 11642936 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-20 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | TECO ESTC CSER PRC SETC | XCNF MAGN NCMP WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6400 | 7000002591 | Landscaping Timbers, 8' (For Loadout) | 2020-01-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 764 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01202001 | Name 4 | Name 4 | 2020-01-20 | USSOLE | 50 | EA | 50 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1710 | 7000002662 | PIPE, 2 S80S DUPLEX 2205 SMLS PIPE PE A7 | 2019-01-15 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 187 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01141901 | Name 2 | Name 2 | 2019-01-14 | USSOLE | 8 | FT | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2830 | 7000002662 | Pipe, 2", S/40S, ASME B36.19M, ASTM A790 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 313 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 20 | FT | 21.66 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6480 | 7000002596 | Stud, 3/4" x 4 1/2" LG., ASTM A193 Gr. B | 2020-02-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 812 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01282001 | Name 4 | Name 4 | 2020-01-29 | USDKFB | 36 | EA | 36 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60985333 | 508 | O/SI- Steam valve VAGL-115693 is corrode | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-05 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.VAGL-115693 | Steam Trap Bypass Valve | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-01 | 119372000000 | 20 | 10 | 1002407397 | GLOBE VALVE,1GL01-A,NEWAY | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 11937179 | 1 | 1 | Stocked Locally (Reservation) | L | [5 empty] | 2020-02-05 | USMNF8 | 1 | EA | 0 | Replace steam valve VAGL-115693 | REL ESTC PRC SETC | APPR MAOK WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 110 | 1000709964 | UNIC,SWAGELOK,SS8106,1/2in | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 789 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 6 | EA | 6 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60837065 | 508 | Bad Pressure Gauge Inst air Dryer #2 | S08 | Air Systems | 2020-02-25 | 2020-07-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.ZBK-11810A | Control Air Dryer No. 2 | 2019-07-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 117686000000 | 10 | 10 | 7000000062 | WK 52902310 | 2020-02-25 | Received at Worksite |  | 2020-02-16 | 2020-02-29 | U182 | 8201 | Stones Main | ST KB A7 | 11768556 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-17 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge Instrument Air Dr | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 02/16/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 750 | 7000003197 | PL SSTC04V-3 SS 4INW CHANNEL TRAY | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 906 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 9 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 290 | 7000002591 | Key cabinet 40 key capacity. Part number | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0140 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 02/25/2020 GG
60686663 | 508 | O/SI #1 Boiler Steam to 16K Hdr Valve | S17 | Steam/Hot H2O | 2020-04-11 | 2019-09-30 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-200A | Steam to 16K Steam Header Valve | 2019-12-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-12 | 115837000000 | 30 | 20 | 7000004211 | Hammer handwheel, HAM-Hand-125 | 2020-04-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11583658 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-18 | USMNF8 | 1 | EA | 0 | Replace passing valve 115-200A | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 90 | 7000003852 | TorcUP Raptor RP-2000 Pneumatic Torque W | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | Stones | 12090727 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 11 | USJRF5 | 2020-01-16 | USJRF5 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A4A 02/15/2020 CMR
61112406 | 508 | 2nd Stg Sep PST upgrade | S22 | Prod Gathering | 2020-04-11 | 2020-06-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.PST-66202-178 | 2nd Stg Separator Press Sfty Transmitter | 2019-12-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-11 | 120837000000 | 20 | 90 | 7000002629 | 13" 150# blind flange - 1/2" hole | 2020-04-11 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 12083677 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-12 | USMNF8 | 2 | EA | 2 | Upgrade PST-66202-178 To Rosemount Trans | REL ESTC GMPS PPRT PRC SETC | APPR EOM MAGN MAOK RUSH WPOK ZPMM | Approved
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 80 | 7000003196 | MS-TCW-308 SWGLK TUBE CUTTER WHEEL | 2020-02-24 | Received at Worksite |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-09 | USNSB4 | 12 | EA | 12 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
61098382 | 508 | Replace Spacer w/ BFV | S26 | Water Treating | 2020-04-03 | 2020-12-04 | O.US.STO.STO.005.724FP | 508OPER | US.WR508A.WT.FL.VABF-124307 | Pump Discharge Isolation Valve | 2019-12-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-05 | 120671000000 | 10 | 10 | 7000000105 | 6" BFV for IGFU | 2020-04-03 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12067108 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-11 | USAMH7 | 2 | EA | 0 | LOTO - IGFU Pump A,B | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 330 | 1002316819 | GARJ,CS,OCTAGONAL,R32,CTD | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 78 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 2 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 350 | 1000070868 | GSKT RJ,CS,OCTAL,R39 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 80 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 3 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 80 | 7000003740 | Rosemount Differential Pressure Transmit | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN110 | Name 2 | Name 2 | 2019-12-18 | USLFA4 | 4 | EA | 4 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 50 | 7000005901 | M20 Earth Tag | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780965 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI77 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 390 | 7000002591 | Hydramax HM07 Load Cell | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 70 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 14 | EA | 14 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
61102085 | 508 | FRC Lifeline discrepancies | S15 | Life Saving | 2020-03-05 | 2020-06-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2020-01-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-05 | 120714000000 | 10 | 30 | 7000004662 | Reflective line line | 2020-03-05 | Received at Worksite | 2020-02-17 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 12071420 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-17 | USMNF8 | 6 | EA | 6 | FRC Lifeline discrepancies | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 360 | 7000002629 | COUPLING,HOSE,CAMLOCK,2DDSS,2in,SS | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 63 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A364 | Name 2 | Name 2 | 2019-10-23 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 50 | 7000002583 | 1/4-20 X 1 SS BOLT W/ 1 NYLON LOCK | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 100 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 980 | 7000003343 | Flat Bar, FB 1.5 X .25, ASTM A36 (PCM - | 2020-03-10 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 98 | 4 | Non-Stock (Purchase Requisition) | N | X |  | PE10041901 | Name 4 | Name 59 | 2019-10-07 | USSOLE | 20 | FT | 20 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 40 | 1000709949 | PLIC,SWAGELOK,SS1610P,1in | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 3 | EA | 3 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
61046320 | 508 | Overhaul helideck standby pump cartridge | S13 | Fire Protect | 2020-04-21 | 2020-05-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33132 | Helideck Firewater Pump | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 120075000000 | 10 | 40 | 7000004211 | Pump shaft Y5685-001 | 2020-04-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12007515 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-20 | USMNF8 | 2 | EA | 0 | Overhaul helideck standby pump cartridge | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
61218667 | 508 | Replace Lifeboat Rations & Water | S15 | Life Saving | 2020-12-10 | 2021-02-17 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.LB | Lifeboats | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-12-11 | 122061000000 | 10 | 80 | 7000004662 | Datrex Water, DX1000W<(>,<)> 4oz (125ml) | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12206109 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-25 | USAWJB | 960 | EA | 0 | Replace Lifeboat Rations & Water | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 160 | 7000002591 | Bolt, 3/8"x 2" LG., SS | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 4 | EA | 4 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 100 | 7000004211 | 5K-500A-DCHKV | 2020-04-14 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Stones | 11477345 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-06-11 | USRAR6 | 1 | EA | 1 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 250 | 7000000052 | AB Ethernet Module | 2019-10-09 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 309 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN092 | Name 23 | Name 23 | 2019-09-27 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1300 | 7000002603 | 12" FLG PROTECTOR (FLANGE, 12",300#, RF | 2019-12-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 146 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12101801 | Name 2 | Name 2 | 2018-12-11 | USSOLE | 19 | EA | 19 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60847987 | 508 | MOC GTG3 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-24000 | Gen #3 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 20 | 7000005901 | Hawke Part Number 121 / A / M20 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780940 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI78 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #3 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6020 | 7000002629 | Concentric Reducer, 3" x 2", BW, Class 7 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 700 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7700 | 7000002629 | Elbowlet, 2" x 1/2", 3000#, FS SCRD, MSS | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1033 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5050 | 7000002629 | REDUCER CONC, 12" X 8" SCH 10S BW CLASS | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 566 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2580 | 7000002603 | GASKET, 8", 300#, RF, 1/8" THICK, SPIRAL | 2019-04-22 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 280 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04081901 | Name 2 | Name 2 | 2019-04-08 | USSOLE | 12 | EA | 12 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 40 | 7000000103 | 8" Super Duplex Remington Floating Ball | 2019-01-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN031 | Name 2 | Name 2 | 2018-11-06 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1600 | 1001210748 | U-BOLT,HDG,ARMORCOAT,3x1/2in,W/4NUT | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 176 | 19 | Modified SP1 - w/o STR & STO / item ctg | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4230 | 7000002629 | FULL FACE BLEED RING, 12", 300#, RF, 1.5 | 2019-11-29 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 473 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11081901 | Name 2 | Name 2 | 2019-11-08 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61042037 | 508 | End Stops OOC - Collar Deck - ZZZ-887106 | S40 | Cargo Handling | 2020-02-09 | 2020-06-30 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-11-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-21 | 120026000000 | 10 | 20 | 1001645331 | BLT HEX,A325,UNC,4in,3/4in,SERMAGARD | 2020-01-18 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | Trolley End Stops | 12002579 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A393 | Name 2 | Name 59 | 2020-02-01 | USSOLE | 48 | EA | 48 | Fabricate End Stops | REL PCNF ESTC GMCO GMPS PPRT PRC SETC | EXEC MAGN MANX WPOK | EXEC
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 100 | 7000000133 | RKI 61-1058RK Sensor, oxygen | 2020-02-28 | Received at Target Location |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG144 | Entity 7 | USKHU3 | 2020-02-05 | USLFA4 | 1 | EA | 1 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1620 | 1001645341 | BLT HEX,A325,UNC,2in,3/4in,SERMAGARD | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 178 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60683738 | 508 | O/SI SDV-66202-870 Failed to Close | S22 | Prod Gathering | 2020-04-02 | 2019-05-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.SDV-66202-870 | 2nd Stg Separator Prod Wtr Shutdown Vlv | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-02 | 115806000000 | 30 | 10 | 7000004211 | 2INVG150 3" ANSI CLASS 150 REDUCE PORT B | 2020-04-02 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | Stones FPSO/Lost | 11580631 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-04-19 | USNSB4 | 1 | EA | 1 | Replace SDV-66202-870 | REL ESTC GMCO GMPS PPRT PRC SETC | APPR EOM MAGN MAOK WP | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 330 | 7000002591 | 4452K114 Straight Connector, 1/2 NPT Fem | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 33 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61137458 | 508 | COP2 Barrier Fluid Mech Seal PRV Failure | S21 | Oil Treating | 2020-02-20 | 2020-07-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.LS-66306E-352E | Lower Shaft Seal Water Tank LSA | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-26 | 121118000000 | 10 | 10 | 7000000035 | WATER REGULATOR- Brass | 2020-02-20 | Received at Worksite | 2020-01-29 | 2020-02-13 | 2020-02-28 | U182 | 8201 | Stones Main | Issued | 12111780 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 20 |  | 2020-01-15 | USMNF8 | 1 | EA | 1 | Isolate Water Supply | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO |  |  | ST1A1B 02/07/2020 CMR
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 50 | 7000000069 | CF N2 Cylinders Amerex | 2020-01-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-10 | USMNF8 | 9 | EA | 0 | Send In/Replace Fire Ext Due Hydro | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Deleted
60440621 | 508 | Replace Laydown Timber - MODs 15, 17, 19 | S40 | Cargo Handling | 2020-03-10 | 2020-06-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.LS | Loading Stations | 2019-08-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 113072000000 | 10 | 60 | 7000002583 | Carbon Steel Wood Drilling Bit, Forstner | 2020-03-10 | Received at Worksite |  | 2019-09-11 |  | U182 | 8201 | Stones Main | ST KB A1 | 11307214 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-06 | USAWJB | 4 | EA | 4 | Replace Laydown Timbers - MOD 15 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAOK RUSH WPOK | EXEC |  |  | PU KB A1
61209166 | 508 | EPAF Emergency Generator within specific | S03 | Elect. Systems | 2020-04-16 | 2020-06-30 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PG.ZAN-11101C | Essential Generator No. 3 | 2020-02-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | S User Defined (SCE) | 2020-04-16 | 121949000000 | 10 | 10 | 7000000083 | Pick-up | 2020-04-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12194882 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-24 | USNSB4 | 2 | EA | 0 | Replace Speed Pick-Up Sensor ESS Gen-3 | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60739071 | 508 | COT 3S IG Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127059 | COT 3 SB IG Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116430000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642967 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 20 | 7000004211 | ANS200x150x350/PN-8 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 1 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61200672 | 508 | Stones Small Civil Projects 2020 |  |  | 2020-12-31 |  | P.US.STO.NF.20.009.7240A | GENERIC |  |  | 2020-02-11 | WO | U100 | GEN | US01 | P16 | [5 empty] | 3 Low | 2020-12-31 | 121848000000 | 10 | 30 | 7000002596 | Studs, 1/2" x 3" LG, w/Nuts, B150 UNS C6 | 2020-02-28 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G97 | 12184838 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST02242002 | Name 4 | Name 60 | 2020-02-27 | USSOLE | 5 | EA | 0 | Stones Small Civil Projects 2020 | REL ESTC PRC SETC | APPR | Approved
60009724 | 508 | MOC Mov-33120-444 does not operator | S13 | Fire Protect | 2020-03-24 | 2019-02-14 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.MOV-33120-444 | FW Pump Outlet to Ring Main Motor Op Vlv | 2018-03-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-26 | 107694000000 | 20 | 20 | 1002065887 | GLAND,CABLE,HAWKE,710/A/3/4"NPT | 2020-03-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 10769362 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-28 | USNSB4 | 4 | EA | 0 | Replace Mov-33120-444 | REL ESTC GMPS PPRT PRC SETC | APPR EOM MANX MAXX WP | Approved
60874068 | 508 | FRC inspection deficiencies | S15 | Life Saving | 2020-02-13 | 2020-03-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2019-08-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-03 | 118106000000 | 10 | 100 | 7000004662 | Deadman Spring Inboard/Outboard (BW-SC33 | 2020-02-13 | Not Shipped |  | 2020-02-13 |  | U182 | 8201 | Stones Main | POD- Questions | 11810577 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-08-04 | USAWJB | 1 | EA | 0 | FRC inspection deficiencies | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD MAGN WPOK | EXEC
61118331 | 508 | 2020 Chemical Order - Engine Room | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 10 | 7000003458 | EMBR18527A.32B | 2020-01-29 | Received at Worksite |  | 2020-01-10 |  | U182 | 8201 | Stones Main | CPORT | 12090688 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200004A | Name 40 | USRRIG | 2020-01-16 | USLFA4 | 1000 | GLL | 1000 | 2020 Chemical Order - Engine Room | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 70 | 7000003197 | M20 Hawke 153AX/M20 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 2 | EA | 2 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
61091318 | 508 | IGFU recycle pump leaking oil | S26 | Water Treating | 2020-04-03 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-03 | 120587000000 | 10 | 10 | 7000004418 | 70.0 MM Mechanical seal | 2020-04-03 | Received at Worksite | 2020-01-27 | 2020-02-07 |  | U182 | 8201 | Stones Main | ST1A2A | 12058720 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-02 | USMNF8 | 1 | EA | 1 | Replace IGFU recycle pump A Mech Seal | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A2A 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 400 | 7000002591 | 2''x12'x2Ply Nylon Straps | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 749 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A384 | Name 2 | Name 2 | 2020-01-11 | USSOLE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6510 | 7000002662 | Pipe, 4", .109 Min Wall, ASTM B466, 90/1 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 862 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 2 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7090 | 1001267394 | ANGL MTL,EQ,STL,20ft,L4x4x3/8in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 967 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 80 | FT | 80 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 50 | 7000002644 | 3" 300# RF FP WKM Floating Ball Valve | 2019-02-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN038 | Name 2 | Name 2 | 2018-11-28 | USSOLE | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60177919 | 508 | Mod 6 - vlv long bolts Diss metals | S04 | Gas Compress | 2020-06-01 | 2019-06-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VABL-771251 | Cooler Press Diff Transmitter Iso Valve | 2019-08-26 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-06-01 | 110146000000 | 10 | 40 | 7000002596 | 5/8-11 HVY NUT A194 B8M SS | 2020-06-01 | Ready for Shipment after Kitting | 2019-10-29 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB D3 | 11014637 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-26 | USNSB4 | 20 | EA | 20 | LO/TO Shutdown Down Process Train, De-In | REL ESTC CSER GMPS PRC SETC | EXEC EOM MAGN MAKD MANX WPOK | EXEC |  |  | PU WPT 11-25-19
60911821 | 508 | Replace starting solenoid on Gen# 3 | S03 | Elect. Systems | 2020-04-28 | 2019-10-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.ES.PG.ZZZ-11101C | Essential Generator No. 3 Engine | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-28 | 118543000000 | 20 | 30 | 7000005901 | 51314-01H Rep. Kit SOLENOID VALVE 3/2 N/ | 2020-04-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11854297 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-18 | USMNF8 | 1 | EA | 0 | Replace starting solenoid | REL ESTC GMPS PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 190 | 7000002591 | Two Wire Earpiece with Kevlar Reinforced | 2020-03-26 | Not Shipped |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 20 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN022520A | Name 41 | USKHU3 | 2020-03-03 | USLFA4 | 10 | EA | 0 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6180 | 1001574897 | GSKT,PERMANITE,SF3300,3in,150# | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 716 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 18 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4530 | 7000002629 | Elbow, 3", 45, S/10S, BW, ASME B16.9, A | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 505 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 1030 | 7000003197 | HOF DIRHOFFMAN A1008CHNFSS STAINLESS | 2020-03-11 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 1090 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-29 | USSOLE | 2 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1260 | 7000002603 | 8" FLG PROTECTOR (FLANGE, 8" 300#, RF | 2019-12-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 142 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12101801 | Name 2 | Name 2 | 2018-12-11 | USSOLE | 24 | EA | 24 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60985462 | 508 | No.3 COP stuffing box bellows leaks | S21 | Oil Treating | 2020-04-25 | 2019-11-25 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301C | Cargo Oil Pump No. 3 | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-27 | 119373000000 | 20 | 10 | 7000000038 | P/N: CVL400-2-P/N435 | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937329 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  | PLWST3-W | Name 3 | USMSLN | 2019-10-09 | USMNF8 | 4 | EA | 0 | Replace COP #3 pump bellows | REL PRT PRC SETC | APPR MAGN WPOK ZPMM | Approved
60756604 | 508 | Vacuum Condenser Heat Exchanger | S17 | Steam/Hot H2O | 2020-04-01 | 2019-06-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.HBG-11508 | COPT Vacuum Condenser Heat Exchanger | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 116627000000 | 20 | 100 | 7000002596 | P/N: 60 QTY: SNB7,M22 X 120MM: STUDS AND | 2020-04-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 11662728 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-02-07 | GW982959 | 60 | EA | 60 | Main condenser tubes leaking | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WP ZPMM ZPVS | Approved
61026238 | 508 | MGCB Pipe Support Bracket Installation | S04 | Gas Compress | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DANOS | US.WR508A.GC.GS.VADB-771017 | Inlet Gas Valve | 2019-11-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-01 | 119851000000 | 10 | 50 | 7000002591 | 2" x 27' U-Hook Ratchet Strap (including | 2020-03-27 | Received at Target Location |  | 2019-11-12 |  | U182 | 8201 | Stones Main | SHF9-F65 | 11985064 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111902 | Name 4 |  | 2019-11-12 | USLFA4 | 2 | EA | 2 | Install 4x A325 3/4 x 3-3/4 Bolts | REL PRT GMPS PRC SETC | APPR MAGN MAOK WP ZPMM | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 70 | 1001642019 | CHNL,C10x15.30,2.6in,0.24in,0.436in,20ft | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 200 | EA | 200 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61089158 | 508 | O/SI BGCA Discharge Valve Passing | S04 | Gas Compress | 2020-02-15 | 2020-01-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VABL-771085 | Compressor SDV Isolation Valve | 2019-12-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 8 User defined period | 2020-02-15 | 120564000000 | 10 | 20 | 7000004751 | 3-COAT PAINT STONES RAL-1023 YELLOW,,,,, | 2020-02-15 | Received at Worksite | 2020-01-13 | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Stones | 12056365 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-24 | USAWJB | 1 | EA | 1 | Replace VABL-771085 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 250 | 7000000040 | Sling, Synthetic, 8’-0", Vert Capacity – | 2019-10-26 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 52 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRRIGG2 | Name 42 | Name 42 | 2019-10-18 | USLFA4 | 3 | EA | 3 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU 10/30/19 PAT
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 210 | 7000002591 | CBT 1T Trolley CBT(P)-0100 | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 1 | EA | 1 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 320 | 7000006192 | Hydro Test | 2020-04-15 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 44 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-18 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 190 | 7000002603 | Gasket, 8", 600#, RF, 1/8" THK. Spiral W | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 115 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 9 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60840044 | 508 | O/SI Slop S Steam Valve Leaking | S17 | Steam/Hot H2O | 2020-04-01 | 2020-01-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGA-115516 | Stbd Steam to Slop Tank Isolation Valve | 2020-01-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-02 | 117719000000 | 20 | 20 | 7000004211 | doxsteel-4 4" FASTENER PASCK FOR ANSI 15 | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11771882 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-07 | USNSB4 | 16 | EA | 0 | Replace Gate valve VAGA -115516 | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 50 | 1000711217 | TEET,SWAGELOK,SS-8-T,1/2in | 2021-03-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB C7 | 11057838 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO182KDC | Name 37 | USRRIG | 2018-07-24 | USLFA4 | 4 | EA | 4 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved |  |  | PU MOD22 1st FLR 09/04/2018 MP
60847988 | 508 | MOC GTG4 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-34000 | Gen #4 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 50 | 7000005901 | M20 Earth Tag | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780943 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI79 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #4 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60871423 | 508 | Drive End Bearing Leaking Oil - BGCA | S04 | Gas Compress | 2020-03-03 | 2020-01-28 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-20000 | Booster Gas Compression System Train A | 2019-11-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-08 | 118080000000 | 10 | 20 | 7000000039 | 200350021 FLOAT LAB SEAL | 2020-03-03 | Received at Worksite | 2019-11-24 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B8 | 11807987 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-05 | USJDJW | 4 | EA | 4 | Erect Scaffold | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU Aaron 01/19/2020
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 40 | 7000003196 | SS-V2NBM8-F8-11486 V-SERIES MANIFOLD | 2021-03-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | ST KB C7 | 11057838 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO182KDC | Name 37 | USRRIG | 2018-07-24 | USLFA4 | 4 | EA | 4 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved |  |  | PU WPT 09/04/2018 AJ
60739069 | 508 | COT 5 P IG netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127053 | COT 5 PS IG Vent Line Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116430000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642965 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 70 | 7000003684 | OIL SAFE UTILITY LID, BLACK 100201 | 2020-03-28 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-19 | USAWJB | 1 | EA | 1 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 570 | 1001723501 | WASHER,FLAT,F436,SERMAGAURD,1/2in | 2020-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 774 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A389 | Name 2 | Name 2 | 2020-01-27 | USSOLE | 220 | EA | 220 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2200 | 1001663814 | SHT PLT SLD MET,4x4ft,1/4in,A572-50 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 242 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3120 | 1001690904 | (PCM-0.23) | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 342 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2030 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2019-02-15 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 225 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02121901 | Name 2 | Name 2 | 2019-02-13 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 260 | 1001816278 | GASW,CL300,316,GPH,NPS6 | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 39 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 7 | EA | 7 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5850 | 1002058431 | NUT,A563-DH,HEXAGONAL,UNC,1/2,SERMAGARD | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 679 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 40 | EA | 40 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 110 | 7000004211 | JWE#1550-G-5K500A | 2020-04-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11477345 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAWJB | 2019-06-11 | USRAR6 | 2 | EA | 0 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 640 | 7000003197 | TB SS4612L09144 SS TRAY 6IN 12W LAD | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 895 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 12 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4350 | 7000002596 | Bolt, 3/4" x 3" LG, ASTM F3125 Gr. A325T | 2019-11-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 487 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11131902 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 78 | EA | 78 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 30 | 7000002629 | 3" Flange Blind 300# RF ASME B16.5 ASTM | 2019-11-29 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | WP 194/ 198 SOLIDS | 11179936 | 534 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 2 | 2019-11-20 | USABCE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 870 | 1001816266 | GASW,CL300-600,316,GPH,NPS1.1/2 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 103 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 320 | 1001645336 | BLT HEX,A325,UNC,3in,3/4in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 732 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231901 | Name 4 | Name 4 | 2019-12-24 | USSOLE | 5 | EA | 5 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 720 | 7000002591 | DRILLFORCE HSS Jobber Length 10 PCS,9/32 | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 72 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 2 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 50 | 7000002596 | 1/16” Stainless aircraft cable, 18”LG, w | 2019-06-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Lower Turret Fire Extingu | 11545759 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A308 | Name 2 | Name 2 | 2019-06-03 | USSOLE | 20 | EA | 20 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60991727 | 508 | Cooling water pump trips on overload. | S03 | Elect. Systems | 2020-03-02 | 2020-04-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.SGR-44301B14F | Switchgear Sect B14 Feeder to PM-12504B | 2019-11-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-02 | 119442000000 | 20 | 20 | 7000002583 | MANUAL MOTOR STARTER, ROTARY, 48 TO 65A | 2020-03-02 | Received at Target Location | 2019-12-03 |  | 2019-11-23 | U182 | 8201 | Stones Main |  | 11944211 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-20 | USMNF8 | 2 | EA | 2 | Ross D - Replace Overload Relay | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN MAKD WPOK XGI ZPMM | TECO
60921250 | 508 | O/SI Steam Inlet Drain Valve Leaking | S17 | Steam/Hot H2O | 2020-03-11 | 2020-03-02 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.SW.VAGL-115552 | Steam Inlet Drain Valve | 2020-01-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 118651000000 | 30 | 60 | 7000002603 | 1-1/2" FLEX CG 150# SP WND GSKT GRF FLR | 2020-03-11 | Received at Worksite | 2020-01-22 |  |  | U182 | 8201 | Stones Main | ST1A3B | 11865065 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | 4073688 | Name 3 |  | 2020-01-11 | USMNF8 | 5 | EA | 5 | Steam Inlet Drain Valve Leaking | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WP ZPMM | Kit Complete |  |  | ST1A3B 02/3/20 GG
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 340 | 7000002629 | 200-DC-SS 2" Camlock DC Male | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 61 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A363 | Name 2 | Name 2 | 2019-10-21 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 110 | 7000002596 | Nut, 1 ½”, ASTM A 194 HH (Xylar-Xylan Co | 2020-01-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G40 | 11545759 | 91 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01142002 | Name 2 | Name 2 | 2020-01-15 | USSOLE | 51 | EA | 51 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 230 | 7000002591 | 4548K225 1 NPT, 3" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60985334 | 508 | O/SI VABF-122008 passing | S18 | Water Systems | 2020-03-10 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VABF-122008 | Filter Backwash Water Outlet Valve | 2019-10-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-10 | 119372000000 | 20 | 30 | 7000002596 | 5/8-11 X 4-1/4" 316 SS BOLTS W/1 FLAT WA | 2020-03-10 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB D7 | 11937180 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-29 | USNSB4 | 16 | EA | 16 | Replace VABF-122008 Butterfly Valve MAJ- | REL ESTC GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved |  |  | PU AMW 12/29/19
60884226 | 508 | Lagging missing on boiler iso valves | S17 | Steam/Hot H2O | 2020-02-07 | 2019-10-05 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.VE115 | Vessel Steam/Tank Heating Systems | 2020-01-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-07 | 118224000000 | 20 | 10 | 7000000132 | Fire blankets 46" x 35" | 2020-02-07 | Received at Worksite | 2020-01-13 | 2020-01-24 | 2020-02-10 | U182 | 8201 | Stones Main | ST1ASIDE | 11822352 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-07 | USMNF8 | 2 | EA | 2 | Replace Lagging on boiler iso valves | TECO CNF ESTC GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 2/5/2020 JH GG
60636179 | 508 | MGC-B Replace all inspection door bolts | S04 | Gas Compress | 2020-04-04 | 2020-02-25 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-11000 | Compressor Package B | 2020-03-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-04 | 115265000000 | 20 | 10 | 7000002596 | 1/2 x 1-1/4" long zinc bolts | 2020-04-04 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11526529 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-15 | USMNF8 | 250 | EA | 0 | MGC-B Replace inspection cover bolts | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6410 | 7000002646 | NEEDLE VALVE, 1/2" 6000 PSI MNPT X FNPT | 2020-01-30 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 771 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222002 | Name 4 | Name 4 | 2020-01-23 | USLFA4 | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60739060 | 508 | COT 5 P HC netherlock fails to lock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.IG.VABF-127020 | COT 5 PS HC Main Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-21 | Not Shipped |  |  | 2020-02-13 | U182 | 8201 | Stones Main | Stones | 11642936 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-20 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | TECO ESTC CSER PRC SETC | XCNF MAGN NCMP WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3480 | 1001816209 | GASW,CL150,316,GPH,NPS4 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 378 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 16 | EA | 16 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 150 | 1000720134 | UNIC,SWAGELOK,SS6006,3/8in | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 793 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 20 | EA | 20 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 150 | 7000000052 | HK32247D31C33 8.5" Injection | 2019-01-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 59 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN039 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 2 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1810 | 7000002662 | PIPE, 8", S/10S (0.148 WT), ASTM A790 UN | 2019-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 199 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01241901 | Name 2 | Name 2 | 2019-01-24 | USSOLE | 21 | FT | 19.7 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 230 | 7000003196 | 316-S1-WPE | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 801 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 90 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60996512 | 508 | Ballast Tank 3S Not Reading in CCR | S19 | Marine Systems | 2020-03-05 | 2020-04-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.TG.LT-557WB3S-977 | Stbd Wtr Ballast Tank #3 Lvl Transmitter | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-05 | 119501000000 | 10 | 10 | 7000000067 | GT403A0C4N Pressure transmitter | 2020-03-05 | Received at Worksite | 2020-01-10 | 2020-01-29 |  | U182 | 8201 | Stones Main | ST KB B7A | 11950147 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-20 | USMNF8 | 1 | EA | 1 | Replace Transmitter / Calibrate | REL PRT GMCO GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU AARON W 01/24/2020 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2020 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2019-02-15 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 224 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02121901 | Name 2 | Name 2 | 2019-02-13 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 300 | 7000002596 | 1/4"-20 x 3" 316SS Hex Head Bolts | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 30 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 50 | EA | 50 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 670 | 7000002591 | GEDORE 31 KR 30-60 Friction Type Ratchet | 2020-03-06 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 67 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 2 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 120 | 7000002603 | Gasket, API 7 1/16”, 15K, Type BX 156 Pe | 2020-01-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G40 | 11545759 | 92 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01142002 | Name 2 | Name 2 | 2020-01-15 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 180 | 7000002629 | Flange, 2", 600#, RFWN, S/80S Bore, ASME | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 114 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61041601 | 508 | O/SI VFD Cabinet Cooling Fan Failed | S03 | Elect. Systems | 2020-02-15 | 2020-11-02 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.VFD-85901 | Turret Variable Frequency Drive | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-15 | 120021000000 | 10 | 10 | 1002493505 | FAN,AC,RITTAL,3244110,12828 l/min,115Vac | 2020-02-15 | Not Shipped |  |  | 2020-02-18 | U182 | 8201 | Stones Main |  | 12002102 | 1 | 1 | Stocked Locally (Reservation) | L | [5 empty] | 2020-02-05 | USAMH7 | 1 | EA | 0 | Cooling fan failed and needs replacement | TECO CNF PRT GMPS PRC SETC | XCNF MAXX SFIX XGI | TECO
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 20 | 7000000069 | MODEL 630 AFFF FOAM WHEEL UNIT | 2020-01-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-10 | USMNF8 | 6 | EA | 0 | Send In/Replace Fire Ext Due Hydro | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Deleted
60985331 | 508 | O/SI Steam Valve VAGL-115635 corrosion | S17 | Steam/Hot H2O | 2020-03-24 | 2020-04-05 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGL-115635 | Steam to Coil 1 Isolation Valve | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-24 | 119372000000 | 20 | 20 | 1002407399 | GLOBE VALVE,1 1/2GL01-A,NEWAY | 2020-03-24 | Received at Worksite | 2020-02-18 |  |  | U182 | 8201 | Stones Main | ST1A1B | 11937177 | 2 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 | USNSB4 | 2020-02-05 | USMNF8 | 1 | EA | 1 | Replace steam valve VAGL-115635 | REL ESTC GMPS PRC SETC | APPR EOM MAKD MAOK WPOK ZPMM | Kit Complete |  |  | ST1A1B 02/07/2020 CMR
60973032 | 508 | MGC-A 3rd Stg Bridle Removal | S04 | Gas Compress | 2020-04-20 | 2020-09-26 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2019-10-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-20 | 119235000000 | 10 | 30 | 7000004751 | 7/8" X 9.5 STUDS AND NUTS | 2020-03-21 | Received at Worksite | 2019-10-10 | 2019-11-30 |  | U182 | 8201 | Stones Main | ST KB C7 | 11923491 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-02 | USAWJB | 16 | EA | 16 | MGC-A 3rd Stg Bridle Removal MOC78183 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU WPT AMW 11/30/19
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 40 | 7000002591 | 1161 belzona quart size | 2020-02-04 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | DIISTO1927 | Entity 1 | USJRF5 | 2020-01-28 | USLFA4 | 10 | EA | 10 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 50 | 7000003852 | Serta Smart Layers AIR Arlington Executi | 2020-03-31 | Not Shipped |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  | CAOA021320 | Name 12 | GC832030 | 2020-02-19 | USLFA4 | 1 | EA | 0 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 400 | 7000002603 | 1 1/2" 600# Snap-On Flange Protectors | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 85 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 3 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 250 | 1001267393 | ANGL MTL,EQ,STL,20ft,L3x3x3/8in | 2020-04-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F90 | 11581210 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11201901 | Name 4 | Name 60 | 2019-11-20 | USABCE | 20 | FT | 20 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 390 | 7000002603 | 1 1/2" 300# Snap-On Flange Protectors | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 84 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 3 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60172773 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-04-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.96T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 110086000000 | 10 | 50 | 7000002596 | Stud, M16x85, ASTM A193 Gr. B7 w/2) ASTM | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008582 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081902 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 18 | EA | 18 | MOC missing steam trap | REL PCNF ESTC GMCO GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 530 | 7000002591 | 4452K254 Straight Reducer, 1/2 x 3/8 NPT | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 53 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60920252 | 508 | Ballast Pump 1 Bellows Leaking | S19 | Marine Systems | 2020-02-16 | 2019-10-27 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-17 | 118636000000 | 10 | 10 | 7000000038 | P/N:436 SEAL PACKING (TOMBO #1850P) | 2020-02-02 | Received at Worksite | 2020-01-07 | 2020-01-20 | 2020-02-25 | U182 | 8201 | Stones Main | GRN MILE MOD 22 | 11863639 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-03 | USAWJB | 2 | EA | 2 | Replace Ballast Pump 1 Bellows | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD RUSH WPOK XGI | TECO |  |  | PU Aaron GRN MILE MOD 22
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 360 | 7000002591 | 4452K432 Tee Connector, 1/4 NPT Female | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 36 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 60 | 1002386497 | OIL,LUBT,SHELL,OMALA S2 G 150,5gal | 2020-03-28 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-13 | USAWJB | 20 | PAI | 20 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
60871423 | 508 | Drive End Bearing Leaking Oil - BGCA | S04 | Gas Compress | 2020-03-03 | 2020-01-28 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-20000 | Booster Gas Compression System Train A | 2019-11-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-08 | 118080000000 | 10 | 40 | 7000003684 | ELRING CURIL T LIQUID GASKET NON-HARDENI | 2020-03-03 | Received at Worksite | 2019-12-30 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B8 | 11807987 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-30 | USAWJB | 2 | EA | 2 | Erect Scaffold | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
61163856 | 508 | PG 372A Leaking Glycerin | S04 | Gas Compress | 2020-04-10 | 2021-01-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.PG-77100A-372A | NDE Lube Oil Supply Pressure Gauge | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 121428000000 | 10 | 10 | 7000000066 | 232.30 4 300PSI 1/2 L | 2020-04-10 | Received at Worksite | 2020-02-14 |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 12142830 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-23 | USAWJB | 1 | EA | 1 | PG 372A Leaking Glycerin | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK WPOK ZPMM | Kit Complete
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4810 | 7000002591 | 2" x 27' U-Hook Ratchet Strap (including | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 533 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 16 | EA | 16 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 690 | 7000003740 | Agency Approval Certificates | 2020-02-21 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 861 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN117 | Name 2 | Name 2 | 2020-01-31 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3410 | 1001768456 | ELB BW,WPB,90DEG,LR,80,NPS2 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 371 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 130 | 7000002591 | Flat Bar, 1/4" x 3", ASTM A36 | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 20 | EA | 20 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3520 | 1000712038 | VNT-2505 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 382 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3650 | 7000002603 | GASKET,GARLOCK,STRESS SAVER XP,4in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 395 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 7 | EA | 7 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61229190 | 508 | Blackwater plumbing restricted in Qtrs. | S09 | Bldg & Qtrs | 2020-04-15 | 2020-04-27 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.BQ.F1 | Main Deck Accomodations | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-15 | 122182000000 | 10 | 20 | 7000002583 | Shipping cost to Houma | 2020-04-15 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12218218 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-03-02 | USMNF8 | 1 | EA | 0 | Apply Vecom Uriclean in urinals | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60055275 | 508 | O/SI Incorrect material on gauge LG-7715 | S04 | Gas Compress | 2020-04-11 | 2019-03-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.LG-77151A-231A | 1st Stage Suction Scrubber Level Gauge | 2019-02-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-11 | 108488000000 | 10 | 10 | 1002360760 | SB2N,B7,2H,UNC,1/2in,2.5in,DOXSTEEL | 2020-04-11 | Ready for Shipment after Kitting | 2019-02-25 | 2019-03-27 |  | U182 | 8201 | Stones Main | ST KB C7 | 10848765 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-02-12 | USJDJW | 16 | EA | 16 | LG-7715 change bolting/gaskets | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
61118330 | 508 | 2020 Chemical Order - Subsea | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 20 | 7000003458 | CORR11612SP.32U | 2020-02-19 | Received at Target Location |  | 2019-12-23 |  | U182 | 8201 | Stones Main | CPORT | 12090687 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST200011AA | Name 40 | USAAN5 | 2020-02-05 | USLFA4 | 1000 | GLL | 1000 | 2020 Chemical Order - Subsea | REL ESTC PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5010 | 7000002629 | 45 DEG ELBOW, 8" SCH 10S LR BW CLASS WP- | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 562 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 150 | 7000003196 | Swagelok 304-S3-WPE | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 15 | EA | 15 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5670 | 7000002629 | Flange, 2", 300#, RFWN, S/40S Bore, ASME | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 661 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 60 | 7000003852 | Stainless Steel 316 Chain 1/4" (7mm) Pro | 2020-01-15 | Received at Worksite |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO2CG0137 | Name 26 | USCRFI | 2020-01-14 | USLFA4 | 60 | EA | 60 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU CAPT. TIM
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1110 | 1002360707 | SB2N,B7,2H,UNC,3/4in,4.5in,DOXSTEEL | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 127 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 520 | 7000002644 | 2" 150# RF FP WKM Floating Ball Valve | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 541 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN104 | Name 2 | Name 2 | 2019-11-22 | USLFA4 | 8 | EA | 8 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60744548 | 508 | LER port side doors leaking water | S09 | Bldg & Qtrs | 2020-03-21 | 2020-05-03 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.BQ | Buildings/Quarters | 2019-11-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-21 | 116489000000 | 10 | 30 | 7000004211 | Packing and Air Freight | 2020-03-21 | Received at Target Location | 2020-02-03 |  |  | U182 | 8201 | Stones Main | Stones | 11648860 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-08 | USAWJB | 1 | EA | 1 | Replace LER doors | REL ESTC GMCO GMPS PPRT PRC SETC | APPR MAGN MAKD MAOK RUSH WP | Kit Complete
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 680 | 7000002591 | General 00187 - SR18V-MS Miniature Autom | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 68 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 10 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 70 | 1001209979 | BLT+N,A193-B7,CTD,UNC,4.1/2,7/8 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 54 | EA | 54 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
60470624 | 508 | Turret Gantry Crane Out of Service | S40 | Cargo Handling | 2020-06-01 | 2019-11-19 | O.US.STO.STO.005.724FP | GHEMSPAR | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-06-01 | 113409000000 | 10 | 10 | 7000000040 | 2 x 50 Emery Cloth P180 | 2020-06-01 | Received at Worksite |  | 2019-07-17 | 2020-01-02 | U182 | 8201 | Stones Main | ST KB B2 | 11340935 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-02-15 | USRAR6 | 1 | EA | 1 | Turret Gantry Crane Out of Service | TECO PCNF ESTC GMPS PPRT PRC SETC | XCNF NCMP WPOK XGI ZPVS | TECO |  |  | PU Marty S 05/07/2019 CR
60928540 | 508 | Bearing Defect on Motor - Replace Motor | S26 | Water Treating | 2020-05-01 | 2019-10-31 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.WT.FL.PM-12405B | Pump Motor | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-05-02 | 118728000000 | 20 | 10 | 7000005901 | E07518EP3YAX280SMF33 100HP 1800RPM TEFC | 2020-09-08 | Received at Worksite | 2020-02-03 | 2020-02-20 |  | U182 | 8201 | Stones Main | Staged | 11872786 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-09 | USNSB4 | 1 | EA | 1 | Rigging Services & Assist Replacing Moto | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK RUSH WPOK | EXEC |  |  | STLD17 02/18/2020 CMR
61134552 | 508 | Helideck foam monitor upgrade MOC 80280 | S13 | Fire Protect | 2020-05-27 | 2020-07-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF331-12100 | FiFi Helideck Foam System | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-27 | 121087000000 | 10 | 70 | 7000002596 | Stud Bolt, 3/4" x 4 1/4", Aluminum Bronz | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H04 | 12108694 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST03022001 | Name 4 | Name 60 | 2020-03-03 | USSOLE | 18 | EA | 0 | Helideck foam monitor upgrade MOC 80280 | REL ESTC PRC SETC | APPR MAGN MANX WP | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 550 | 1000717280 | BAR FL,1/4,3in | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 55 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 20 | FT | 20 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 80 | 7000000133 | Lapco FR Long Sleeve Henley in Khaki wit | 2019-12-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Turritella TDR Improvemen | 11545759 | 87 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO1127191 | Name 2 | Name 2 | 2019-12-03 | USSOLE | 154 | EA | 154 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
60629364 | 508 | GT-5 Replace air inlet button plugs | S03 | Elect. Systems | 2020-03-15 | 2020-02-21 | O.US.STO.STO.005.724FP | GGTSSLTB | US.WR508A.ES.PG.LAN-11150 | Gas Turbine Power Generation Package 5 | 2019-07-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-15 | 115191000000 | 10 | 30 | 7000003739 | Conduit Plug PN 1739574 | 2020-03-15 | Received at Worksite |  | 2020-01-20 |  | U182 | 8201 | Stones Main | ST KB B7B | 11519120 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-24 | USAWJB | 4 | EA | 4 | GT-5 Replace air inlet button plugs | REL PRT GMPS PRC SETC | EXEC MAGN MAOK WPOK | EXEC |  |  | PU Aaron 01/19/2020
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 760 | 1002058431 | NUT,A563-DH,HEXAGONAL,UNC,1/2,SERMAGARD | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 76 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 22 | EA | 22 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60725219 | 508 | Replace Suction and Discharge Gauges | S18 | Water Systems | 2020-02-09 | 2020-04-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PG-12110A-102 | Pump Suction Pressure Gauge | 2019-12-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-09 | 116277000000 | 10 | 20 | 7000000062 | WK TAG SS TAG Mfr: WIKA INSTRUMENT CORP | 2020-02-09 | Received at Worksite | 2020-01-13 | 2020-01-29 |  | U182 | 8201 | Stones Main | ST KB A6 | 11627685 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 2 | Replace Suction and Discharge Gauges | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 2/5/2020 JH GG
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 130 | 7000003852 | Magic Chef MCBR240B1 Refrigerator, 2.4 c | 2021-03-03 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO020320A | Name 43 | USCRFI | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | DLVD 2/24/2020 GG
61002670 | 508 | 3M Active Carbon Fine Filter Cartridge | S18 | Water Systems | 2020-02-04 | 2020-03-05 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZAJ-12106 | FW Activated Fine Filter | 2020-02-16 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Normal | 2020-02-06 | 119587000000 | 10 | 10 | 1002133957 | FILTER ELEMENT,0210-HAC24870,HATENBOE | 2020-02-04 | Received at Worksite |  |  | 2020-02-16 | U182 | 8201 | Stones Main |  | 11958668 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  |  |  | 2019-10-20 | EW_BTCJOB | 30 | EA | 30 | 3M Active Carbon Filter Cartridge Replac | TECO CNF ESTC GMPS PRC SETC | XCNF MAOK WPOK XGI | TECO |  |  | ST1A2C 02/07/2020 CMR
61041514 | 508 | SDTA Leaking Actuator XV-309 | S19 | Marine Systems | 2020-04-03 | 2020-05-06 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.BB.XV-1123P-309 | WB Tank No. 3P Suct/Disch Ballast Valve | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-06 | 120021000000 | 20 | 20 | 7000004212 | INTERNATIONAL AIR FREIGHT/CUSTOMS CLEARA | 2020-04-03 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 12002095 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  |  | USNSB4 | 2020-03-02 | USNSB4 | 1 | EA | 0 | Erect Scaffold Platform | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 10 | 7000002591 | 4548K131 1/4 NPT, 7/8" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 360 | 1001763958 | SB2N,A193-B7,CTD,UNC,7.5in,1in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 81 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 18 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60747150 | 508 | COT 3 P HC Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127026 | COT 3 PS HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651962 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60737049 | 508 | Drive End Bearing Leaking Oil - BGCB | S04 | Gas Compress | 2020-03-25 | 2019-06-29 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.CM-77102B | HV Electric Mtr Booster Gas Compressor B | 2019-06-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-27 | 116406000000 | 10 | 40 | 7000000039 | Tube of Curil-T | 2020-03-25 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | Lost by GOM DC | 11640554 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-09-05 | USRAR6 | 2 | EA | 2 | LOTO- BGC B and lube oil pump | REL GMPS PRC SETC | EXEC EOM MAGN MAOK RUSH WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6070 | 7000002629 | Elbow, 1/2", 45, SW, 400 PSIG WOG, ASME | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 705 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 12 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 60 | 7000002629 | FLANGE, 3", 150#, RF, WN, ASTM A105N, AS | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1090 | 7000002596 | STUD BOLTS, 3/4" DIA. X 11" LONG, ASTM A | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 125 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1650 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 181 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 12 | EA | 12 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3360 | 1001774309 | RECB,WPB,40,NPS10x4 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 366 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1120 | 1001759324 | SB2N,A193B8MCL2,UNC,4.5in,3/4in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 128 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 22 | EA | 22 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60701549 | 508 | PCV internals in poor condition | S13 | Fire Protect | 2020-04-25 | 2020-02-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PCV-33151B-456 | Seawater Pump Outlet Press Control Valve | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-25 | 116003000000 | 10 | 10 | 7000002646 | Part No: VM27491071E | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | WR.508A Stones | 11600323 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USFOL2 | 2019-09-30 | USFOL2 | 1 | EA | 0 | Replace PCV 456 | REL GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4330 | 1001622962 | SHT PLT SLD MET,4x8ft,3/8in | 2019-11-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 485 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11131902 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 20 | 100 | 7000002596 | Hex head plug M42 w/O-ring, Hollow | 2020-01-28 | Received at Worksite |  | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB B5 | 11783572 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-23 | USMNF8 | 20 | EA | 20 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC |  |  | PU AARON W
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3860 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2019-11-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 436 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10311902 | Name 2 | Name 2 | 2019-10-31 | USSOLE | 124 | EA | 124 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60797130 | 508 | Multiple Cells High Internal Resistance | S03 | Elect. Systems | 2020-07-19 | 2019-12-11 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.CV.BAT-55601A | Navigation Battery Set A | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-07-21 | 117215000000 | 20 | 10 | 7000005901 | a602/500 6 OPZV420 BATTERY | 2021-01-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11721531 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-11 | USNSB4 | 12 | EA | 0 | Remove & Replace Batteries from BAT-5560 | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 130 | 7000003197 | Nylon Washer ¾” | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 6 | EA | 6 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 10 | 1001207642 | PIPE,API 5L-B/X42,BLACK,STD,12in,SRL | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 20 | FT | 20 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
60470624 | 508 | Turret Gantry Crane Out of Service | S40 | Cargo Handling | 2020-06-01 | 2019-11-19 | O.US.STO.STO.005.724FP | GHEMSPAR | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-06-01 | 113409000000 | 10 | 70 | 7000000040 | Shouldered Eyebolt for Parking DAWG Rele | 2020-06-01 | Received at Worksite |  | 2019-07-17 | 2020-01-02 | U182 | 8201 | Stones Main | ST KB B2 | 11340935 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-02-15 | USRAR6 | 1 | EA | 1 | Turret Gantry Crane Out of Service | TECO PCNF ESTC GMPS PPRT PRC SETC | XCNF NCMP WPOK XGI ZPVS | TECO |  |  | PU Marty S 05/07/2019 CR
61134552 | 508 | Helideck foam monitor upgrade MOC 80280 | S13 | Fire Protect | 2020-05-27 | 2020-07-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF331-12100 | FiFi Helideck Foam System | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-27 | 121087000000 | 10 | 30 | 7000002629 | Flange, 6", 150#, FF, WN, Min Wall .134, | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H04 | 12108694 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST03022001 | Name 4 | Name 60 | 2020-03-03 | USSOLE | 2 | EA | 0 | Helideck foam monitor upgrade MOC 80280 | REL ESTC PRC SETC | APPR MAGN MANX WP | Approved
61006508 | 508 | Replace BGC A position indicator couplin | S04 | Gas Compress | 2020-04-01 | 2020-04-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.ZZZ-77102A | Booster Gas Compressor Package A | 2020-01-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-03 | 119629000000 | 30 | 10 | 7000003464 | DXP-L21GNEB TOPWORX, ALUM, 2-GO SPDT, XP | 2020-04-01 | Received at Worksite | 2020-01-23 |  |  | U182 | 8201 | Stones Main | Stones | 11962884 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-01 | USNSB4 | 12 | EA | 12 | Replace BGC-A Valve Position Indicators | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | ST1B1SIDE 02/07/2020 CMR
60756604 | 508 | Vacuum Condenser Heat Exchanger | S17 | Steam/Hot H2O | 2020-04-01 | 2019-06-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.HBG-11508 | COPT Vacuum Condenser Heat Exchanger | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 116627000000 | 10 | 20 | 7000000101 | p/n: Tubes, naval-brass, 16x1.0tx6103L , | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 11662728 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2019-10-14 | GW982959 | 2000 | EA | 0 | Main condenser tubes leaking | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WP ZPMM ZPVS | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1360 | 7000002596 | 5/8'' Tapered Washers-Galv | 2019-12-27 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | Crane Access Platform | 11581207 | 136 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A380 | Name 2 | Name 59 | 2019-12-24 | USSOLE | 20 | EA | 20 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 20 | 20 | 1002360782 | SB2N,B7,2H,UNC,5/8in,4in,DOXSTEEL | 2020-02-18 | Received at Worksite |  | 2020-02-20 | 2020-02-21 | U182 | 8201 | Stones Main | ST KB D3 | 10754707 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-03-11 | USNSB4 | 12 | EA | 12 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO |  |  | PU AMW
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 160 | 1000718628 | PIPE MET,API5L-X42,80/XH,2.3/8in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 210 | FT | 210 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 840 | 7000002591 | DRILLFORCE (5 Pcs) 31/64 in. x 5-7/8 in. | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 84 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 3 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 820 | 7000002591 | DRILLFORCE (5 Pcs) 29/64 in. x 5-5/8 in. | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 82 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 3 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 130 | 7000003739 | 136612-1 GEAR,PINION | 2020-02-24 | Received at Target Location |  |  | 2020-02-26 | U182 | 8201 | Stones Main | STONES | 12155706 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO
61015475 | 508 | MGC B-TT-77100B-374B need to be replaced | S04 | Gas Compress | 2020-04-07 | 2020-04-21 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.TT-77100B-374B | NDE Lube Oil Return Temp Transmitter | 2019-11-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-07 | 119725000000 | 20 | 20 | 7000000062 | *Mfr: WIKA INSTRUMENT CORP *Mfr pn: WK M | 2020-04-07 | Received at Worksite | 2020-02-04 |  |  | U182 | 8201 | Stones Main | ST1A2C | 11972503 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-18 | USNSB4 | 1 | EA | 1 | Replace Yokogawa Transmitter & Temperatu | REL GMPS PRC SETC | APPR EOM MAGN MAKD MAOK RUSH WPOK ZPMM | Kit Complete |  |  | ST1A1B 02/18/2020 CMR
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 470 | 7000002629 | 3" 600# RF Pressure Rated Skillet CS A36 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 92 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 1 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 300 | 1001207670 | PIPE MET,API 5L-B/X42,160,2in | 2020-05-13 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G14 | 11581210 | 30 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12091901 | Name 4 | Name 60 | 2019-12-09 | USSOLE | 21 | FT | 19.4 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60739062 | 508 | COT 4 P HC line Netherlock | S06 | General | 2020-04-01 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127022 | COT 4 PS HC Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642938 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60430795 | 508 | O/SI Missing Gaskets on SW Lift | S18 | Water Systems | 2020-04-11 | 2019-04-30 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.VE122-10000 | Vessel Sea Water Lift System | 2018-11-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-13 | 112970000000 | 10 | 20 | 7000002603 | 1-1/2 FLEX CGI 150# SP WND GSKT GRF FLR | 2020-01-11 | Received at Worksite |  | 2018-12-15 |  | U182 | 8201 | Stones Main | ST KB D3 | 11296986 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2018-11-06 | USAWJB | 24 | EA | 24 | Install Missing Gaskets on SW Lift | REL PRT GMPS PRC SETC | EXEC MAGN MANX WPOK | EXEC |  |  | PU M. Shephered 12/14/2018 AJ
61151919 | 508 | P.Crane swing gearbox sight glass cloudy | S40 | Cargo Handling | 2020-10-31 | 2021-01-07 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-10-31 | 121288000000 | 10 | 40 | 7000006081 | Copper washer, 423000600,, | 2020-10-31 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12128844 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-06 | USMNF8 | 3 | EA | 0 | Replace port crane gearbox sight glass | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2290 | 1001664310 | BLT HEX,A325,UNC,2.1/2in,3/4in,SERMAGARD | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 251 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 84 | EA | 98 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7230 | 1001583857 | ELB BW,WPB,180DEG,LR,40S,1.1/2in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 981 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6320 | 1001816206 | GASW,CL150,316,GPH,NPS10 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 740 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12271901 | Name 4 | Name 4 | 2019-12-26 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60675075 | 508 | O/SI PV Bulkhead Main Steam Stop | S17 | Steam/Hot H2O | 2020-03-25 | 2019-09-24 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.115-331V | Steam to Separater Isolation Valve | 2019-12-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-26 | 115709000000 | 80 | 30 | 7000004211 | EP-GVB20X25KM, F-7421 FORGED STEELL GLOB | 2020-06-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11570942 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-02 | USNSB4 | 1 | EA | 0 | De-Isolate | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 230 | 7000002596 | M22 x 12" A193 B7 BN Xylan Stud b | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 4 | EA | 4 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60562362 | 508 | O/SI Passing Valve 3rd stage PST-330A MG | S04 | Gas Compress | 2020-03-10 | 2019-03-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VAMO-771031 | Pressure Transmitter Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 114424000000 | 20 | 20 | 7000000104 | Needle Valve, monoflange- slimline bolte | 2020-03-10 | Received at Worksite |  | 2020-02-07 |  | U182 | 8201 | Stones Main | ST KB D5 | 11442408 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-02-15 | USNSB4 | 1 | EA | 1 | Replace Defective Valve 3rd stage PST-33 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4460 | 1001645336 | BLT HEX,A325,UNC,3in,3/4in | 2019-11-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 498 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141903 | Name 4 | Name 4 | 2019-11-14 | USABCE | 22 | EA | 22 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 350 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 735 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231901 | Name 4 | Name 4 | 2019-12-24 | USSOLE | 37 | EA | 37 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60737049 | 508 | Drive End Bearing Leaking Oil - BGCB | S04 | Gas Compress | 2020-03-25 | 2019-06-29 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.CM-77102B | HV Electric Mtr Booster Gas Compressor B | 2019-06-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-27 | 116406000000 | 10 | 70 | 7000003684 | PERMATEX 81724 SENSOR-SAFE ULTRA BLUE | 2020-03-25 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB A4 | 11640554 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-30 | USAWJB | 2 | EA | 2 | LOTO- BGC B and lube oil pump | REL GMPS PRC SETC | EXEC EOM MAGN MAOK RUSH WPOK | EXEC |  |  | STKBA4 2/3/20 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 700 | 7000000052 | EXT,20#,ABC,HIGH PERFORMANCE | 2020-03-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1015 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-16 | USSOLE | 4 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 780 | 7000002629 | FLANGE, 1 1/2", 300#, RF, SW, ASTM A182 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 94 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61165407 | 508 | Install Needle Valve on PG-33120-732 | S13 | Fire Protect | 2020-03-10 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33120-732 | SW Booster Pump Inlet Pressure Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-10 | 121447000000 | 10 | 10 | 1000719976 | COIMC,SWAGELOK,SS60016,3/8x3/8NPT | 2020-03-10 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144692 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 2 | EA | 2 | Install Needle Valve on PG-33120-732 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60815108 | 508 | ER S/W Hypochlorite Analyzer Malfunction | S18 | Water Systems | 2020-03-03 | 2019-12-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZZZ-12214 | Chlorine Analyser Assembly | 2019-10-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-04 | 117437000000 | 20 | 10 | 7000005901 | W3T158828 CARD SENSOR CPL MICRO 2000 PT1 | 2020-06-01 | Received at Worksite | 2019-12-05 | 2020-01-20 |  | U182 | 8201 | Stones Main | ST1A6B | 11743717 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-15 | USNSB4 | 1 | EA | 1 | Replace Hypochlorite Meter | REL PRT GMCO GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU AARON W 01/19/2020
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 620 | 1001207632 | PIPE MET,API 5L-B/X42,STD,3in,SRL | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 62 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 21 | FT | 20.25 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 110 | 7000002646 | V2-507SDT-XB 1/2" MNPT x FNPT; 316SS; 6 | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 41 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-17 | USSOLE | 17 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
61074267 | 508 | O/SI SDV-66201-864 Needs Replacement | S22 | Prod Gathering | 2020-03-10 | 2020-01-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.SDV-66201-864 | Separator Crude Oil Outlet Shutdown Vlv | 2020-01-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-11 | 120397000000 | 10 | 20 | 7000002596 | 7/8 X 6-1/4 (6 FTF) TEFLON CTD ZINC STUD | 2020-03-10 | Received at Worksite | 2020-01-02 | 2020-02-08 |  | U182 | 8201 | Stones Main | ST1A4B | 12039685 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-10 | USMNF8 | 20 | EA | 20 | LOTO and Deinventory 1 stage Separator | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW ST1A4B
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 300 | 7000002644 | Model# 320F-23-CGF-23 WKM 3" 600# Floati | 2020-08-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 34 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-16 | USSOLE | 4 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 240 | 1001816212 | GASW,CL150,316,GPH,NPS1.1/2 | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 24 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60014436 | 508 | Non OEM Valve PUPD-10903-MIS003 | S19 | Marine Systems | 2020-02-25 | 2019-02-20 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PR.PUPD-10903-MIS | Cylinder No. 1 HP Fuel Oil Pump | 2019-01-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 107753000000 | 10 | 30 | 7000005901 | VALVE FOR D+16MM | 2020-04-15 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST KB B6 | 10775349 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-02 | USNSB4 | 2 | EA | 2 | Replace Non-OEM Valve PUPD-10903-MIS003 | REL CNF PRT GMPS PRC SETC | SCHD EOM MAGN MAOK WPOK | EXEC |  |  | PU 02/16/20 AMW
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 260 | 7000002591 | 4452K412 90 Degree Elbow Connector, 1/4 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 26 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 50 | 7000004211 | ANS200x150x350/PN-20 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 2 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60960149 | 508 | SDV-938A Passing on MGC-A | S04 | Gas Compress | 2020-07-10 | 2020-09-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.SDV-77135A-938 | Gas Outlet Start Up Line Shutdown Valve | 2019-11-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-07-10 | 119089000000 | 20 | 10 | 7000004211 | VALVE: TRUNNION MOUNTED BALL VALVE, REDU | 2020-10-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11908867 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-05 | USNSB4 | 1 | EA | 0 | Replace Defective Valve SDV-77135A-938A | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1860 | 7000002603 | GASKET, 12", 300#, RF, 1/8" THK., SPIRAL | 2019-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 204 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01241901 | Name 2 | Name 2 | 2019-01-24 | USSOLE | 6 | EA | 6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 790 | 7000002629 | BLIND FLANGE, 1 1/2", 300#, RF, ASTM A1 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 95 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60655411 | 508 | Discharge check valve passing | S08 | Air Systems | 2020-02-27 | 2019-09-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11805 | Top Up Start Air Compressor | 2019-11-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-27 | 115485000000 | 20 | 30 | 7000002646 | 6294-XXXX 00000 PACKING COST | 2020-02-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11548488 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-22 | USNSB4 | 1 | EA | 0 | Replace Check Valve On Start Air Compres | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAOK WPOK | Deleted
60701549 | 508 | PCV internals in poor condition | S13 | Fire Protect | 2020-04-25 | 2020-02-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PCV-33151B-456 | Seawater Pump Outlet Press Control Valve | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-25 | 116003000000 | 30 | 30 | 7000002646 | Part No: KLINGERSIL 4401 | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | WR.508A Stones | 11600323 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USFOL2 | 2019-09-30 | USFOL2 | 1 | EA | 0 | Replace PCV 456 | REL GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7210 | 7000002662 | Pipe; 6" X s/40 (6.625 x 0.280), API 5L | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 979 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20.65 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 280 | 1001697917 | BLT HEX,316,UNC,1/4in,1.1/4in | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 28 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 100 | EA | 100 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 780 | 1001816211 | GASW,CL150,316,GPH,NPS2 | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose |  | 11179936 | 1044 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-23 | USSOLE | 3 | EA | 3 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7600 | 1002301613 | SB2N,B8M CL2,8M,UNC,5/8in,5.00in | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 1022 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-16 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6100 | 1001574910 | FLG SW,C70600,FF,CL150,2in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 708 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 31 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 730 | 7000003197 | PL SSTF06SFC-3 SS 6INW CHANNEL TRAY COVE | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 904 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 8 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7760 | 7000002603 | 2" Flange Protectors 3", 300#, RFWN | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1039 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61112406 | 508 | 2nd Stg Sep PST upgrade | S22 | Prod Gathering | 2020-04-11 | 2020-06-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.PST-66202-178 | 2nd Stg Separator Press Sfty Transmitter | 2019-12-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-11 | 120837000000 | 20 | 30 | 1002360776 | SB2N,B7,2H,UNC,5/8in,5.5in,DOXSTEEL | 2020-04-11 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B3 | 12083677 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-23 | USNSB4 | 4 | EA | 4 | Upgrade PST-66202-178 To Rosemount Trans | REL ESTC GMPS PPRT PRC SETC | APPR EOM MAGN MAOK RUSH WPOK ZPMM | EXEC |  |  | STKBDB3 2/3/20 GG
60760732 | 508 | 2Y PLC Battery Replacement | S20 | Monitor & Ctrl | 2021-05-22 | 2021-08-20 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.MC.PL | Monitoring and Control Panels | 2019-05-25 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Normal | 2021-05-22 | 116776000000 | 10 | 20 | 7000000039 | YOKOGAWA P/N S9548FA BATTERY,, | 2021-05-22 | Received at Worksite | 2019-11-26 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 11677557 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-15 | USRAR6 | 12 | EA | 12 | 2Y PLC/Yokogawa Battery Replacement | REL CSER GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU AARON W 01/19/2020
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 260 | 7000002603 | Flange Protectors 10", 300#, RF | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 122 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1110 | 7000002591 | Product Type Code: Smart-Ex02-ROW-DZ1AIC | 2020-03-06 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 111 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STENG22520 | Name 44 | USRRIG | 2020-02-27 | USLFA4 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61163869 | 508 | MeOH Inj Limit Switch Swap MOC 69266 | S10 | Chem Injection | 2020-04-01 | 2020-03-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.CI.ZZZ-12870 | Turret Methanol Injection System | 2020-01-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-01 | 121427000000 | 10 | 10 | 7000000062 | Custom Machined Valve Adaptors | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12142743 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-27 | USNSB4 | 14 | EA | 0 | Install TopWorx Limit Switch MeOH Inject | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60848029 | 508 | OSI N2 HMI DEGRADING | S08 | Air Systems | 2020-05-06 | 2019-09-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.AT-11820-600 | Oxygen Analyser | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-05-06 | 117810000000 | 10 | 20 | 7000003740 | Front panel assy LCD: X2GC, X2F, X2FD; s | 2020-05-06 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST KB D3 | 11781007 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 24 | USNSB4 | 2019-08-23 | USNSB4 | 1 | EA | 1 | Replace Front Screen/Keypad, N2 Analyzer | REL PCNF PRT GMPS PRC SETC | EXEC EOM MAGN WPOK | EXEC |  |  | PU 02/16/20 AMW
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 590 | 7000002591 | 4452K263 Straight Reducer, 1 x 1/2 NPT F | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 59 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 100 | 7000002596 | Flat Washer, 3/8", ASTM F436 or equivale | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 14 | EA | 14 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
60544614 | 508 | Mechanical seal is leaking | S18 | Water Systems | 2020-06-02 | 2019-07-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216A | No. 1 Main/COPT Condenser Cooling Pump | 2019-12-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 114224000000 | 10 | 40 | 7000004211 | Line bearing, SVS350M-41 | 2020-06-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11422404 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-15 | USMNF8 | 1 | EA | 0 | Mechanical seal is leaking | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4300 | 1002360782 | SB2N,B7,2H,UNC,5/8in,4in,DOXSTEEL | 2019-11-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 482 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11121901 | Name 4 | Name 4 | 2019-11-12 | USLFA4 | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 420 | 1001411555 | MODULE,1756-OB16I,ALLENB | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 428 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 4 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 580 | 7000002629 | TEE, 8" X 8", S/10S (0.148 WT) X S/10S ( | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 74 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5980 | 7000002662 | Pipe, 1/2", SMLS Class 700, 90/10 CuNi A | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 696 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 10 | FT | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 140 | 7000002591 | Stud, M22 x 10", ASTM A193 Gr. B7 w/ASTM | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 22 | EA | 22 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1150 | 1001697784 | WASH GEN,SS316,FLAT,7/8in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 131 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 344 | EA | 344 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 160 | 7000003852 | PhysiciansCare by First Aid Only 90546 . | 2020-03-01 | Received at Worksite |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0148 | Entity 7 | USCRFI | 2020-02-12 | USLFA4 | 20 | EA | 20 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU CARGO 2/24/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1230 | 1001645338 | BLT HEX,A325,UNC,2.1/4in,3/4in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 139 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061802 | Name 2 | Name 2 | 2018-12-07 | USSOLE | 156 | EA | 156 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60989629 | 508 | COPT SW #3 Pump mechanical seal leak | S18 | Water Systems | 2020-04-14 | 2019-12-06 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216C | No. 3 Main/COPT Condenser Cooling Pump | 2019-12-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-14 | 119420000000 | 10 | 70 | 7000004211 | Mechanical seal set, SVS350M-MS-SET-PN54 | 2020-04-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11942032 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-13 | USMNF8 | 1 | EA | 0 | COPT SW #3 Pump mechanical seal leak | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2150 | 7000002596 | STUD BOLTS, 5/8" DIA. X 3 1/2" LONG, AS | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 237 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 36 | EA | 36 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 740 | 1001641854 | FLG BLIND,A105,RF, CL150,4in,W/TAP,1/2in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 90 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61134552 | 508 | Helideck foam monitor upgrade MOC 80280 | S13 | Fire Protect | 2020-05-27 | 2020-07-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF331-12100 | FiFi Helideck Foam System | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-27 | 121087000000 | 10 | 60 | 7000002596 | Stud Bolt, 5/8" x 3 3/4", Aluminum Bronz | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H04 | 12108694 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST03022001 | Name 4 | Name 60 | 2020-03-03 | USSOLE | 18 | EA | 0 | Helideck foam monitor upgrade MOC 80280 | REL ESTC PRC SETC | APPR MAGN MANX WP | Approved
60628343 | 508 | O/SI Leaking CI Hose coupling in Stab Pl | S19 | Marine Systems | 2020-04-25 | 2019-04-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-89001A | Umb Fluid #1 Upr Stabplate FL Connector | 2019-04-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-27 | 115180000000 | 10 | 20 | 7000003196 | BH9MF16MF20 BULKHEAD FITTING | 2020-04-25 | Received at Target Location |  | 2019-09-22 |  | U182 | 8201 | Stones Main | ST KB B7B | 11517991 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-04-22 | USJDJW | 1 | EA | 1 | REPLACE LEAKING BULKHEAD FITTING | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU WPT STKB B7
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 10 | 7000003197 | 2’ LED Luminary, 5K Lu LLEDA15LU2D | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 2 | EA | 2 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
60133131 | 508 | O/SI COT 2S Stripping Valve Failed | S21 | Oil Treating | 2021-11-01 | 2018-07-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6632S-364 | Crude Oil to/from COT 2 SBB Valve | 2018-06-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2021-11-01 | 109520000000 | 10 | 10 | 7000000105 | REPAIR KIT 8" NAKAKITA VALVE (10K-000A, | 2021-11-01 | Received at Worksite |  | 2018-10-17 |  | U182 | 8201 | Stones Main | ST KB D5 | 10951956 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-06-12 | USNSB4 | 1 | EA | 1 | Replace Soft Goods - 663-OT-109 XV-364 C | REL PCNF PRT CSER GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU Aaron 10/03/2018
61208363 | 508 | Latching Dog Tubing to Hose Replacement | S19 | Marine Systems | 2020-04-02 | 2020-04-11 | P.US.STO.NF.20.010.7240A | 508ACR | US.WR508A.MA.PS.ZZZ-87412A | BTM Bouy Stinger Bell | 2020-02-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-04-02 | 121937000000 | 50 | 10 | 7000000098 | 12PS-5000-SS-FJFJ-30” ¾” Hose Assembly – | 2020-04-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12193721 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-20 | USNSB4 | 12 | EA | 0 | Replace Tubing Lines With Hose, Latching | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61155246 | 508 | Install Barring Device on MGCA | S04 | Gas Compress | 2020-03-03 | 2020-07-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-03 | 121329000000 | 10 | 50 | 7000002591 | 3038A22 (27/64" drill bit) | 2019-11-01 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST1A6C | 12132852 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0006 | Name 17 | JP832018 | 2020-01-27 | USLFA4 | 2 | EA | 2 | Install Barring Device on MGCA | REL PCNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC |  |  | ST1A6C 02/16/20 AMW
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 170 | 7000003739 | 903556C1 O-RING,SAE 166,VITON | 2020-02-24 | Received at Target Location |  |  | 2020-02-26 | U182 | 8201 | Stones Main | STONES | 12155706 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 210 | 7000004751 | Keckley 2" 600# Floating Ball Valve | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN115 | Name 2 | Name 2 | 2020-01-30 | USSOLE | 2 | EA | 2 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
61091311 | 508 | Bunrt comp cord on Warehouse A/C unit. | S14 | HVAC | 2020-02-04 | 2020-01-29 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.HVAC-10820 | Warehouse HVAC System | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-04 | 120587000000 | 10 | 10 | 7000004451 | Power plug , HYM07MP223 | 2020-02-04 | Ready for Shipment after Kitting | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7D | 12058713 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-08 | USMNF8 | 2 | EA | 2 | Loto Warehouse AC unit | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO |  |  | PU Aaron 1/19/2020
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1000 | 7000002591 | Shackle, 8 1/2 Ton Crosby (G-2130) w/1.150 | 2020-04-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 100 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10281901 | Name 4 | Name 59 | 2019-10-29 | USABCE | 4 | EA | 4 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61048407 | 508 | Secure Lifeboat Lifejacket Boxes | S15 | Life Saving | 2020-02-04 | 2020-11-07 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.PP-AW | Air & Water Survival Personal Prot Equip | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-05 | 120100000000 | 10 | 20 | 7000000111 | 3/8" flat washers for life jacket boxes | 2020-02-04 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7B | 12010041 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-12 | USAMH7 | 32 | EA | 32 | Secure Lifeboat Lifejacket Boxes | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 400 | 7000002591 | Hydramax HM07 ADPT KIT SUIT, 1-5/8IN, 8U | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 71 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 14 | EA | 14 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
60975393 | 508 | O/SI BGCB Discharge Valve Passing | S04 | Gas Compress | 2020-02-15 | 2021-12-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VABL-771293 | Outlet Gas SDV Isolation Valve | 2019-12-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 8 User defined period | 2020-02-15 | 119261000000 | 10 | 20 | 7000004753 | 3-COAT PAINT STONES RAL-1023 YELLOW,,,,, | 2020-02-15 | Received at Target Location | 2020-01-13 | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Stones | 11926135 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-24 | USAWJB | 1 | EA | 1 | Replace VABL-771293 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 30 | 7000002591 | Grainger 8oz ballpeen hammer #22UM25 | 2020-01-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0005 | Name 8 | USCRFI | 2020-01-13 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
60739066 | 508 | COT 4 Port vent netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127050 | COT 4 PS Vent Gas Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642942 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61109055 | 508 | Hilti clip installation engine room | S06 | General | 2020-10-05 | 2020-12-11 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GN.MI.HG | Handrails & Grating | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-10-06 | 120800000000 | 10 | 20 | 7000002583 | 10 BX 412689 DX cartridge 6.8/11 M10 STD | 2020-10-05 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12079993 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USMRRO | 2020-02-18 | USMRRO | 10 | EA | 0 | Hilti clip installation engine room | REL PPRT PRC SETC | APPR MAGN WPOK ZPMM | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 150 | 1001708483 | BLT HEX,A325,UNC,2.1/4in,1/2in | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 10 | EA | 10 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 60 | 7000002603 | Gasket, 1 1/2", Spiral Wound Flex Gasket | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 3 | EA | 3 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 370 | 7000002591 | 2''x6'x2Ply Nylon Straps | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 746 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A384 | Name 2 | Name 2 | 2020-01-11 | USSOLE | 6 | EA | 6 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 10 | 1000711441 | VBAT,SWAGELOK,SS-65TF16,1in,2000psi | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 3 | EA | 3 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 660 | 7000002629 | TEE, 12" X 12", S/10S (0.180 WT) X S/10S | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 82 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4690 | 7000002629 | Flange, 3", 300#, RFWN, S/40S Bore, ASME | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 521 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4100 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 460 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 68 | EA | 68 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 10 | 7000002591 | 30 Gallon Flammable Manual Close Safety | 2020-01-28 | Received at Worksite |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0004 | Name 17 | USKHU3 | 2020-01-08 | USLFA4 | 1 | EA | 1 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU RICK W
60908998 | 508 | Passing SPSV 049 MAJ 12202A | S18 | Water Systems | 2020-02-20 | 2020-02-14 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PSV-12202A-902 | Filter Pressure Safety Valve | 2019-10-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-20 | 118510000000 | 10 | 10 | 7000002646 | 2" Valve MODEL 33A WITH HOOD | 2020-05-20 | Received at Worksite |  | 2020-02-08 | 2020-02-26 | U182 | 8201 | Stones Main | ST1A5B | 11851034 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-03 | USNSB4 | 1 | EA | 1 | Replace SPSV 049 MAJ 12202A | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | ST1A5B 02/07/2020 CMR
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 190 | 7000003852 | DEWALT Screwdriver Bit Set, Impact Ready | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
60756604 | 508 | Vacuum Condenser Heat Exchanger | S17 | Steam/Hot H2O | 2020-04-01 | 2019-06-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.HBG-11508 | COPT Vacuum Condenser Heat Exchanger | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 116627000000 | 10 | 50 | 7000000101 | p/n: Gasket, non-Asbestos, 3t ,Item 18. | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 11662728 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2019-10-14 | GW982959 | 4 | EA | 0 | Main condenser tubes leaking | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WP ZPMM ZPVS | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 180 | 7000003197 | B-Line SS6CC-04-144 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 7 | EA | 7 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 940 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2020-02-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F13 | 11581207 | 94 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09191901 | Entity 3 | Name 59 | 2019-09-19 | USSOLE | 5 | EA | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 220 | 7000003344 | Grating, Fibergrate Safe T-Span 1 1/2" D | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 5 | EA | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 370 | 7000002591 | 28mm ½” drive crowfoot socket. Part numb | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 37 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG014 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS2 | 10 | 7000003196 | Swagelok SS-16-HRN-12 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Seawater Eductor | 11545759 | 64 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI59 | Name 2 | Name 2 | 2019-10-23 | USSOLE | 4 | EA | 4 | Shop Order Sheets - I&E Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 60 | 7000002591 | IWISS Wire Rope Crimping Tool for Alumin | 2019-06-13 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Lower Turret Fire Extingu | 11545759 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A31 | Name 2 | Name 2 | 2019-06-07 | USDKFB | 1 | EA | 1 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 140 | 7000002591 | 3M Cold Shrink (3M 8425-8) | 2019-11-26 | Received at Target Location |  |  | 2020-02-14 | U182 | 8201 | Stones Main | Onsite Danos Has | 11882270 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI65 | Name 2 | Name 58 | 2019-11-06 | USSOLE | 4 | EA | 5 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
61153324 | 508 | Structural connector rod end bearing dam | S19 | Marine Systems | 2020-03-10 | 2020-07-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-88503 | Structural Connector No. 3 | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-12 | 121305000000 | 10 | 10 | 7000000111 | Rod end bearings, SFE1245 | 2020-03-10 | Received at Worksite | 2020-01-24 | 2020-02-07 |  | U182 | 8201 | Stones Main | Issued | 12130528 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 28 |  | 2020-01-16 | USMNF8 | 9 | EA | 9 | Replace rod end bearings on LVDT | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
61046320 | 508 | Overhaul helideck standby pump cartridge | S13 | Fire Protect | 2020-04-21 | 2020-05-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33132 | Helideck Firewater Pump | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 120075000000 | 10 | 20 | 7000004211 | WEAR RING 83776-001 | 2020-04-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12007515 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-20 | USMNF8 | 2 | EA | 0 | Overhaul helideck standby pump cartridge | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 610 | 7000002591 | 4452K142 Plug with External Hex Drive, | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 61 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 70 | 7000002629 | FLANGE, 2", 150#, RF, WN, ASTM A105N, AS | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1720 | 1002301613 | SB2N,B8M CL2,8M,UNC,5/8in,5.00in | 2019-01-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 189 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01171901 | Name 2 | Name 2 | 2019-01-18 | USDSVB | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 10 | 80 | 7000000068 | DK BOOT-2 DOUBLE LEG SHRINK BOOT KIT | 2020-02-07 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | Issued | 11614811 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 7 | USNSB4 | 2019-09-28 | USAWJB | 2 | EA | 2 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 580 | 7000003740 | Rosemount Product Drawing | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 690 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN109 | Name 2 | Name 2 | 2019-12-17 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
61042037 | 508 | End Stops OOC - Collar Deck - ZZZ-887106 | S40 | Cargo Handling | 2020-02-09 | 2020-06-30 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-11-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-21 | 120026000000 | 10 | 10 | 7000003343 | 4"x 4" x 1/2" A36 Angle, Galvanized | 2020-01-18 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | Trolley End Stops | 12002579 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A393 | Name 2 | Name 59 | 2020-02-01 | USSOLE | 20 | FT | 20 | Fabricate End Stops | REL PCNF ESTC GMCO GMPS PPRT PRC SETC | EXEC MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7130 | 1001267401 | CHANNEL,4in,5.4lb/ft,20ft | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 971 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 240 | 7000002603 | FLAT RING GASKET, 3", 150#, RF, FLEXIBLE | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 37 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 9 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5590 | 7000002662 | Pipe, 2", S/40S, ASME B36.19M, ASTM A790 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 653 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 20 | FT | 22.13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 700 | 7000002629 | BLIND FLANGE, 8", 300#, RF, ASTM A182 GR | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 86 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7020 | 1000721717 | U-BOLT,GALV+NEOPRENE,2x3/8in,W/4NUT | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 950 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052001 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 25 | EA | 25 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4970 | 7000002629 | 90 DEG ELBOW, 4" SCH 40 LR BW ASTM A234 | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 558 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 11 | EA | 11 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 270 | 1001697911 | BLT HEX,316,UNC,1/4in,1in | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 27 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 100 | EA | 100 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60352956 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-10 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33320 | No. 1 Starboard Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-11 | 112105000000 | 10 | 10 | 1001618989 | OIL FILTER,359-BUKH0202,ALXR-RYN | 2020-02-10 | Received at Worksite |  | 2019-10-20 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210548 | 1 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 | USAWJB | 2019-07-17 | USRAR6 | 1 | EA | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
61112406 | 508 | 2nd Stg Sep PST upgrade | S22 | Prod Gathering | 2020-04-11 | 2020-06-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.PST-66202-178 | 2nd Stg Separator Press Sfty Transmitter | 2019-12-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-11 | 120837000000 | 20 | 60 | 1000709357 | PLUG,PIPE,THREADED,1/2in,SS-8-P,SWAGELOK | 2020-04-11 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B3 | 12083677 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-28 | USNSB4 | 2 | EA | 2 | Upgrade PST-66202-178 To Rosemount Trans | REL ESTC GMPS PPRT PRC SETC | APPR EOM MAGN MAOK RUSH WPOK ZPMM | EXEC |  |  | ST1A3C 02/3/20 GG
61042035 | 508 | Install Fall protection for IG platform | S06 | General | 2020-02-09 | 2020-01-03 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.IG | Inert Gas/Vent Systems | 2020-01-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-09 | 120026000000 | 20 | 10 | 7000000132 | Swing gate, 32" | 2020-02-09 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-09 | U182 | 8201 | Stones Main | WHSE FLOOR | 12002575 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-09 | USMNF8 | 2 | EA | 2 | Install Fall protection for IG platform | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1FLR 01/29/20 GG
60569071 | 508 | Replace Seals on Coupling | S19 | Marine Systems | 2020-05-07 | 2019-07-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2020-03-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-07 | 114501000000 | 20 | 10 | 1000599007 | OIL,HYDR,SHELL,OMALA S2 G 680,20l | 2020-05-07 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11450113 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2019-12-17 | USMNF8 | 2 | EA | 0 | Replace O-rings on Coupling | REL ESTC PRC SETC | APPR MAXX WP ZPMM | Approved
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 60 | 7000003197 | HWKE DIRECT ITEM HAWKE M20 LOCKNUT Pn: 7 | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11780965 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | Name 58 | 2019-10-29 | USNSB4 | 4 | EA | 0 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC PRC SETC | APPR EOM MAGN WP ZPMM | Deleted
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 780 | 7000002591 | DRILLFORCE (5 Pcs) 25/64 in. x 5-1/8 in. | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 78 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 3 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 570 | 1001917715 | CAP PIPE SW,A105,CL3K,NPS2 | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 57 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60699172 | 508 | O/SI Valve XV-1122S-326 over rotating Ba | S19 | Marine Systems | 2020-04-08 | 2019-10-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.BB.XV-1122S-326 | WB Tank No. 1S Water Line Ballast Valve | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-09 | 115978000000 | 50 | 80 | 7000004211 | Hydraulic Actuator Model HAA-D08 | 2020-04-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11597808 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 1 | EA | 0 | Valve over rotating | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 580 | 7000002591 | 4452K262 Straight Reducer, 1 x 3/8 NPT F | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 58 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61221684 | 508 | Steam Expansion Bellows critical spare | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-22 | P.US.STO.NF.20.015.7240A | 508ERENG | US.WR508A.GU.SW.VE115-32000 | Boiler System Steam Distribution | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-06-02 | 122096000000 | 10 | 80 | 7000003323 | Documentation for line items 1 - 7 with | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12209639 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAMH7 | 2020-03-02 | USRAR6 | 1 | EA | 0 | Shut down steam system | CRTD PRC | INIT RUSH WP | Approved
60440621 | 508 | Replace Laydown Timber - MODs 15, 17, 19 | S40 | Cargo Handling | 2020-03-10 | 2020-06-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.LS | Loading Stations | 2019-08-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 113072000000 | 10 | 80 | 7000002583 | 0.5 HP General Duty Keyless Air Drill, P | 2020-03-10 | Received at Worksite |  | 2019-09-11 |  | U182 | 8201 | Stones Main | ST KB A1 | 11307214 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-06 | USAWJB | 1 | EA | 1 | Replace Laydown Timbers - MOD 15 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAOK RUSH WPOK | EXEC |  |  | PU KB A1
61152125 | 508 | SUB order to replace GT2 oil scavenger p | S03 | Elect. Systems | 2020-07-01 | 2020-07-11 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PG.M-3500-1 | Turbine Scavenge Pump A Motor | 2020-01-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-07-02 | 121291000000 | 20 | 20 | 7000000084 | GT2 oil scavenger pump motor | 2020-07-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12129125 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-13 | USAMH7 | 1 | EA | 0 | Perform Mechanical Isolation To Replace | REL PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 160 | 7000000039 | 8570-12-304 Plug, 110v,16Amp Series, Yel | 2020-03-03 | Not Shipped |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 16 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOELEC001 | Name 30 | JP832018 | 2020-02-04 | USLFA4 | 12 | EA | 0 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | Deleted
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 60 | 1000709969 | ADIMC,SWAGELOK,SS12TA112,3/4x3/4NPT | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 3 | EA | 3 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
60133132 | 508 | COT 2S - 450MM | S21 | Oil Treating | 2021-01-01 | 2018-06-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6632S-365 | Crude Oil to/from COT 2 SB Valve | 2018-06-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2021-01-02 | 109520000000 | 10 | 10 | 7000000105 | REPAIR KIT 18" NAKAKITA VALVE (10K-450A, | 2021-01-01 | Received at Worksite |  | 2018-10-17 |  | U182 | 8201 | Stones Main | ST KB D5 | 10951957 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-06-12 | USNSB4 | 1 | EA | 1 | Replace Soft Goods - 663-OT-107 XV-365 C | REL ESTC CSER GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU Aaron 10/03/2018
61141209 | 508 | OPS cabinet needs latches | S19 | Marine Systems | 2020-12-13 | 2020-12-30 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-89901 | Turret Oil Pressurization System HPU | 2020-01-30 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-12-13 | 121161000000 | 10 | 10 | 7000002583 | Door latch, square drive cam lock | 2020-02-27 | Received at Worksite | 2020-02-11 | 2020-02-19 |  | U182 | 8201 | Stones Main | ST KB B6 | 12116064 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-30 | USMNF8 | 6 | EA | 6 | OPS cabinet needs latches | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 02/19/20 AMW
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 320 | 7000002591 | 4452K113 Straight Connector, 3/8 NPT Fe | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 32 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1410 | 7000002629 | SPEC BLIND,3" 300, ASTM A790 UNS S31803 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 157 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5680 | 7000002629 | Blind Flange, 3", 300#, RF, ASME B16.5, | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 662 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6640 | 7000002629 | Flange, 4", SO, 150#, FF, Min Wall .109, | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 875 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 450 | 7000002662 | PIPE, 8", S/10S (0.148 WT), ASTM A790 UN | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 61 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 105 | FT | 98.5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 670 | 7000002591 | 1"x2' Kevlar nylon strap protector | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 924 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A396 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 6 | EA | 6 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7190 | 7000002662 | 10" X s/40 (10.75 x 0.365), API 5L X52 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 977 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 21 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1280 | 7000002603 | 4" FLG PROTECTOR (FLANGE, 4", 150#, RF | 2019-12-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 144 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12101801 | Name 2 | Name 2 | 2018-12-11 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2980 | 1002316829 | GASW,CL300/600,316/316L,GPH,2in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 328 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1320 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-12-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 148 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12101801 | Name 2 | Name 2 | 2018-12-11 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3030 | 7000002629 | Blind Flanges, 2", 300#, RF, ASME B16.5, | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 333 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 10 | 10 | 7000003513 | L-1661-36 JONTECH Humidity Sensor L-1661 | 2020-02-07 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | Issued | 11614811 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 7 | USNSB4 | 2019-06-18 | USNSB4 | 1 | KIT | 1 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 720 | 1001664310 | BLT HEX,A325,UNC,2.1/2in,3/4in,SERMAGARD | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 72 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 42 | EA | 42 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60958935 | 508 | MGC A 2nd Stage Gas Outlet DBB Passing | S04 | Gas Compress | 2021-04-01 | 2020-03-10 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VADB-771003 | Heat Exchanger Isolation Valve | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2021-04-02 | 119075000000 | 10 | 30 | 7000000039 | 6" 600 gasket | 2021-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 11907487 | 3 | 4 | Non-Stock (Purchase Requisition) | N | [5 empty] | 2020-02-11 | USJDJW | 2 | EA | 0 | hang rigging MGC A 2nd Stage Gas Outlet | REL CSER PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 20 | 60 | 7000004211 | LOCKING WASHER 146<(>,<)> 20031-024 | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A2B | 11762536 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 1 | Replace pump cover on Jockey Pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved |  |  | ST1A2B 02/18/2020 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 110 | 1001676781 | SHT PLT SLD MET,4x4ft,1/2in,A572 GR.50 | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60860117 | 508 | Corrosion flange leaking | S19 | Marine Systems | 2020-03-10 | 2020-01-23 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2020-01-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-11 | 117953000000 | 20 | 10 | 7000005901 | OA,US,AEL AMERICAS,ELECTRICAL MATL,EA | 2020-03-10 | Received at Target Location | 2020-02-28 |  |  | U182 | 8201 | Stones Main | STONES | 11795259 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 1 | EA | 1 | Corrosion flange leaking | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WPOK ZPMM | Kit Complete
61141212 | 508 | Repair Sea Water Pipe Water Maker #2 | S18 | Water Systems | 2020-03-03 | 2020-03-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZAN-12102 | No. 2 Fresh Water Generator | 2020-02-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-03 | 121163000000 | 10 | 10 | 7000000079 | Airgas welding rods for copper nickel | 2020-03-03 | Received at Worksite | 2020-02-16 |  | 2020-02-16 | U182 | 8201 | Stones Main | Issued | 12116307 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-01-07 | USAMH7 | 1 | EA | 1 | Repair Sea Water Pipe Water Maker #2 | TECO CNF PRT GMCO GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 02/16/20 AMW
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 460 | 7000002591 | Hydratight Air Pump w/ Stainless Tank | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 77 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 3 | EA | 3 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 210 | 7000004461 | ¾” FNPT x 1” FNPT Anderson Greenwood PSV | 2019-10-16 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | JOB NO: 2335 | 11545759 | 45 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN095 | Name 2 | Name 2 | 2019-10-09 | USSOLE | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 160 | 7000000039 | One(1) Det-tronics Q1201 Green Laser(#00 | 2020-02-28 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20ACR00 | Name 9 | USCRFI | 2020-01-28 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 60 | 7000000039 | YMD-8529 HOSE ASSEMBLY X27"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 160 | 7000003852 | 9527 Product 6" x 9" Clear Adhesive Top | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 32 |  | 2020-02-18 | USAWJB | 10 | EA | 10 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 120 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 94 | EA | 94 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60717786 | 508 | #3 latching dog cylinder bolts are broke | S19 | Marine Systems | 2020-02-18 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-21 | 116191000000 | 50 | 60 | 7000002596 | M24-3.0 PITCH X 65MM, SOCKET HEAD CAPSCR | 2019-06-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | PO Canceled Mike Nettles | 11619069 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3/60717786 |  | 2019-05-20 | USMNF8 | 8 | EA | 0 | Replace broken bolts in the cylinder #3 | REL ESTC GMCO GMPS PRC SETC | APPR MAGN WP ZPMM | Deleted
61219225 | 508 | GT #5 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-4 | Generator #5 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 10 | 7000003763 | 8MGT-1120-12 POLY CHAIN BELT | 2020-04-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206809 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #5 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7960 | 7000002629 | Cap, 2", SW, 400 PSIG WOG, ASME B16.11, | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 1081 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-28 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 650 | 7000003197 | PL SS4606L09144 SS TRAY 6IN 6W LAD | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 896 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 3 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60729276 | 508 | O/SI Valve Stuck in Closed Position | S18 | Water Systems | 2020-02-20 | 2019-11-30 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.122-131V | Pump Suction Valve | 2019-05-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-20 | 116320000000 | 10 | 20 | 7000004211 | PAINT-SHELL, SHELL PAINT SPECIFICATIONS | 2020-02-20 | Received at Worksite |  | 2019-07-13 |  | U182 | 8201 | Stones Main | Issued | 11632019 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 | USNSB4 | 2019-05-13 | USNSB4 | 1 | EA | 1 | Replace Butterfly Valve | REL CNF PRT GMPS PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC |  |  | PU Aaron 07/08/2019
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1850 | 7000002629 | FLANGE, 12", 300#, RF, WN, ASTM A182 GR | 2019-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 203 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01241901 | Name 2 | Name 2 | 2019-01-24 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7940 | 7000002629 | Reducing Tee, 2" x 1/2", SW, 400 PSIG, W | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 1079 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-28 | USSOLE | 14 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 70 | 1000789908 | COIMC,SWAGELOK,SS810112,1/2x3/4NPT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 785 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 5 | EA | 5 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7970 | 1001574910 | FLG SW,C70600,FF,CL150,2in | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 1082 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-28 | USSOLE | 6 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 450 | 7000003197 | Earth Tag for 3/4" Connector | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 837 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 3 | EA | 3 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7740 | 1002301610 | SB2N,B8M CL2,8M,UNC,5/8in,3.50in | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1037 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 36 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1210 | 1000717280 | BAR FL,1/4,3in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 137 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061802 | Name 2 | Name 2 | 2018-12-07 | USSOLE | 40 | FT | 40 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 680 | 7000002629 | THREAD-O-LET, 12" X 3/4", 6000#, FS, MSS | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 84 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 60 | 7000003196 | Swagelok 304-S3-WPE | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 15 | EA | 15 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2270 | 7000002591 | Fabreeka #700 Epoxy Adhesive Additional | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 249 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 250 | 7000002596 | 5/8" x 2 Hex Head Machine Bolt A320-L7 A | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 12 | EA | 12 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60717782 | 508 | EPAF Seal Protection alarms/operates | S04 | Gas Compress | 2020-04-01 | 2019-06-21 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.CBA-77163B | 2nd Stage Booster Gas Compressor B | 2019-06-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-04-01 | 116191000000 | 20 | 10 | 7000003740 | Guided Wave Radar 5301HS2S1V3BM00045AAE7 | 2020-04-01 | Received at Worksite |  | 2019-09-16 |  | U182 | 8201 | Stones Main | ST1A1C | 11619065 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-06-20 | USNSB4 | 1 | EA | 1 | Install New Level Transmitters | REL PCNF PRT GMPS PRC SETC | EXEC EOM MAGN MAOK RUSH WPOK | EXEC |  |  | ST1A1C 09/22/2019 CMR
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 10 | 40 | 7000003852 | Insignia 6' DisplayPort Cable | 2020-05-16 | Not Shipped |  | 2020-01-19 |  | U182 | 8201 | Stones Main | STONES | 11783572 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 22 | USNSB4 | 2019-08-10 | USMNF8 | 9 | EA | 0 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC
60959167 | 508 | Ballast Pump #1 Suction Px Gauge | S19 | Marine Systems | 2020-02-04 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.BB.PG-11201A-246 | Ballast Pump No. 1 Suct Pressure Gauge | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-04 | 119075000000 | 20 | 20 | 7000000062 | WK 47442334 Description: IV20 in-line 1/ | 2020-02-04 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7D | 11907503 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 33 | USNSB4 | 2019-10-21 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge, Ballast Pump #1 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD WPOK XGI | TECO |  |  | PU AARON W 01/19/2020
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 110 | 7000003196 | 1/2" Union Tee (Swagelok Part Number SS-81 | 2019-11-19 | Received at Target Location |  |  | 2020-02-14 | U182 | 8270 | Danos - Amelia | Onsite Danos Has | 11882270 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI66 | Name 15 | Name 58 | 2019-11-06 | USABCE | 2 | EA | 2 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 580 | 7000002629 | Pipe Nipple, 1 1/4" x 6" LG, S/40 (1.660 | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 58 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1200 | 1000718609 | PIPE,1",XH,2.17#,CS,PEBFW,SRL,0.179,SML | 2020-05-07 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G04 | 11581207 | 120 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031901 | Name 4 | Name 59 | 2019-12-04 | USSOLE | 21 | FT | 21 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 10 | 7000000069 | Fire Extinguishers 2.5 GALLON CG250 FOAM | 2020-01-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-10 | USMNF8 | 30 | EA | 0 | Send In/Replace Fire Ext Due Hydro | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Deleted
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 40 | 7000000039 | YMD-8529 HOSE ASSEMBLY X33"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61174165 | 508 | Puchase FW Pump | S13 | Fire Protect | 2020-06-02 |  | P.US.STO.NF.20.008.7240A | 508MECH | US.WR508A.GU.FP.PBE-33122 | Fwd Firewater Booster Pump | 2020-01-27 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-02 | 121546000000 | 10 | 10 | 1002595494 | PUMP,IRONPUMP,QH20/320,1950/2885m/h | 2020-06-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 12154603 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2020-01-28 | GW982959 | 1 | EA | 0 | Puchase FW Pump | REL ESTC PRC SETC | APPR | Approved
61218667 | 508 | Replace Lifeboat Rations & Water | S15 | Life Saving | 2020-12-10 | 2021-02-17 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.LB | Lifeboats | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-12-11 | 122061000000 | 10 | 40 | 7000004662 | Datrex Water, DX1000W<(>,<)> 4oz (125ml) | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12206109 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-25 | USAWJB | 1920 | EA | 0 | Replace Lifeboat Rations & Water | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61046320 | 508 | Overhaul helideck standby pump cartridge | S13 | Fire Protect | 2020-04-21 | 2020-05-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33132 | Helideck Firewater Pump | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 120075000000 | 10 | 30 | 7000004211 | JOURNAL BEARING 81874-001 | 2020-04-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12007515 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-20 | USMNF8 | 2 | EA | 0 | Overhaul helideck standby pump cartridge | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
61054608 | 508 | 3M Breathing Air Compressor Output Test | S08 | Air Systems | 2020-02-25 | 2020-02-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.VE118-50000 | Fwd TR Breathing Air System | 2019-11-17 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 1 Safety / TI Critical | 2020-02-25 | 120173000000 | 20 | 10 | 7000002591 | P/N: THE AIRCHECK KIT W/ CGA ADAPTOR K90 | 2020-02-25 | Received at Target Location |  | 2020-02-07 |  | U182 | 8201 | Stones Main | WPT Desk | 12017311 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-02-07 | GW982959 | 1 | EA | 1 | 3M Breathing Air Compressor Output Test | REL CNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2260 | 7000002591 | Fabreeka #700 Epoxy Adhesive Kit with 50 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 248 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4470 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-11-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 499 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141903 | Name 4 | Name 4 | 2019-11-14 | USABCE | 44 | EA | 44 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 40 | 7000000101 | 1" Stainless Steel 304 Street L 90 Degre | 2020-04-29 | Received at Worksite | 2019-11-27 | 2020-01-29 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772908 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 5 | EA | 5 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO |  |  | ST1A1C 01/22/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 660 | 7000002591 | 2"x6' Kevlar nylon strap protector | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 923 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A396 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 6 | EA | 6 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5540 | 7000002629 | 2" x 27' U-Hook Ratchet Strap (including | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 615 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 28 | EA | 28 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7750 | 7000002644 | Ball Valve, 3/4", VBT-1502D | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1038 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60739080 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-03-17 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-242 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-17 | 116430000000 | 10 | 30 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-06-05 | Received at Worksite | 2020-01-29 | 2020-02-16 |  | U182 | 8201 | Stones Main | ST KB B7C | 11642976 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 1 | LO/TO Isolate LCP ZZZ-11923 LCP#3 | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 02/16/20 AMW
60991728 | 508 | Replace Coolant in Thruster VFD | S03 | Elect. Systems | 2020-03-10 | 2020-10-05 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.VFD-45010 | Turret Thruster Variable Frequency Drive | 2019-11-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-03-10 | 119442000000 | 10 | 20 | 7000003948 | Havoline Dex-Cool Automotive Antifreeze | 2020-03-10 | Received at Target Location | 2019-11-11 |  |  | U182 | 8201 | Stones Main | Stones | 11944212 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-11-05 | USRAR6 | 6 | GLL | 6 | Replace coolant in Thruster VFD. | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WP | Kit Complete
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 190 | 7000002591 | Burr Bit, SC-5, Single Cut, Cylindrical | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 645 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 10 | EA | 10 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5480 | 7000002629 | 4" 300 RFWN Flange Protectors | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 609 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1930 | 7000002603 | GASKET, 4" 150#, RF, 1/8" THK, SPIRAL W | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 215 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7670 | 7000002629 | Elbow, 2", LR 90, S/40S, BW, ASME B16.9 | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1030 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 210 | 7000002591 | 11/16" Hogan Bits REG mag drill bits | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 647 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 10 | EA | 10 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60739081 | 508 | VPI test fail COT 5 STBD | S21 | Oil Treating | 2020-02-05 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-243 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-09-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 116430000000 | 20 | 10 | 7000005901 | P.0244110036 AVC 02 CL1 A1 VPI MANIFOLD | 2020-04-25 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-09 | U182 | 8201 | Stones Main | ST KB B7F | 11642977 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-18 | USNSB4 | 1 | EA | 1 | Repair VPI XV-6635S-243 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU Aaron ST1A1B 01/19/2020 C
61178975 | 508 | Fire extinguishers hydro due June 2020 | S13 | Fire Protect | 2020-04-27 | 2020-07-28 | P.US.STO.NF.20.007.7240A | 508COPER | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-02-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-28 | 121602000000 | 10 | 10 | 7000005811 | 15# extinguishers CO2 | 2020-04-27 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12160190 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-27 | USMNF8 | 16 | EA | 0 | Replace expired fire extinguishers | REL ESTC PRC SETC | APPR MAGN WP ZPMM | Approved
60344326 | 508 | VABL-777050 Ext Stm Leak | S05 | Gas Dist | 2021-04-30 | 2019-03-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GD.FG.VABL-777050 | Superheater PCV Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2021-04-30 | 112007000000 | 20 | 30 | 1001816278 | GASW,CL300,316,GPH,NPS6 | 2021-04-30 | Received at Worksite | 2019-02-21 | 2019-03-06 |  | U182 | 8201 | Stones Main | ST KB D3 | 11200701 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-01-30 | USNSB4 | 2 | EA | 2 | Repair Valve VABL-777050 | REL PRT CSER GMPS PRC SETC | EXEC EOM MAKD MAOK WPOK | EXEC |  |  | PU 03/03/2019 AJ
61175895 | 508 | No.1 LO Purifier Break-over | S06 | General | 2020-02-19 | 2021-01-22 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.LO.ZAK-11711A | Main Lube Oil Purifier No. 1 | 2020-01-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-19 | 121567000000 | 10 | 10 | 1002469025 | SPARE PART SET,2059-9902-210,GEA | 2020-02-19 | Received at Worksite |  | 2020-02-08 |  | U182 | 8201 | Stones Main | ST KB A3 | 12156715 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2020-01-29 | USAWJB | 1 | EA | 1 | No.1 LO Purifier Break-over | REL PCNF PRT GMPS PRC SETC | SCHD MAOK WPOK | EXEC |  |  | ST1A2C 02/07/2020 CMR
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 90 | 1000715365 | SEALANT,THREAD,SWAGELOK,MS-PTS-50 | 2019-11-19 | Received at Target Location |  |  | 2020-02-14 | U182 | 8270 | Danos - Amelia | Onsite Danos Has | 11882270 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI66 | Name 15 | Name 58 | 2019-11-06 | USABCE | 1 | EA | 1 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60175730 | 508 | PCV-77703-966A Passing Through | S05 | Gas Dist | 2020-03-25 | 2018-12-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GD.FG.PCV-77703-966A | Buyback Gas to HP Scrubber Pres Ctrl Vlv | 2018-11-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-27 | 110121000000 | 20 | 10 | 7000000104 | PCV-77703-966A Type 3251-1 Control Valve | 2020-03-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 11/28 | 11012083 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2018-10-29 | USNSB4 | 1 | EA | 0 | Set Up Rigging & Assist Replacement Of P | REL PRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 30 | 7000000133 | 8x8 3M Adhesive signs stating “DO NOT TI | 2020-02-26 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia |  | 11545759 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN072 |  |  | 2019-06-13 | USGBI5 | 6 | EA | 6 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
61026238 | 508 | MGCB Pipe Support Bracket Installation | S04 | Gas Compress | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DANOS | US.WR508A.GC.GS.VADB-771017 | Inlet Gas Valve | 2019-11-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-01 | 119851000000 | 10 | 40 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2020-03-27 | Received at Target Location |  | 2019-11-12 |  | U182 | 8201 | Stones Main | SHF9-F65 | 11985064 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111902 | Name 4 |  | 2019-11-12 | USLFA4 | 10 | EA | 10 | Install 4x A325 3/4 x 3-3/4 Bolts | REL PRT GMPS PRC SETC | APPR MAGN MAOK WP ZPMM | EXEC
60804117 | 508 | Missing Autoclave Plugs on Methanol DBB | S10 | Chem Injection | 2020-02-21 | 2019-12-14 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.CI.VADB-1281002 | Flare to Knock Out Drum Isolation Valve | 2019-11-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-21 | 117297000000 | 10 | 10 | 7000000412 | MI CP902507SOG CP90-2507SOG 9/16 In Hp F | 2020-04-01 | Received at Worksite | 2020-01-07 | 2020-01-20 | 2020-02-20 | U182 | 8201 | Stones Main | Issued | 11729727 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 45 | USNSB4 | 2019-11-14 | USNSB4 | 2 | EA | 2 | Install Autoclave Plugs, Methanol DBB VA | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU Aaron 01/19/2020
61114758 | 508 | O/SI SDV-77163A-904A Passing By | S04 | Gas Compress | 2020-02-15 | 2020-06-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.SDV-77163A-904 | 2nd Stg Compressor Out Gas Shutdown Vlv | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-15 | 120863000000 | 10 | 10 | 7000004751 | 8" 300 RF Full Port, GVI G4 Trunnion, 31 | 2020-02-15 | Received at Worksite | 2020-01-23 | 2020-02-07 | 2020-02-18 | U182 | 8201 | Stones Main | GKA002/STBD laydown | 12086293 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 59 | 2019-12-27 | USAWJB | 1 | EA | 1 | Replace SDV-77163A-904A | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 20 | 7000005901 | Hawke Part Number 121 / A / M20 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780965 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI77 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 370 | 7000002591 | 2 Pack Heavy-Duty Bar Mat Pad PVC Rubber | 2020-02-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 37 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 1 | EA | 1 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61165413 | 508 | Install Needle Valve on PG-33120-733 | S13 | Fire Protect | 2020-03-10 | 2020-03-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33120-733 | SW Booster Pump Outlet Pressure Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-10 | 121447000000 | 10 | 10 | 1000719976 | COIMC,SWAGELOK,SS60016,3/8x3/8NPT | 2020-03-10 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144698 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 2 | EA | 2 | Install Needle Valve on PG-33120-733 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60701397 | 508 | Leaking Globe/Check Valve on Hydrophore | S18 | Water Systems | 2020-04-11 | 2019-10-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.121-20V | Tank Outlet Check Valve | 2020-01-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-11 | 116003000000 | 10 | 50 | 1001206218 | BLT+N,A193-B7,CTD,UNC,2.1/2,1/2 | 2020-02-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Requested PO canceled AMW | 11600310 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-28 | USAWJB | 10 | EA | 0 | LO/TO Perform Isolations To Repair Globe | REL ESTC PRC SETC | APPR EOM MAGN MANX RUSH WPOK ZPMM | Deleted
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 40 | 7000000069 | Water extinguishers | 2020-01-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-10 | USMNF8 | 12 | EA | 0 | Send In/Replace Fire Ext Due Hydro | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Deleted
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 310 | 1001768455 | ELB BW,WPB,90DEG,LR,160,NPS2 | 2020-05-13 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G14 | 11581210 | 31 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12091901 | Name 4 | Name 60 | 2019-12-09 | USSOLE | 4 | EA | 4 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60847989 | 508 | MOC GTG5 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-44000 | Gen #5 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 90 | 7000005901 | NK Technologies AT2-420-24L-FT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780944 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI80 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 2 | EA | 2 | SAEP LO/TO Isolate GTG #5 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 570 | 1000709049 | TAPE,ELEC,66',3/4",RED | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 849 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 10 | EA | 10 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60985462 | 508 | No.3 COP stuffing box bellows leaks | S21 | Oil Treating | 2020-04-25 | 2019-11-25 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301C | Cargo Oil Pump No. 3 | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-27 | 119373000000 | 20 | 20 | 7000000038 | P/N:436 SEAL PACKING (TOMBO #1850P) | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937329 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  | PLWST3-W | Name 3 | USMSLN | 2019-10-09 | USMNF8 | 4 | EA | 0 | Replace COP #3 pump bellows | REL PRT PRC SETC | APPR MAGN WPOK ZPMM | Approved
60985462 | 508 | No.3 COP stuffing box bellows leaks | S21 | Oil Treating | 2020-04-25 | 2019-11-25 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301C | Cargo Oil Pump No. 3 | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-27 | 119373000000 | 20 | 40 | 7000000038 | FULL SET OF BOLTS ON ATTACHED | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937329 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  | PLWST3-W | Name 3 | USMSLN | 2019-10-09 | USMNF8 | 4 | EA | 0 | Replace COP #3 pump bellows | REL PRT PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7530 | 7000002591 | Safety Snap Hook, 7/16", Galv., Crosby-L | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1011 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7580 | 7000002603 | GASKET,GARLOCK,STRESS SAVER XP,2in | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 1020 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-16 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1770 | 7000002629 | FLANGE, 12", 300#, RF, WN, ASTM A182 GR | 2019-01-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 194 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01171902 | Name 2 | Name 2 | 2019-01-18 | USDSVB | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2680 | 7000002646 | 1/2" Needle Valve VNT-2505SD (See attach | 2019-06-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 291 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06041902 | Name 2 | Name 2 | 2019-06-04 | USDKFB | 7 | EA | 7 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3550 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 385 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61006508 | 508 | Replace BGC A position indicator couplin | S04 | Gas Compress | 2020-04-01 | 2020-04-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.ZZZ-77102A | Booster Gas Compressor Package A | 2020-01-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-03 | 119629000000 | 30 | 20 | 7000003464 | DXS-L21GNEB TOPWORX, 316 SST ENCLOUSER,2 | 2020-04-01 | Received at Worksite | 2020-01-23 |  |  | U182 | 8201 | Stones Main | Stones | 11962884 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-01 | USNSB4 | 12 | EA | 12 | Replace BGC-A Valve Position Indicators | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | ST1B1SIDE 02/07/2020 CMR
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 470 | 7000000098 | PPA 100 1" POLYPRO PART A | 2020-03-16 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 47 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOET00120 | Name 3 | USCRFI | 2020-02-09 | USLFA4 | 11 | EA | 11 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A3C 2/24/2020 GG
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 40 | 1002316828 | GASW,CL300/600,316/316L,GPH,1.1/2in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 49 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 1 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61219231 | 508 | GT #1 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113 | Generator #1 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 40 | 7000003763 | 8MX-80S-12 SPKT | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206815 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #1 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61023509 | 508 | Grating on green mile needs replacing. | S19 | Marine Systems | 2020-06-01 | 2019-12-25 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.HG | Handrails, Stairways, Grating | 2020-02-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-06-02 | 119822000000 | 10 | 80 | 1001723500 | WASHER,LOCK,F436,SERMAGAURD,1/2in | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G87 | 11982221 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02172001 | Name 4 | Name 60 | 2020-02-19 | USSOLE | 36 | EA | 36 | Grating on green mile needs replacing. | REL ESTC PRC SETC | APPR EOM MAGN MANX WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 680 | 1002119303 | WASHER,FLAT,F436,SERMAGARD,0.177in,1in | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 68 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 14 | EA | 14 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60760732 | 508 | 2Y PLC Battery Replacement | S20 | Monitor & Ctrl | 2021-05-22 | 2021-08-20 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.MC.PL | Monitoring and Control Panels | 2019-05-25 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Normal | 2021-05-22 | 116776000000 | 10 | 10 | 1001236860 | BATTERY,NRC,YOKOGAWA,S9129FA,2.4V | 2021-05-22 | Received at Worksite | 2019-11-26 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 11677557 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 | USMSLN | 2019-10-15 | USRAR6 | 11 | EA | 11 | 2Y PLC/Yokogawa Battery Replacement | REL CSER GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A1C 02/08/2020 CMR 9EA
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 40 | 7000002596 | Cotter Key Hair Pin Style, for use on 3/ | 2019-06-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Lower Turret Fire Extingu | 11545759 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A308 | Name 2 | Name 2 | 2019-06-03 | USSOLE | 30 | EA | 30 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 340 | 7000002591 | 4452K115 Straight Connector, 3/4 NPT Fem | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 34 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 80 | 7000003852 | Primeda VGA Extenders,1080P VGA Over Sin | 2020-03-31 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | CAOA021320 | Name 12 | USRRIG | 2020-02-19 | USLFA4 | 2 | EA | 2 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 170 | 7000002591 | Nut, 3/8", SS | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 8 | EA | 8 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 20 | 7000003196 | Swagelok SS-1610-1-16 | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 6 | EA | 6 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 110 | 7000004213 | KE35/14 SASAKURA KE35 P/N 14 GLOBE VALVE | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61049139 | 508 | HP/LP Piston Failure | S08 | Air Systems | 2020-02-12 | 2020-01-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11804A | Start Air Compressor No. 1 | 2020-02-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-14 | 120119000000 | 10 | 20 | 1002404742 | HP PISTON,3404MK,SPERRE | 2020-02-12 | Not Shipped | 2020-02-13 | 2020-02-13 |  | U182 | 8201 | Stones Main | ST KB A3 | 12011865 | 2 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 1 | EA | 0 | Rebuild Start Compressor #1 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAKD MAXX RUSH WPOK | EXEC
61193230 | 508 | CAT 2 CAIR3609 galvanic corroded gasket | S10 | Chem Injection | 2020-03-22 | 2020-04-01 | O.US.STO.STO.005.724FP | 508OPER | US.WR508A.GU.CI.TS128-11000 | Biocide Injection System | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-22 | 121762000000 | 10 | 10 | 1001201442 | GASKET,SPW,FLEXITAL,CGI,316,CL150,2in | 2020-03-22 | Received at Worksite | 2020-02-11 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B4 | 12176239 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 6 | EA | 6 | CAT 2 CAIR3609 galvanic corroded gasket | REL ESTC GMPS PRC SETC | EXEC MAKD MAOK WPOK | EXEC
60246898 | 508 | Damaged Hoses on stab plate #2 | S19 | Marine Systems | 2020-03-10 | 2019-07-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89003A | Umb Fluid #2 Upr Stabplate FL Connector | 2019-10-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-03-11 | 110924000000 | 20 | 50 | 7000000101 | NAS 6 FLUSHING W/HW525 NITROGEN PURGED L | 2020-04-29 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | ETA 12/18 | 11092386 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-07 | USNSB4 | 1 | EA | 1 | LO/TO Perform Isolations *2-Man Rule In | REL PRT GMPS PRC SETC | APPR EOM MAGN MAOK WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 390 | 7000002591 | 2''x10'x2Play Nylon Straps | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 748 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A384 | Name 2 | Name 2 | 2020-01-11 | USSOLE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1380 | 1001811045 | FLWN,A105,CL150,STD,NPS12 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 154 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 150 | 7000003197 | Earth Tag ¾” | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 6 | EA | 6 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6980 | 7000002591 | 1 kg of Belzona 1161 | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 946 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 550 | 7000000052 | Solids Handling Control Panel w/ Panel V | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 617 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN106 | Entity 4 | Entity 4 | 2019-11-26 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 290 | 1001180705 | NUT,N228SS6,COOP-BLI | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 821 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 150 | EA | 150 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1690 | 7000002603 | 6"300# RFWN FLANGE PROTECTOR | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 185 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60915161 | 508 | Ess Generator 1 Overspeed Test failure | S03 | Elect. Systems | 2020-04-28 | 2019-10-26 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.ES.PG.ZZZ-11101A | Essential Generator No. 1 Engine | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-28 | 118572000000 | 10 | 10 | 7000005901 | Univer valve CL-111A SENSIBLE BALL PUSH | 2020-06-12 | Received at Worksite | 2020-01-28 |  |  | U182 | 8201 | Stones Main | Stones | 11857150 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-02 | USNSB4 | 2 | EA | 2 | LO/TO Isolate Essential Generator #1 | REL ESTC GMCO GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | ST1A1B 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 250 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-12-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 651 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12121902 | Name 4 | Name 4 | 2019-12-13 | USSOLE | 28 | EA | 28 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2940 | 7000002629 | Flange, 2", 300#, RFWN, S/40S Bore, ASME | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 324 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60696550 | 508 | Spare parts for MGC's | S04 | Gas Compress | 2020-02-09 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GC | Gas Compression | 2020-02-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-02-09 | 115950000000 | 10 | 30 | 7000000033 | Ring Set Renewal: D-R Part No: 100019142 | 2020-02-09 | Received at Worksite |  |  | 2020-02-10 | U182 | 8201 | Stones Main | ST1A2B | 11595045 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-04-11 | USRAR6 | 5 | EA | 5 | Check in spare compressor parts | TECO ESTC GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO |  |  | PU MIKE N 2/8/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1130 | 1001697822 | WASH GEN,SS316,FLAT,3/4in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 129 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 76 | EA | 76 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6520 | 7000002662 | Pipe, 3", .095 Min Wall, ASTM B466, 90/1 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 863 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 160 | FT | 160 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6460 | 1001816265 | GASW,CL300-600,316,GPH,NPS3 | 2020-02-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 810 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01282001 | Name 4 | Name 4 | 2020-01-29 | USDKFB | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3950 | 7000002591 | Neoprene Strips, 1/8" x 3 1/2" W x 11" L | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 445 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11011902 | Name 4 | Name 4 | 2019-11-01 | USSOLE | 110 | EA | 110 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60696550 | 508 | Spare parts for MGC's | S04 | Gas Compress | 2020-02-09 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GC | Gas Compression | 2020-02-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-02-09 | 115950000000 | 10 | 40 | 7000000033 | Stud D-R Part No: R89158JX08044 | 2020-02-09 | Ready for Shipment after Kitting |  |  | 2020-02-10 | U182 | 8201 | Stones Main | ST1A2B | 11595045 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-04-11 | USRAR6 | 2 | EA | 2 | Check in spare compressor parts | TECO ESTC GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO |  |  | PU Marty 06/10/2019 Per Aaron
60975393 | 508 | O/SI BGCB Discharge Valve Passing | S04 | Gas Compress | 2020-02-15 | 2021-12-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VABL-771293 | Outlet Gas SDV Isolation Valve | 2019-12-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 8 User defined period | 2020-02-15 | 119261000000 | 10 | 40 | 7000004751 | 8" 300 RF Flex Gaskets,,,,,,,, | 2020-02-15 | Received at Worksite | 2020-01-13 | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Stones | 11926135 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-24 | USAWJB | 2 | EA | 2 | Replace VABL-771293 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO
60958935 | 508 | MGC A 2nd Stage Gas Outlet DBB Passing | S04 | Gas Compress | 2021-04-01 | 2020-03-10 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VADB-771003 | Heat Exchanger Isolation Valve | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2021-04-02 | 119075000000 | 10 | 20 | 7000000039 | 1" x 6-3/4" studs w/2 nuts each | 2021-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 11907487 | 2 | 4 | Non-Stock (Purchase Requisition) | N | [5 empty] | 2020-02-11 | USJDJW | 24 | EA | 0 | hang rigging MGC A 2nd Stage Gas Outlet | REL CSER PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61112406 | 508 | 2nd Stg Sep PST upgrade | S22 | Prod Gathering | 2020-04-11 | 2020-06-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.PST-66202-178 | 2nd Stg Separator Press Sfty Transmitter | 2019-12-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-11 | 120837000000 | 20 | 40 | 1000710973 | NPHT,SWAGELOK,SS-8-HN,1/2in,NPTM | 2020-04-11 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B3 | 12083677 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-28 | USNSB4 | 1 | EA | 1 | Upgrade PST-66202-178 To Rosemount Trans | REL ESTC GMPS PPRT PRC SETC | APPR EOM MAGN MAOK RUSH WPOK ZPMM | EXEC |  |  | ST1A3C 02/3/20 GG
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 120 | 7000002596 | 0004 2473-3003 00000 1/2 X 3 (2-3/4 FT | 2020-02-24 | Received at Target Location |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-15 | USNSB4 | 8 | EA | 8 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
60744548 | 508 | LER port side doors leaking water | S09 | Bldg & Qtrs | 2020-03-21 | 2020-05-03 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.BQ | Buildings/Quarters | 2019-11-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-21 | 116489000000 | 10 | 10 | 7000004211 | D1.3 Class H120, STL. WEATHER & GAS TIGH | 2020-03-21 | Received at Target Location | 2020-02-03 |  |  | U182 | 8201 | Stones Main | Stones | 11648860 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-08 | USAWJB | 1 | EA | 1 | Replace LER doors | REL ESTC GMCO GMPS PPRT PRC SETC | APPR MAGN MAKD MAOK RUSH WP | Kit Complete
60636179 | 508 | MGC-B Replace all inspection door bolts | S04 | Gas Compress | 2020-04-04 | 2020-02-25 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-11000 | Compressor Package B | 2020-03-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-04 | 115265000000 | 10 | 20 | 7000002596 | 1/2 x 1-1/4" long zinc Nut | 2020-04-04 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11526529 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-15 | USMNF8 | 500 | EA | 0 | Replace inspection cover bolts | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60184795 | 508 | Repair HCV-77202-842 | S39 | Gas Treating | 2021-03-01 | 2019-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.HCV-77202-842 | TEG Contactor Choke Valve | 2018-08-22 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2021-03-01 | 110226000000 | 10 | 10 | 1002360780 | SB2N,B7,2H,UNC,5/8in,4.5in,DOXSTEEL | 2021-03-01 | Received at Worksite |  | 2019-05-09 |  | U182 | 8201 | Stones Main | ST KB D1 | 11022591 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-08-07 | USNSB4 | 16 | EA | 16 | Repair HCV-77202-842 | REL PRT CSER GMCO GMPS PRC SETC | EXEC MAGN MAOK WPOK | EXEC |  |  | PU Marty S 05/07/2019 CR
60544614 | 508 | Mechanical seal is leaking | S18 | Water Systems | 2020-06-02 | 2019-07-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216A | No. 1 Main/COPT Condenser Cooling Pump | 2019-12-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 114224000000 | 10 | 20 | 7000004211 | Packing PN: 31, SVS350M-31 | 2020-06-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11422404 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-15 | USMNF8 | 1 | EA | 0 | Mechanical seal is leaking | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 350 | 7000002591 | 4452K116 Straight Connector, 1 NPT Femal | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 35 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60942274 | 508 | Replace Chain Bucket - Hoist ZZZ-874125 | S40 | Cargo Handling | 2020-04-18 | 2020-06-30 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-11-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-04-18 | 118880000000 | 10 | 10 | 7000000040 | Stainless steel Chain Bucket | 2020-04-18 | Received at Worksite | 2020-02-20 |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 11887982 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-04 | USCMFR | 1 | EA | 1 | Install S.S Chain Bucket ZZZ-874125 | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 290 | 7000002629 | 2" x 1 1/2" NIPPLE CONC. SWAGE SCH 80S T | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 56 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A363 | Name 2 | Name 2 | 2019-10-21 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 70 | 7000003323 | Model# SPFW-32FC32SS3-32FC32SS3-120 | 2019-09-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 30 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN082 | Name 2 | Name 2 | 2019-08-19 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60958245 | 508 | Slew Drive Mounting Bolts- STBD CRN | S40 | Cargo Handling | 2020-02-25 | 2020-09-17 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2020-02-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-25 | 119064000000 | 10 | 10 | 7000000040 | Swing Drive Mounting Bolts | 2020-02-25 | Received at Worksite | 2020-02-22 | 2020-02-22 | 2020-02-22 | U182 | 8201 | Stones Main | MOD 22 GRN Mile | 11906448 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-23 | USCMFR | 108 | EA | 108 | S. Babin Relocate Crane Slew Gbox Drain | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF EOM MAGN MAKD MAOK RUSH WPOK XGI | TECO |  |  | PU A. WISTRAND 12-20-19
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 440 | 7000002591 | 4452K168 Bushing Adapter, 3/4 Male x 1/4 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 44 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60172773 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-04-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.96T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 110086000000 | 10 | 10 | 7000002629 | Pipe Nipple, 40mm x 12" Lg, S/80, STPG41 | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008582 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081902 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 2 | EA | 2 | MOC missing steam trap | REL PCNF ESTC GMCO GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 160 | 7000003196 | Swagelok SS-TBP12 | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 50 | EA | 50 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60246898 | 508 | Damaged Hoses on stab plate #2 | S19 | Marine Systems | 2020-03-10 | 2019-07-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89003A | Umb Fluid #2 Upr Stabplate FL Connector | 2019-10-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-03-11 | 110924000000 | 20 | 30 | 7000000101 | ASSY-13/4HPPA, 39FT 4IN OAL ALL SS 9/16" | 2020-04-29 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | ETA 12/18 | 11092386 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-07 | USNSB4 | 1 | EA | 1 | LO/TO Perform Isolations *2-Man Rule In | REL PRT GMPS PRC SETC | APPR EOM MAGN MAOK WP ZPMM | Approved
61102257 | 508 | P.Crane radiator fan shroud corroded | S40 | Cargo Handling | 2020-05-10 | 2020-06-10 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-10 | 120716000000 | 10 | 60 | 7000006081 | Guard sheet 21827 | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12071582 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 2 | EA | 0 | P.Crane radiator fan shroud corroded | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
60686665 | 508 | O/SI Passing #1 Boiler Drum Vent Valve | S17 | Steam/Hot H2O | 2020-04-01 | 2019-09-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.NAC-11503A | Auxiliary Boiler No. 1 | 2019-12-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-02 | 115837000000 | 30 | 20 | 7000004211 | FLANGE PACK, flange pack to include all | 2020-05-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11583660 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-04 | USNSB4 | 1 | EA | 0 | Replace Boiler #1 Vent Valve, 20k x 25mm | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61175103 | 508 | Barrier Fluid HPU Sample Mod | S24 | Subsea Systems | 2020-03-03 | 2020-03-19 | O.US.STO.STO.002.724FP | 508ACR | US.WR508A.SE.OH.ZZZ-12865 | Barrier Fluid Hydraulic Power Unit | 2020-01-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-03 | 121557000000 | 10 | 30 | 7000003196 | 2507-600-1-6 MALE CONNECTOR | 2020-03-03 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7A | 12155741 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-29 | USNSB4 | 8 | EA | 8 | Install Needle Valves & Fabricate Tubing | REL GMPS PRC SETC | SCHD EOM MAGN MAOK WPOK | EXEC |  |  | PU A WISTRAND 02/24/2020
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 190 | 7000002591 | Lock Washer, 3/8", SS | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 8 | EA | 8 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3210 | 7000002596 | BLT HEX,A325,UNC,4.3/8n,3/4in,HDG | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 351 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61219229 | 508 | GT #4 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-3 | Generator #4 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-21 | 122068000000 | 10 | 10 | 7000003763 | 8MGT-1120-12 POLY CHAIN BELT | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206813 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #4 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7060 | 1001271537 | ANGL MTL,EQ,CS,20ft,L3x3x1/4in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 964 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 60 | FT | 60 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61175054 | 508 | 33192A foam pump fail | S13 | Fire Protect | 2020-03-03 | 2021-01-21 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.GU.FP.HS-33192-455C | Foam Sys Ctrl Pnl Start/Stop Hand Switch | 2020-02-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-03 | 121557000000 | 10 | 10 | 1002407096 | INPUT/OUTPUT BOARD,99-5835-01,EATON | 2020-03-03 | Not Shipped |  | 2020-02-28 |  | U182 | 8201 | Stones Main | ST2A6B3 | 12155710 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | ET-Name 46 |  | 2020-02-28 | USCWJG | 1 | EA | 0 | Install I/O Board | REL CNF PRT PRC SETC | EXEC WP | EXEC
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 340 | 7000000133 | OGIO Stratagem Pack, 411067 | 2020-11-07 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main | STONES | 11419724 | 34 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 47 |  | 2020-01-07 | USCWJG | 230 | EA | 230 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 110 | 7000003197 | Earth Tag M20 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 2 | EA | 2 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 110 | 7000006081 | PP-304-050 1/2 PIPE PLUGS S/S | 2020-04-29 | Received at Target Location | 2020-02-13 |  | 2020-02-22 | U182 | 8201 | Stones Main | STONES | 11772908 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-13 | USAWJB | 4 | EA | 4 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 170 | 1001759324 | SB2N,A193B8MCL2,UNC,4.5in,3/4in | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 643 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 28 | EA | 28 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7030 | 1001573338 | PAD,DELRIN,BLACK,2x1/8in | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 951 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052001 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 25 | EA | 25 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6150 | 7000002629 | Tyco Type MV10 Spray Nozzle, 1/2" | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 713 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 20 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7160 | 1001582225 | BAR FL,3/8in,3in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 974 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 590 | 7000003740 | Rosemount Documentation, Certifications | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 691 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN109 | Name 2 | Name 2 | 2019-12-17 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 60 | 7000003196 | 3/4" 2507-1214-1 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 784 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 20 | EA | 20 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 140 | 7000002591 | 3" Flange Protectors | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 250 | 1001759240 | SB2N,A193B8MCL2,UNC,5.25in,5/8in | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 121 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 9 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61098380 | 508 | Biocide Chemical Inj for Cargos & Drains | S21 | Oil Treating | 2020-09-28 | 2020-11-27 | C.US.STO.FI.19.012.1230A | 508CI&E | US.WR508A.OT.SS.VE663-70000 | Cargo Tank Systems | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-09-28 | 120671000000 | 10 | 50 | 7000000052 | PAINT ASSEMBLIES IN LINE 10 PER BELOW | 2020-09-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 12067106 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI76 | Name 2 | Name 61 | 2020-01-23 | USSOLE | 12 | EA | 10 | Biocide Chemical Inj for Cargos & Drains | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 120 | 7000003740 | Certificate of Compliance | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN110 | Name 2 | Name 2 | 2019-12-18 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 640 | 1001581841 | SHT PLT SLD MET,4x8ft,1/2in,A572-50 | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 64 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118336 | 508 | 2020 Lube Oils / Grease - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 70 | 7000003947 | 5 gallon pail of Shell Omala S2 GX 68 oi | 2020-12-31 | Not Shipped |  | 2020-01-08 |  | U182 | 8201 | Stones Main | CPORT | 12090693 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOMEC0013 | Name 17 | JP832018 | 2020-02-24 | USLFA4 | 1 | PAI | 0 | 2020 Lube Oils / Grease - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60737049 | 508 | Drive End Bearing Leaking Oil - BGCB | S04 | Gas Compress | 2020-03-25 | 2019-06-29 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.CM-77102B | HV Electric Mtr Booster Gas Compressor B | 2019-06-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-27 | 116406000000 | 10 | 30 | 7000000039 | 200731584 GAP SEAL | 2020-03-25 | Received at Worksite |  | 2019-07-04 |  | U182 | 8201 | Stones Main | ST KB A4 | 11640554 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-06-07 | USJDJW | 4 | EA | 4 | LOTO- BGC B and lube oil pump | REL GMPS PRC SETC | EXEC EOM MAGN MAOK RUSH WPOK | EXEC |  |  | PU Aaron 07/08/2019
60655411 | 508 | Discharge check valve passing | S08 | Air Systems | 2020-02-27 | 2019-09-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11805 | Top Up Start Air Compressor | 2019-11-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-27 | 115485000000 | 20 | 20 | 7000002646 | 6294-XXXX 00000 VALVE GASKET | 2020-03-26 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11548488 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-22 | USNSB4 | 2 | EA | 0 | Replace Check Valve On Start Air Compres | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAOK WPOK | Deleted
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 200 | 7000002591 | Flange Protectors for 20", JIS 5K, FF Fl | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 6 | EA | 6 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60989313 | 508 | Erratic Speed Reading Steam Turbine #3 | S21 | Oil Treating | 2020-02-11 | 2020-04-04 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.OT.SS.CPI-66301C | Steam Turbine Control Panel | 2019-10-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-11 | 119417000000 | 20 | 40 | 7000005901 | CABLE CLAMPS FOR SECURING CABLES | 2020-02-11 | Received at Worksite | 2019-11-21 | 2020-01-19 | 2020-02-19 | U182 | 8201 | Stones Main | ST1A5B | 11941691 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | 3.54 | 2019-10-24 | USNSB4 | 20 | EA | 20 | Replace Existing Cable With Shielded Cab | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD WPOK XGI | TECO |  |  | PU AMW ST1A5B
60908998 | 508 | Passing SPSV 049 MAJ 12202A | S18 | Water Systems | 2020-02-20 | 2020-02-14 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PSV-12202A-902 | Filter Pressure Safety Valve | 2019-10-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-20 | 118510000000 | 10 | 20 | 7000002646 | MILL TEST REPORT | 2020-05-20 | Received at Worksite |  | 2020-02-08 | 2020-02-26 | U182 | 8201 | Stones Main | ST1A5B- Not painted | 11851034 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-03 | USNSB4 | 1 | EA | 1 | Replace SPSV 049 MAJ 12202A | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | ST1A5B 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 840 | 1001816205 | GASW,CL150,316,GPH,NPS12 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 100 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2180 | 7000003343 | HSS Tubing, TS 6 X 6 X 3/8, ASTM A500 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 240 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 60 | FT | 60 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 140 | 1000720178 | TEE,UNION,SWAGELOK,SS-600-3,3/8in | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 792 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 50 | EA | 50 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1190 | 1001642013 | (Please provide 40' joints) | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 135 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061802 | Name 2 | Name 2 | 2018-12-07 | USSOLE | 40 | FT | 40 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61187003 | 508 | Deficiencies found on IAC#3 Service | S08 | Air Systems | 2020-04-05 | 2021-01-28 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11801C | No. 3 Air Compressor | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-06 | 121692000000 | 10 | 10 | 7000000034 | Bonded seal | 2020-04-05 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12169170 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-04 | USMNF8 | 4 | EA | 0 | Fix Deficiencies found on IAC#3 Service | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2850 | 7000002629 | Concentric Reducer, 3" x 2", S/10S x S/4 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 315 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60900220 | 508 | Fire Station 093 passing valve | S13 | Fire Protect | 2020-02-18 | 2020-02-14 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.FP.VASV-331130 | Firewater to Helideck Fire Hydrant | 2019-08-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-18 | 118408000000 | 30 | 20 | 7000004211 | 3-NPN-GSK-105 | 2020-02-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11840847 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-11-03 | USAWJB | 10 | EA | 0 | Fire Station 093 passing valve | REL PCNF ESTC PPRT PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 510 | 7000002629 | PLUG, 3/4", SC, HEX HEAD, ASTM A182 GR F | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 67 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3430 | 1001807372 | FLWN,A105,CL150,40,NPS4 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 373 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 16 | EA | 16 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60859590 | 508 | O/SI Leaking DB valve HPU | S24 | Subsea Systems | 2020-04-11 | 2020-01-18 | O.US.STO.STO.002.724FP | 508ACR | US.WR508A.SE.OH.PSV-55473A-001 | HPU Hyd Oil Supply Pressure Safety Valve | 2019-08-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-11 | 117945000000 | 10 | 10 | 7000000103 | MI BV0509FMP04FMP0210ERV10K* | 2020-04-11 | Ready for Shipment after Kitting | 2019-11-01 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB D7 | 11794479 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-22 | USNSB4 | 1 | EA | 1 | Replace Oliver Valve DBB BH-2 SubSea HPU | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4340 | 1001581841 | SHT PLT SLD MET,4x8ft,1/2in,A572-50 | 2019-11-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 486 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11131902 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60629360 | 508 | GT #1 Replace Air intake button plugs | S03 | Elect. Systems | 2020-03-15 | 2020-02-21 | O.US.STO.STO.005.724FP | GGTSSLTB | US.WR508A.ES.PG.LAN-11110 | Gas Turbine Power Generation Package 1 | 2019-07-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-15 | 115191000000 | 10 | 10 | 7000003739 | Conduit Plug PN 1739574 | 2020-03-15 | Received at Target Location |  | 2019-09-11 |  | U182 | 8201 | Stones Main | Dist to Solar Tech | 11519116 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 48 | USAWJB | 2019-07-17 | USRAR6 | 4 | EA | 4 | GT #1 Replace Air intake button plugs | REL PRT GMPS PRC SETC | EXEC MAGN MAOK WPOK | EXEC |  |  | PU WPT STKB B7
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 120 | 7000003739 | 904934C1 BEARING,BALL,RADIAL,2.3622 ID | 2020-02-24 | Received at Target Location |  |  | 2020-02-26 | U182 | 8201 | Stones Main | STONES | 12155706 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO
60470624 | 508 | Turret Gantry Crane Out of Service | S40 | Cargo Handling | 2020-06-01 | 2019-11-19 | O.US.STO.STO.005.724FP | GHEMSPAR | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-06-01 | 113409000000 | 10 | 80 | 7000000040 | Connecting Link Between Eyebolt and Chai | 2020-06-01 | Received at Worksite |  | 2019-07-17 | 2020-01-02 | U182 | 8201 | Stones Main | ST KB B2 | 11340935 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-02-15 | USRAR6 | 1 | EA | 1 | Turret Gantry Crane Out of Service | TECO PCNF ESTC GMPS PPRT PRC SETC | XCNF NCMP WPOK XGI ZPVS | TECO |  |  | PU Marty S 05/07/2019 CR
61155246 | 508 | Install Barring Device on MGCA | S04 | Gas Compress | 2020-03-03 | 2020-07-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-03 | 121329000000 | 10 | 80 | 7000003517 | 92620A725 (1/2" x 1-3/8" grade 8 bolts) | 2019-11-01 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST1A6C | 12132852 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0006 | Name 17 | JP832018 | 2020-01-27 | USLFA4 | 2 | PK | 2 | Install Barring Device on MGCA | REL PCNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC |  |  | ST1A6C 02/16/20 AMW
60686663 | 508 | O/SI #1 Boiler Steam to 16K Hdr Valve | S17 | Steam/Hot H2O | 2020-04-11 | 2019-09-30 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-200A | Steam to 16K Steam Header Valve | 2019-12-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-12 | 115837000000 | 30 | 10 | 7000004211 | 200MM Globe Valve, 316 SS Trim, JIS flan | 2020-04-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11583658 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-18 | USMNF8 | 1 | EA | 0 | Replace passing valve 115-200A | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61179018 | 508 | FRC Engine Turbo Exhaust piping corroded | S15 | Life Saving | 2020-04-25 | 2020-07-27 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-25 | 121603000000 | 10 | 10 | 7000005811 | Elbow Gasket | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12160259 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-03 | USMNF8 | 1 | EA | 0 | Replace FRC Engine Turbo Exhaust piping | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61098380 | 508 | Biocide Chemical Inj for Cargos & Drains | S21 | Oil Treating | 2020-09-28 | 2020-11-27 | C.US.STO.FI.19.012.1230A | 508CI&E | US.WR508A.OT.SS.VE663-70000 | Cargo Tank Systems | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-09-28 | 120671000000 | 10 | 90 | 7000000052 | FULL ASSEMBLY, TORQUE TO SPEC AND EXPEDI | 2020-03-02 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 12067106 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI76 | Name 2 | Name 61 | 2020-02-17 | USSOLE | 1 | EA | 0 | Biocide Chemical Inj for Cargos & Drains | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 340 | 7000002591 | Dow Corning Molykote 55 Oring Grease 5.3 | 2020-02-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 34 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 5 | EA | 5 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60708311 | 508 | Faulty check valve on FW Gen # 3 | S18 | Water Systems | 2020-04-22 | 2019-10-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.VACH-122504 | Pump Discharge Check Valve | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-22 | 116082000000 | 10 | 30 | 7000005901 | P/N: 6", FLEX GASKET, RATED 150PSI | 2020-04-22 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 11608239 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-01-23 | GW982959 | 2 | EA | 2 | LOTO- Electric motor FW#3 | REL ESTC GMPS PRC SETC | APPR MAGN WP ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 310 | 1001708482 | BLT HEX,A325,UNC,2.3/4in,5/8in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 31 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 25 | EA | 25 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60840044 | 508 | O/SI Slop S Steam Valve Leaking | S17 | Steam/Hot H2O | 2020-04-01 | 2020-01-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGA-115516 | Stbd Steam to Slop Tank Isolation Valve | 2020-01-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-02 | 117719000000 | 20 | 10 | 7000004211 | 4-150-CSGOSY-G 4" 150 C/S GATE VALVE OSI | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11771882 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-07 | USNSB4 | 1 | EA | 0 | Replace Gate valve VAGA -115516 | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 250 | 1001167726 | CARTRIDGE,HILTI,412689,BROWN,M10 | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 1 | BX | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60717786 | 508 | #3 latching dog cylinder bolts are broke | S19 | Marine Systems | 2020-02-18 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-21 | 116191000000 | 10 | 10 | 7000003852 | Drill Hog Silver & Deming Drill Bit Set | 2020-02-18 | Received at Worksite |  | 2019-10-27 | 2020-02-07 | U182 | 8201 | Stones Main | Issued | 11619069 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 14 |  | 2019-05-20 | USMNF8 | 1 | EA | 1 | Gather tools and equipment | TECO PRT GMCO GMPS PRC SETC | XCNF MAGN MAOK NCMP WPOK XGI | TECO |  |  | PU Aaron 06/11/2019 CMR
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 50 | 7000006081 | PP-304-050 1/2 PIPE PLUGS S/S | 2020-03-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-13 | USAWJB | 4 | EA | 0 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
61102257 | 508 | P.Crane radiator fan shroud corroded | S40 | Cargo Handling | 2020-05-10 | 2020-06-10 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-10 | 120716000000 | 10 | 90 | 7000006081 | Guard sheet 21830 | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12071582 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 2 | EA | 0 | P.Crane radiator fan shroud corroded | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 20 | 7000002662 | PIPE, 6", S/10S (0.134 WT), ASTM A790, S | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 3 | FT | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4410 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2019-11-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 493 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141901 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 36 | EA | 36 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5280 | 1002360784 | SB2N,B7,2H,UNC,5/8in,3.5in,DOXSTEEL | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 589 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 32 | EA | 32 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 970 | 7000005901 | 3M Part No. FP301-3/8-WHITE-100' | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 957 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI87 | Name 2 | Name 2 | 2020-02-08 | USSOLE | 3 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60847989 | 508 | MOC GTG5 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-44000 | Gen #5 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 70 | 7000005901 | MLTFC4H-LP316 50 PER PACK | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780944 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI80 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 1 | EA | 1 | SAEP LO/TO Isolate GTG #5 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5790 | 1001816127 | GASW,CL300-600,316,GPH,NPS2 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 673 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60902666 | 508 | O/SI MGC-A 3rd Stg Inlet Double Block | S04 | Gas Compress | 2020-06-09 | 2020-08-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VADB-771008 | Inlet Gas Valve | 2019-09-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-06-09 | 118436000000 | 20 | 10 | 7000004211 | 6DB02-F GALPERTI BB18 Ball Valve D.B.B. | 2021-03-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11843611 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-10-14 | USNSB4 | 1 | EA | 0 | Rigging Services & Assist Replacing DBB | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60564308 | 508 | PSV is Leaking Passing Valve | S18 | Water Systems | 2020-02-10 | 2020-01-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PSV-12106-381 | Filter Pressure Safety Valve | 2019-11-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-10 | 114449000000 | 10 | 10 | 7000005901 | 6310-000038 SAFETY VALVE S/S | 2020-04-10 | Received at Worksite | 2019-12-12 | 2020-01-19 | 2020-02-09 | U182 | 8201 | Stones Main | ST KB B7B | 11444851 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-12 | USNSB4 | 1 | EA | 1 | Replace Leaking PSV-12106-381 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 2/5/2020 JH GG
61006507 | 508 | PSV test kits | S21 | Oil Treating | 2020-02-11 | 2020-10-15 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.VE663-00000 | Cargo Oil Pump Systems | 2020-01-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-17 | 119629000000 | 10 | 10 | 7000002596 | 1" studs, Teflon coated w nuts | 2020-02-11 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-25 | U182 | 8201 | Stones Main | ST1A3A | 11962883 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 16 | EA | 16 | Install PSV Testt kits | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 700 | 7000002591 | DRILLFORCE HSS Jobber Length 10 PCS,13/6 | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 70 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 2 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60945723 | 508 | 6M Swivel LPU Maintenance | S19 | Marine Systems | 2020-03-21 | 2020-02-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-89910 | Prod Swivel Local Pressurization Unit | 2019-09-15 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Normal | 2020-03-21 | 118920000000 | 20 | 10 | 7000000104 | Parker Olair Integrated Gas Valve for LP | 2020-03-21 | Not Shipped |  | 2020-01-11 |  | U182 | 8201 | Stones Main | STONES | 11891983 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-11 | USAMH7 | 3 | EA | 0 | 6M LPU Accumulator Bladder Insp | REL PPRT PRC SETC | APPR MAGN WPOK ZPMM | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 70 | 1002150255 | SHT PLT SLD MET,4x4ft,3/8in,A572-50 | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 1 | EA | 1 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 290 | 7000002596 | 5/16" x 2 3/4" 316 SS Cap Bolt AND Nut | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 12 | EA | 12 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60796832 | 508 | DP gauge broke on Air dryer #2 | S08 | Air Systems | 2020-03-03 | 2019-12-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.ZBK-11810A | Control Air Dryer No. 2 | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-03 | 117212000000 | 10 | 10 | 7000005901 | KNAF-31 LINE FILTER COMPLETE & D.P.G | 2020-03-03 | Received at Worksite | 2020-02-05 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB A1 | 11721238 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-15 | USNSB4 | 1 | EA | 1 | Replace Differential Pressure Gauge | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 02/19/20 AMW
60989629 | 508 | COPT SW #3 Pump mechanical seal leak | S18 | Water Systems | 2020-04-14 | 2019-12-06 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216C | No. 3 Main/COPT Condenser Cooling Pump | 2019-12-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-14 | 119420000000 | 10 | 50 | 7000004211 | Packing, SVS350M-54-3 | 2020-04-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11942032 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-13 | USMNF8 | 1 | EA | 0 | COPT SW #3 Pump mechanical seal leak | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
61137456 | 508 | LPU CABINET LEAK | S19 | Marine Systems | 2020-03-03 | 2020-12-30 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.MA.PS.ZZZ-89920 | Seal Isolation Local Pressurization Unit | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-03 | 121118000000 | 10 | 20 | 7000003852 | Sponge Neoprene Stripping W/Adhesive 1-1 | 2020-03-03 | Received at Worksite | 2020-02-07 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B8 | 12111778 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-03 | USMNF8 | 1 | EA | 1 | Replace LPU CABINET ZZZ-89920 Door seal | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2070 | 7000002629 | THREAD-O-LET, 12" X 1/2", 3000#, FS, MSS | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 229 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5200 | 7000002603 | GASKET, 1 1/2" 300LB, 1/8" THICK, RF SPI | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 581 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60636182 | 508 | OEM recommends elbow replacement | S08 | Air Systems | 2020-02-25 | 2019-04-25 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.HBG-11853A | No. 1 Air Compressor Oil Separator | 2019-10-30 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-25 | 115265000000 | 10 | 30 | 7000000034 | Seal Washer P/N 0653 1227 00 | 2020-02-25 | Received at Worksite | 2020-02-05 | 2020-02-20 |  | U182 | 8201 | Stones Main | ST KB A3 | 11526532 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-30 | USRAR6 | 4 | EA | 4 | Replace elbow on compress 1,2,3,4 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK RUSH WPOK | EXEC |  |  | PU 02/19/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1610 | 1001223835 | I-ROD,F/U-BOLT,INODO3,1/2x3in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 177 | 19 | Modified SP1 - w/o STR & STO / item ctg | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 10 | 7000003852 | Casio Men's W800H-1AV Classic Sport Watc | 2021-05-26 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main | STONES | 11419724 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19BBSM1 | Name 11 | USKHU3 | 2019-10-15 | USLFA4 | 17 | EA | 17 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/01/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3250 | 1001708318 | NUT,A563-DH,HEXAGONAL,UNC,3/4in,GALV | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 355 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 160 | EA | 160 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 880 | 7000002591 | Cone Style Burbits | 2020-03-03 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia |  | 11179936 | 1078 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-28 | USLFA4 | 20 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5690 | 7000002629 | Blind Flange, 3", 300#, RF, ASME B16.5, | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 663 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 7 | EA | 7 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 20 | 7000000103 | 12" Super Duplex Remington Floating Ball | 2019-01-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN031 | Name 2 | Name 2 | 2018-11-06 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60172772 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-03-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.95T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 110086000000 | 10 | 50 | 7000002603 | Gasket, 40mm, FF, JIS 16K, JIS B2220, No | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008581 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081901 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 6 | EA | 6 | MOC missing steam trap | REL PCNF ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3280 | 7000002646 | Check Valve, 3", VCF-301D (See Attached | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 358 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161903 | Name 4 | Name 4 | 2019-10-16 | USLFA4 | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 490 | 7000000098 | 38 VITS SQFT 3/8" THK VITON SHEET PACKIN | 2020-03-16 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 49 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOET00120 | Name 3 | USCRFI | 2020-02-09 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1 FLR 2/24/2020 GG
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 90 | 7000003684 | LIGHT DUTY AIR-POWERED RECIPROCATING SAW | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60453594 | 508 | 26-PL664001- Install permanent Pipe Supp | S21 | Oil Treating | 2020-02-18 | 2019-11-10 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-18 | 113218000000 | 10 | 10 | 7000003343 | Angle, L6x4x1/4, ASTM A36 | 2020-01-22 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | JOB: SHF9-F92 | 11321849 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221902 | Name 4 |  | 2019-11-22 | USLFA4 | 20 | FT | 20 | 26-PL664001- Install permanent Pipe Supp | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
61137456 | 508 | LPU CABINET LEAK | S19 | Marine Systems | 2020-03-03 | 2020-12-30 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.MA.PS.ZZZ-89920 | Seal Isolation Local Pressurization Unit | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-03 | 121118000000 | 10 | 10 | 7000003852 | 3M Hi-Strength 90 Spray Adhesive, Clear, | 2020-03-03 | Received at Worksite | 2020-02-07 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B8 | 12111778 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-03 | USMNF8 | 1 | EA | 1 | Replace LPU CABINET ZZZ-89920 Door seal | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 10 | 90 | 7000000068 | DK 1535-02120 DEKORON RTV HIGH TEMP END | 2020-02-07 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | Issued | 11614811 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 7 | USNSB4 | 2019-09-28 | USAWJB | 1 | EA | 1 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 160 | 7000002603 | Gasket, 12", JIS 10K, 1/16" THK, Garlock | 2020-01-17 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01152001 | Name 4 | Name 60 | 2020-01-16 | USSOLE | 4 | EA | 4 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 10 | 50 | 7000003852 | Displayport Cable 10ft, BIFALE DP Cable | 2020-05-16 | Received at Target Location |  | 2020-01-19 |  | U182 | 8201 | Stones Main | STONES | 11783572 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 22 | USNSB4 | 2019-08-10 | USMNF8 | 5 | EA | 5 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC
60959164 | 508 | COP #1 Disch Px Gauge | S21 | Oil Treating | 2020-05-24 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PG-66301A-342A | Cargo Oil Pump #1 Disch Pressure Gauge | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-05-24 | 119075000000 | 10 | 20 | 7000000062 | WK TAG Mfr: WIKA INSTRUMENT CORP Mfr p | 2020-05-24 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 11907500 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-21 | USNSB4 | 1 | EA | 1 | LO/TO Perform Isolations | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAOK WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4110 | 1002051542 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 461 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 6 | EA | 6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5360 | 7000002644 | NEEDLE VALVE, 1/2" 6000 PSI MNPT X FNPT | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 597 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2230 | 1001842232 | FLBL,A105,RF,CL150,NPS4 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 245 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 16 | EA | 16 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 410 | 1001621007 | GLAND,HAWKE,501453UNIVB3/4NPT,BRS | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 833 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 44 | EA | 44 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60661316 | 508 | Seals M.E. Exhaust Valves 4,5,6 leaking | S19 | Marine Systems | 2020-04-28 | 2019-09-12 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.PR.XXX-109-MIS-00 | Main Engine Cylinder No. 4 | 2020-02-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-03 | 115550000000 | 30 | 10 | 7000000030 | Maintenance Kit, Exhaust valve 7972-2200 | 2020-04-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11555015 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-12 | USNSB4 | 3 | EA | 0 | MAN - Rpl Seals on Exhaust Valves 4,5,6 | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM ZPVS | Approved
60747148 | 508 | COT 3 P HC Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127014 | COT 3 PS HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651960 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 260 | 7000003740 | RMT-DOC-CERT-Q7:Q7, Agency Approval Cert | 2020-03-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 26 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN118 | Name 2 | Name 2 | 2020-01-31 | USLFA4 | 1 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 280 | 7000002603 | Flange Protectors 8" 600#, RF | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 124 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61221684 | 508 | Steam Expansion Bellows critical spare | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-22 | P.US.STO.NF.20.015.7240A | 508ERENG | US.WR508A.GU.SW.VE115-32000 | Boiler System Steam Distribution | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-06-02 | 122096000000 | 10 | 60 | 7000003323 | Expansion Joint EJ-540586-A | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12209639 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAMH7 | 2020-03-02 | USRAR6 | 1 | EA | 0 | Shut down steam system | CRTD PRC | INIT RUSH WP | Approved
60699172 | 508 | O/SI Valve XV-1122S-326 over rotating Ba | S19 | Marine Systems | 2020-04-08 | 2019-10-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.BB.XV-1122S-326 | WB Tank No. 1S Water Line Ballast Valve | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-09 | 115978000000 | 40 | 10 | 7000004211 | Repair Kit for Hydraulic Actuator Model | 2020-04-06 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11597808 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 2 | EA | 0 | Prep tank for entry | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 20 | 7000004213 | KE35/5 SASAKURA KE35- PN:5 GLOBE VALVE | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 15 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60585840 | 508 | Latch Mech Hydr Vlvs-Incorrect Material | S19 | Marine Systems | 2020-03-25 | 2019-03-27 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-25 | 114695000000 | 10 | 20 | 7000000104 | CXHA-XZN/AP AISI316 check valve | 2020-03-25 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | ETA 10/31 | 11469454 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-02-19 | USAWJB | 1 | EA | 1 | Replace Latch Mech Hydr Valves | REL ESTC GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 470 | 7000002591 | 4452K173 Bushing Adapter, 1 Male x 1/4 F | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 47 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 230 | 7000000103 | Cortec Compact Trunnion Mounted Ball Val | 2020-04-20 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | JOB NO: 2335 | 11545759 | 93 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-16 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 130 | 7000002591 | 1/2 x 2 Line 316SS Tubing Straps | 2019-11-26 | Received at Target Location |  |  | 2020-02-14 | U182 | 8201 | Stones Main | Onsite Danos Has | 11882270 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI65 | Name 2 | Name 58 | 2019-11-06 | USSOLE | 25 | EA | 25 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
61219225 | 508 | GT #5 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-4 | Generator #5 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 20 | 7000003763 | 8MX-31S-12 1210 GT2SPKT | 2020-04-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206809 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #5 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61175103 | 508 | Barrier Fluid HPU Sample Mod | S24 | Subsea Systems | 2020-03-03 | 2020-03-19 | O.US.STO.STO.002.724FP | 508ACR | US.WR508A.SE.OH.ZZZ-12865 | Barrier Fluid Hydraulic Power Unit | 2020-01-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-03 | 121557000000 | 10 | 10 | 7000003196 | SS-26VF6 WHITY MINI BARSTOCK VAL | 2020-03-03 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7A | 12155741 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-29 | USNSB4 | 4 | EA | 4 | Install Needle Valves & Fabricate Tubing | REL GMPS PRC SETC | SCHD EOM MAGN MAOK WPOK | EXEC |  |  | PU A WISTRAND 02/24/2020
60655411 | 508 | Discharge check valve passing | S08 | Air Systems | 2020-02-27 | 2019-09-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11805 | Top Up Start Air Compressor | 2019-11-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-27 | 115485000000 | 10 | 40 | 7000000034 | Valve for NRV KV 65, Type: Starting Air | 2020-04-12 | Received at Worksite |  | 2020-02-16 | 2020-03-01 | U182 | 8201 | Stones Main | Issued | 11548488 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 13 | USNSB4 | 2019-11-26 | USNSB4 | 1 | EA | 1 | LO/TO Compressor #1, Single Isolation | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 02/16/20 AMW
60796835 | 508 | No. 2 F.W. Gen Ejector P/P Gauge leaking | S18 | Water Systems | 2020-02-08 | 2019-08-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PBE-12204B | No. 2 FW Generator Ejector Pump | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-08 | 117212000000 | 10 | 10 | 7000000066 | WK 52900518 200PSI 1/2 L 316SS-CASE 3.1 | 2020-03-09 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7A | 11721241 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-22 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge FPBE-12204B | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 2/5/2020 JH GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7660 | 7000002629 | Elbow, 3", LR 90, S/10S, BW, ASME B16.9 | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1029 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 740 | 7000003463 | 1783-SFP100LX | 2020-03-18 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1065 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-26 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
61019557 | 508 | N2 Generation Membrane Filter E Repair | S08 | Air Systems | 2020-03-01 | 2019-12-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.MAK-11827E | E Membrane Filter | 2019-10-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-01 | 119776000000 | 10 | 30 | 7000002603 | 3/4 FLEX CG 150# SP WND GSKT GRF FLR | 2020-03-01 | Received at Worksite | 2019-11-06 | 2020-02-16 | 2020-03-02 | U182 | 8201 | Stones Main | STA1 Side | 11977557 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USAWJB | 2 | EA | 2 | N2 Generation Membrane Filter E Repair | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1550 | 1002309186 | SB2N,B8M CL2,8M,UNC,3/4in,5.00in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 171 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 26 | EA | 26 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 8000 | 7000002596 | Stud Bolt, 5/8" x 3 1/2", Aluminum Bronz | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 1085 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-28 | USSOLE | 28 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6870 | 7000002596 | STUD BOLTS, 5/8" DIA. X 3 1/2" LONG, AST | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 935 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 40 | EA | 40 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7280 | 1001687567 | SHT PLT SLD MET,4x8ft,1.1/2in,A572 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 986 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 250 | 1002220507 | CABLE TIE,PANDUIT,MLTFC2SCP3+,7.9x0.18in | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 200 | EA | 200 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 470 | 7000002591 | 13/16'' Hogan Bits REG mag drill bits | 2020-01-20 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 760 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A383 | Name 2 | Name 2 | 2020-01-18 | USSOLE | 20 | EA | 20 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 230 | 7000003852 | Penn Championship Tennis Balls - Regular | 2020-02-28 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO012920A | Name 43 | USCRFI | 2020-01-30 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | DLVD OIM 02/21/2020 GG
60739067 | 508 | COT 4 Port IG netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127051 | COT 4 PS IG Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642943 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60879643 | 508 | 16000 HR service due #1 Air Compressor | S08 | Air Systems | 2020-02-04 | 2019-09-04 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11801A | No. 1 Air Compressor | 2019-09-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 4 Complete by 4 Weeks | 2020-02-05 | 118173000000 | 10 | 20 | 7000000083 | Oil Separator Kit | 2020-02-04 | Received at Worksite |  | 2020-01-20 | 2020-02-04 | U182 | 8201 | Stones Main | ST1FLR1 09/26/2019 CMR | 11817325 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-09-19 | USRAR6 | 4 | EA | 4 | 16000 HR service due #1 Air Compressor | TECO CNF ESTC GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU ST1FLR1 10/02/2019 RMA DISPOSE
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 300 | 7000002596 | 1 3/8" x 14" A193 B7 B&N, Teflon stud | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 75 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 14 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60975393 | 508 | O/SI BGCB Discharge Valve Passing | S04 | Gas Compress | 2020-02-15 | 2021-12-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VABL-771293 | Outlet Gas SDV Isolation Valve | 2019-12-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 8 User defined period | 2020-02-15 | 119261000000 | 10 | 10 | 7000004751 | 8" 300 RF Full Port, GVI G4 Trunnion, 31 | 2020-02-15 | Received at Worksite | 2020-01-13 | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Stones | 11926135 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-24 | USAWJB | 1 | EA | 1 | Replace VABL-771293 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 350 | 7000002603 | Flange Protector 2", 150#, FF, Flange | 2020-05-13 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G14 | 11581210 | 35 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12091901 | Name 4 | Name 60 | 2019-12-09 | USSOLE | 4 | EA | 4 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 10 | 1001622964 | STL SECT MAR,BEAM,6in,5.990in,20ft | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 20 | FT | 20 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 40 | 7000004213 | KE35/7 SASAKURA KE35 P/N 7 NIPPLE | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
61089158 | 508 | O/SI BGCA Discharge Valve Passing | S04 | Gas Compress | 2020-02-15 | 2020-01-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VABL-771085 | Compressor SDV Isolation Valve | 2019-12-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 8 User defined period | 2020-02-15 | 120564000000 | 10 | 40 | 7000004753 | 8" 300 RF Flex Gaskets,,,,,,,,,,,,,,,, | 2020-02-15 | Received at Worksite | 2020-01-13 | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Stones | 12056365 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-24 | USAWJB | 2 | EA | 2 | Replace VABL-771085 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 60 | 7000004213 | KE35/9 SASAKURA KE35 P/N 9 ORIFICE | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 11937331 | 19 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 100 | 7000004211 | ANS200x150x350/PN-29 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 2 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4040 | 7000003344 | Plate, 1" x 96" x 96", ASTM A572 50 (PCM | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 454 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 430 | 1001676781 | SHT PLT SLD MET,4x4ft,1/2in,A572 GR.50 | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 56 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 310 | 1001708405 | CABLE,AMER-CBL,37-102-618 BS,12PR,16AWG | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 823 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 462 | FT | 462 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60884538 | 508 | 12pack N2 bottles rack 3600psi | S08 | Air Systems | 2020-02-18 | 2020-02-05 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.TS118 | Topsides Air & Nitrogen Systems | 2019-09-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-18 | 118225000000 | 10 | 10 | 7000000122 | N1 C23C142 | 2020-02-18 | Ready for Shipment after Kitting | 2020-01-08 | 2020-01-24 | 2020-01-26 | U182 | 8201 | Stones Main | Set in place | 11822473 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 49 |  | 2019-09-10 | USABDF | 1 | EA | 1 | 12pack N2 bottles rack 3600psi | TECO CNF ESTC GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5820 | 7000002591 | 2" x 27' U-Hook Ratchet Strap (including | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 676 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 12 | EA | 12 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4860 | 7000002662 | PIPE 1 1/2" SCH 40S, SMLS B.E., ASME ASM | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 547 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 20 | FT | 19.75 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60840919 | 508 | Relocate PORT CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-02-25 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-25 | 117729000000 | 10 | 20 | 7000000101 | 1" Elbow Stainless Steel 304 Fitting 90 | 2020-02-25 | Received at Worksite | 2019-11-27 | 2020-01-20 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772907 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 5 | EA | 5 | Relocate Crane Slew G-box Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD MAOK NCMP WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 150 | 7000002629 | ELBOW, 14", S/80 (0.750 WT), LR, 90, BW, | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 28 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2240 | 1001710109 | PIPE MET,X52,STD,2in | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 246 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 21 | FT | 21 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60616647 | 508 | O/SI Replace Barrier Fluid VADB-857039 | S24 | Subsea Systems | 2020-06-01 | 2019-08-09 | O.US.STO.STO.002.724FP | 508ACR | US.WR508A.SE.OH.ZZZ-12865 | Barrier Fluid Hydraulic Power Unit | 2019-02-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-01 | 115047000000 | 10 | 10 | 7000003196 | DB12M4M2V15 | 2020-04-01 | Received at Worksite |  | 2019-05-14 |  | U182 | 8201 | Stones Main | ST KB D7 | 11504662 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-02-18 | USAWJB | 1 | EA | 1 | Replace VADB-857039 Barrier Fluid HPU | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU MARTY 4-2-19 MJP
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 100 | 7000003852 | Newdora Hammock with Mosquito Net 2 Pers | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 630 | 1000709300 | CONN_ELEC,SPADE TERM,2,18RA-10F,THOMASBE | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 855 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 300 | EA | 300 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 160 | 1002132222 | CABLE TIE,PANDUIT,MLTFC4H,14.3x0.31 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 300 | EA | 300 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1630 | 1001645338 | BLT HEX,A325,UNC,2.1/4in,3/4in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 179 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 9 | EA | 9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3760 | 1001676781 | SHT PLT SLD MET,4x4ft,1/2in,A572 GR.50 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 406 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 50 | 7000002629 | Reducing Tee, 3" x 2", S/10S, ASME B16.9 | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 810 | 7000002591 | DRILLFORCE (5 Pcs) 7/16 in. x 5-1/2 in. | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 81 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 3 | EA | 3 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60470624 | 508 | Turret Gantry Crane Out of Service | S40 | Cargo Handling | 2020-06-01 | 2019-11-19 | O.US.STO.STO.005.724FP | GHEMSPAR | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-06-01 | 113409000000 | 10 | 20 | 7000000040 | Tube Lubrimatic Grease | 2020-06-01 | Received at Worksite |  | 2019-07-17 | 2020-01-02 | U182 | 8201 | Stones Main | ST KB B2 | 11340935 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-02-15 | USRAR6 | 1 | EA | 1 | Turret Gantry Crane Out of Service | TECO PCNF ESTC GMPS PPRT PRC SETC | XCNF NCMP WPOK XGI ZPVS | TECO |  |  | PU Marty S 05/07/2019 CR
60629360 | 508 | GT #1 Replace Air intake button plugs | S03 | Elect. Systems | 2020-03-15 | 2020-02-21 | O.US.STO.STO.005.724FP | GGTSSLTB | US.WR508A.ES.PG.LAN-11110 | Gas Turbine Power Generation Package 1 | 2019-07-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-15 | 115191000000 | 10 | 30 | 7000003739 | Conduit Plug PN 1739574 | 2020-03-15 | Received at Worksite |  | 2020-01-20 |  | U182 | 8201 | Stones Main | ST KB B7B | 11519116 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-24 | USAWJB | 4 | EA | 4 | GT #1 Replace Air intake button plugs | REL PRT GMPS PRC SETC | EXEC MAGN MAOK WPOK | EXEC |  |  | PU Aaron 01/19/2020
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 130 | 7000003196 | MS-MHSU-O-E-B | 2020-12-31 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 13 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 9 | USJRF5 | 2020-01-27 | USAWJB | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 110 | 7000002591 | Digital Sound Level Meter Kit, NIST Item | 2021-01-24 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  | HSESTO004 | Name 21 | USJRF5 | 2020-01-24 | USLFA4 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 480 | 7000000098 | 18 VITS SQFT 1/8" THICK VITON SHEET PACK | 2020-03-16 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 48 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOET00120 | Name 3 | USCRFI | 2020-02-09 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1 FLR 2/24/2020 GG
61219230 | 508 | GT #3 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-2 | Generator #3 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 30 | 7000003763 | 1210 28MM TL BUSHING 119588 | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206814 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #3 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 20 | 7000004211 | KE35/5 SASAKURA KE35- PN:5 GLOBE VALVE | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 120 | 1000712038 | VALVE,NEEDLE,1/2in,SS,H1RDS44Q,ANDRS-GR | 2019-10-18 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 35 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN091 | Name 2 | Name 2 | 2019-09-23 | USGBI5 | 1 | EA | 1 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 950 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2020-02-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F13 | 11581207 | 95 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09191901 | Entity 3 | Name 59 | 2019-09-19 | USSOLE | 5 | EA | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61131893 | 508 | Mooring Hawser QRH spring | S19 | Marine Systems | 2020-02-28 | 2020-02-22 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.PS.ZZZ-88631 | Mooring Quick Release Hook | 2020-01-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-28 | 121058000000 | 10 | 10 | 7000000057 | Mooring hawser QRH spring replacement | 2020-02-28 | Not Shipped |  | 2020-02-23 |  | U182 | 8201 | Stones Main | Warehouse | 12105763 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-12 | USAMH7 | 2 | EA | 0 | Mooring Hawser QRH spring | REL CNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC
61104543 | 508 | Rebuild MPV on #4 Inst Air Comp | S08 | Air Systems | 2020-02-27 | 2020-06-11 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11801D | No. 4 Air Compressor | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-28 | 120737000000 | 10 | 10 | 7000000412 | Minimum Pressure Valve kit | 2020-02-27 | Received at Worksite | 2020-02-11 | 2020-02-11 | 2020-02-14 | U182 | 8201 | Stones Main | ST KB B3 | 12073700 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-08 | USAMH7 | 2 | EA | 2 | Rebuild MPV on #4 Inst Air Comp | TECO CNF GMPS PPRT PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI ZPMM | TECO |  |  | PU 2/5/2020 JH GG
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 130 | 1000720185 | CAIC,SWAGELOK,SS810C,1/2in | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 2 | EA | 2 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
60874068 | 508 | FRC inspection deficiencies | S15 | Life Saving | 2020-02-13 | 2020-03-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2019-08-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-03 | 118106000000 | 10 | 80 | 7000004662 | Valve D Main Block for Winch (BW-SC33) | 2020-02-13 | Not Shipped |  | 2020-02-13 |  | U182 | 8201 | Stones Main | POD- Questions | 11810577 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-08-04 | USAWJB | 1 | EA | 0 | FRC inspection deficiencies | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD MAGN WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 560 | 7000002591 | 1002407993 NOZZLE,SPRINKLER,TYCO-FIS,AED | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 618 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN107 | Name 2 | Name 2 | 2019-11-26 | USSOLE | 20 | EA | 20 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5180 | 7000002603 | GASKET, 4" 300LB, 1/8" THICK, RF SPIRAL | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 579 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 9 | EA | 9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 490 | 7000000052 | Hex SDSS DBB Injection Quill | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 538 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN105 | Name 2 | Name 2 | 2019-11-22 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2810 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 305 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7820 | 7000002629 | Flanges, 1", 150#, RF, SW, S/10S Bore, A | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1052 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 19 | EA | 19 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60698903 | 508 | Water Clarifier Inj Pump B PSV-044B Fail | S10 | Chem Injection | 2020-03-17 | 2020-04-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.CI.PSV-12821B-044 | B Pump H2 Discharge Press Safety Valve | 2019-04-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-03-17 | 115974000000 | 10 | 20 | 1002408933 | VALVE,RELIEF,MARSEA,14480-20.M089 | 2019-07-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB B7A | 11597439 | 2 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 |  | 2019-04-13 | USMNF8 | 1 | EA | 1 | Water Clarifier Inj Pump B PSV-044B Fail | REL ESTC GMPS PRC SETC | APPR MAXX WPOK ZPMM | Approved |  |  | PU AARON 09/29/2019 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2330 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 255 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 244 | EA | 275 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61134552 | 508 | Helideck foam monitor upgrade MOC 80280 | S13 | Fire Protect | 2020-05-27 | 2020-07-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF331-12100 | FiFi Helideck Foam System | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-27 | 121087000000 | 10 | 40 | 1001646140 | GASKET,GARLOCK,36010-0008,CL150,3in | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H04 | 12108694 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST03022001 | Name 4 | Name 60 | 2020-03-03 | USSOLE | 7 | EA | 0 | Helideck foam monitor upgrade MOC 80280 | REL ESTC PRC SETC | APPR MAGN MANX WP | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 200 | 7000000040 | TDR Rigging Equipment Package | 2019-10-26 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 46 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRRIGGING | USCWE2 | USCWE2 | 2019-10-17 | USLFA4 | 1 | EA | 1 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1040 | 7000002591 | 3/4'' #17124, Rotaloc Cutter. Pilot. M4056 | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 104 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 6 | EA | 6 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118336 | 508 | 2020 Lube Oils / Grease - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 50 | 7000003946 | Shell Corena S4 R 46 | 2020-02-10 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | CPORT | 12090693 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200010A | Entity 6 | JP832018 | 2020-02-05 | USLFA4 | 4 | DR | 4 | 2020 Lube Oils / Grease - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 490 | 7000003343 | Beam, W10 X 30, ASTM A992 | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 49 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 120 | FT | 120 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 320 | 7000002629 | 2 NIPPLE SCH 80S TBE 4 A790 GR 53 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 59 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A363 | Name 2 | Name 2 | 2019-10-21 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 540 | 7000002591 | DMM-44/100 Multi-Meter Fuse 440mA 1000V | 2021-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 54 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN012620A | Name 3 | USCRFI | 2020-02-12 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A5C 2/24/2020 GG
61199783 | 508 | Replace Lifejacket Water Lights | S15 | Life Saving | 2020-04-01 | 2020-03-10 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.PP-AW | Air & Water Survival Personal Prot Equip | 2020-03-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 121839000000 | 10 | 10 | 7000000132 | Daniamant L6A-Ex life jacket lights | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12183926 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-03-03 | USAMH7 | 450 | EA | 0 | Replace Lifejacket Water Lights | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60352955 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-09 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33310 | No. 1 Port Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-10 | 112105000000 | 10 | 30 | 1002386483 | OIL,LUBT,SHELL,ROTELLA T4 TP 15W 40,1gal | 2020-02-09 | Received at Worksite |  | 2019-10-20 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210547 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-07-17 | USRAR6 | 2 | GLL | 2 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
60739071 | 508 | COT 3S IG Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127059 | COT 3 SB IG Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116430000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642967 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60871423 | 508 | Drive End Bearing Leaking Oil - BGCA | S04 | Gas Compress | 2020-03-03 | 2020-01-28 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-20000 | Booster Gas Compression System Train A | 2019-11-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-08 | 118080000000 | 10 | 50 | 7000003684 | PERMATEX 81724 SENSOR-SAFE ULTRA BLUE | 2020-03-03 | Received at Worksite | 2019-12-30 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B8 | 11807987 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-30 | USAWJB | 2 | EA | 2 | Erect Scaffold | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | STKBB8 02/3/20 GG
60739054 | 508 | 6S HC Netherlock Not Locking Open/Close | S06 | General | 2020-04-01 | 2019-11-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127005 | COT 6 SB HC Main Isolation Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642930 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 80 | 1001772393 | GARJ,SS316,OCTAL,R24 | 2021-03-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Gas Riser Pressure Gauge | 11057838 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A176 | Entity 3 | USRRIG | 2018-08-06 | USSOLE | 5 | EA | 5 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved
60661354 | 508 | O/SI Steam Inlet is Passing | S17 | Steam/Hot H2O | 2020-03-10 | 2019-09-07 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-337V | Steam to No. 2 COPT Isolation Valve | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 115550000000 | 30 | 10 | 7000004211 | 150-20K-F7314-CSxBT, 150mm JIS 20K CS An | 2020-05-09 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11555034 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-21 | USNSB4 | 1 | EA | 0 | Replace Valve 115-337V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61219225 | 508 | GT #5 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-4 | Generator #5 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 30 | 7000003763 | 1210 28MM TL BUSHING 119588 | 2020-04-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206809 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #5 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5510 | 7000002629 | 1" 300 RFWN Flange Protectors | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 612 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 560 | 1000708886 | TAPE,ELEC,3M,SUPER 33 PLUS,Blk,66ft | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 848 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 10 | EA | 10 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 790 | 1001759244 | SB2N,A193B8MCL2,UNC,3.25in,5/8in | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose |  | 11179936 | 1045 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-23 | USSOLE | 5 | EA | 5 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 30 | 7000002662 | PIPE, 4", S/10S (0.120 WT), ASTM A790, S | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | FT | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 600 | 7000002629 | WELD-O-LET, 8" X 2" (2" S/40S (0.154 WT) | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 76 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1700 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 186 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60959163 | 508 | COP #2 Disch Px Gauge | S21 | Oil Treating | 2020-02-04 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PG-66301B-342B | Discharge Pressure Gauge | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-04 | 119075000000 | 10 | 10 | 7000005901 | WK MISC Mfr: WIKA INSTRUMENT CORP Mfr | 2020-05-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11907499 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-10-23 | USNSB4 | 1 | EA | 0 | LO/TO Perform Isolations | REL ESTC CSER GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Deleted |  |  | PU AARON W 01/19/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 830 | 1001816127 | GASW,CL300-600,316,GPH,NPS2 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 99 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 6 | EA | 6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61035030 | 508 | TDR Corroded bolts on Sea riser clamps | S06 | General | 2020-04-01 | 2020-05-03 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GN.MI.RI | Risers | 2019-12-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-01 | 119955000000 | 20 | 20 | 7000003852 | Combination Wrench, SAE, 2-3/16in Size | 2020-04-01 | Received at Worksite | 2020-02-03 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST1A3A | 11995472 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3/Name 14 |  | 2020-02-02 | USMNF8 | 2 | EA | 2 | Replace Riser clamp bolts | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5130 | 7000002629 | SOCKOLET, 8 X 1/2" 3000LB ASTM A182 GRAD | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 574 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 30 | 7000000103 | 8" Duplex Remington Floating Ball Valve | 2019-01-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN031 | Name 2 | Name 2 | 2018-11-06 | USSOLE | 4 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
61118330 | 508 | 2020 Chemical Order - Subsea | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000003458 | CORR11612SP.32U | 2021-01-29 | Received at Target Location |  | 2019-12-23 |  | U182 | 8201 | Stones Main | CPORT | 12090687 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200005A | Name 40 | USAAN5 | 2020-01-16 | USLFA4 | 500 | GLL | 500 | 2020 Chemical Order - Subsea | REL ESTC PRC SETC | EXEC STDG | EXEC
61019557 | 508 | N2 Generation Membrane Filter E Repair | S08 | Air Systems | 2020-03-01 | 2019-12-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.MAK-11827E | E Membrane Filter | 2019-10-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-01 | 119776000000 | 10 | 10 | 1001550694 | MEMBRANE,MODULE,PARKFLT,SS316L,SA1508SS | 2020-03-01 | Received at Worksite | 2019-11-06 | 2020-02-16 | 2020-03-02 | U182 | 8201 | Stones Main | STA1 Side | 11977557 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2019-10-28 | USAWJB | 1 | EA | 1 | N2 Generation Membrane Filter E Repair | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A1SIDE 02/07/2020 CMR
61155246 | 508 | Install Barring Device on MGCA | S04 | Gas Compress | 2020-03-03 | 2020-07-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-03 | 121329000000 | 10 | 60 | 7000003514 | 98023A033 (flat washers) | 2019-11-01 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST1A6C | 12132852 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0006 | Name 17 | JP832018 | 2020-01-27 | USLFA4 | 1 | BX | 1 | Install Barring Device on MGCA | REL PCNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC |  |  | ST1A6C 02/16/20 AMW
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 90 | 1001816215 | GASW,CL150,316,GPH,NPS1/2 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 2 | EA | 2 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
60959173 | 508 | COP1 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-06 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PBE-66301A | Cargo Oil Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-12 | 119077000000 | 10 | 50 | 7000000038 | 3/8" tube x 3/8" tube x 1/4" fnpt SS tee | 2020-03-06 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 11907749 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-17 | USRAR6 | 2 | EA | 2 | Add seal flush plan 12 to COP1 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1080 | 7000002591 | 11/16" Hogan Bits REG mag drill bits | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 108 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 6 | EA | 6 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 630 | 7000003344 | Plate, 3/8" x 120" x 240", A572 GR50 | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 63 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 170 | 7000002662 | Pipe 2.875 OD 0.203 WT, ASTM A53 Gr. B | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 21 | FT | 22.1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 60 | 7000000039 | YMD-8529 HOSE ASSEMBLY X27"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 450 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-11-20 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 45 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06141901 | Name 2 | Name 59 | 2019-06-17 | USDKFB | 12 | EA | 12 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 520 | 1001267393 | ANGL MTL,EQ,STL,20ft,L3x3x3/8in | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 52 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 60 | FT | 60 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 150 | 7000000103 | HK322U7D31433Z Hex Double Block and Blee | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN112 | Name 2 | Name 2 | 2020-01-21 | USSOLE | 4 | EA | 4 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60920252 | 508 | Ballast Pump 1 Bellows Leaking | S19 | Marine Systems | 2020-02-16 | 2019-10-27 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-17 | 118636000000 | 10 | 30 | 7000000038 | P/N:437 SEAL PACKING (TOMBO #1850P) | 2020-02-02 | Received at Worksite | 2020-01-07 | 2020-01-20 | 2020-02-25 | U182 | 8201 | Stones Main | GRN MILE MOD 22 | 11863639 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-03 | USAWJB | 2 | EA | 2 | Replace Ballast Pump 1 Bellows | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD RUSH WPOK XGI | TECO |  |  | PU Aaron GRN MILE MOD 22
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 80 | 7000003852 | Dexas 3517-J2728 Slimcase 2 Storage Clip | 2020-02-01 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO200006 | Name 10 | USRRIG | 2020-01-19 | USLFA4 | 4 | EA | 0 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | Deleted |  |  | PU DOYLE
60871423 | 508 | Drive End Bearing Leaking Oil - BGCA | S04 | Gas Compress | 2020-03-03 | 2020-01-28 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-20000 | Booster Gas Compression System Train A | 2019-11-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-08 | 118080000000 | 10 | 10 | 7000000039 | 200757101 FLOAT LAB SEAL | 2020-03-03 | Received at Worksite | 2019-11-24 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B8 | 11807987 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-05 | USJDJW | 4 | EA | 4 | Erect Scaffold | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU Aaron 01/19/2020
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 90 | 7000002591 | PILOT G2 Premium Refillable & Retractabl | 2020-02-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200006 | Name 10 | USRRIG | 2020-01-21 | USLFA4 | 4 | EA | 4 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61200672 | 508 | Stones Small Civil Projects 2020 |  |  | 2020-12-31 |  | P.US.STO.NF.20.009.7240A | GENERIC |  |  | 2020-02-11 | WO | U100 | GEN | US01 | P16 | [5 empty] | 3 Low | 2020-12-31 | 121848000000 | 10 | 40 | 7000002596 | Studs, 1/2" x 2 1/2" LG, w/Nuts, B150 UN | 2020-02-28 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G97 | 12184838 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST02242002 | Name 4 | Name 60 | 2020-02-27 | USSOLE | 5 | EA | 0 | Stones Small Civil Projects 2020 | REL ESTC PRC SETC | APPR | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 850 | 1001816209 | GASW,CL150,316,GPH,NPS4 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 101 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4650 | 7000002629 | Plug, 3/4", SC, Hex head, ASME B16.11, A | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 517 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7470 | 1002062557 | WASHER,FLAT,F436,0.177in,7/8in,SERMAGARD | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1005 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 28 | EA | 28 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60847987 | 508 | MOC GTG3 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-24000 | Gen #3 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 50 | 7000005901 | M20 Earth Tag | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780940 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI78 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #3 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60847989 | 508 | MOC GTG5 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-44000 | Gen #5 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 30 | 7000005901 | M20 Nylon Washer | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780944 | 12 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI80 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 3 | SAEP LO/TO Isolate GTG #5 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1530 | 7000002629 | FLANGE, 6" 300, RFWN, SCH 10S,ASME B16.5 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 169 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 380 | 7000002644 | BALL VALVE, 3", 3BL02-A (SEE ATTACHED) | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 51 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60720325 | 508 | O/SI Steam Drain Valve Leaking | S17 | Steam/Hot H2O | 2020-03-10 | 2019-06-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGA-115586 | LP Steam at FR 68 Drain Valve | 2019-12-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-10 | 116218000000 | 20 | 20 | 7000004211 | FLANGE PACK 150-Gate valve .Flange Pack | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11621843 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-19 | USNSB4 | 1 | EA | 0 | Remove & Replace Steam Valve VAGA-11558 | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 460 | 1001049226 | TERMINAL BLOCK,ALLENB,1756-TBNH,20pin | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 432 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 6 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60936971 | 508 | GT2 Gas Fuel Valve Bolts Recalled | S03 | Elect. Systems | 2020-04-01 | 2020-03-07 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.FCV-11120-130 | Generator #2 Fuel Gas Flow Control Valve | 2020-01-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 118822000000 | 10 | 10 | 7000003739 | 601722C1 KIT,HDWR,PECC VALVE | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11882241 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | STANDARD | 2020-01-21 | USAWJB | 1 | EA | 0 | GT1 Gas Fuel Valve Bolts Recalled | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7390 | 1001645341 | BLT HEX,A325,UNC,2in,3/4in,SERMAGARD | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 997 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 16 | EA | 16 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118367 | 508 | 2020 Catering - Material | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 30 | 7000002591 | Crestware Stainless Steel Disher Item # | 2020-02-28 | Received at Worksite |  | 2020-01-15 |  | U182 | 8201 | Stones Main | STONES | 12090704 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOR11620A | Camp Boss | USJRF5 | 2020-01-16 | USLFA4 | 2 | EA | 2 | 2020 Catering - Material | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU KEITH 02/15/2020
61074214 | 508 | PIC-77703-966 Water Ingress | S05 | Gas Dist | 2020-02-27 | 2019-12-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GD.FG.PG-77703-383 | Buy-Back Gas Outlet Press Gauge | 2020-01-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-02-27 | 120397000000 | 10 | 10 | 7000003740 | Inline Pressure Transmitter | 2020-04-27 | Ready for Shipment after Kitting | 2020-01-02 | 2020-01-20 | 2020-03-01 | U182 | 8201 | Stones Main | ST KB A3 | 12039671 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-04 | USNSB4 | 1 | EA | 1 | Replace PT-77703-966 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD WPOK XGI | TECO |  |  | PU Aaron 1/19/2020
60936973 | 508 | GT4 Gas Fuel Valve Bolts Recalled | S03 | Elect. Systems | 2020-04-01 | 2020-03-07 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.FCV-11140-130 | Generator #4 Fuel Gas Flow Control Valve | 2020-01-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 118822000000 | 10 | 10 | 7000003739 | 601722C1 KIT,HDWR,PECC VALVE | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11882243 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | STANDARD | 2020-01-21 | USAWJB | 1 | EA | 0 | GT1 Gas Fuel Valve Bolts Recalled | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 150 | 7000002629 | 2 CL150 Flange ASME B16.5 RF A182 F53 D5 | 2019-11-26 | Received at Target Location |  |  | 2020-02-14 | U182 | 8201 | Stones Main | Onsite Danos Has | 11882270 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI65 | Name 2 | Name 58 | 2019-11-06 | USSOLE | 2 | EA | 2 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60847991 | 508 | MOC GTG1 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-04000 | Gen #1 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117810000000 | 10 | 10 | 7000005903 | Amercable Part Number 37-102-308 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780966 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI76 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 120 | FT | 120 | SAEP LO/TO Isolate GTG #1 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 190 | 7000004751 | Keckley 2" 300# Floating Ball Valve | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN115 | Name 2 | Name 2 | 2020-01-30 | USSOLE | 2 | EA | 2 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60797147 | 508 | A/C Condenser Intermittent Operation | S40 | Cargo Handling | 2020-03-24 | 2019-08-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-07-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-27 | 117216000000 | 20 | 10 | 7000000057 | Visionaire; Pt# 10-10-7071 Condenser coi | 2020-03-24 | Received at Worksite |  | 2019-09-16 |  | U182 | 8201 | Stones Main | ST KB C5 | 11721562 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-31 | USNSB4 | 1 | EA | 1 | Hoist Up Materials/Tools. Secondary Ass | REL PCNF PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU WPT Marty 09/13/2019 TREED
60828495 | 508 | TCP TT-66302-331 Missing | S21 | Oil Treating | 2020-02-20 | 2019-12-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.TT-66302-331 | Tank Cleaning Pump Temp Transmitter | 2019-10-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-20 | 117590000000 | 10 | 10 | 7000005901 | B2100 PT100TP-S-254 TEMPERATURE TRANSMIT | 2020-06-19 | Received at Worksite | 2020-01-17 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B6 | 11759006 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-08 | USNSB4 | 1 | EA | 1 | Replace Defective Temperature Device TT- | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK RUSH WPOK | EXEC |  |  | ST1A6B 02/3/20 GG
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 80 | 7000002596 | Cap Bolts, 3/8" x 2" Lg., SAE Grade 5 He | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 14 | EA | 14 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
61209426 | 508 | Sub-Order To Purchase Magnets In Advance | S19 | Marine Systems | 2020-03-24 | 2020-04-15 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2020-02-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-24 | 121952000000 | 10 | 20 | 7000003517 | BUTTON HEAD HEX DRIVE SCREW STAINLESS ST | 2020-03-24 | Received at Worksite | 2020-02-26 |  |  | U182 | 8201 | Stones Main | Stones | 12195195 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-02-18 | USNSB4 | 2 | PK | 2 | Sub-Order To Purchase Magnets in advance | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 90 | 7000003684 | OIL SAFE 10.0QT. DRUM 101010 | 2020-03-28 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-19 | USAWJB | 1 | EA | 1 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2860 | 7000002629 | Threadolet, 3" x 1/2", 3000#, FS MSS-SP- | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 316 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60878945 | 508 | FWD FW Pump Hydraulic Tank Upgrade | S13 | Fire Protect | 2020-06-01 | 2019-09-30 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.ABJ-33127 | Fwd Firewater Pump Hydraulic Oil Tank | 2019-09-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-06-06 | 118166000000 | 10 | 10 | 7000002591 | hydraulic oil tank steel plate 5mm | 2020-06-01 | Received at Worksite | 2020-01-21 |  |  | U182 | 8201 | Stones Main |  | 11816567 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  |  |  | 2019-09-24 | USJDJW | 1 | EA | 1 | Install LOTO | REL PRT GMPS PRC SETC | APPR EOM MAGN MAKD MAOK RUSH WPOK ZPMM | Kit Complete
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5840 | 7000002596 | Bolt, 1/2" x 1 1/2" LG, ASTM F3125 Gr. | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 678 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 40 | EA | 40 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7550 | 7000002591 | Belzona 1111 (Super Metal), 1 kg | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1014 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 90 | 7000000133 | RKI 61-5007RK Sensor, IR, hydrocarbons | 2020-02-28 | Received at Target Location |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG144 | Entity 7 | USKHU3 | 2020-02-05 | USLFA4 | 1 | EA | 1 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60986290 | 508 | OSI Passing steam valve VAGL-115617 | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-05 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGL-115617 | Steam Inlet Drain Valve | 2020-01-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-01 | 119384000000 | 10 | 30 | 7000004211 | doxsteel-1 DOXSTEEL FASTENER FLANGE PACK | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11938370 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-03 | USNSB4 | 1 | EA | 0 | Replace COT5S Steam Inlet Drain Valve VA | REL ESTC GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7070 | 1001267393 | ANGL MTL,EQ,STL,20ft,L3x3x3/8in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 965 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60989629 | 508 | COPT SW #3 Pump mechanical seal leak | S18 | Water Systems | 2020-04-14 | 2019-12-06 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216C | No. 3 Main/COPT Condenser Cooling Pump | 2019-12-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-14 | 119420000000 | 10 | 40 | 7000004211 | Line bearing, SVS350M-41 | 2020-04-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11942032 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-13 | USMNF8 | 1 | EA | 0 | COPT SW #3 Pump mechanical seal leak | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 200 | 7000002591 | 13/16'' Hogan Bits REG mag drill bits | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 646 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 20 | EA | 20 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60517728 | 508 | Tilting Skillet Repair | S03 | Elect. Systems | 2020-02-04 | 2019-06-11 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.PDP-44310 | Galley Distribution Panel | 2019-03-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 113927000000 | 10 | 30 | 7000005901 | 3754076 MOTOR LA312200+0020004H FUTURA | 2020-02-04 | Received at Worksite |  | 2020-02-03 | 2020-02-09 | U182 | 8201 | Stones Main | James Brunton | 11392705 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-30 | USAWJB | 1 | EA | 1 | Repair Tilting Skillet | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN WPOK XGI | TECO |  |  | PU 2/5/2020 JB GG
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 120 | 7000003197 | Nylon Washer ¾” | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 6 | EA | 6 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
60706937 | 508 | MGCB Install DP Gauges @ Witches Hats | S04 | Gas Compress | 2020-03-18 | 2019-10-15 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.ZZZ-77100B | Compressor Package B | 2019-07-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-23 | 116076000000 | 20 | 10 | 7000002644 | DP Gauge 0-50 psi, Orange research 1502D | 2020-03-18 | Received at Worksite | 2019-11-13 |  |  | U182 | 8201 | Stones Main | ST KB D4 | 11607627 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-18 | USMNF8 | 1 | EA | 1 | Erect Scaffold 1st/2nd St. Scrubbers | REL PCNF ESTC GMPS PPRT PRC SETC | APPR EOM MAGN MAKD MAOK RUSH WPOK ZPMM | Kit Complete |  |  | PU WPT AMW 11/30/19
60352956 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-10 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33320 | No. 1 Starboard Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-11 | 112105000000 | 10 | 20 | 1001618990 | FUEL FILTER,359-BUKH0201,ALXR-RYN | 2020-02-10 | Received at Worksite |  | 2019-10-20 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210548 | 2 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 | USAWJB | 2019-07-17 | USRAR6 | 1 | EA | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 20 | 30 | 1001816211 | GASW,CL150,316,GPH,NPS2 | 2020-02-18 | Received at Worksite |  | 2020-02-20 | 2020-02-21 | U182 | 8201 | Stones Main | ST KB D3 | 10754707 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-03-11 | USNSB4 | 2 | EA | 2 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO |  |  | PU AMW
60959173 | 508 | COP1 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-06 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PBE-66301A | Cargo Oil Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-12 | 119077000000 | 10 | 70 | 7000000038 | 3/8" fnpt SS needle valve | 2020-03-06 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 11907749 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-17 | USRAR6 | 2 | EA | 2 | Add seal flush plan 12 to COP1 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 420 | 7000002603 | 2" 600# Snap-On Flange Protectors | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 87 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 4 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 280 | 7000002644 | Model# 320F-23TTF-23 WKM 3" 300# Floatin | 2020-08-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 32 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-16 | USSOLE | 4 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 70 | 7000002591 | 8" pipe Capacity Strap Wrench https://w | 2020-02-26 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOELEC020 | Name 30 | Name 30 | 2019-08-15 | USLFA4 | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU SHAWN 9/2/2019 CMR
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 350 | 7000002591 | 24mm ½” drive crowfoot socket. Part numb | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 35 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG014 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60616642 | 508 | O/SI Replace Barrier Fluid VADB-85756 | S24 | Subsea Systems | 2020-06-01 | 2019-08-10 | O.US.STO.STO.002.724FP | 508ACR | US.WR508A.SE.OH.ZZZ-12865 | Barrier Fluid Hydraulic Power Unit | 2019-02-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-01 | 115046000000 | 10 | 10 | 7000003196 | DB12M4M2V15 | 2020-06-01 | Received at Worksite |  | 2019-05-14 |  | U182 | 8201 | Stones Main | ST KB D7 | 11504647 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-02-18 | USAWJB | 1 | EA | 1 | Replace VADB-85756 Barrier Fluid HPU | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU Marty S 05/07/2019 CR
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 100 | 7000003740 | Rosemount Product Drawing | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN110 | Name 2 | Name 2 | 2019-12-18 | USLFA4 | 4 | EA | 4 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 270 | 7000002644 | Model# 320F-23TTF-23 WKM 2" 300# Floatin | 2020-08-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 31 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-16 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 410 | 7000002603 | 2" 300# Snap-On Flange Protectors | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 86 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 3 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 230 | 7000003740 | Rosemount Scalable Advanced Level Transm | 2020-03-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 23 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN118 | Name 2 | Name 2 | 2020-01-31 | USLFA4 | 8 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
61057325 | 508 | Faulty level trans LT-77121A-917A MGC A | S04 | Gas Compress | 2020-06-02 | 2019-12-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.MBF-77121A | 2nd Stage Suction Scrubber | 2019-11-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Complete by 2 Weeks | 2020-06-04 | 120203000000 | 30 | 20 | 7000000065 | ZT4510.79 Level transmitter | 2020-06-02 | Received at Worksite |  | 2020-02-08 |  | U182 | 8201 | Stones Main | ST1A6B | 12020299 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-19 | USMNF8 | 1 | EA | 1 | Replace level trans LT-77121A-917A | REL PRT GMPS PRC SETC | APPR MAGN WPOK ZPMM | EXEC |  |  | PU AMW 12/29/19
60701397 | 508 | Leaking Globe/Check Valve on Hydrophore | S18 | Water Systems | 2020-04-11 | 2019-10-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.121-20V | Tank Outlet Check Valve | 2020-01-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-11 | 116003000000 | 20 | 10 | 7000004211 | 5K 40mm GGG20 SDNR GLOBE VALVE, FULL 316 | 2020-04-11 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | Issued -Wrong valve | 11600310 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 50 | USNSB4 | 2019-05-19 | USNSB4 | 1 | EA | 1 | Drain Hydrophore Tank | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MANX WPOK ZPMM | EXEC |  |  | ST1A2C 02/18/2020 CMR
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 40 | 7000002591 | 2" 150# Hydro/Paddle/Slip-Blind, CS 516 | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 1 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 110 | 7000003684 | LITTLE GIANT EXTENDED FUNNEL 100069, 6PK | 2020-03-28 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-19 | USAWJB | 1 | EA | 1 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000003852 | Logitech MK710 Wireless Keyboard and Mou | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | Stones | 12090697 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 32 | USRRIG | 2020-01-18 | USAWJB | 1 | EA | 1 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU AW 01/29/20 GG
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000002591 | Grainger 1-1/2 sink strainers #415F64 | 2020-01-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0005 | Name 8 | USCRFI | 2020-01-13 | USLFA4 | 3 | EA | 3 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 300 | 7000002591 | 4452K416 90 Degree Elbow Connector, 1 NP | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 30 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 70 | 7000002591 | 6" 1500# Spectacle Blind, CS 516 Gr-70, | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 2 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7430 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1001 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-15 | USSOLE | 160 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7040 | 1000710996 | FTG_PIPE,PLG,1/2",SS | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 952 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052001 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 22 | EA | 22 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3880 | 7000002596 | SB2N,B8M CL2,8M,UNC,7/8in,7.50in | 2019-11-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 438 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10311902 | Name 2 | Name 2 | 2019-10-31 | USSOLE | 15 | EA | 15 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5860 | 1001723501 | WASHER,FLAT,F436,SERMAGAURD,1/2in | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 680 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 40 | EA | 40 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7720 | 7000002629 | Plug, 3/4", SC, Hex head, ASME B16.11, A | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1035 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 3 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3390 | 1000710070 | FTG_PIPE,THDOLET,36",3/4",1/2",CS,3000# | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 369 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 650 | 7000003740 | Rosemount Scalable Pressure Transmitter | 2020-02-21 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 857 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN117 | Name 2 | Name 2 | 2020-01-31 | USLFA4 | 2 | EA | 2 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3380 | 7000002629 | Weldolet, 12" x 2", STD x S/80, MSS-SP-9 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 368 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2310 | 1001664294 | BLT HEX,A325,UNC,2.3/4in,3/4in,SERMAGARD | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 253 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 760 | 1000710324 | FTG_PIPE,PLUG,3/4",316 SS | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose |  | 11179936 | 1042 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-23 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4420 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2019-11-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 494 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141901 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 36 | EA | 36 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2410 | 1001676333 | BLT HEX,A325,UNC,2.1/4in,5/8in | 2019-04-08 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 263 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011905 | Name 2 | Name 2 | 2019-04-02 | USSOLE | 70 | EA | 70 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61155246 | 508 | Install Barring Device on MGCA | S04 | Gas Compress | 2020-03-03 | 2020-07-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-03 | 121329000000 | 10 | 10 | 7000002591 | 8973K913 Corrosion-Resistant 3003 Alumi | 2019-11-01 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST1A6C | 12132852 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0006 | Name 17 | JP832018 | 2020-01-27 | USLFA4 | 1 | EA | 1 | Install Barring Device on MGCA | REL PCNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC |  |  | ST1A6C 02/16/20 AMW
60973122 | 508 | MGC-B 3rd Stg Bridle Removal | S04 | Gas Compress | 2020-04-18 | 2020-09-25 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-10000 | Main Gas Compression System Train B | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-19 | 119235000000 | 10 | 20 | 7000004753 | 3-COAT PAINT BLIND FLANGES | 2020-03-19 | Received at Worksite | 2020-01-06 | 2020-01-06 |  | U182 | 8201 | Stones Main | ST KB C7 | 11923512 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 59 | 2019-10-02 | USAWJB | 4 | EA | 4 | MGC-B 3rd Stg Bridle Removal MOC78183 | REL PRT GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU WPT AMW 11/30/19
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 130 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 2 | EA | 2 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
60569415 | 508 | O/SI Cargo Valve 241 Hydraulic Leaking | S21 | Oil Treating | 2020-03-24 | 2019-01-31 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-241 | Crude Oil to/from Fwd COTs On/Off Valve | 2019-07-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Complete by 2 Weeks | 2020-04-06 | 114505000000 | 20 | 20 | 7000004212 | INTERNATIONAL AIR FREIGHT AND PACKING CH | 2020-03-24 | Received at Target Location |  | 2019-09-11 |  | U182 | 8201 | Stones Main |  | 11450504 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  |  | USNSB4 | 2019-07-02 | USNSB4 | 1 | EA | 1 | Drain 5S Tank To Repair Hydraulic Actuat | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU WPT STKB A4
61161325 | 508 | 3M Active Carbon Fine Filter Cartridge R | S18 | Water Systems | 2020-04-20 | 2020-06-04 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZAJ-12106 | FW Activated Fine Filter | 2020-01-20 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Normal | 2020-04-20 | 121398000000 | 10 | 10 | 1002133957 | FILTER ELEMENT,0210-HAC24870,HATENBOE | 2020-04-20 | Received at Worksite |  | 2020-01-20 |  | U182 | 8201 | Stones Main | ST1A2C | 12139752 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2020-01-19 | EW_BTCJOB | 30 | EA | 30 | 3M Active Carbon Filter Cartridge Replac | REL ESTC GMPS PRC SETC | EXEC MAOK | EXEC |  |  | ST1A2C 01/21/2020 CMR
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 30 | 1000709396 | NPHT,SWAGELOK,SS-8-HLN-2.00,1/2in,NPTM | 2019-11-19 | Received at Target Location |  |  | 2020-02-14 | U182 | 8270 | Danos - Amelia | Onsite Danos Has | 11882270 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI66 | Name 15 | Name 58 | 2019-11-06 | USABCE | 2 | EA | 2 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 160 | 1002316823 | GASW,CL150,316/316L,GPH,2in | 2019-11-26 | Received at Target Location |  |  | 2020-02-14 | U182 | 8201 | Stones Main | Onsite Danos Has | 11882270 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI65 | Name 2 | Name 58 | 2019-11-06 | USSOLE | 2 | EA | 2 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60739061 | 508 | COT 4 S HC Netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127021 | COT 4 SB HC Main Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642937 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 270 | 7000002603 | Flange Protectors, 2", 300#, RF | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 123 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 480 | 7000002629 | 3" 2500# R32 Pressure Rated Skillet CS A | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 93 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 1 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61178974 | 508 | Fire extinguishers expiring March 2020 | S13 | Fire Protect | 2020-03-13 | 2020-03-26 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-02-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-13 | 121602000000 | 10 | 10 | 7000005811 | 15# extinguishers CO2 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12160189 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-27 | USMNF8 | 69 | EA | 0 | Fire extinguishers expiring March 2020 | REL ESTC PRC SETC | APPR MAGN RUSH WP | Approved
60921250 | 508 | O/SI Steam Inlet Drain Valve Leaking | S17 | Steam/Hot H2O | 2020-03-11 | 2020-03-02 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.SW.VAGL-115552 | Steam Inlet Drain Valve | 2020-01-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 118651000000 | 20 | 70 | 7000002603 | 1/2 X 3-1/2" DOX PLTD STUD | 2020-03-10 | Received at Worksite | 2020-01-22 |  |  | U182 | 8201 | Stones Main | ST1A3B | 11865065 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-15 | USMNF8 | 50 | EA | 50 | Shut down steam system | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WP ZPMM | Kit Complete |  |  | ST1A3B 02/3/20 GG
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 20 | 7000002596 | BLT+N,A193B8MCL2,UNC,10in,1.5/8n | 2019-05-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E35 | 11545759 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05291902 | Name 2 | Name 2 | 2019-05-29 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
61170198 | 508 | Faulty Press Trans LACT Skid | S21 | Oil Treating | 2020-04-25 | 2021-01-20 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-25 | 121499000000 | 10 | 20 | 1000711217 | TEET,SWAGELOK,SS-8-T,1/2in | 2020-04-25 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB B7E | 12149917 | 2 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2020-01-26 | USAWJB | 1 | EA | 1 | MOC 79792 Faulty Press Trans LACT Skid | REL ESTC GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved |  |  | ST1A1C 02/07/2020 CMR
60959163 | 508 | COP #2 Disch Px Gauge | S21 | Oil Treating | 2020-02-04 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PG-66301B-342B | Discharge Pressure Gauge | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-04 | 119075000000 | 20 | 30 | 7000000066 | WK MISC Mfr: WIKA INSTRUMENT CORP Mfr | 2020-02-04 | Received at Worksite |  |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB A5 | 11907499 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 33 | USNSB4 | 2019-10-29 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge PG-342B, COP #2 D | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN WPOK XGI | TECO
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 180 | 7000002591 | MPACT NAP Foam Noise Reduction Ear tips | 2020-03-26 | Not Shipped |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 19 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN022520A | Name 41 | USKHU3 | 2020-03-03 | USLFA4 | 5 | EA | 0 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 910 | 7000004754 | 1/2" x 0.065 317L SMLS SS Coated Tubing | 2020-03-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 930 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI84 | Name 2 | Name 2 | 2020-02-04 | USSOLE | 160 | FT | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5340 | 7000002644 | BALL VALVE, 1/2" FULL PORT 3705 PSI MNPT | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 595 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 790 | 7000003463 | PC-KL9D3YP01M | 2020-03-18 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1070 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-26 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4560 | 7000002629 | Flange, 2", 300#, RFWN, S/40S Bore, ASME | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 508 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3440 | 7000002629 | Blind Flange, 12", 150#, RF, ASME B16.5, | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 374 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6910 | 1001663813 | SHT PLT SLD MET,4x4ft,1in,A572-50 | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 939 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 330 | 1002292481 | SB2N,B7,2H,UNC,5/8in,3.75in,CTD | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 46 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1660 | 7000002596 | STUD BOLT, 3/4" X 5 1/2" ASTM A193 GR B8 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 182 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60739075 | 508 | O/SI Actuator Seal Test Fail 2 STBD | S21 | Oil Treating | 2020-03-24 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6632S-364 | Crude Oil to/from COT 2 SBB Valve | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-24 | 116430000000 | 10 | 10 | 7000004212 | HAA-D10-RK HYD. ROTARY ACTUATOR - (DOUBL | 2020-03-24 | Received at Worksite | 2019-11-11 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB B8 | 11642971 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-03 | USNSB4 | 2 | EA | 2 | LO/TO Perform Isolations. | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
61023509 | 508 | Grating on green mile needs replacing. | S19 | Marine Systems | 2020-06-01 | 2019-12-25 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.HG | Handrails, Stairways, Grating | 2020-02-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-06-02 | 119822000000 | 10 | 10 | 1000856876 | Requestor: Gavin LeBlanc | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G87 | 11982221 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02172001 | Name 4 | Name 60 | 2020-02-19 | USSOLE | 1 | EA | 1 | Grating on green mile needs replacing. | REL ESTC PRC SETC | APPR EOM MAGN MANX WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 20 | 7000002629 | 2" Flange Blind 300# RF ASME B16.5, 3/4" N | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 47 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 2 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60352955 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-09 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33310 | No. 1 Port Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-10 | 112105000000 | 10 | 50 | 7000000133 | Marine Packing PN 400-RUDD0010 | 2020-02-09 | Received at Worksite |  | 2019-10-20 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210547 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-07-17 | USRAR6 | 1 | EA | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 30 | 7000000069 | 15# Loaner extinguishers CO2 | 2020-01-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-10 | USMNF8 | 9 | EA | 0 | Send In/Replace Fire Ext Due Hydro | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Deleted
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 90 | 7000005811 | Water extinguishers | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 12 | EA | 0 | Send In/Replace Fire Ext Due Hydro | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60874068 | 508 | FRC inspection deficiencies | S15 | Life Saving | 2020-02-13 | 2020-03-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2019-08-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-03 | 118106000000 | 10 | 90 | 7000004662 | Winch Tank Reservoir 0-40 Mpa Gauge | 2020-02-13 | Not Shipped |  | 2020-02-13 |  | U182 | 8201 | Stones Main | POD- Questions | 11810577 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-08-04 | USAWJB | 1 | EA | 0 | FRC inspection deficiencies | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD MAGN WPOK | EXEC
60544614 | 508 | Mechanical seal is leaking | S18 | Water Systems | 2020-06-02 | 2019-07-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216A | No. 1 Main/COPT Condenser Cooling Pump | 2019-12-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 114224000000 | 10 | 60 | 7000004211 | Packing pn:60A, SVS350M-60A | 2020-06-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11422404 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-15 | USMNF8 | 1 | EA | 0 | Mechanical seal is leaking | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
61118331 | 508 | 2020 Chemical Order - Engine Room | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 50 | 7000003458 | SCAL16359A.32B | 2020-01-29 | Received at Target Location |  | 2020-01-10 |  | U182 | 8201 | Stones Main | CPORT | 12090688 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200004A | Name 40 | USRRIG | 2020-01-16 | USLFA4 | 1000 | GLL | 1000 | 2020 Chemical Order - Engine Room | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61134940 | 508 | Calibrate and return mooring hawser load | S19 | Marine Systems | 2020-04-01 |  | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-88631 | Mooring Quick Release Hook | 2020-01-22 | WO | U100 | 72RE | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 2 Medium | 2020-04-01 | 121091000000 | 10 | 10 | 7000000057 | Recalibrate, return 300t mooring hawser | 2020-04-01 | Received at Worksite |  | 2020-01-22 | 2020-02-02 | U182 | 8201 | Stones Main | Green mile | 12109107 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-10 | USAMH7 | 1 | EA | 1 | Calibrate and rtn mooring load cell pin | TECO ESTC GMPS PRC SETC | XCNF MAGN XGI | TECO |  |  | STMOD 21 01/30/2020 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2050 | 7000002629 | WELD-O-LET, 12" X 2" (2" S/40S (0.154 WT | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 227 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60986290 | 508 | OSI Passing steam valve VAGL-115617 | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-05 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGL-115617 | Steam Inlet Drain Valve | 2020-01-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-01 | 119384000000 | 10 | 20 | 7000004211 | 49448-9 R10, 1" ANSI CLASS 150 FORGED ST | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11938370 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-03 | USNSB4 | 1 | EA | 0 | Replace COT5S Steam Inlet Drain Valve VA | REL ESTC GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61193600 | 508 | Install bolt in swing gate on IG platfor | S06 | General | 2020-04-25 | 2020-08-04 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.IG | Inert Gas/Vent Systems | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-25 | 121766000000 | 10 | 10 | 7000002596 | 1/2" x 6" Carriage bolts | 2020-04-25 | Received at Target Location |  | 2020-02-08 |  | U182 | 8201 | Stones Main | STONES | 12176649 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-08 | USMNF8 | 8 | EA | 8 | Install bolt in swing gate on IG platfor | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1780 | 7000002629 | ELBOW, 12, S/10S (0.180 WT), LR, 90 DEG. | 2019-01-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 195 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01171902 | Name 2 | Name 2 | 2019-01-18 | USDSVB | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 300 | 7000000052 | Mounting Hardware | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 416 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN099 | Name 2 | Name 2 | 2019-10-29 | USLFA4 | 2 | EA | 2 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 80 | 7000004213 | KE35/11 SASAKURA KE35 P/N 11 GLOBE VALVE | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 490 | 1000710996 | FTG_PIPE,PLG,1/2",SS | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 65 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4640 | 7000002629 | Threadolet, 3" x 3/4", 3000#, FS MSS-SP- | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 516 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60636182 | 508 | OEM recommends elbow replacement | S08 | Air Systems | 2020-02-25 | 2019-04-25 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.HBG-11853A | No. 1 Air Compressor Oil Separator | 2019-10-30 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-25 | 115265000000 | 10 | 10 | 7000000034 | Nipple P/N 0603 5120 03 | 2020-02-25 | Received at Worksite | 2020-02-05 | 2020-02-20 |  | U182 | 8201 | Stones Main | ST KB A3 | 11526532 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-30 | USRAR6 | 4 | EA | 4 | Replace elbow on compress 1,2,3,4 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK RUSH WPOK | EXEC |  |  | PU 02/19/20 AMW
60172772 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-03-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.95T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 110086000000 | 10 | 70 | 7000002591 | 40mm Flange Protectors | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008581 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081901 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 6 | EA | 6 | MOC missing steam trap | REL PCNF ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60737097 | 508 | VPI test fail COT 5 Port | S21 | Oil Treating | 2020-02-10 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-663UD-293 | Crude Oil To COT 5 PS O/O Valve | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-10 | 116406000000 | 20 | 10 | 7000005901 | P.0244110028 AVC 02 CL1 A1 VPI MANIFOLD | 2020-04-30 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7F | 11640602 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-13 | USNSB4 | 1 | EA | 1 | Repair VPI XV-663UD-293 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU Aaron ST1A1B 01/19/2020 C
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 10 | 7000002591 | Hempel Hempadur Quattro 17634 Red (shade | 2020-02-04 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | DIISTO1927 | Entity 1 | USJRF5 | 2020-01-28 | USLFA4 | 4 | EA | 4 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61179018 | 508 | FRC Engine Turbo Exhaust piping corroded | S15 | Life Saving | 2020-04-25 | 2020-07-27 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-25 | 121603000000 | 10 | 30 | 7000005811 | Exhaust Elbow | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12160259 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-03 | USMNF8 | 1 | EA | 0 | Replace FRC Engine Turbo Exhaust piping | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60985328 | 508 | O/SI Rtrn Vlv VAGA-115505 corrosion/leak | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-05 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.VAGA-115505 | Port Condensate from COT 5 Isol Valve | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 119372000000 | 20 | 10 | 7000000104 | 2-1/2 Neway gate valve | 2020-06-01 | Received at Worksite | 2020-02-13 |  |  | U182 | 8201 | Stones Main | ST1A5B | 11937174 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-04 | USMNF8 | 1 | EA | 1 | Shut down steam system | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | ST1A5B AMW
60737086 | 508 | VPI test fail 5S | S21 | Oil Treating | 2020-02-08 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-223 | Crude Oil to/from COT 5 On/Off SB Valve | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-08 | 116406000000 | 20 | 10 | 7000005901 | P.0244110037 AVC 02 CL1 A1 VPI MANIFOLD | 2020-04-28 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7F | 11640591 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-12 | USNSB4 | 1 | EA | 1 | Repair VPI XV-6635S-223 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 100 | 7000000039 | PR Electronics 5909 Loop Link Communicat | 2020-01-30 | Ready for Shipment after Kitting |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20001SJ | ACT Name 51 | USJRF5 | 2020-01-20 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 430 | 7000000098 | 1" RENEGADE BLUE EACH 1" X 6FT CHEMICAL | 2020-03-16 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 43 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOET00120 | Name 3 | USCRFI | 2020-02-09 | USLFA4 | 3 | EA | 3 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1 FLR 2/24/2020 GG
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 890 | 7000002591 | DEWALT Wire Brush, Crimped, 1-Inch (DW49 | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 89 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 6 | EA | 6 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60747148 | 508 | COT 3 P HC Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127014 | COT 3 PS HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651960 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60737094 | 508 | Solenoid Valve test fail Slop STBD | S21 | Oil Treating | 2020-03-17 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-663SS-231 | Crude Oil to/frm Slop Tank On/Off SB Vlv | 2019-08-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-17 | 116406000000 | 20 | 10 | 7000000070 | BiFold 24D/M/50 FP02/S0A/C3/43/SC/V/67A- | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 10/23 | 11640599 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-08-27 | USNSB4 | 1 | EA | 0 | Repair Solenoid Valve Slop STBD | REL PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 60 | 7000000133 | 637167 Nike DriFit Vertical Mesh Polo in | 2019-12-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Turritella TDR Improvemen | 11545759 | 85 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO1127191 | Name 2 | Name 2 | 2019-12-03 | USSOLE | 21 | EA | 21 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 650 | 7000002591 | 4452K146 Plug with External Hex Drive, 1 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 65 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 480 | 7000002591 | Panels of Helimesh 25 per the attached d | 2019-12-08 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 48 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06251901 | USACJL | Name 59 | 2019-06-25 | USSOLE | 6 | EA | 6 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1330 | 1001837030 | CAP PIPE SW,A105,CL3K,NPS1.1/2 | 2019-12-27 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 133 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A381 | Name 2 | Name 59 | 2019-12-24 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60815109 | 508 | SWLift Hypochlorite Analyzer not working | S18 | Water Systems | 2020-03-03 | 2019-12-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZZZ-12204 | Chlorine Analyser Assembly | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-04 | 117437000000 | 20 | 20 | 7000005901 | W3T331891 MICRO/DEOX 2000 230VAC C/W WET | 2020-06-01 | Received at Worksite | 2019-12-16 | 2020-01-20 |  | U182 | 8201 | Stones Main | MOD 22 FLOOR | 11743718 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-21 | USNSB4 | 1 | EA | 1 | Replace Hypochlorite Meter | REL PRT GMCO GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 20 | 1000711277 | VALVE,BALL,SWAGELOK,SS-45S12,2500psig | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 2 | EA | 2 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 150 | 7000002591 | Blind Flange, 20", JIS 5K, ASME 16.5, AS | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 3 | EA | 3 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 310 | 1001664232 | WASHER,FLAT,SS316,1/4in | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 31 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 400 | EA | 400 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3610 | 1001663814 | SHT PLT SLD MET,4x4ft,1/4in,A572-50 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Stones Solids Tie-in | 11179936 | 391 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161902 | Name 4 | Name 4 | 2019-10-17 | USGBI5 | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1180 | 1001566525 | (Please provide 40' joints) | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 134 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061802 | Name 2 | Name 2 | 2018-12-07 | USSOLE | 80 | FT | 80 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 610 | 1000716645 | ADH,INSUL,12 OZ SPRAY CAN,1602,3M | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 853 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 4 | EA | 4 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
61006507 | 508 | PSV test kits | S21 | Oil Treating | 2020-02-11 | 2020-10-15 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.VE663-00000 | Cargo Oil Pump Systems | 2020-01-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-17 | 119629000000 | 10 | 40 | 7000002603 | 8" 316 300# spiral wound gasket | 2020-02-11 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-25 | U182 | 8201 | Stones Main | ST1A3A | 11962883 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 9 | EA | 9 | Install PSV Testt kits | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
60470624 | 508 | Turret Gantry Crane Out of Service | S40 | Cargo Handling | 2020-06-01 | 2019-11-19 | O.US.STO.STO.005.724FP | GHEMSPAR | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-06-01 | 113409000000 | 10 | 30 | 7000000040 | Spray Lube Aerokroil | 2020-06-01 | Received at Worksite |  | 2019-07-17 | 2020-01-02 | U182 | 8201 | Stones Main | ST KB B2 | 11340935 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-02-15 | USRAR6 | 1 | EA | 1 | Turret Gantry Crane Out of Service | TECO PCNF ESTC GMPS PPRT PRC SETC | XCNF NCMP WPOK XGI ZPVS | TECO |  |  | PU Marty S 05/07/2019 CR
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 80 | 1002301610 | SB2N,B8M CL2,8M,UNC,5/8in,3.50in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 53 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 48 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 460 | 7000000098 | PPD 100 1" POLYPRO PART D | 2020-03-16 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 46 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOET00120 | Name 3 | USCRFI | 2020-02-09 | USLFA4 | 11 | EA | 11 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A3C 2/24/2020 GG
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 200 | 1002301612 | SB2N,B8M CL2,8M,UNC,3/4in,3.50in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 65 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 4 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 60 | 7000004213 | KE35/9 SASAKURA KE35 P/N 9 ORIFICE | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1280 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2020-05-07 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G04 | 11581207 | 128 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031901 | Name 4 | Name 59 | 2019-12-04 | USSOLE | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60921250 | 508 | O/SI Steam Inlet Drain Valve Leaking | S17 | Steam/Hot H2O | 2020-03-11 | 2020-03-02 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.SW.VAGL-115552 | Steam Inlet Drain Valve | 2020-01-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 118651000000 | 30 | 10 | 7000002596 | 1/2 X 3 (2-3/4 FTF) DOX PLTD STUD | 2020-03-11 | Received at Worksite | 2020-01-22 |  |  | U182 | 8201 | Stones Main | ST1A3B | 11865065 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | 4073688 | Name 3 |  | 2020-01-11 | USMNF8 | 42 | EA | 42 | Steam Inlet Drain Valve Leaking | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WP ZPMM | Kit Complete |  |  | ST1A3B 02/3/20 GG
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 60 | 7000005811 | Fire Extinguishers 2.5 GALLON CG250 FOAM | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 30 | EA | 30 | Send In/Replace Fire Ext Due Hydro | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60737087 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-03-17 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-240 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-17 | 116406000000 | 20 | 10 | 7000000070 | BiFold FP03/S0A/C3/43/SC/V/67A- | 2020-06-05 | Received at Worksite | 2019-12-10 |  |  | U182 | 8201 | Stones Main | ETA 10/31 | 11640592 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-27 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635S-240 | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2540 | 7000003344 | Plate, 1/2" x 96" x 96", ASTM A572 Gr. 5 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 276 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04041901 | Name 2 | Name 2 | 2019-04-05 | USDSVB | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60177919 | 508 | Mod 6 - vlv long bolts Diss metals | S04 | Gas Compress | 2020-06-01 | 2019-06-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VABL-771251 | Cooler Press Diff Transmitter Iso Valve | 2019-08-26 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-06-01 | 110146000000 | 10 | 30 | 7000002596 | 5/8-11 X 3-1/2 STUD BOLT A193 B8M SS | 2020-06-01 | Ready for Shipment after Kitting | 2019-10-29 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB D3 | 11014637 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-26 | USNSB4 | 4 | EA | 4 | LO/TO Shutdown Down Process Train, De-In | REL ESTC CSER GMPS PRC SETC | EXEC EOM MAGN MAKD MANX WPOK | EXEC |  |  | PU WPT 11-25-19
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3620 | 1001676781 | SHT PLT SLD MET,4x4ft,1/2in,A572 GR.50 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Stones Solids Tie-in | 11179936 | 392 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161902 | Name 4 | Name 4 | 2019-10-17 | USGBI5 | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60935789 | 508 | COP2 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-10 | 2019-10-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 118809000000 | 10 | 10 | 7000000038 | 1/4” mnpt x 3/8” tube SS fitting (for se | 2020-03-10 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11880945 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-26 | USAWJB | 1 | EA | 1 | Install mechanical seal flush plan 12 | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 820 | 1001816277 | GASW,CL300,316,GPH,NPS8 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 98 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 23 | EA | 23 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 130 | 1000709964 | UNIC,SWAGELOK,SS8106,1/2in | 2019-11-20 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI68 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 2 | EA | 2 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
61006507 | 508 | PSV test kits | S21 | Oil Treating | 2020-02-11 | 2020-10-15 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.VE663-00000 | Cargo Oil Pump Systems | 2020-01-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-17 | 119629000000 | 10 | 60 | 7000002603 | 6" flex 150# spiral wound gasket | 2020-02-11 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-25 | U182 | 8201 | Stones Main | ST1A3A | 11962883 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 2 | EA | 2 | Install PSV Testt kits | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
61219230 | 508 | GT #3 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-2 | Generator #3 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 50 | 7000003763 | 2012 1-7/16 BUSHING | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206814 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #3 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 190 | 7000002591 | Item # 5WE27 (mm machinery key kit) | 2020-02-21 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0008 | Name 17 | USHBE9 | 2020-01-30 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A6C 02/18/2020 CMR
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 10 | 7000004213 | KE35/1-4-SET | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 14 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61085450 | 508 | Heavily Corroded Casing / Seal Bolts | S18 | Water Systems | 2020-02-14 | 2020-05-23 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12215 | Auxiliary Cooling Pump | 2020-01-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-14 | 120521000000 | 10 | 20 | 7000000111 | Bolts for 61085450 | 2020-02-14 | Received at Worksite | 2020-01-21 | 2020-02-03 | 2020-02-20 | U182 | 8201 | Stones Main | ST KB A5 | 12052102 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-04 | USAMH7 | 2 | EA | 2 | M Furrow Replace Casing/Seal Bolts | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 2/5/2020 JH GG
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 30 | 1000853766 | ANGL MTL,UNEQ,CS,20ft,3X2X1/4in | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 20 | FT | 20 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 850 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2020-01-12 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 85 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08051901 | Entity 3 | Name 59 | 2019-08-05 | USDKFB | 148 | EA | 148 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60453594 | 508 | 26-PL664001- Install permanent Pipe Supp | S21 | Oil Treating | 2020-02-18 | 2019-11-10 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-18 | 113218000000 | 10 | 50 | 7000002596 | Bolt, 5/8" x 1 1/2" LG, ASTM A325 (Serma | 2020-01-22 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | JOB: SHF9-F92 | 11321849 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221902 | Name 4 |  | 2019-11-22 | USLFA4 | 5 | EA | 5 | 26-PL664001- Install permanent Pipe Supp | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60975188 | 508 | XV-12202A-912 Fails to Open | S18 | Water Systems | 2020-02-06 | 2019-10-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.XV-12202A-912 | Filter Backwash On/Off Control Valve | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-02-06 | 119260000000 | 10 | 30 | 7000002596 | 5/8 X 7 (6-3/4 FTF) DOX PLTD STUD BOLT | 2020-02-06 | Received at Worksite |  | 2019-12-28 | 2020-02-10 | U182 | 8201 | Stones Main | ST KB B2 | 11925969 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 1 | USAWJB | 2019-10-04 | USAWJB | 16 | EA | 16 | LOTO System - Confirm Isolation | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU AMW 12/29/19
61118367 | 508 | 2020 Catering - Material | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 50 | 7000003454 | Cambro Polycarbonate Round Food Storage | 2020-02-28 | Not Shipped |  | 2020-01-15 |  | U182 | 8201 | Stones Main | STONES | 12090704 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOR11620A | Camp Boss | USJRF5 | 2020-01-16 | USLFA4 | 1 | PK | 0 | 2020 Catering - Material | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60874068 | 508 | FRC inspection deficiencies | S15 | Life Saving | 2020-02-13 | 2020-03-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2019-08-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-03 | 118106000000 | 10 | 40 | 7000004662 | ARMS Lifeboat Fuel Filter, Steyr SE | 2020-02-13 | Received at Worksite |  | 2020-02-13 |  | U182 | 8201 | Stones Main | Put in Stock | 11810577 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-04 | USAWJB | 1 | EA | 1 | FRC inspection deficiencies | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD MAGN WPOK | EXEC |  |  | PU 02/16/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6970 | 7000002591 | Gallon of Fabreeka #700 Epoxy | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 945 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60959166 | 508 | Replace Ballast Pump #2 Px Gauge | S19 | Marine Systems | 2020-07-06 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.BB.PG-11201B-258 | Ballast Pump No. 2 Suct Pressure Gauge | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-07-06 | 119075000000 | 10 | 20 | 7000000062 | WK 47442334 IV20 in-line 1/2 NPT M - 1/2 | 2020-07-06 | Received at Worksite | 2019-12-09 |  |  | U182 | 8201 | Stones Main | ST1A1B | 11907502 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-21 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge, Ballast Pump #2 | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD WPOK ZPMM | Kit Complete |  |  | PU AARON W 01/19/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3100 | 1001622964 | (PCM-0.23) | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 340 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 120 | FT | 120 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 220 | 7000000052 | AB 10 Slot Rack | 2019-10-09 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 306 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN092 | Name 23 | Name 23 | 2019-09-27 | USGBI5 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 590 | 1001931007 | ELB BW,WPB,90DEG,LR,STD,NPS12 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 75 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 230 | 7000002603 | FLAT RING GASKET, 6", 150#, RF, FLEXIBLE | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 36 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 5 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5600 | 7000002629 | Lateral 45, 3" x 3", S/10S, BW, (Dim. P | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 654 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 130 | 7000002629 | WELD-O-LET, 14" X 3" (3" S/XXS (0.600 WT | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 26 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1960 | 7000002596 | STUD BOLTS, 5/8" DIA. X 6" LONG, ASTM A1 | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 218 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3160 | 1001574309 | (PCM-0.23) | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 346 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 140 | 7000003197 | Serrated Washer ¾” | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 6 | EA | 6 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6930 | 7000003344 | Plate, 3/8" x 24" x 24", ASTM A572 Gr. 5 | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 941 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60975189 | 508 | XV-12202B-924 Fails to Open | S18 | Water Systems | 2020-02-07 | 2019-10-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.XV-12202B-924 | Filter Backwash On/Off Control Valve | 2019-10-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-02-07 | 119260000000 | 10 | 30 | 7000002596 | 5/8 X 7 (6-3/4 FTF) DOX PLTD STUD BOLT | 2020-02-07 | Received at Worksite |  | 2020-01-20 | 2020-02-14 | U182 | 8201 | Stones Main | ST KB D5 | 11925970 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-10-04 | USAWJB | 16 | EA | 16 | LOTO System - Confirm Isolation | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 440 | 7000002591 | 10'x 12' Clear Plastic Tarp | 2020-01-20 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 753 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A373 | Name 2 | Name 2 | 2020-01-14 | USSOLE | 6 | EA | 6 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 120 | 7000002596 | Stud Bolts, 5/8" x 3 1/2" LG., ASTM A320 | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 9 | EA | 9 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 370 | 7000002591 | Hydramax HM06 Load Cell Spring Assist | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 68 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 18 | EA | 18 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 120 | 7000002591 | 4548K173 1/2 NPT, 2" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60453594 | 508 | 26-PL664001- Install permanent Pipe Supp | S21 | Oil Treating | 2020-02-18 | 2019-11-10 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-18 | 113218000000 | 10 | 30 | 7000003344 | Plate, 1/4" x 24" x 24", ASTM A572 Gr.50 | 2020-01-22 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | JOB: SHF9-F92 | 11321849 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221902 | Name 4 |  | 2019-11-22 | USLFA4 | 1 | EA | 1 | 26-PL664001- Install permanent Pipe Supp | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60440621 | 508 | Replace Laydown Timber - MODs 15, 17, 19 | S40 | Cargo Handling | 2020-03-10 | 2020-06-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.LS | Loading Stations | 2019-08-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 113072000000 | 10 | 20 | 7000002583 | M20-2.50 Hex Nut, Plain Finish, A2 Stain | 2020-03-10 | Received at Worksite |  | 2019-09-11 |  | U182 | 8201 | Stones Main | ST KB A1 | 11307214 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-05 | USAWJB | 1 | EA | 1 | Replace Laydown Timbers - MOD 15 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAOK RUSH WPOK | EXEC |  |  | PU KB A1
60557093 | 508 | O/SI Passing Valve VABL-661050 | S22 | Prod Gathering | 2020-02-15 | 2019-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.FM.VABL-661050 | Test Fluids Manual Isolation Valve | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-15 | 114365000000 | 10 | 60 | 7000002603 | R-46-GA6 Gasket Octagonal ASME B16.20 CL | 2020-01-07 | Received at Target Location |  | 2020-02-11 | 2020-02-20 | U182 | 8270 | Danos - Amelia | VABL-661055 Valve Change | 11436470 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A387 | Name 2 | Name 59 | 2020-01-29 | USSOLE | 3 | EA | 3 | Replace VABL-661050 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK RUSH WPOK XGI | TECO
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 20 | 30 | 7000003196 | SS-400-61 BULKHEAD UNION | 2019-12-08 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | Issued | 11614811 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 7 | USNSB4 | 2019-06-20 | USNSB4 | 2 | EA | 2 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 170 | 1000709977 | ADAPTOR,TUBE,SWAGELOK,SS12TA18,3/4x1/2in | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 4 | EA | 4 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60848029 | 508 | OSI N2 HMI DEGRADING | S08 | Air Systems | 2020-05-06 | 2019-09-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.AT-11820-600 | Oxygen Analyser | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-05-06 | 117810000000 | 10 | 30 | 7000003740 | In-line filter stainless steel; hose con | 2020-05-06 | Received at Target Location |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST KB D3 | 11781007 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 24 | USNSB4 | 2019-08-23 | USNSB4 | 1 | EA | 1 | Replace Front Screen/Keypad, N2 Analyzer | REL PCNF PRT GMPS PRC SETC | EXEC EOM MAGN WPOK | EXEC |  |  | PU 02/16/20 AMW
60739056 | 508 | COT 4 STBD netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127009 | COT 4 SB HC Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642932 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60747149 | 508 | COT 2 STBD HC line Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127023 | COT 2 SB HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651961 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 510 | 7000002629 | 316 SS 1 1/4" M camlock X 1 1/4" M NPT | 2020-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 765 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A382 | Name 2 | Name 2 | 2020-01-20 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
61193291 | 508 | AxTech Study - Bell Latching Mechanism | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.010.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-02-07 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 121764000000 | 10 | 10 | 7000000098 | 12PS-5000-SS-FJFJ-30" | 2020-12-31 | Not Shipped |  | 2020-02-07 |  | U182 | 8201 | Stones Main | Stones | 12176389 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAMH7 | 2020-02-11 | USRAR6 | 12 | EA | 0 | AxTech Study - Bell Latching Mechanism | REL ESTC PRC SETC | EXEC | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5170 | 7000002603 | GASKET, 8" 300LB, 1/8" THICK, RF SPIRAL | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 578 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 13 | EA | 13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60776392 | 508 | Unit SW Outlet Valve has a hole in it. | S18 | Water Systems | 2020-05-07 | 2019-11-25 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.VADI-122010 | Unit SW Outlet Vent Valve | 2020-01-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-07 | 116933000000 | 20 | 10 | 7000005901 | 1.5" Valve DPHRM ANSI 150 SGI | 2020-05-07 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11693340 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-13 | USMNF8 | 2 | EA | 0 | ISO inlet piping- Drain | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 870 | 7000003197 | PL SSW06DO SS DROP OUT 6INW | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 918 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 3 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
61187003 | 508 | Deficiencies found on IAC#3 Service | S08 | Air Systems | 2020-04-05 | 2021-01-28 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11801C | No. 3 Air Compressor | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-06 | 121692000000 | 10 | 40 | 7000000034 | Assembly ,1623181080 | 2020-04-05 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12169170 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-04 | USMNF8 | 2 | EA | 0 | Fix Deficiencies found on IAC#3 Service | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 210 | 7000000103 | 3" Duplex Remington Floating Ball Valve | 2019-12-17 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 293 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN085 | Name 2 | Name 2 | 2019-09-05 | USSOLE | 17 | EA | 17 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7100 | 7000003343 | Angle, L6 X 4 X .3125, ASTM A36 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 968 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7290 | 7000003344 | Plate, .25" x 24" x 24", API 2H Gr. 50 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 987 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 570 | 7000003740 | Rosemount Vibrating Fork Liquid Level De | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 689 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN109 | Name 2 | Name 2 | 2019-12-17 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6470 | 1001816127 | GASW,CL300-600,316,GPH,NPS2 | 2020-02-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 811 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01282001 | Name 4 | Name 4 | 2020-01-29 | USDKFB | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4540 | 7000002629 | Elbow, 2", LR 90, S/40S, BW, ASME B16.9 | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 506 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 80 | 7000002596 | 5/8 X 3-1/2 (3-1/4 FTF) DOX PLTD STUD | 2020-04-01 | Received at Worksite | 2019-12-19 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 12027172 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-01 | USAWJB | 4 | EA | 4 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 250 | 7000002591 | 4548K227 1 NPT, 5" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 150 | 7000003852 | wisedry [ 5 LBS ] Silica Gel Beads Reusa | 2020-03-01 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG014 | Name 52 | USCRFI | 2020-02-04 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
60737085 | 508 | VPI test fail COT 5 STBD | S21 | Oil Treating | 2020-02-08 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-222 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-09-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-08 | 116406000000 | 20 | 20 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-04-28 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-10 | U182 | 8201 | Stones Main | ST KB B7F | 11640590 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-16 | USNSB4 | 1 | EA | 1 | Repair VPI XV-6635S-222 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 60 | 7000003852 | AmazonBasics Computer Speakers for Deskt | 2020-03-31 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | CAOA021320 | Name 12 | USRRIG | 2020-02-19 | USLFA4 | 1 | EA | 1 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60924104 | 508 | Missing Button for ESS. Gen. #2 LO diff. | S03 | Elect. Systems | 2020-04-28 | 2020-03-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.ES.PG.ZZZ-11101C | Essential Generator No. 3 Engine | 2020-01-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-28 | 118682000000 | 10 | 10 | 7000005901 | 50905-04E 3 WAY VALVE | 2020-04-28 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B7B | 11868168 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-17 | USMNF8 | 1 | EA | 1 | Replace Missing Button on ESS. Gen. #2 | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
60440621 | 508 | Replace Laydown Timber - MODs 15, 17, 19 | S40 | Cargo Handling | 2020-03-10 | 2020-06-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.LS | Loading Stations | 2019-08-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 113072000000 | 10 | 90 | 7000002583 | Hex Fixed Die, Metric, Die Thread Size: | 2020-03-10 | Received at Target Location |  | 2019-09-11 |  | U182 | 8201 | Stones Main | ST KB A1 | 11307214 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-06 | USAWJB | 1 | EA | 1 | Replace Laydown Timbers - MOD 15 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAOK RUSH WPOK | EXEC |  |  | PU KB A1
60737049 | 508 | Drive End Bearing Leaking Oil - BGCB | S04 | Gas Compress | 2020-03-25 | 2019-06-29 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.CM-77102B | HV Electric Mtr Booster Gas Compressor B | 2019-06-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-27 | 116406000000 | 10 | 50 | 7000000039 | Tubes of Ultra Blue | 2020-03-25 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | Lost by GOM DC | 11640554 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-09-05 | USRAR6 | 2 | EA | 2 | LOTO- BGC B and lube oil pump | REL GMPS PRC SETC | EXEC EOM MAGN MAOK RUSH WPOK | EXEC
60655411 | 508 | Discharge check valve passing | S08 | Air Systems | 2020-02-27 | 2019-09-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11805 | Top Up Start Air Compressor | 2019-11-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-27 | 115485000000 | 20 | 10 | 7000002646 | 6294-XXXX 00000 VALVE FOR NRV KV 65 | 2020-03-26 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11548488 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-22 | USNSB4 | 1 | EA | 0 | Replace Check Valve On Start Air Compres | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAOK WPOK | Deleted
61218667 | 508 | Replace Lifeboat Rations & Water | S15 | Life Saving | 2020-12-10 | 2021-02-17 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.LB | Lifeboats | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-12-11 | 122061000000 | 10 | 50 | 7000004662 | Datrex Emergency Food Ration, 2400kcal | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12206109 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-25 | USAWJB | 40 | EA | 0 | Replace Lifeboat Rations & Water | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 110 | 1002360864 | SB2N,B7,2H,UNC,7/8in,5in,DOXSTEEL | 2021-03-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Gas Riser Pressure Gauge | 11057838 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A176 | Entity 3 | USRRIG | 2018-08-06 | USSOLE | 10 | EA | 10 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6990 | 1001645331 | BLT HEX,A325,UNC,4in,3/4in,SERMAGARD | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 947 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 20 | 10 | 7000003852 | TEMCo 3/4" Female NPT Thread 3/4" Body P | 2020-01-28 | Received at Target Location |  | 2020-01-19 |  | U182 | 8201 | Stones Main | Stones | 11783572 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-03 | USMNF8 | 1 | EA | 1 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC
60517728 | 508 | Tilting Skillet Repair | S03 | Elect. Systems | 2020-02-04 | 2019-06-11 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.PDP-44310 | Galley Distribution Panel | 2019-03-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 113927000000 | 10 | 10 | 7000005901 | 3754076 MOTOR LA312200+0020004H FUTURA | 2020-02-04 | Received at Target Location |  | 2020-02-03 | 2020-02-09 | U182 | 8201 | Stones Main | Stones/ Lost by GOM DC | 11392705 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-09 | USNSB4 | 1 | EA | 1 | Repair Tilting Skillet | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN WPOK XGI | TECO |  |  | PU 02/13/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6310 | 7000002629 | Blind Flange, 10", 150#, RF, ASME B16.5, | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 739 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12271901 | Name 4 | Name 4 | 2019-12-26 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 730 | 1001807372 | FLWN,A105,CL150,40,NPS4 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 89 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 30 | 7000003852 | Arctic TumblersStainless Steel Camping & | 2021-05-26 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main | STONES | 11419724 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19BBSM1 | Name 11 | USKHU3 | 2019-10-15 | USLFA4 | 20 | EA | 20 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/01/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 60 | 7000002629 | 8" 300 # ASME B16.5 ASTM A182 GR F53 TAP | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 632 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3490 | 1002360864 | SB2N,B7,2H,UNC,7/8in,5in,DOXSTEEL | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 379 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118362 | 508 | 2020 Onshore Lab Analysis Services | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000000133 | GEN 99 GOODS,OTHER,LOWSPEND | 2021-02-20 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090699 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | HSESTO003 | Name 21 | USKHU3 | 2020-01-21 | USLFA4 | 2 | EA | 2 | 2020 Onshore Lab Analysis Services | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU CARLOS A. 02/07/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 40 | 1000832345 | PIPE MET,B42,160,6.5/8in | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | FT | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 860 | 7000003197 | TB SSWCHGC-HDW COMB HOLD DOWN/GUIDE CLAM | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 917 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 80 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7080 | 1000840560 | ANGL MTL,UNEQ,CS,20ft,4x3x1/4in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 966 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1070 | 7000003852 | LouisvilleLadder 10-Foot Fiberglass Step | 2021-03-31 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 107 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST20CG0146 | MarineForman | USCRFI | 2020-02-20 | USCDP7 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60739085 | 508 | 663UD-XV-299 Actuator & VPI test fail | S21 | Oil Treating | 2020-03-26 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-663UD-299 | Crude Oil O/O to COT 2 PS Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-29 | 116430000000 | 111 | 10 | 7000004212 | HAA-D05-RK A-SHIN HI VAL Co. Full Repair | 2020-06-14 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Stones | 11642981 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-11 | USNSB4 | 2 | EA | 2 | Repair Hydraulic Actuator Cargo Valve XV | REL GMPS PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61098380 | 508 | Biocide Chemical Inj for Cargos & Drains | S21 | Oil Treating | 2020-09-28 | 2020-11-27 | C.US.STO.FI.19.012.1230A | 508CI&E | US.WR508A.OT.SS.VE663-70000 | Cargo Tank Systems | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-09-28 | 120671000000 | 10 | 10 | 7000000052 | FULL STAINLESS STEEL TANK COVER ASSEMBLY | 2020-09-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 12067106 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI76 | Name 2 | Name 61 | 2019-12-23 | USSOLE | 12 | EA | 10 | Biocide Chemical Inj for Cargos & Drains | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 220 | 7000004751 | Keckley 3" 600# Floating Ball Valve | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN115 | Name 2 | Name 2 | 2020-01-30 | USSOLE | 4 | EA | 4 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 920 | 7000002591 | Neiko 00206A 1/2 Inch Drive Premium Brea | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 92 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 3 | EA | 3 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60507050 | 508 | STB Vent N2 snuffing system rusting | S06 | General | 2020-03-10 | 2019-02-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.ZZZ-12707 | Cargo Vent Stacks N2 Stuffing System | 2019-06-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-11 | 113805000000 | 10 | 30 | 7000000039 | 100=T5500=S=D=04=L=600PSI PRESSURE GAUGE | 2020-06-08 | Received at Target Location |  | 2019-06-07 |  | U182 | 8201 | Stones Main | ETA 11/21 | 11380546 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-04-09 | USNSB4 | 1 | EA | 1 | Replace Rusted Components Starboard Vent | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MAOK WPOK ZPMM | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 190 | 7000005901 | 247 110v, 16amp Straight Connector | 2020-03-03 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOELEC001 | Name 30 | USCRFI | 2020-02-04 | USLFA4 | 12 | EA | 12 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 370 | 7000002591 | 4452K433 Tee Connector, 3/8 NPT Female | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 37 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61102085 | 508 | FRC Lifeline discrepancies | S15 | Life Saving | 2020-03-05 | 2020-06-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2020-01-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-05 | 120714000000 | 10 | 20 | 7000004662 | Door Rope, HR-7 | 2020-03-05 | Received at Worksite | 2020-02-17 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 12071420 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-17 | USMNF8 | 2 | EA | 2 | FRC Lifeline discrepancies | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 190 | 1000718545 | PIPE MET,A106 GR B,BARE,80,4.1/2in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 21 | FT | 21 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 80 | 1001663814 | SHT PLT SLD MET,4x4ft,1/4in,A572-50 | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 1 | EA | 1 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 90 | 7000000039 | 32SFO SPLIT FLANGE KIT 2" CODE 61 | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 4 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 320 | 7000002591 | Belzona Spatulas | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 32 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 16 | EA | 16 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60172773 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-04-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.96T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 110086000000 | 10 | 30 | 7000002629 | Flange, 40mm, FF, Slip-on, JIS 16K, JIS | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008582 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081902 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 2 | EA | 2 | MOC missing steam trap | REL PCNF ESTC GMCO GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 250 | 7000002596 | M22" x 2 1/2" A193 B7 Cap Bolt, Xylan | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 10 | EA | 10 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 930 | 7000005901 | Hawke 501/453 UNIV B 1/2" NPT Brass | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 953 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI87 | Name 2 | Name 2 | 2020-02-08 | USSOLE | 4 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 140 | 1002360783 | SB2N,B7,2H,UNC,5/8in,3.75in,DOXSTEEL | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 640 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 16 | EA | 16 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5310 | 7000002596 | STUD BOLT, 7/8" X 5 1/2" ASTM A193 GRADE | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 592 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 132 | EA | 132 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3630 | 7000002596 | I-Rod, 5/8" x 8" Lg. | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Stones Solids Tie-in | 11179936 | 393 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161902 | Name 4 | Name 4 | 2019-10-17 | USGBI5 | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 200 | 7000002629 | FULL FACE BLEED RING, 6", 300#, RF, 1.5" | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 33 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3570 | 1001566525 | TUBING,SQUARE,A500-B,4x4x1/4in | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Stones Solids Tie-in | 11179936 | 387 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161902 | Name 4 | Name 4 | 2019-10-17 | USGBI5 | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60737088 | 508 | VPI test fail COT 5 STBD | S21 | Oil Treating | 2020-02-05 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-241 | Crude Oil to/from Fwd COTs On/Off Valve | 2019-09-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 116406000000 | 20 | 20 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-04-25 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-09 | U182 | 8201 | Stones Main | ST KB B7F | 11640593 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-16 | USNSB4 | 1 | EA | 1 | Repair VPI XV-6635S-241 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 970 | 1002309186 | SB2N,B8M CL2,8M,UNC,3/4in,5.00in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 113 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 8010 | 7000002603 | Flange Protectors for Flange, 2", SW, 15 | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 1086 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-28 | USSOLE | 6 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3660 | 7000002603 | GASKET,GARLOCK,STRESS SAVER XP,3in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 396 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61066906 | 508 | R/R UTI G21570,G21954,G23321,& G23322 | S21 | Oil Treating | 2020-06-02 |  | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.OT.SS | Storage/Sales | 2019-12-21 | WO | U100 | 72RE | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 2 Medium | 2020-06-02 | 120314000000 | 20 | 10 | 7000000065 | Shipping cost 128.36 | 2020-06-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12031383 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-04 | USMNF8 | 1 | EA | 0 | JM Test R/R UTI G23322 | REL ESTC PRC SETC | APPR | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6370 | 7000002596 | Stud, 5/8" x 6" LG., ASTM A193 Gr. B8M C | 2020-01-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 756 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01142001 | Name 4 | Name 4 | 2020-01-14 | USSOLE | 92 | EA | 92 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3190 | 7000002596 | BLT HEX,A325,UNC,3.3/4in,3/4in,HDG | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 349 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 22 | EA | 22 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2750 | 7000002629 | Blind Flange, 3", 300#, RF, ASME B16.5, | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 299 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60739067 | 508 | COT 4 Port IG netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127051 | COT 4 PS IG Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642943 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60797145 | 508 | Faulty Defrost component Galley Upright | S09 | Bldg & Qtrs | 2020-03-24 | 2019-12-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.BQ.ROOM-213 | Galley | 2019-08-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-24 | 117216000000 | 10 | 20 | 7000000086 | Accommodations Unit | 2020-03-24 | Received at Worksite | 2020-01-16 |  |  | U182 | 8201 | Stones Main | WHSE FLOOR | 11721560 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-15 | USNSB4 | 1 | EA | 1 | Replace Faulty Components Galley Upright | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM ZPVS | Kit Complete |  |  | ST1FLR 01/30/2020 GG
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 600 | 7000003852 | Wilton 20412 4 Pound Head, 12-Inch ... | 2020-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 60 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0011 | Name 29 | USRRIG | 2020-02-18 | USLFA4 | 8 | EA | 8 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60985323 | 508 | Port crane leaking exhaust pipe | S40 | Cargo Handling | 2020-03-24 | 2020-06-30 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZBE-87401 | Port Side Pedestal Crane Engine | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-27 | 119372000000 | 10 | 30 | 7000002596 | Exhaust bolts 5/8 x 2" long, SST | 2020-03-24 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A1B | 11937169 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-15 | USMNF8 | 8 | EA | 8 | Install Rigging on Port crane | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved |  |  | ST1A1B 02/18/2020 CMR
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 60 | 7000003739 | 1031438 BEARING,BALL,RADIAL,2.1654 ID | 2020-01-19 | Received at Worksite |  | 2020-02-16 | 2020-02-26 | U182 | 8201 | Stones Main | ST KB B2 | 12155706 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-28 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO |  |  | PU 02/16/20 AMW
60828048 | 508 | Emergency Kits for Lifeboats STONES | S15 | Life Saving | 2020-06-01 |  | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.LS.LB | Lifeboats | 2019-07-04 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 117583000000 | 10 | 50 | 7000002591 | Klein Model# 5180 Tool Bag Orange | 2020-06-01 | Received at Target Location |  |  | 2020-01-31 | U182 | 8201 | Stones Main | At CR 07/17 | 11758304 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-07-04 | USDHIE | 5 | EA | 5 | Stage all kits as directed by Leadership | TECO ESTC CSER GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO
61089158 | 508 | O/SI BGCA Discharge Valve Passing | S04 | Gas Compress | 2020-02-15 | 2020-01-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VABL-771085 | Compressor SDV Isolation Valve | 2019-12-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 8 User defined period | 2020-02-15 | 120564000000 | 10 | 30 | 7000004753 | 7/8" X 5-1/2" Teflon Coated Studs w/ Nut | 2020-02-15 | Received at Worksite | 2020-01-13 | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Stones | 12056365 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-24 | USAWJB | 24 | EA | 24 | Replace VABL-771085 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 840 | 1002064539 | BLT HEX,A325,UNC,5/8in,4in,SERMAGARD | 2020-01-12 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 84 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08051901 | Entity 3 | Name 59 | 2019-08-05 | USDKFB | 74 | EA | 74 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60708311 | 508 | Faulty check valve on FW Gen # 3 | S18 | Water Systems | 2020-04-22 | 2019-10-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.VACH-122504 | Pump Discharge Check Valve | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-22 | 116082000000 | 10 | 20 | 7000005901 | P/N: STANDARD 3/4 TEFLON COATED BOLTS & | 2020-04-22 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 11608239 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2020-01-23 | GW982959 | 16 | EA | 0 | LOTO- Electric motor FW#3 | REL ESTC GMPS PRC SETC | APPR MAGN WP ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 560 | 7000002629 | Cap 1 1/4", STD, 3000#, SW, ASTM A234 Gr | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 56 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 930 | 1002064480 | BLT HEX,A325,UNC,3/4in,3.1/4in,SERMAGARD | 2020-02-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F13 | 11581207 | 93 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09191901 | Entity 3 | Name 59 | 2019-09-19 | USSOLE | 5 | EA | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 110 | 7000002591 | 4548K171 1/2 NPT, 1-1/8" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60548443 | 508 | Hawser reel anchor link arm | S19 | Marine Systems | 2020-04-21 | 2020-09-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.PS.ZZZ-88630 | Hawser Storage Reel | 2019-10-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114265000000 | 10 | 10 | 7000000109 | P/N: Hawser Reel Anchor Link Arm & Hawse | 2020-04-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 3/30/20 | 11426455 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2019-10-24 | GW982959 | 1 | EA | 0 | LOTO Hawser reel | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM ZPVS | Approved
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 180 | 7000003852 | SanDisk 256GB Extreme SDXC UHS-I Card - | 2020-12-31 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 53 |  | 2020-02-24 | USAWJB | 2 | EA | 2 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61120838 | 508 | O/SI MGCB LT-926D Range Failure | S04 | Gas Compress | 2020-04-11 | 2020-02-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.LCV-77131D-926 | 3rd Stage Scrubber D Level Control Valve | 2019-12-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-11 | 120938000000 | 10 | 10 | 1002408872 | TRDP,YOKOGAWA,EJA110EJMSWG924EBSF2D1N4 | 2020-04-11 | Received at Worksite |  | 2019-12-27 |  | U182 | 8201 | Stones Main | STA4A | 12093763 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2019-12-27 | USAWJB | 1 | EA | 1 | Replace MGCB LT-926D | REL PCNF PRT GMPS PRC SETC | EXEC MAOK WPOK | EXEC
60698903 | 508 | Water Clarifier Inj Pump B PSV-044B Fail | S10 | Chem Injection | 2020-03-17 | 2020-04-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.CI.PSV-12821B-044 | B Pump H2 Discharge Press Safety Valve | 2019-04-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-03-17 | 115974000000 | 10 | 10 | 1002404535 | BALL VALVE,BV1116FMP3710EV915KF+,BIFOLD | 2019-07-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones FPSO | 11597439 | 1 | 19 | Modified SP1 - w/o STR & STO / item ctg | L |  |  |  | Name 3 |  | 2019-04-13 | USMNF8 | 1 | EA | 0 | Water Clarifier Inj Pump B PSV-044B Fail | REL ESTC GMPS PRC SETC | APPR MAXX WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5950 | 7000002662 | Pipe, 6", SMLS Class 700, 90/10 CuNi All | 2019-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 693 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 10 | FT | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3200 | 7000002596 | BLT HEX,A325,UNC,4.25in,3/4in,HDG | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 350 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3830 | 7000002629 | Bolted Shoe Type Support for 3" Pipe, Pe | 2019-11-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 414 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST10241901 | Name 4 | Name 4 | 2019-10-25 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6280 | 1001676255 | PIPE MET,A106 GR.B,STD,10in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 736 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12271901 | Name 4 | Name 4 | 2019-12-26 | USSOLE | 20 | FT | 21.1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 90 | 7000004213 | KE35/12 SASAKURA KE35 P/N 12 UNION JOINT | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 20 | 7000000101 | 1" Elbow Stainless Steel 304 Fitting 90 | 2020-04-29 | Received at Worksite | 2019-11-27 | 2020-01-29 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772908 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 5 | EA | 5 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO |  |  | ST1A1C 01/22/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5880 | 7000003344 | Plate, 1/4" x 24" x 24", ASTM A240 UNS S | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 682 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 380 | 1000709172 | ANALOG INPUT MODULE,1756IF16,ALLENB | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 424 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1910 | 1001641854 | FLG BLIND,A105,RF, CL150,4in,W/TAP,1/2in | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 213 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3470 | 1001816205 | GASW,CL150,316,GPH,NPS12 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 377 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 10 | 10 | 7000003852 | COMOK Hydraulic Grease Fitting Kit, 10Pc | 2020-05-16 | Received at Target Location |  | 2020-01-19 |  | U182 | 8201 | Stones Main | Issued | 11783572 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 14 | USNSB4 | 2019-08-10 | USMNF8 | 2 | EA | 2 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC |  |  | PU KIM C
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7520 | 7000002591 | Cold Shut, 3/16" Forged Steel | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1010 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 270 | 7000002591 | ½” drive ratchet wrench 15” Proto. Part | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 27 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0140 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 560 | 7000006081 | Draka Wide Mouth Wire Rope Calipers with | 2020-02-21 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 56 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOMEB214A | Name 3 | USJRF5 | 2020-02-16 | USLFA4 | 2 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 140 | 7000002629 | Concentric Reducer, 3" x 2", S/80S, BW, | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 110 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 310 | 7000006192 | Parker Monoflange Valve MFY200H32T1500F | 2020-04-15 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 43 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-18 | USSOLE | 8 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 40 | 7000005901 | M20 Serrated Washer | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780965 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI77 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60683738 | 508 | O/SI SDV-66202-870 Failed to Close | S22 | Prod Gathering | 2020-04-02 | 2019-05-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.SDV-66202-870 | 2nd Stg Separator Prod Wtr Shutdown Vlv | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-02 | 115806000000 | 30 | 20 | 1001816210 | GASW,316/316L,GPH,CL150,NPS3 | 2020-04-02 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB D3 | 11580631 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-04-19 | USNSB4 | 2 | EA | 2 | Replace SDV-66202-870 | REL ESTC GMCO GMPS PPRT PRC SETC | APPR EOM MAGN MAOK WP | EXEC |  |  | PU Aaron 07/08/2019
61179029 | 508 | SUP Engine Only Starts on Both Batteries | S15 | Life Saving | 2020-03-28 | 2020-07-27 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 121603000000 | 10 | 10 | 7000005811 | Marine Batteries,12v Odyssey 34/78 | 2020-03-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12160291 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-03 | USMNF8 | 2 | EA | 0 | Engine Only Starts on Both Batteries | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 700 | 7000002591 | 4452K241 Cap, 1 NPT | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 70 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60749169 | 508 | TFR-44301B cooling fin leaks. | S03 | Elect. Systems | 2020-05-01 | 2019-07-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.TFR-44301B | Essential Transformer | 2019-10-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-05-08 | 116544000000 | 10 | 10 | 7000003946 | FR3 Transformer Oil | 2020-05-01 | Not Shipped |  | 2020-02-22 |  | U182 | 8201 | Stones Main | Stones | 11654425 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAWJB | 2020-02-19 | USRAR6 | 6 | DR | 0 | Stage All Materials & Tote Tanks To Main | REL PCNF PRT PRC SETC | APPR MAGN RUSH WP | EXEC
61085450 | 508 | Heavily Corroded Casing / Seal Bolts | S18 | Water Systems | 2020-02-14 | 2020-05-23 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12215 | Auxiliary Cooling Pump | 2020-01-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-14 | 120521000000 | 10 | 10 | 7000000111 | Bolts for 61085450 | 2020-02-14 | Received at Worksite | 2020-01-21 | 2020-02-03 | 2020-02-20 | U182 | 8201 | Stones Main | ST KB A5 | 12052102 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-04 | USAMH7 | 12 | EA | 12 | M Furrow Replace Casing/Seal Bolts | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 2/5/2020 JH GG
61184264 | 508 | broken discharge pulsation damper 12869 | S10 | Chem Injection | 2020-06-20 | 2021-01-26 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CI.MBL-12869 | D Pump Discharge Pulsation Damper | 2020-02-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-06-20 | 121654000000 | 10 | 30 | 7000000103 | PAR EPD100-0-0205, Discharge Pulsation d | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12165420 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-11 | USMNF8 | 1 | EA | 0 | broken discharge pulsation damper 12869 | REL ESTC GMPS PRC SETC | APPR MAGN WP ZPMM | Approved
61070410 | 508 | Jockey Pump B Disch check valve VACH-331 | S13 | Fire Protect | 2020-04-01 | 2019-12-23 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.VACH-331017 | SW Jockey Pump to Foam Rm Outlet Valve | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 120355000000 | 10 | 10 | 7000003464 | 4" WAFER CHECK VALVE, 4-H15BAPF-9 | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12035458 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-05 | USMNF8 | 2 | EA | 0 | Replace check valve VACH-331017 | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
61200672 | 508 | Stones Small Civil Projects 2020 |  |  | 2020-12-31 |  | P.US.STO.NF.20.009.7240A | GENERIC |  |  | 2020-02-11 | WO | U100 | GEN | US01 | P16 | [5 empty] | 3 Low | 2020-12-31 | 121848000000 | 10 | 10 | 7000002603 | Gasket, 1", Flat Ring, Compressed Inorga | 2020-02-28 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G97 | 12184838 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST02242002 | Name 4 | Name 60 | 2020-02-27 | USSOLE | 3 | EA | 0 | Stones Small Civil Projects 2020 | REL ESTC PRC SETC | APPR | Approved
61049139 | 508 | HP/LP Piston Failure | S08 | Air Systems | 2020-02-12 | 2020-01-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11804A | Start Air Compressor No. 1 | 2020-02-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-14 | 120119000000 | 10 | 50 | 7000005901 | 3834 BEARING SHELL U/L 220-300 | 2020-02-12 | Received at Worksite | 2020-02-13 | 2020-02-13 |  | U182 | 8201 | Stones Main | ST KB A3 | 12011865 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-13 | USMNF8 | 4 | EA | 4 | Rebuild Start Compressor #1 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAKD MAXX RUSH WPOK | EXEC |  |  | ST1A1C 02/07/2020 CMR
60507054 | 508 | PBE12216B Suction Valve Actuator Failing | S18 | Water Systems | 2020-04-01 | 2019-02-05 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.122-8V | Pump Suction Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-01 | 113806000000 | 10 | 10 | 7000000070 | DT-12 DYNATORQUE Model: DT-12 with 14" H | 2020-04-01 | Received at Worksite |  | 2019-04-16 |  | U182 | 8201 | Stones Main | Wrong Actuator | 11380553 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | engn rm Entity 3 | USNSB4 | 2019-01-10 | USNSB4 | 1 | EA | 1 | Replace #2 COPT Pump Suction Valve | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK | EXEC |  |  | PU Aaron 4/13/2019 CR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7480 | 7000002596 | Lag Bolt, HH 5/8" x 3-1/2" long, 316L SS | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1006 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-15 | USSOLE | 200 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 160 | 1001768450 | ELB BW,WPB,90DEG,LR,XXS,NPS3 | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4380 | 1002058423 | WASHER,LOCK,F436,SERMAGARD,3/4in | 2019-11-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 490 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11131902 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 78 | EA | 78 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4590 | 1001759324 | SB2N,A193B8MCL2,UNC,4.5in,3/4in | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 511 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 100 | EA | 100 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 500 | 7000003197 | Brady Part Number M21-250-C-342 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 842 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 3 | EA | 3 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2880 | 7000002629 | Elbow, 3", LR 90, S/40S, BW, ASME B16.9 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 318 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5830 | 1002047398 | STL SECT MAR,BEAM,8.110in,4.015in,20ft | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 677 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6260 | 7000002603 | Flange Protectors, 2", SW, 150#, FF | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 724 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 34 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4180 | 7000002596 | 10" U-Bolt (Galv.) w/(6) Nuts (Galv.) an | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 468 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 35 | EA | 35 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 980 | 7000005901 | 3M Part No. FP301-1-48"- White-5Pcs | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 958 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI87 | Name 2 | Name 2 | 2020-02-08 | USSOLE | 1 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 980 | 7000002596 | STUD BOLTS, 7/8" DIA. X 7 1/2" LONG, AS | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 114 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60737100 | 508 | VPI & actuator test fail Slop Port | S21 | Oil Treating | 2020-02-10 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SW.XV-663SP-678 | Produced Water/Slop Tank Decant Line Vlv | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-10 | 116406000000 | 20 | 20 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-04-30 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7F | 11640605 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-16 | USNSB4 | 1 | EA | 1 | Repair VPI XV-663SP-678 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 450 | 7000000098 | 1" RENEGADE BLUE EACH 1" X 50FT CHEMICAL | 2020-03-16 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 45 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOET00120 | Name 3 | USCRFI | 2020-02-09 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1 FLR 2/24/2020 GG
61057325 | 508 | Faulty level trans LT-77121A-917A MGC A | S04 | Gas Compress | 2020-06-02 | 2019-12-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.MBF-77121A | 2nd Stage Suction Scrubber | 2019-11-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Complete by 2 Weeks | 2020-06-04 | 120203000000 | 30 | 10 | 7000000065 | ZT4510.70 Level transmitter | 2020-06-02 | Not Shipped |  | 2020-02-08 |  | U182 | 8201 | Stones Main | STONES | 12020299 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-11-19 | USMNF8 | 1 | EA | 0 | Replace level trans LT-77121A-917A | REL PRT GMPS PRC SETC | APPR MAGN WPOK ZPMM | EXEC
61050323 | 508 | Hydraulic hose outer layer damaged | S21 | Oil Treating | 2020-03-06 | 2019-12-13 | O.US.STO.STO.005.724FP | 508DANOS | US.WR508A.OT.SS.ZZZ-66410 | Offloading Hose Reel | 2019-11-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 4 Complete by 4 Weeks | 2020-03-06 | 120124000000 | 20 | 20 | 7000000098 | 1/2" X 6-1/2'ft Hose, 4300 PSI | 2020-03-06 | Received at Worksite |  | 2019-12-21 |  | U182 | 8201 | Stones Main | Issued | 12012401 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 54 |  | 2019-11-15 | USMNF8 | 1 | EA | 1 | Replace Hydraulic hose | REL PCNF PRT GMPS PRC SETC | SCHD MAGN MAOK WPOK | EXEC |  |  | PU CLAUDIU
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 70 | 7000003739 | 298970R1 RING,RETAINING,SPIRAL | 2020-01-19 | Received at Worksite |  | 2020-02-16 | 2020-02-26 | U182 | 8201 | Stones Main | ST KB B2 | 12155706 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-28 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO |  |  | PU 02/16/20 AMW
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 110 | 7000003684 | UNCOATED CARBIDE-TIPPED STEEL DRILL BIT | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 3 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60526908 | 508 | TG-77130A-311A BROKEN | S04 | Gas Compress | 2020-05-05 | 2019-12-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.TG-77130A-311A | CM Inlet Temperature Gauge | 2019-05-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-05-05 | 114027000000 | 10 | 10 | 7000000062 | TG-12402-117 THI-100-A+AMX TEMPERATURE G | 2020-05-05 | Received at Worksite | 2019-10-29 |  |  | U182 | 8201 | Stones Main | MMR316 | 11402692 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-05-28 | USNSB4 | 1 | EA | 1 | Replace Produced Water Temperature Gauge | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD WPOK ZPMM | Kit Complete
60828048 | 508 | Emergency Kits for Lifeboats STONES | S15 | Life Saving | 2020-06-01 |  | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.LS.LB | Lifeboats | 2019-07-04 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 117583000000 | 10 | 20 | 7000002591 | Dorcy Industrial Rechargeable Lantern | 2020-06-01 | Received at Target Location |  |  | 2020-01-31 | U182 | 8201 | Stones Main | Issued | 11758304 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Entity 5 |  | 2019-07-04 | USDHIE | 5 | EA | 5 | Stage all kits as directed by Leadership | TECO ESTC CSER GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO |  |  | PU 10/31/19 J WELBORN
60675078 | 508 | O/SI PV Bulkhead Main Steam Stop Bypass | S17 | Steam/Hot H2O | 2020-04-25 | 2019-09-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.115-332V | Isolation Valve Bypass Valve | 2019-12-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-25 | 115709000000 | 30 | 20 | 7000004211 | FLANGE PACK flange pack to include all f | 2020-07-09 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11570945 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-02 | USNSB4 | 1 | EA | 0 | Job Lead, Replace 1" Globe Valve SW.115- | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 10 | 7000003739 | 901722440 LOCKNUT,BEARING | 2020-01-19 | Received at Worksite |  | 2020-02-16 | 2020-02-26 | U182 | 8201 | Stones Main | ST KB B2 | 12155706 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-28 | USAWJB | 2 | EA | 2 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO |  |  | PU 02/16/20 AMW
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 30 | 7000002591 | 3" 2500# Hydro/Paddle Blind, CS 516 Gr-7 | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 1 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
60172773 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-04-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.96T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 110086000000 | 10 | 20 | 7000002629 | Elbow, 40mm, LR 90°BW, JIS B2312, PS410 | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008582 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081902 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 1 | EA | 1 | MOC missing steam trap | REL PCNF ESTC GMCO GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 240 | 7000002596 | 5/8" x 1-1/4" Hex Head Machined Bolts A3 | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 24 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 12 | EA | 12 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
61165404 | 508 | Install Needle Valve on PG-33110-731 | S13 | Fire Protect | 2020-03-05 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33110-731 | Firewater Lift Pump Outlet Press Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-05 | 121447000000 | 10 | 20 | 7000003196 | OA,US,SWAGELOK,FITTINGS,EA | 2020-03-05 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144688 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 1 | EA | 1 | Install Needle Valve on PG-33110-731 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 910 | 1001816207 | GASW,CL150,316,GPH,NPS8 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 107 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4770 | 7000002596 | Bolt, 3/4" x 3" LG, ASTM F3125 Gr. A325 | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 529 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 82 | EA | 82 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4820 | 1000718546 | PIPE MET,A106-B,BARE,40,4.1/2in | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 543 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 140 | FT | 147 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4320 | 7000003344 | Plate, 1/4" x 24" x 24", ASTM A240 UNS S | 2019-11-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 484 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11131902 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 70 | 7000002644 | 4" 150# RF FP WKM Floating Ball Valve | 2019-02-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN038 | Name 2 | Name 2 | 2018-11-28 | USSOLE | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4740 | 7000002591 | Neoprene Strips, 1/8" thick x 3 1/2" wid | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 526 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 58 | EA | 58 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60636182 | 508 | OEM recommends elbow replacement | S08 | Air Systems | 2020-02-25 | 2019-04-25 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.HBG-11853A | No. 1 Air Compressor Oil Separator | 2019-10-30 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-25 | 115265000000 | 10 | 20 | 7000000034 | Elbow P/N 0560 0200 30 | 2020-02-25 | Received at Worksite | 2020-02-05 | 2020-02-20 |  | U182 | 8201 | Stones Main | ST KB A3 | 11526532 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-30 | USRAR6 | 4 | EA | 4 | Replace elbow on compress 1,2,3,4 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK RUSH WPOK | EXEC |  |  | PU 02/19/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1160 | 1002047397 | (Please provide 40' joints) | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 132 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061802 | Name 2 | Name 2 | 2018-12-07 | USSOLE | 40 | FT | 40 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 770 | 7000002629 | FLANGE, 12", 300#, RF, WN, ASTM A182 GR | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 93 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 19 | EA | 19 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61023509 | 508 | Grating on green mile needs replacing. | S19 | Marine Systems | 2020-06-01 | 2019-12-25 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.HG | Handrails, Stairways, Grating | 2020-02-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-06-02 | 119822000000 | 10 | 60 | 1002058431 | NUT,A563-DH,HEXAGONAL,UNC,1/2,SERMAGARD | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G87 | 11982221 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02172001 | Name 4 | Name 60 | 2020-02-19 | USSOLE | 36 | EA | 36 | Grating on green mile needs replacing. | REL ESTC PRC SETC | APPR EOM MAGN MANX WPOK ZPMM | Approved
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 40 | 7000002596 | M10 X 30 MM SOCKET HEAD CAPSCREW (ASTM | 2020-04-01 | Received at Worksite | 2019-12-19 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 12027172 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-01 | USAWJB | 10 | EA | 10 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
60888917 | 508 | Faulty Temp Probe on Swivel | S19 | Marine Systems | 2020-04-11 | 2020-02-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89650 | Electrical Power & Signal Swivel | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-11 | 118279000000 | 20 | 20 | 7000005901 | RP115 DRAIN TAP FOR IND & MARINE ATMOSPH | 2020-06-10 | Ready for Shipment after Kitting | 2019-12-09 | 2019-12-21 |  | U182 | 8201 | Stones Main | ST KB B4 | 11827852 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-23 | USNSB4 | 1 | EA | 1 | Replace Temperature Safety Transmitter O | REL ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MAKD RUSH WPOK | EXEC |  |  | PU WPT ST KB B4
60739061 | 508 | COT 4 S HC Netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127021 | COT 4 SB HC Main Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642937 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60935788 | 508 | O/SI Passing Loading Valve COT 3P | S21 | Oil Treating | 2020-02-11 | 2020-08-24 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-663UD-297 | Crude Oil O/O to COT 3 PS Valve | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-11 | 118802000000 | 20 | 10 | 1002400499 | SEAT,427 AC001-12"-3,ISLIP-FC | 2020-02-11 | Not Shipped |  | 2020-01-15 |  | U182 | 8201 | Stones Main | ST KB D5 | 11880243 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-01-08 | USNSB4 | 1 | EA | 0 | Rebuild Loading Valve | REL PRT PRC SETC | EXEC RUSH WPOK | Deleted
60628814 | 508 | Pitstop Damaged/Leaking Bulkhead fitting | S19 | Marine Systems | 2020-02-24 | 2019-04-24 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-89007A | Stabplate #4 Up Signal/Optical Connector | 2019-07-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-24 | 115186000000 | 10 | 20 | 7000003196 | BH16MF20 | 2020-02-24 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B7A | 11518591 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-30 | USAWJB | 1 | EA | 1 | Replace Bulkhead Fitting | REL ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MAOK RUSH WPOK | EXEC |  |  | STKBB7A 2/3/20 GG
61114758 | 508 | O/SI SDV-77163A-904A Passing By | S04 | Gas Compress | 2020-02-15 | 2020-06-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.SDV-77163A-904 | 2nd Stg Compressor Out Gas Shutdown Vlv | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-15 | 120863000000 | 10 | 60 | 7000002591 | Global Industrial™ Folding Floor Crane w | 2020-02-04 | Received at Target Location | 2020-01-27 | 2020-02-07 | 2020-02-18 | U182 | 8201 | Stones Main | SDV-77163A-904A | 12086293 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A385 | Name 2 | Name 59 | 2020-01-27 | USSOLE | 1 | EA | 1 | Replace SDV-77163A-904A | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 80 | 7000002591 | 4548K155 3/8 NPT, 3" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1300 | 7000002596 | BLT HEX,A325,UNC,6n,5/8in | 2020-05-14 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | Crane Access Platform | 11581207 | 130 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A372 | Name 2 | Name 59 | 2019-12-09 | USSOLE | 56 | EA | 56 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 20 | 20 | 7000004211 | Plug, Hex Head 67, 20099-163 | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A2B | 11762536 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 1 | Replace pump cover on Jockey Pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved |  |  | ST1A2B 02/18/2020 CMR
60629364 | 508 | GT-5 Replace air inlet button plugs | S03 | Elect. Systems | 2020-03-15 | 2020-02-21 | O.US.STO.STO.005.724FP | GGTSSLTB | US.WR508A.ES.PG.LAN-11150 | Gas Turbine Power Generation Package 5 | 2019-07-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-15 | 115191000000 | 10 | 10 | 7000003739 | Conduit Plug PN 1739574 | 2020-03-15 | Received at Target Location |  | 2019-10-15 |  | U182 | 8201 | Stones Main | Dist to Solar Tech | 11519120 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 48 | USAWJB | 2019-07-17 | USRAR6 | 4 | EA | 4 | GT-5 Replace air inlet button plugs | REL PRT GMPS PRC SETC | EXEC MAGN MAOK WPOK | EXEC |  |  | PU AARON 09/29/2019 CMR
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 240 | 7000002596 | Stud, 3/4" x 6 3/4" LG., ASTM A193 Gr. B | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 120 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 9 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 70 | 7000000133 | 637167 Nike DriFit Vertical Mesh Polo in | 2019-12-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Turritella TDR Improvemen | 11545759 | 86 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO1127191 | Name 2 | Name 2 | 2019-12-03 | USSOLE | 13 | EA | 13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 270 | 7000002591 | Cuisinart SS-20 Coffee Center 10-Cup The | 2020-02-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 27 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 1 | EA | 1 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 660 | 7000002596 | Bolt, 1" x 3 3/4" LG, ASTM F3125 Gr. A32 | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 66 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 14 | EA | 14 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60797147 | 508 | A/C Condenser Intermittent Operation | S40 | Cargo Handling | 2020-03-24 | 2019-08-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-07-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-27 | 117216000000 | 20 | 20 | 7000000057 | Suction hose Visionaire; Pt# 35-7070-004 | 2020-03-24 | Received at Worksite |  | 2019-10-17 |  | U182 | 8201 | Stones Main | ST KB c5 | 11721562 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-17 | USMNF8 | 2 | EA | 2 | Hoist Up Materials/Tools. Secondary Ass | REL PCNF PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | ST1A6C 01/29/20 GG
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 560 | 7000002591 | 4452K258 Straight Reducer, 3/4 x 1/2 NP | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 56 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1140 | 1001573042 | SHT PLT SLD MET,4x4in,1/2in | 2020-04-15 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F64 | 11581207 | 114 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111901 | Name 4 | Name 59 | 2019-11-12 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1270 | 1000671260 | SUPER METAL,POLYMER,BELZONA,1111,Gry,1kg | 2020-05-07 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G04 | 11581207 | 127 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031901 | Name 4 | Name 59 | 2019-12-04 | USSOLE | 1 | KG | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS2 | 30 | 1000710906 | ADIMC,SWAGELOK,SS-12-T,JGF,3/4in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Seawater Eductor | 11545759 | 66 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI59 | Name 2 | Name 2 | 2019-10-23 | USSOLE | 2 | EA | 2 | Shop Order Sheets - I&E Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 10 | 7000006081 | 304-050X3 PIPE NIPPLE 1/2 X 3'' LG.S/S | 2020-03-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-13 | USAWJB | 4 | EA | 0 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
60246898 | 508 | Damaged Hoses on stab plate #2 | S19 | Marine Systems | 2020-03-10 | 2019-07-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89003A | Umb Fluid #2 Upr Stabplate FL Connector | 2019-10-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-03-11 | 110924000000 | 20 | 40 | 7000000101 | ASSY-25/4PPA, 18FT 11IN OAL ALL SS TYPE | 2020-04-29 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ETA 12/18 | 11092386 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-07 | USNSB4 | 2 | EA | 2 | LO/TO Perform Isolations *2-Man Rule In | REL PRT GMPS PRC SETC | APPR EOM MAGN MAOK WP ZPMM | Approved
60985334 | 508 | O/SI VABF-122008 passing | S18 | Water Systems | 2020-03-10 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VABF-122008 | Filter Backwash Water Outlet Valve | 2019-10-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-10 | 119372000000 | 20 | 20 | 7000004211 | PAINT-SHELL SHELL PAINT SPECIFICATIONS | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937180 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-10-29 | USNSB4 | 1 | EA | 0 | Replace VABF-122008 Butterfly Valve MAJ- | REL ESTC GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 110 | 1000055943 | COIMC,SWAGELOK,SS81018,1/2x1/2NPT | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 5 | EA | 5 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4370 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-11-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 489 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11131902 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 74 | EA | 74 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 190 | 7000002662 | 1" x 0.065 317L SMLS Uncoated Tubing | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 260 | FT | 260 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2950 | 7000002629 | Flange, 2", 300#, RFWN, S/160 Bore, ASME | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 325 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 1 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60973122 | 508 | MGC-B 3rd Stg Bridle Removal | S04 | Gas Compress | 2020-04-18 | 2020-09-25 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-10000 | Main Gas Compression System Train B | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-19 | 119235000000 | 10 | 60 | 7000002603 | R24 Ring Joint Gaskets CPlated Oval | 2020-02-11 | Received at Target Location | 2020-01-06 | 2020-01-06 |  | U182 | 8270 | Danos - Amelia | 3RD Stage Suction | 11923512 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A361 | Name 2 | Name 59 | 2019-10-21 | USSOLE | 10 | EA | 10 | MGC-B 3rd Stg Bridle Removal MOC78183 | REL PRT GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU WPT AMW 11/30/19
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 240 | 7000003197 | Panduit MMP350W38-C316 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 24 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 100 | EA | 100 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5610 | 7000002629 | Concentric Reducer, 3" x 2", S/10S x S/4 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 655 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 60 | 7000005901 | M20 Locknut | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780965 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI77 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 160 | 7000003852 | Grilljoy 20PCS Heavy Duty BBQ Grill Tool | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
61134552 | 508 | Helideck foam monitor upgrade MOC 80280 | S13 | Fire Protect | 2020-05-27 | 2020-07-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF331-12100 | FiFi Helideck Foam System | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-27 | 121087000000 | 10 | 80 | 7000002603 | Flange Protectors 3", 150#, FF | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H04 | 12108694 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST03022001 | Name 4 | Name 60 | 2020-03-03 | USSOLE | 2 | EA | 0 | Helideck foam monitor upgrade MOC 80280 | REL ESTC PRC SETC | APPR MAGN MANX WP | Approved
60921879 | 508 | #1 Ballast pump bulkhead seal/gland temp | S19 | Marine Systems | 2020-02-20 | 2019-10-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.BB.TT-11201A-253 | Pump Rm Bulkhead Temperature Transmitter | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-20 | 118663000000 | 20 | 10 | 7000005901 | B2100 PT100TP-S-254 TEMPERATURE TRANSMIT | 2020-05-20 | Received at Worksite | 2020-01-17 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B6 | 11866310 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-01 | USNSB4 | 2 | EA | 2 | Replace Rodax Temperature Transmitter On | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK RUSH WPOK | EXEC |  |  | ST1A6B 02/3/20 GG
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 90 | 7000000133 | Lapco FR Long Sleeve Henley in Khaki wit | 2019-12-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Turritella TDR Improvemen | 11545759 | 88 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO1127191 | Name 2 | Name 2 | 2019-12-03 | USSOLE | 34 | EA | 34 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 210 | 7000002596 | 5/8” x 3-1/4” Stud Bolt ASTM A193 GR B8M | 2019-10-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | STONES | 11545759 | 47 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 15 | Name 15 | 2019-10-18 | USABCE | 16 | EA | 16 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 510 | 7000003852 | Crucial MX500 500GB 3D NAND SATA 2.5 Inc | 2021-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 51 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN012620A | Name 3 | USRRIG | 2020-02-12 | USLFA4 | 5 | EA | 5 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 130 | 7000004213 | Customs IMPORT DUTIES/TAX/CUSTOMS BROKER | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 13 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 70 | 7000002591 | 4548K153 3/8 NPT, 2" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 110 | 7000002591 | Lion Post Consumer Recycled Plastic Clip | 2020-02-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200006 | Name 10 | USRRIG | 2020-01-21 | USLFA4 | 2 | EA | 2 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60739058 | 508 | COT 3 Stbd HC Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127013 | COT 3 SB HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642934 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 490 | 7000002591 | 4452K175 Bushing Adapter, 1 Male x 1/2 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 49 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61118331 | 508 | 2020 Chemical Order - Engine Room | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 40 | 7000003458 | HSCV19021A.32B | 2020-01-29 | Received at Target Location |  | 2020-01-10 |  | U182 | 8201 | Stones Main | CPORT | 12090688 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200004A | Name 40 | USRRIG | 2020-01-16 | USLFA4 | 1000 | GLL | 1000 | 2020 Chemical Order - Engine Room | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2910 | 7000002629 | Elbow, 2", LR 90, S/40S, BW, ASME B16.9 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 321 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 400 | 7000003197 | 501/453 UNIV C2 1-1/2" Brass | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 832 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 18 | EA | 18 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 90 | 7000002629 | FLANGE, 6", 300#, RF, WN, ASTM A182 GR. | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6240 | 7000002603 | Flange Protectors, 6", SO, 150#, FF | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 722 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 800 | 7000003197 | SSW606VFCVO9012 SS VTD. FLNG CVR 6INW OV | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 911 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 2 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 40 | 7000002591 | ½ x 2 Line 316SS Tubing Straps | 2019-11-27 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI67 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 25 | EA | 25 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6300 | 1001807375 | FLWN,A105,CL150,40,NPS10 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 738 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12271901 | Name 4 | Name 4 | 2019-12-26 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 610 | 7000002629 | WELD-O-LET, 12" X 4" (4" S/40/STD (0.237 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 77 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6920 | 7000003344 | Plate, 1/2" x 24" x 24", ASTM A572 Gr. 5 | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 940 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 290 | 1001763952 | SB2N,A193-B7,CTD,UNC,10in,1in | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 42 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 740 | 7000003197 | SSTF04SHB9012SS 4INW CHNL TRAY H90 12INR | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 905 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 8 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2510 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2019-04-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 273 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04021905 | Name 2 | Name 2 | 2019-04-03 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4940 | 7000002629 | FLANGE, 2" 150 LB RFWN SCH 40 ASTM A105 | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 555 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 330 | 7000003852 | DEWALT Titanium Drill Bit Set, Pilot Poi | 2020-12-07 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 33 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES11 |  |  | 2019-11-11 | USABCE | 2 | EA | 2 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 30 | 7000002596 | M10 X 30 MM HEX HEAD BOLT | 2020-04-01 | Received at Worksite | 2019-12-19 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 12027172 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-01 | USAWJB | 10 | EA | 10 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
61165407 | 508 | Install Needle Valve on PG-33120-732 | S13 | Fire Protect | 2020-03-10 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33120-732 | SW Booster Pump Inlet Pressure Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-10 | 121447000000 | 10 | 20 | 7000003196 | Stainless Steel Integral Bonnet Needle V | 2020-03-10 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144692 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 1 | EA | 1 | Install Needle Valve on PG-33120-732 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 120 | 7000003852 | WJPILIS Smart Watch Touchscreen Bluetoot | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 380 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 38 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 70 | EA | 70 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 320 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 32 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 18 | EA | 18 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61114758 | 508 | O/SI SDV-77163A-904A Passing By | S04 | Gas Compress | 2020-02-15 | 2020-06-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.SDV-77163A-904 | 2nd Stg Compressor Out Gas Shutdown Vlv | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-15 | 120863000000 | 10 | 40 | 7000004751 | 8" 300 RF Flex Gaskets,,,,,,,, | 2020-02-15 | Received at Worksite | 2020-01-23 | 2020-02-07 | 2020-02-18 | U182 | 8201 | Stones Main | ST KB D7 | 12086293 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 59 | 2019-12-27 | USAWJB | 2 | EA | 2 | Replace SDV-77163A-904A | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3A 01/30/2020 GG
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 330 | 7000006192 | MTRs | 2020-04-15 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 45 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-18 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 140 | 1000257039 | PLIC,SWAGELOK,SS810P,1/2in | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 2 | EA | 2 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3580 | 7000002662 | Pipe, 3 1/2", S/40, API 5L Grade X52 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Stones Solids Tie-in | 11179936 | 388 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161902 | Name 4 | Name 4 | 2019-10-17 | USGBI5 | 21 | FT | 21 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 700 | 7000002591 | 22 X 36 WHITE POLY SAND BAG | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 928 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A395 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 60 | EA | 60 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 80 | 7000002591 | Elbow, 20", S/20, 45 LR, BE, ASME B16.9 | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 1 | EA | 1 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 710 | 7000002629 | FLANGE, 8", 300#, RF, WN, ASTM A182 GR. | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 87 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 24 | EA | 24 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 750 | 7000002629 | Thrd Hex Nipple 3/4" x 3" LG,316SS | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose |  | 11179936 | 1041 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-23 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2520 | 7000002629 | FLANGE, 8", 300#, RF, WN, SCH 40S, ASTM | 2019-04-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 274 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04021905 | Name 2 | Name 2 | 2019-04-03 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 160 | 7000000052 | Documentation | 2019-01-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 60 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN039 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SLB1 | 20 | 7000003862 | Fabricated pipe spools | 2019-02-01 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Turritella | 11179936 | 210 | 4 | Non-Stock (Purchase Requisition) | N |  |  | 732822TUR | Name 2 | Name 2 | 2019-02-01 | USGBI5 | 3 | EA | 0 | Mechanical Shop Labor | REL SETC | APPR MAGN | Deleted
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 30 | 70 | 7000002596 | Hex head plug M42 w/O-ring, Hollow | 2020-05-16 | Received at Worksite |  | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB B5 | 11783572 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-21 | USMNF8 | 5 | EA | 5 | Install new grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC |  |  | PU AARON W
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2120 | 1001816277 | GASW,CL300,316,GPH,NPS8 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 234 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 10 | 7000004213 | KE35/1-4-SET | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 400 | 7000002644 | BALL VALVE, 3/4", VBT-1502SD | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 53 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6220 | 1001574544 | BLT+N,651,UNC,3.1/2in,5/8in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 720 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 72 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 60 | 7000003196 | SS-TBC8 Cush-A-Clamp-1/2" Case | 2020-02-24 | Received at Worksite |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-09 | USNSB4 | 25 | EA | 25 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
60998635 | 508 | O/SI Passing Valve Boiler #2 Vent Valve | S17 | Steam/Hot H2O | 2020-04-01 | 2019-12-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.NAC-11503B | Auxiliary Boiler No. 2 | 2019-12-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119540000000 | 20 | 20 | 7000004211 | FLANGE PACK, flange pack to include all | 2020-05-31 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11953957 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-12 | USNSB4 | 1 | EA | 0 | LO/TO Perform Isolations | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61187003 | 508 | Deficiencies found on IAC#3 Service | S08 | Air Systems | 2020-04-05 | 2021-01-28 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11801C | No. 3 Air Compressor | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-06 | 121692000000 | 10 | 20 | 7000000034 | Hex Nipple | 2020-04-05 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12169170 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-04 | USMNF8 | 2 | EA | 0 | Fix Deficiencies found on IAC#3 Service | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60909926 | 508 | Purifier 2 By-Pass valve not functioning | S06 | General | 2020-06-15 | 2020-08-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.LO.117-48V | Lube Oil Purifier Supply Pump #2 Valve | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-06-15 | 118521000000 | 10 | 10 | 7000004211 | 5K-25-GLB/UB-BRZ-100 | 2020-06-15 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11852103 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-10 | USNSB4 | 1 | EA | 0 | Replace By-Pass Gate Valve 117-48V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 20 | 90 | 7000003197 | TB RC10-10F INS NYL FORK TERM 12-10 #10 | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11780965 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-11-04 | USNSB4 | 50 | EA | 0 | Install GTG #2 Vent Fan FANS MOC-71695 | REL ESTC PRC SETC | APPR EOM MAGN WP ZPMM | Deleted
60989317 | 508 | Port crane Emer load lowering hoses bad | S40 | Cargo Handling | 2020-02-18 | 2019-12-05 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-12-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 119417000000 | 10 | 10 | 7000000098 | 3/8 X 25FT. HYDRAULIC HOSE FJICEE FITTIN | 2020-02-18 | Received at Worksite | 2019-12-26 | 2020-01-20 | 2020-02-18 | U182 | 8201 | Stones Main | ST KB C1 | 11941695 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-28 | USCMFR | 1 | EA | 1 | Port Crane Emer Load lowering hoses bad | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK RUSH WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60911821 | 508 | Replace starting solenoid on Gen# 3 | S03 | Elect. Systems | 2020-04-28 | 2019-10-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.ES.PG.ZZZ-11101C | Essential Generator No. 3 Engine | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-28 | 118543000000 | 20 | 10 | 7000005901 | 51313-03E SOLENOID VALVE 3/2 N/C | 2020-04-28 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 11854297 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-18 | USMNF8 | 1 | EA | 1 | Replace starting solenoid | REL ESTC GMPS PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 50 | 7000004213 | KE35/8 SASAKURA KE35 P/N 8 ORIFICE FLANG | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 18 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 2 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 370 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 37 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 18 | EA | 18 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 50 | 7000000039 | YMD-8529 HOSE ASSEMBLY X49"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 70 | 7000000052 | Documentation | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2301 | 11340898 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN103 | ORION | ORION | 2019-11-19 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 120 | 1001207579 | PIPE MET,SA106 GR.B,STD,1in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 42 | FT | 40.96 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 950 | 7000002591 | Milwaukee 14-37-0105 18V Wet/Dry Vac Hos | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 95 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 2 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 90 | 7000003852 | Logitech MK270 Wireless Keyboard and Mou | 2020-04-05 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | AJH021620 | Name 12 | USRRIG | 2020-02-19 | USCDP7 | 1 | EA | 1 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60847991 | 508 | MOC GTG1 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-04000 | Gen #1 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117810000000 | 10 | 90 | 7000005901 | TBN Stakon Part Number RC10-10F 50 BOX | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780966 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI76 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 1 | EA | 1 | SAEP LO/TO Isolate GTG #1 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60891772 | 508 | Hiller Deficiencies | S13 | Fire Protect | 2020-03-21 | 2020-02-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2019-08-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-21 | 118312000000 | 10 | 50 | 7000000108 | KIDDE Wintergreen Odorizer (06-231867-21 | 2020-03-04 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 09/20 | 11831177 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO19CG112 | USFDY0 |  | 2019-08-19 | USABCE | 1 | EA | 0 | Hiller Deficiiencies | REL PRT GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 790 | 7000002591 | DRILLFORCE (5 Pcs) 13/32 in. x 5-1/4 in. | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 79 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 3 | EA | 3 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 40 | 7000002662 | Pipe, 3", S/10S, ASME B36.19M, ASTM A790 | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 21 | FT | 20.3 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60085018 | 508 | O/SI XV-6636P-215 6 COT-#3 Cargo Line | S21 | Oil Treating | 2020-03-12 | 2018-06-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6636P-215 | Crude Oil to/from COT 6 On/Off PS Valve | 2018-05-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-13 | 108964000000 | 10 | 20 | 1002400774 | O-RING PACKING,427 AC002-26"-13,ISLIP-FC | 2020-03-12 | Received at Worksite |  | 2018-05-14 |  | U182 | 8201 | Stones Main | ST KB B4 | 10896408 | 2 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 |  | 2018-05-08 | USNSB4 | 2 | EA | 2 | Replace Soft Goods XV-6636P-215 | REL ESTC GMPS PRC SETC | EXEC EOM MAOK WPOK | EXEC |  |  | PU AARON 6/11/2018
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 80 | 7000003684 | OIL SAFE PREMIUM HAND PUMP, BLACK 102301 | 2020-03-28 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-19 | USAWJB | 1 | EA | 1 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
61221684 | 508 | Steam Expansion Bellows critical spare | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-22 | P.US.STO.NF.20.015.7240A | 508ERENG | US.WR508A.GU.SW.VE115-32000 | Boiler System Steam Distribution | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-06-02 | 122096000000 | 10 | 20 | 7000003323 | Expansion Joint EJ-540582-A | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12209639 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAMH7 | 2020-03-02 | USRAR6 | 2 | EA | 0 | Shut down steam system | CRTD PRC | INIT RUSH WP | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 240 | 7000000039 | SQFT 1/8" GYLON SHEET 1/8" THK x 60" x | 2020-03-01 | Not Shipped |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 24 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO200149 | Entity 6 | USCRFI | 2020-02-17 | USLFA4 | 1 | EA | 0 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60847988 | 508 | MOC GTG4 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-34000 | Gen #4 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 30 | 7000005901 | M20 Nylon Washer | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780943 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI79 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #4 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4720 | 1002058431 | NUT,A563-DH,HEXAGONAL,UNC,1/2,SERMAGARD | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 524 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 118 | EA | 118 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60985462 | 508 | No.3 COP stuffing box bellows leaks | S21 | Oil Treating | 2020-04-25 | 2019-11-25 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301C | Cargo Oil Pump No. 3 | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-27 | 119373000000 | 20 | 30 | 7000000038 | P/N:437 SEAL PACKING (TOMBO #1850P) | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937329 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  | PLWST3-W | Name 3 | USMSLN | 2019-10-09 | USMNF8 | 4 | EA | 0 | Replace COP #3 pump bellows | REL PRT PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 460 | 7000003197 | 3/4" Locknut | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 838 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 3 | EA | 3 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 140 | 7000003196 | Swagelok MS-STR-4 | 2019-11-20 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI68 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 1 | EA | 1 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 260 | 1001697913 | BLT HEX,316,UNC,1/4in,1/2in | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 26 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 100 | EA | 100 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 310 | 7000000086 | Model# 1783-ETAP1F AB EtherNet/IP Tap w/ | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 417 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5460 | 7000002629 | 12" 300 RFWN Flange Protectors | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 607 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1670 | 7000002603 | 12", 150#, RFWN FLANGE PROTECTOR | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 183 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61222441 | 508 | Replace With the Correct Pressure Gauge | S19 | Marine Systems | 2020-03-21 | 2021-02-22 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.PR.PG-LOS-ET | Lube Oil Expansion Tank Pressure Gauge | 2020-02-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-21 | 122105000000 | 10 | 10 | 7000003852 | CARBO Instruments 2 1-2" Pressure Gauge, | 2020-03-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 12210496 | 1 | 4 | Non-Stock (Purchase Requisition) | N | [5 empty] | 2020-02-29 | USMNF8 | 4 | EA | 0 | Replace Pressure Gauge on expansion tank | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61155246 | 508 | Install Barring Device on MGCA | S04 | Gas Compress | 2020-03-03 | 2020-07-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-03 | 121329000000 | 10 | 40 | 7000002591 | 8773A53 (27/64" drill bit) | 2019-11-01 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST1A6C | 12132852 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0006 | Name 17 | JP832018 | 2020-01-27 | USLFA4 | 2 | EA | 2 | Install Barring Device on MGCA | REL PCNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC |  |  | ST1A6C 02/16/20 AMW
60989320 | 508 | O/SI Condensate return valve VAGA-115522 | S17 | Steam/Hot H2O | 2020-04-01 | 2020-04-05 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.VAGA-115522 | Stbd Condensate from COT 2 Iso Valve | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-02 | 119417000000 | 20 | 10 | 7000000104 | 2-1/2 Neway gate valve | 2020-04-01 | Received at Worksite | 2020-02-13 |  |  | U182 | 8201 | Stones Main | ST1A5B | 11941698 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-04 | USMNF8 | 1 | EA | 1 | Shut down steam system | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | ST1A5B AMW
60839364 | 508 | Check Valve VACH-331020 Passing by | S13 | Fire Protect | 2020-06-01 | 2020-01-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.VACH-331020 | SW Jockey Pump to Helideck Check Valve | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-01 | 117712000000 | 10 | 30 | 7000004212 | 5/8"-11 X 6 1/2" long Silica Bronze Studs | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11771154 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-15 | USNSB4 | 8 | EA | 0 | Replace Check Valve VACH-331020 | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60739057 | 508 | COT 4 Port HC line Netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127010 | COT 4 PS HC Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642933 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 100 | 7000003197 | Serrated Washer M20 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 2 | EA | 2 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
61118330 | 508 | 2020 Chemical Order - Subsea | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 30 | 7000003458 | SCAL16555SP.32U | 2020-02-26 | Not Shipped |  | 2019-12-23 |  | U182 | 8201 | Stones Main | CPORT | 12090687 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  | 20OP0014AA | Name 40 | USAAN5 | 2020-02-12 | USLFA4 | 500 | GLL | 0 | 2020 Chemical Order - Subsea | REL ESTC PRC SETC | EXEC STDG | EXEC
61134557 | 508 | BTM Spare/Inner Seal PCV-5 passing | S19 | Marine Systems | 2020-03-25 | 2020-02-26 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-88511C | Turret/BTM No. 3 Spare/Inner Seal | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-25 | 121087000000 | 10 | 10 | 7000000066 | Pressure Regulator, Type : Piston Sensed | 2020-03-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12108700 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-20 | USNSB4 | 1 | EA | 0 | Replace PCV-5, BTM Spare/Inner Seal | REL PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 90 | 7000003458 | BIOC16298A.32B | 2020-02-26 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200013A | Name 3 | USAAN5 | 2020-02-12 | USLFA4 | 500 | GLL | 492 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 80 | 7000005901 | Brady Part No. M21-187-C-342 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780965 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI77 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 1 | EA | 1 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60426272 | 508 | O/SI BSW 198 O-ring seal failure | S22 | Prod Gathering | 2020-06-01 | 2019-04-22 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.AT-66207-198 | Crude Oil Outlet Water In Oil Analyser | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-01 | 112913000000 | 20 | 30 | 7000000039 | 215A817 - VITON DC-3510 Seal Kit Consist | 2020-06-01 | Received at Worksite |  | 2019-04-02 |  | U182 | 8201 | Stones Main | ST KB D3 | 11291300 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-01-16 | USNSB4 | 1 | EA | 1 | Reinstall Temperature Transmitter w/ New | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU 4/4/2019 CR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1130 | 1001572758 | SHT PLT SLD MET,4x4in,1/4in | 2020-04-15 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F64 | 11581207 | 113 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111901 | Name 4 | Name 59 | 2019-11-12 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60958039 | 508 | Slew Drive Mounting Bolts- PORT CRN | S40 | Cargo Handling | 2020-02-25 | 2020-09-17 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-09-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-26 | 119064000000 | 10 | 10 | 7000000040 | Swing Drive Mounting Bolts | 2020-02-25 | Ready for Shipment after Kitting | 2019-11-27 | 2019-12-27 | 2020-02-22 | U182 | 8201 | Stones Main | MOD 22 GRN Mile | 11906378 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-23 | USCMFR | 108 | EA | 108 | Relocate Crane Slew Gbox Drain | TECO ESTC GMPS PPRT PRC SETC | XCNF EOM MAGN MAKD NCMP RUSH WPOK XGI | TECO
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 50 | 7000002591 | 600 ¼” Manilla Rope | 2020-02-04 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | DIISTO1927 | Entity 1 | USJRF5 | 2020-01-28 | USLFA4 | 6 | EA | 6 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60985323 | 508 | Port crane leaking exhaust pipe | S40 | Cargo Handling | 2020-03-24 | 2020-06-30 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZBE-87401 | Port Side Pedestal Crane Engine | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-27 | 119372000000 | 30 | 10 | 7000006081 | OA,US,SPARROW,LIFT,GOOD/PASSENGER,EA | 2020-03-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11937169 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-10 | USMNF8 | 1 | EA | 0 | Replace Port crane exhaust Pipe | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 590 | 7000002629 | Pipe Nipple, 1" x 12" LG, S/80 (1.315 x | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 59 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60921250 | 508 | O/SI Steam Inlet Drain Valve Leaking | S17 | Steam/Hot H2O | 2020-03-11 | 2020-03-02 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.SW.VAGL-115552 | Steam Inlet Drain Valve | 2020-01-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 118651000000 | 30 | 30 | 7000002596 | 5/8 X 3-1/2 (3-1/4 FTF) DOX PLTD STUD | 2020-03-11 | Received at Worksite | 2020-01-22 |  |  | U182 | 8201 | Stones Main | ST1A3B | 11865065 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | 4073688 | Name 3 |  | 2020-01-11 | USMNF8 | 20 | EA | 20 | Steam Inlet Drain Valve Leaking | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WP ZPMM | Kit Complete |  |  | ST1A3B 02/3/20 GG
60859588 | 508 | Replace Offload Station Leak Test Valve | S21 | Oil Treating | 2020-06-02 | 2020-01-20 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.VACH-664001 | Pressure Test Connect Valve | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 117945000000 | 10 | 30 | 1001763845 | SB2N,A193-B7,CTD,UNC,4.5in,5/8in | 2020-06-02 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Stones | 11794476 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-02-19 | USRAR6 | 8 | EA | 8 | Replace Offload Station Leak Test Valve | REL ESTC GMPS PRC SETC | APPR EOM MAGN MANX WPOK | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 60 | 7000002603 | Gasket, 10", 300#, RF, 1/8" THK. Spiral | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 102 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 9 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 120 | 7000002591 | Dexas 3517-J2728 Slimcase 2 Storage Clip | 2020-02-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200006 | Name 10 | USRRIG | 2020-01-21 | USLFA4 | 4 | EA | 4 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 270 | 7000002591 | 4452K413 90 Degree Elbow Connector, 3/8 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 27 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 290 | 7000002591 | 4452K415 90 Degree Elbow Connector, 3/4 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60847987 | 508 | MOC GTG3 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-24000 | Gen #3 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 60 | 7000005901 | M20 Locknut | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780940 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI78 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #3 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 100 | 7000004213 | KE35/13 SASAKURA KE35 P/N 13 LONG NIPPLE | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61089207 | 508 | Slip hazard inside GT1 enclosure | S03 | Elect. Systems | 2020-04-28 | 2020-06-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.LAN-11110 | Gas Turbine Power Generation Package 1 | 2019-12-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-28 | 120563000000 | 10 | 10 | 7000003852 | CRC (05084-12PK) Brakleen Non-Chlorinate | 2020-04-28 | Received at Worksite | 2019-12-17 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST1A6C | 12056334 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-11 | USMNF8 | 1 | EA | 1 | LOTO GT1 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A6C 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 760 | 7000003463 | FT-ADSX-STSM | 2020-03-18 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1067 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-26 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 90 | 1001772401 | GARJ,SS316,OCTAL,R16 | 2021-03-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Gas Riser Pressure Gauge | 11057838 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A176 | Entity 3 | USRRIG | 2018-08-06 | USSOLE | 5 | EA | 5 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved
61151918 | 508 | Port crane exhaust rain cap bad | S40 | Cargo Handling | 2020-06-13 | 2020-07-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZBE-87401 | Port Side Pedestal Crane Engine | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-13 | 121288000000 | 10 | 20 | 7000006081 | Rain cap, SST 482880-017,, | 2020-06-13 | Received at Target Location | 2020-03-02 |  |  | U182 | 8201 | Stones Main | STONES | 12128843 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-04 | USMNF8 | 2 | EA | 2 | Replace- Port crane exhaust rain cap | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4150 | 7000002596 | Bolt, 3/4" x 4 1/2" Lg., ASTM F3125 Gr. | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 465 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 54 | EA | 54 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1350 | 1001931007 | ELB BW,WPB,90DEG,LR,STD,NPS12 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 151 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2920 | 7000002629 | Elbow, 2", LR 90, S/160, BW, ASME B16.9 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 322 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60172773 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-04-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.96T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-10 | 110086000000 | 10 | 90 | 7000004211 | 20K 40mm Globe valve | 2020-04-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11008582 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-12 | USMNF8 | 2 | EA | 0 | MOC missing steam trap | REL PCNF ESTC GMCO GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 30 | 7000002662 | ½” x 0.049 317L SMLS Uncoated Tubing | 2019-11-27 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI67 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 40 | FT | 40 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 170 | 7000003197 | B-LINE B22SS6 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 30 | EA | 30 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
61114758 | 508 | O/SI SDV-77163A-904A Passing By | S04 | Gas Compress | 2020-02-15 | 2020-06-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.SDV-77163A-904 | 2nd Stg Compressor Out Gas Shutdown Vlv | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-15 | 120863000000 | 10 | 30 | 7000004751 | 7/8" X 5-1/2" Telfon Coated Studs w/ Nut | 2020-02-15 | Received at Worksite | 2020-01-23 | 2020-02-07 | 2020-02-18 | U182 | 8201 | Stones Main | ST KB D7 | 12086293 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 59 | 2019-12-27 | USAWJB | 24 | EA | 24 | Replace SDV-77163A-904A | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3A 01/30/2020 GG
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 230 | 1001816211 | GASW,CL150,316,GPH,NPS2 | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
61165408 | 508 | Install Needle Valve on PG-33120-730 | S13 | Fire Protect | 2020-03-10 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33120-730 | FW Lift Pump Inlet Pressure Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-10 | 121447000000 | 10 | 20 | 7000003196 | Stainless Steel Integral Bonnet Needle V | 2020-03-10 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144693 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 1 | EA | 1 | Install Needle Valve on PG-33120-730 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60739070 | 508 | COT 3 S IG Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127058 | COT 3 SB IG Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116430000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642966 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 70 | 7000000039 | YMD-8529 HOSE ASSEMBLY X31"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 40 | 7000002662 | Pipe, 1 1/4", S/80, ASTM A53 Gr. B | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 20 | FT | 23 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 50 | 7000000039 | YMD-8529 HOSE ASSEMBLY X49"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60007323 | 508 | O/SI Cargo Ballast Valve Actuator Fail | S21 | Oil Treating | 2020-03-18 | 2018-08-14 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6636P-215 | Crude Oil to/from COT 6 On/Off PS Valve | 2018-06-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-19 | 107665000000 | 10 | 10 | 7000002645 | TOP | 2020-03-18 | Ready for Shipment after Kitting | 2018-08-08 | 2018-08-29 |  | U182 | 8201 | Stones Main | ST KB D7 | 10766450 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-06-08 | USNSB4 | 5 | EA | 5 | Replace Soft Goods In Cargo Ballast Valv | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 8-25-18 WPT
60921250 | 508 | O/SI Steam Inlet Drain Valve Leaking | S17 | Steam/Hot H2O | 2020-03-11 | 2020-03-02 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.SW.VAGL-115552 | Steam Inlet Drain Valve | 2020-01-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 118651000000 | 30 | 20 | 7000002596 | 5/8 X 4-1/4 (4 FTF) DOX PLTD STUD BOLT | 2020-03-11 | Received at Worksite | 2020-01-22 |  |  | U182 | 8201 | Stones Main | ST1A3B | 11865065 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | 4073688 | Name 3 |  | 2020-01-11 | USMNF8 | 24 | EA | 24 | Steam Inlet Drain Valve Leaking | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WP ZPMM | Kit Complete |  |  | ST1A3B 02/3/20 GG
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000003852 | Guantai DVIExtender with KVM - AV Access | 2021-03-01 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20O0112 | Name 12 | USRRIG | 2020-01-13 | USLFA4 | 2 | EA | 2 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | DLVD 2/2/2020 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1970 | 7000002596 | STUD BOLTS, 5/8" DIA. X 3 1/2" LONG, AS | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 219 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 670 | 7000003197 | SS H104-1/2X12SS SS THRD ROD | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 898 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 12 | EA | 12 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60739054 | 508 | 6S HC Netherlock Not Locking Open/Close | S06 | General | 2020-04-01 | 2019-11-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127005 | COT 6 SB HC Main Isolation Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642930 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5110 | 7000002629 | THREADOLET, 12 X 1/2" 3000LB ASTM A182 G | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 572 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60661352 | 508 | O/SI Steam Inlet is Passing | S17 | Steam/Hot H2O | 2020-03-10 | 2019-09-07 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-410V | Steam to No. COW Pump Isolation Valve | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 115550000000 | 30 | 30 | 7000004211 | ham-hand-125 HAMMER HANDWHEEL | 2020-05-09 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11555032 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-21 | USNSB4 | 1 | EA | 0 | Replace Valve 115-410V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61179241 | 508 | Faulty Humidity transmitter RHT-108403 i | S14 | HVAC | 2020-03-18 | 2020-03-27 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.RHT-108403 | Battery Room Temperature Transmitter | 2020-02-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-18 | 121604000000 | 10 | 10 | 7000005901 | HMT360-1D22BCA1B3BA5A10 HMT360 INTRINSIC | 2020-03-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12160404 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-20 | USNSB4 | 1 | EA | 0 | Replace & Calibrate LER Batt Humidity/Te | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60959164 | 508 | COP #1 Disch Px Gauge | S21 | Oil Treating | 2020-05-24 | 2020-09-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PG-66301A-342A | Cargo Oil Pump #1 Disch Pressure Gauge | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-05-24 | 119075000000 | 10 | 10 | 7000000062 | WK MISC $1,282.2500 $1,282.25 22 Days | 2020-05-24 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 11907500 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-21 | USNSB4 | 1 | EA | 1 | LO/TO Perform Isolations | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAOK WPOK ZPMM | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 230 | 7000002596 | 5/8" x 3-3/4" All Thread B01 ASTM A320-L | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 16 | EA | 16 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6540 | 7000002662 | Pipe, 1/2", .065 Min Wall, ASTM B466, 90 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 865 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 10 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2010 | 1001664285 | BLT HEX,A325,UNC,1.1/2in,5/8in | 2019-02-15 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 223 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02121901 | Name 2 | Name 2 | 2019-02-13 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 220 | 7000002591 | Pilot for mag drill bit | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 648 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 20 | EA | 20 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5730 | 1002316829 | GASW,CL300/600,316/316L,GPH,2in | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 667 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 3 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60936970 | 508 | GT1 Gas Fuel Valve Bolts Recalled | S03 | Elect. Systems | 2020-04-01 | 2020-03-07 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.FCV-11110-130 | Generator #1 Fuel Gas Flow Control Valve | 2020-01-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 118822000000 | 10 | 10 | 7000003739 | 601722C1 KIT,HDWR,PECC VALVE | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11882240 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USMSLN | 2019-10-17 | USRAR6 | 1 | EA | 0 | Replace Recalled Fuel valve bolts | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4510 | 7000002629 | Elbow, 3", LR 90, S/40S, BW, ASME B16.9 | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 503 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60756604 | 508 | Vacuum Condenser Heat Exchanger | S17 | Steam/Hot H2O | 2020-04-01 | 2019-06-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.HBG-11508 | COPT Vacuum Condenser Heat Exchanger | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 116627000000 | 10 | 80 | 7000002596 | THREADED BOLTS AND NUTS Cap screw Teflon | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A2C | 11662728 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-01-16 | GW982959 | 40 | EA | 40 | Main condenser tubes leaking | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WP ZPMM ZPVS | Approved |  |  | ST1A3B 02/18/2020 CMR
60663676 | 508 | Actuator Assembly Malfunction | S06 | General | 2020-05-07 | 2019-09-14 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.HC.TCV-12501-410 | FW Coolers Outlet Temp Control Valve | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-07 | 115578000000 | 20 | 30 | 7000005901 | Cylinder positioner , IP200-120 | 2020-05-07 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11557766 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-03 | USMNF8 | 1 | EA | 0 | Replace Actuator Assembly | REL ESTC GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
61050323 | 508 | Hydraulic hose outer layer damaged | S21 | Oil Treating | 2020-03-06 | 2019-12-13 | O.US.STO.STO.005.724FP | 508DANOS | US.WR508A.OT.SS.ZZZ-66410 | Offloading Hose Reel | 2019-11-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 4 Complete by 4 Weeks | 2020-03-06 | 120124000000 | 20 | 30 | 7000000098 | Hose for offloading hose reel | 2020-03-06 | Received at Worksite |  | 2020-02-19 |  | U182 | 8201 | Stones Main | ST KB A6 | 12012401 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 55 |  | 2020-02-03 | USAMH7 | 1 | EA | 1 | Replace Hydraulic hose | REL PCNF PRT GMPS PRC SETC | SCHD MAGN MAOK WPOK | EXEC |  |  | PU 02/19/20 AMW
60921249 | 508 | O/SI Isolation Valve Packing Leak | S17 | Steam/Hot H2O | 2020-04-02 | 2020-03-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGA-115514 | Stbd Steam to COT 6 Isolation Valve | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-03 | 118650000000 | 60 | 20 | 7000004211 | Doxsteel-4 4" FASTENER PASCK FOR ANSI 15 | 2020-04-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11864984 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-16 | USNSB4 | 16 | EA | 0 | Replace Valve VAGA-115514 | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 280 | 7000003343 | Angle, L4x4x3/4, ASTM A36 (PCM-0.23) | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 728 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231901 | Name 4 | Name 4 | 2019-12-24 | USSOLE | 20 | FT | 20 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2620 | 7000002603 | GASKET, 12", 300#, RF, 1/8" THICK, SPIRA | 2019-04-22 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 284 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04081901 | Name 2 | Name 2 | 2019-04-08 | USSOLE | 12 | EA | 12 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 20 | 40 | 7000003852 | Swpeet 180Pcs Grease Fitting Cap Assortm | 2020-01-28 | Received at Target Location |  | 2020-01-19 |  | U182 | 8201 | Stones Main | Issued | 11783572 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-03 | USMNF8 | 1 | EA | 1 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC |  |  | PU AARON W
61112406 | 508 | 2nd Stg Sep PST upgrade | S22 | Prod Gathering | 2020-04-11 | 2020-06-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.PST-66202-178 | 2nd Stg Separator Press Sfty Transmitter | 2019-12-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-11 | 120837000000 | 20 | 10 | 7000003740 | SCALABLE PRESSURE TRANSMITTER 3051S2TG3A | 2020-04-11 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B3 | 12083677 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-23 | USNSB4 | 1 | EA | 1 | Upgrade PST-66202-178 To Rosemount Trans | REL ESTC GMPS PPRT PRC SETC | APPR EOM MAGN MAOK RUSH WPOK ZPMM | EXEC |  |  | ST1A3C 02/3/20 GG
60797147 | 508 | A/C Condenser Intermittent Operation | S40 | Cargo Handling | 2020-03-24 | 2019-08-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-07-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-27 | 117216000000 | 20 | 30 | 7000000057 | Discharge hose Visionaire; Pt# 35-7070-0 | 2020-03-24 | Received at Worksite |  | 2019-10-17 |  | U182 | 8201 | Stones Main | ST KB c5 | 11721562 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-17 | USMNF8 | 2 | EA | 2 | Hoist Up Materials/Tools. Secondary Ass | REL PCNF PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | ST1A6C 01/29/20 GG
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 200 | 7000004751 | Keckley 3" 300# Floating Ball Valve | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN115 | Name 2 | Name 2 | 2020-01-30 | USSOLE | 4 | EA | 4 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60871421 | 508 | O/SI TEG Reboiler Stripping Gas PCV-001 | S39 | Gas Treating | 2020-03-10 | 2020-01-29 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.PCV-77211-001 | TEG Reboiler Pressure Control Valve | 2019-09-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-10 | 118080000000 | 20 | 30 | 7000003464 | FISHER 1"300RF MR95H WCC STEEL BODY, 15- | 2020-03-10 | Received at Worksite |  | 2019-12-28 |  | U182 | 8201 | Stones Main | ST KB D1 | 11807985 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-23 | USNSB4 | 1 | EA | 1 | Replace 1" Fisher Valve TEG Reboiler Str | REL PRT GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU AMW 12/29/19
60959173 | 508 | COP1 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-06 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PBE-66301A | Cargo Oil Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-12 | 119077000000 | 10 | 10 | 7000000038 | 1/4" mnpt x 3/8" tube SS fitting (for se | 2020-03-06 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 11907749 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-17 | USRAR6 | 1 | EA | 1 | Add seal flush plan 12 to COP1 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 170 | 1002360784 | SB2N,B7,2H,UNC,5/8in,3.5in,DOXSTEEL | 2019-11-26 | Received at Target Location |  |  | 2020-02-14 | U182 | 8201 | Stones Main | Onsite Danos Has | 11882270 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI65 | Name 2 | Name 58 | 2019-11-06 | USSOLE | 5 | EA | 5 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 90 | 7000004213 | KE35/12 SASAKURA KE35 P/N 12 UNION JOINT | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 800 | 7000002591 | DRILLFORCE (5Pcs) 27/64 in. x 5-3/8 in. | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 80 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 3 | EA | 3 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 90 | 7000002596 | . Nut, 3/8", ASTM A194 Gr. 2H or equival | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 14 | EA | 14 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 360 | 7000002591 | Coilhose Pneumatics PE0417-100D Polyethy | 2020-02-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 36 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 3 | EA | 3 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60453594 | 508 | 26-PL664001- Install permanent Pipe Supp | S21 | Oil Treating | 2020-02-18 | 2019-11-10 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-18 | 113218000000 | 10 | 80 | 7000002596 | 2" x 27' U-Hook Ratchet Strap (including | 2020-01-22 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | JOB: SHF9-F92 | 11321849 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221902 | Name 4 |  | 2019-11-22 | USLFA4 | 2 | EA | 2 | 26-PL664001- Install permanent Pipe Supp | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 330 | 7000002591 | Dremel 454 3/16" Grinding Stone, 2 Pack | 2020-02-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 33 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 6 | EA | 6 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 310 | 7000002591 | 4452K112 Straight Connector, 1/4 NPT Fem | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 31 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 460 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-11-20 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 46 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06141901 | Name 2 | Name 59 | 2019-06-17 | USDKFB | 12 | EA | 12 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60453594 | 508 | 26-PL664001- Install permanent Pipe Supp | S21 | Oil Treating | 2020-02-18 | 2019-11-10 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-02-18 | 113218000000 | 10 | 20 | 7000003343 | Pipe, 2" (2.375" OD) x 0.218WT, ASTM A53 | 2020-01-22 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | JOB: SHF9-F92 | 11321849 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221902 | Name 4 |  | 2019-11-22 | USLFA4 | 20 | FT | 21 | 26-PL664001- Install permanent Pipe Supp | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 130 | 1001991793 | PIPE MET,API 5L-X42,BARE,40,1.1/2in,SRL | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 126 | FT | 126.6 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 150 | 1000718629 | PIPE,2-3/8,SCH 40,3.65#,BEVEL,0.,2674760 | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 105 | FT | 108.52 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60701397 | 508 | Leaking Globe/Check Valve on Hydrophore | S18 | Water Systems | 2020-04-11 | 2019-10-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.121-20V | Tank Outlet Check Valve | 2020-01-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-11 | 116003000000 | 20 | 20 | 7000004211 | PAINT-SHELL, SHELL PAINT SPECIFICATIONS | 2020-04-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ST KB B6 | 11600310 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  |  | USNSB4 | 2019-05-19 | USNSB4 | 1 | EA | 0 | Drain Hydrophore Tank | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MANX WPOK ZPMM | EXEC
61118367 | 508 | 2020 Catering - Material | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 60 | 7000003454 | Cambro Carbonate Food Storage Container | 2020-02-28 | Not Shipped |  | 2020-01-15 |  | U182 | 8201 | Stones Main | STONES | 12090704 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOR11620A | Camp Boss | USJRF5 | 2020-01-16 | USLFA4 | 1 | PK | 0 | 2020 Catering - Material | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 130 | 7000000133 | RKI 81-0142RK-04 Gas cylinder | 2020-02-28 | Received at Target Location |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG144 | Entity 7 | USKHU3 | 2020-02-05 | USLFA4 | 1 | EA | 1 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60737087 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-03-17 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-240 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-17 | 116406000000 | 20 | 30 | 7000005901 | P.0244110037 AVC 02 CL1 A1 VPI MANIFOLD | 2020-06-05 | Received at Worksite | 2019-12-10 |  |  | U182 | 8201 | Stones Main | ST1A1B | 11640592 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635S-240 | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | PU 01/19/2020 AMW
60739055 | 508 | COT 5 P HC netherlock fails to lock | S06 | General | 2020-04-01 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127008 | COT 5 PS HC Main Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642931 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 770 | 7000003197 | TB SSTC06V-3 SS 316 6IN WIDTH VENTILATED | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 908 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 8 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 270 | 7000003197 | MCT Transit RM Modules, RM 40/10-32 EX ( | 2020-04-06 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 27 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI92 | Name 2 | USMCS1 | 2020-02-19 | USLFA4 | 2 | EA | 0 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4030 | 7000003344 | Plate, 3/4" x 96" x 96", ASTM A572 50 (P | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 453 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5090 | 7000002629 | THREADOLET, 4 X 1/2" 3000LB ASTM A105 | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 570 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 130 | 7000002603 | Gaskets 4" 150# FR 1/8" THK SPIRAL WOUND | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 639 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 180 | 7000003852 | GearLight LED Tactical Flashlight S1000 | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 710 | 7000003197 | PL SSTF04SFC-3 SS 4INW CHANNEL TRAY COVE | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 902 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 9 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3540 | 7000002603 | 4" Flange Protectors, 4", 150#, RF | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 384 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 16 | EA | 16 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3420 | 1001811045 | FLWN,A105,CL150,STD,NPS12 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 372 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5890 | 1002150255 | SHT PLT SLD MET,4x4ft,3/8in,A572-50 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 683 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61165408 | 508 | Install Needle Valve on PG-33120-730 | S13 | Fire Protect | 2020-03-10 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33120-730 | FW Lift Pump Inlet Pressure Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-10 | 121447000000 | 10 | 10 | 1000719976 | COIMC,SWAGELOK,SS60016,3/8x3/8NPT | 2020-03-10 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144693 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 2 | EA | 2 | Install Needle Valve on PG-33120-730 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60163073 | 508 | O/SI HCV-835 Stripped Out | S39 | Gas Treating | 2020-02-15 | 2018-07-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.HCV-77401-835 | Gas Export Pipeline HCV | 2018-08-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-15 | 109935000000 | 10 | 20 | 7000000104 | WEIR 25 mm (1”) Class 2500 BV503 Globe V | 2020-02-15 | Received at Worksite |  | 2019-05-08 | 2020-02-18 | U182 | 8201 | Stones Main | ST KB D1 | 10993478 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-08-07 | USNSB4 | 1 | EA | 1 | Replace HCV-835 Hand Choke Valve | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU Aaron W. 5/18/19
60352955 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-09 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33310 | No. 1 Port Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-10 | 112105000000 | 10 | 60 | 1001726076 | ALTERNATOR BELT,400-BELT0001,ALXR-RYN | 2020-02-09 | Received at Worksite |  | 2019-11-29 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210547 | 6 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 | USAWJB | 2019-11-29 | USAWJB | 1 | EA | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 140 | 7000006429 | EMBR18527A.32B | 2020-03-18 | Not Shipped |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 15 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO20020AA | Name 3 | USRRIG | 2020-03-03 | USLFA4 | 2000 | GLL | 0 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60739065 | 508 | COT 4S Vent netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127049 | IG Vent COT 4 SB Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642941 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 280 | 7000002591 | U Brands Contempo Magnetic Dry Erase Boa | 2020-02-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 28 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 1 | EA | 1 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60440621 | 508 | Replace Laydown Timber - MODs 15, 17, 19 | S40 | Cargo Handling | 2020-03-10 | 2020-06-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.LS | Loading Stations | 2019-08-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 113072000000 | 10 | 50 | 7000002583 | Carbon Steel Wood Drilling Bit, Auger St | 2020-03-10 | Received at Worksite |  | 2019-09-11 |  | U182 | 8201 | Stones Main | ST KB A1 | 11307214 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-06 | USAWJB | 5 | EA | 5 | Replace Laydown Timbers - MOD 15 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAOK RUSH WPOK | EXEC |  |  | PU KB A1
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1090 | 7000002591 | LOTO kit With LOTO Do-Not Operate Tags 1 | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 109 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 80 | 7000002591 | 4" 1500# Spectacle Blind, CS 516 Gr-70, | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 2 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 600 | 7000002591 | 4452K264 Straight Reducer, 1 x 3/4 NPT F | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 60 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 30 | 7000003852 | REFICCER Office Chair High Back Leather | 2020-03-31 | Received at Target Location |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | CAOA021320 | Name 12 | USRRIG | 2020-02-19 | USLFA4 | 1 | EA | 1 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 10 | 7000002596 | All-thrd stud 3/8” θ x 2”Lg, ASTM A307 G | 2019-06-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Lower Turret Fire Extingu | 11545759 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A308 | Name 2 | Name 2 | 2019-06-03 | USSOLE | 20 | EA | 20 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 210 | 7000003852 | Arachnid Cricket Pro Tournament-quality | 2020-03-16 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN020720A | Name 3 | USCRFI | 2020-02-09 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | DLVD OIM 02/20/2020 GG
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 670 | 7000002591 | 4452K237 3/8 NPT | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 67 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 730 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 73 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 125 | EA | 125 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 50 | 7000002591 | Stud, 7/8" x 10 1/2", ASTM A193 Gr. B7 w | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 18 | EA | 18 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60739068 | 508 | COT 5S IG netherlock fail to lock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127052 | COT 5 SB IG Vent Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642944 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 90 | 1000709955 | COIMC,SWAGELOK,SS1210112,3/4x3/4NPT | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 14 | EA | 14 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60430795 | 508 | O/SI Missing Gaskets on SW Lift | S18 | Water Systems | 2020-04-11 | 2019-04-30 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.VE122-10000 | Vessel Sea Water Lift System | 2018-11-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-13 | 112970000000 | 10 | 10 | 1002360753 | SB2N,B7,2H,UNC,1/2in,4.25in,DOXSTEEL | 2020-01-11 | Received at Worksite |  | 2018-12-15 |  | U182 | 8201 | Stones Main | ST KB D3 | 11296986 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2018-11-02 | USAWJB | 100 | EA | 100 | Install Missing Gaskets on SW Lift | REL PRT GMPS PRC SETC | EXEC MAGN MANX WPOK | EXEC |  |  | PU M. Shephered 12/14/2018 AJ
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2590 | 7000002596 | STUD BOLTS, 7/8" DIA. X 7 1/2" LONG, AST | 2019-04-22 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 281 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04081901 | Name 2 | Name 2 | 2019-04-08 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3340 | 1001789575 | TEEB,WPB,40,NPS4 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 364 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4060 | 7000002596 | Bolt, 5/8" x 1 3/4 Lg ASTM F3125 GrA325 | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 456 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 700 | 7000003197 | SSTF04HBC9012SS 4INW CHNL TRAY H90 12INR | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 901 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 8 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6210 | 1001722419 | BLT+N,C65100,UNC,4in,5/8in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 719 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 36 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2170 | 1001642081 | STL SECT MAR,BEAM,7.995in,20ft,A992 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 239 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 60 | FT | 60 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 220 | 7000003196 | 316-S1-PP-6T | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 800 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 90 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 80 | 1002309190 | SB2N,B8M CL2,8M,UNC,7/8in,5.50in | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 634 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 28 | EA | 28 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 640 | 7000002629 | THREADOLET, 8 X 1/2" 3000LB ASTM A182 GR | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 818 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01292002 | Name 4 | Name 4 | 2020-01-30 | USSOLE | 1 | EA | 1 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60959173 | 508 | COP1 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-06 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PBE-66301A | Cargo Oil Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-12 | 119077000000 | 10 | 60 | 7000000038 | 2-1/2" lower mount gauge 0-300 psi 1/4" | 2020-03-06 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 11907749 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-17 | USRAR6 | 2 | EA | 2 | Add seal flush plan 12 to COP1 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 970 | 7000002591 | DustOff Disposable Compressed Gas Duste | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 97 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 140 | 7000003740 | Agency Approval Certificates | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN110 | Name 2 | Name 2 | 2019-12-18 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 830 | 7000002591 | DRILLFORCE (5 Pcs) 15/32 in. x 5-3/4 in. | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 83 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 3 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 210 | 1002316822 | GASW,CL150,316/316L,GPH,1.1/2in | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 2 | EA | 2 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60009724 | 508 | MOC Mov-33120-444 does not operator | S13 | Fire Protect | 2020-03-24 | 2019-02-14 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.MOV-33120-444 | FW Pump Outlet to Ring Main Motor Op Vlv | 2018-03-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-26 | 107694000000 | 20 | 10 | 1001660355 | CONNECTOR,CABLE,ARLINGTN,TMCX075A,M25 | 2020-03-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 10769362 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-28 | USNSB4 | 4 | EA | 0 | Replace Mov-33120-444 | REL ESTC GMPS PPRT PRC SETC | APPR EOM MANX MAXX WP | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 380 | 7000003852 | Arlington DVFR1W-1 Recessed Electrical/O | 2021-03-01 | Not Shipped |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 38 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO0215RDA | Electricians | USJRF5 | 2020-02-20 | USCDP7 | 1 | EA | 0 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 280 | 7000002591 | 4452K414 90 Degree Elbow Connector, 1/2 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 28 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 770 | 1001723501 | WASHER,FLAT,F436,SERMAGAURD,1/2in | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 77 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 22 | EA | 22 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 180 | 7000002591 | 1-1/2” NIPPLE SCH 80S TBE 4" LONG ASTM 1 | 2019-10-18 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 42 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN091 | Name 2 | Name 2 | 2019-09-23 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 110 | 7000003458 | AFMR19017A.32B | 2020-03-04 | Not Shipped |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 12 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO200012A | Name 3 | USRRIG | 2020-02-19 | USLFA4 | 500 | GLL | 0 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60901900 | 508 | BHU unit for Overseas Tampa | S11 | Communications | 2020-04-14 | 2019-10-16 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.GU.CO.PF566-21000 | GPS Tanker Berthing | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-14 | 118427000000 | 10 | 10 | 7000000057 | Tanker BHU unit assembly, 2U cardframe m | 2020-04-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 11/29 | 11842708 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAWJB | 2019-09-05 | USRAR6 | 1 | EA | 0 | BHU unit for Overseas Tampa | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
61118367 | 508 | 2020 Catering - Material | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 40 | 7000002591 | Crestware Stainless Steel Disher Item #4 | 2020-02-28 | Received at Worksite |  | 2020-01-15 |  | U182 | 8201 | Stones Main | STONES | 12090704 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOR11620A | Camp Boss | USJRF5 | 2020-01-16 | USLFA4 | 4 | EA | 4 | 2020 Catering - Material | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU KEITJH 02/15/2020
60246898 | 508 | Damaged Hoses on stab plate #2 | S19 | Marine Systems | 2020-03-10 | 2019-07-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89003A | Umb Fluid #2 Upr Stabplate FL Connector | 2019-10-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-03-11 | 110924000000 | 20 | 60 | 7000000101 | 3/8X18'11"5KSSFJ 18FT-11IN X 3/8" FIREFL | 2020-04-29 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ETA 11/13 | 11092386 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-07 | USNSB4 | 2 | EA | 2 | LO/TO Perform Isolations *2-Man Rule In | REL PRT GMPS PRC SETC | APPR EOM MAGN MAOK WP ZPMM | Approved
60739055 | 508 | COT 5 P HC netherlock fails to lock | S06 | General | 2020-04-01 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127008 | COT 5 PS HC Main Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642931 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 90 | 7000004211 | ANS200x150x350/PN-27 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 2 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60839364 | 508 | Check Valve VACH-331020 Passing by | S13 | Fire Protect | 2020-06-01 | 2020-01-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.VACH-331020 | SW Jockey Pump to Helideck Check Valve | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-01 | 117712000000 | 10 | 10 | 7000004212 | 3" 150# Crane Duo-Check II H15SPF1-169 C | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11771154 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-15 | USNSB4 | 1 | EA | 0 | Replace Check Valve VACH-331020 | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60517728 | 508 | Tilting Skillet Repair | S03 | Elect. Systems | 2020-02-04 | 2019-06-11 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PD.PDP-44310 | Galley Distribution Panel | 2019-03-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 113927000000 | 10 | 20 | 7000005901 | 3754077 TRANSFORMER CB9140AE2+ FUTURA | 2020-02-04 | Received at Worksite |  | 2020-02-03 | 2020-02-09 | U182 | 8201 | Stones Main | STA3B/ Lost, not on shelf | 11392705 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-09 | USNSB4 | 1 | EA | 1 | Repair Tilting Skillet | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN WPOK XGI | TECO |  |  | PU 2/5/2020 JB GG
60985329 | 508 | O/SI Passing steam valve VAGL-115503 | S17 | Steam/Hot H2O | 2020-04-01 | 2020-04-04 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.VAGL-115503 | Steam Trap Isolation Valve | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-02 | 119372000000 | 20 | 10 | 1002407397 | GLOBE VALVE,1GL01-A,NEWAY | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11937175 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2020-02-05 | USMNF8 | 1 | EA | 1 | Shut down steak system | REL ESTC GMPS PRC SETC | APPR MAOK WPOK ZPMM | Approved |  |  | ST1A1C 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2760 | 7000002603 | Gasket, 3", 300#, RF, Pikotek Insulating | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 300 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4310 | 7000002603 | 2" Flange Protectors for Flange, 2", 150 | 2019-11-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 483 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11121901 | Name 4 | Name 4 | 2019-11-12 | USLFA4 | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2930 | 7000002629 | Flange, 3", 300#, RFWN, S/10S Bore, ASME | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 323 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 38 | EA | 38 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3930 | 1002058431 | NUT,A563-DH,HEXAGONAL,UNC,1/2,SERMAGARD | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 443 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11011902 | Name 4 | Name 4 | 2019-11-01 | USSOLE | 232 | EA | 232 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5120 | 7000002629 | SOCKOLET, 8 X 1 1/2" 3000LB ASTM A182 GR | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 573 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60900220 | 508 | Fire Station 093 passing valve | S13 | Fire Protect | 2020-02-18 | 2020-02-14 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.FP.VASV-331130 | Firewater to Helideck Fire Hydrant | 2019-08-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-18 | 118408000000 | 30 | 10 | 7000004211 | Bib Nose Hydrant Reducing valve ANSI CLA | 2020-02-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11840847 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-11-03 | USAWJB | 10 | EA | 0 | Fire Station 093 passing valve | REL PCNF ESTC PPRT PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 440 | 1000968170 | MODULE,SLOT FILLER,ALLENB,1756-N2 | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 430 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 4 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60737084 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-02-08 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-219 | Crude Oil to/from Fwd COT'S On/Off Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-08 | 116406000000 | 10 | 20 | 7000000070 | MI FP03/S0A/C3/43/SC/V/67A- 24D/M/50 | 2020-04-28 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-10 | U182 | 8201 | Stones Main | ST KB B6 | 11640589 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635S-219 | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 90 | 1000709396 | NPHT,SWAGELOK,SS-8-HLN-2.00,1/2in,NPTM | 2019-11-20 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI68 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 2 | EA | 2 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
61006508 | 508 | Replace BGC A position indicator couplin | S04 | Gas Compress | 2020-04-01 | 2020-04-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.ZZZ-77102A | Booster Gas Compressor Package A | 2020-01-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-03 | 119629000000 | 30 | 30 | 7000003464 | HARDWARE 316SS MOUNTING HARDWARE FOR TOP | 2020-04-01 | Received at Worksite | 2020-01-23 |  |  | U182 | 8201 | Stones Main | Stones | 11962884 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-01 | USNSB4 | 8 | EA | 8 | Replace BGC-A Valve Position Indicators | REL ESTC GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | ST1B1SIDE 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3050 | 7000002603 | 2" Flange Protectors, 3", 300 RFWN | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 335 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 140 | 7000002646 | ½” Swagelok Check Valve, MNPT, 6000 PSI | 2019-10-18 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 38 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN091 | Name 2 | Name 2 | 2019-09-23 | USGBI5 | 1 | EA | 1 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1310 | 7000002596 | 5/8'' Tapered Washers-Galv | 2020-05-14 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | Crane Access Platform | 11581207 | 131 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A372 | Name 2 | Name 59 | 2019-12-09 | USSOLE | 20 | EA | 20 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61155254 | 508 | Production Swivel Bearing Flush | S19 | Marine Systems | 2020-03-03 | 2020-03-11 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.MS895 | Production Swivel Stack | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-03 | 121329000000 | 10 | 10 | 1002386972 | OIL,LUBT,SHELL,OMALA S4 GXV 460,20 l | 2020-03-03 | Received at Worksite | 2020-02-17 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A2B | 12132861 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-02-04 | USMNF8 | 5 | PAI | 4 | Production Swivel Bearing Flush | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAXX WPOK | EXEC |  |  | ST1A2B 02/12/2020 CMR 4ea
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 320 | 1001807843 | FLSO,A105,RF,CL150,NPS2 | 2020-05-13 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G14 | 11581210 | 32 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12091901 | Name 4 | Name 60 | 2019-12-09 | USSOLE | 4 | EA | 4 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 30 | 7000003344 | Plate, 1/4" x 48" x 48", ASTM A36 | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 1 | EA | 1 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
60701397 | 508 | Leaking Globe/Check Valve on Hydrophore | S18 | Water Systems | 2020-04-11 | 2019-10-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.121-20V | Tank Outlet Check Valve | 2020-01-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-11 | 116003000000 | 20 | 80 | 7000000103 | 5k 40mm Globe valve | 2020-04-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11600310 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-11 | USMNF8 | 1 | EA | 0 | Drain Hydrophore Tank | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
60440621 | 508 | Replace Laydown Timber - MODs 15, 17, 19 | S40 | Cargo Handling | 2020-03-10 | 2020-06-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.LS | Loading Stations | 2019-08-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 113072000000 | 10 | 10 | 7000002583 | 3 X 8 X 8 MARINE GRADE .6 PRESSURE | 2020-03-10 | Received at Worksite |  | 2019-09-11 |  | U182 | 8201 | Stones Main | Starboard laydown | 11307214 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-05 | USAWJB | 32 | EA | 32 | Replace Laydown Timbers - MOD 15 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAOK RUSH WPOK | EXEC |  |  | PU CARGO TEAM
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 360 | 7000002591 | MILWAUKEE Magnetic Drill Press, 120VAC, | 2020-06-30 | Received at Target Location |  | 2019-12-12 |  | U182 | 8201 | Stones Main | STONES | 11739629 | 36 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO110EREN | Name 56 |  | 2019-12-12 | USABCE | 1 | EA | 1 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 20 | 40 | 7000003196 | SS-400-9 ELBOW UNION | 2019-12-08 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | Issued | 11614811 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 7 | USNSB4 | 2019-06-20 | USNSB4 | 2 | EA | 2 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
60836536 | 508 | Replace hour counter of Water Maker #1 | S18 | Water Systems | 2020-04-21 | 2020-06-27 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-11-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-21 | 117681000000 | 10 | 10 | 7000005901 | 2125009 HOUR METER 230V RK6 50/60HZ | 2020-04-21 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11768107 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-20 | USNSB4 | 1 | EA | 0 | Replace Hour Counter Of Water Maker #1 | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61118367 | 508 | 2020 Catering - Material | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 10 | 7000003454 | Martex Brentwood 60X30 Cotton Bath Towel | 2020-02-28 | Not Shipped |  | 2020-01-15 |  | U182 | 8201 | Stones Main | STONES | 12090704 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOR11620A | Camp Boss | USJRF5 | 2020-01-16 | USLFA4 | 15 | PK | 0 | 2020 Catering - Material | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4250 | 1001816211 | GASW,CL150,316,GPH,NPS2 | 2019-11-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 477 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11121901 | Name 4 | Name 4 | 2019-11-12 | USLFA4 | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2140 | 7000002596 | STUD BOLTS, 7/8" DIA. X 7 1/2" LONG, AS | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 236 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011903 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 12 | EA | 12 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2770 | 1002316830 | GASW,CL300/600,316/316L,GPH,3in | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 301 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 55 | EA | 55 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6110 | 7000002629 | Butt Weld Boss, 6" x 3", Class 700, 90/1 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 709 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4130 | 7000002596 | Bolt, 3/4" x 3 3/4" Lg., ASTM F3125 Gr. | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 463 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 102 | EA | 102 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60055275 | 508 | O/SI Incorrect material on gauge LG-7715 | S04 | Gas Compress | 2020-04-11 | 2019-03-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.LG-77151A-231A | 1st Stage Suction Scrubber Level Gauge | 2019-02-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-11 | 108488000000 | 10 | 20 | 1002360785 | SB2N,B7,2H,UNC,5/8in,3.25in,DOXSTEEL | 2020-04-11 | Ready for Shipment after Kitting | 2019-02-25 | 2019-03-27 |  | U182 | 8201 | Stones Main | ST KB C7 | 10848765 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-02-12 | USJDJW | 8 | EA | 8 | LG-7715 change bolting/gaskets | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
60998635 | 508 | O/SI Passing Valve Boiler #2 Vent Valve | S17 | Steam/Hot H2O | 2020-04-01 | 2019-12-12 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.NAC-11503B | Auxiliary Boiler No. 2 | 2019-12-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119540000000 | 20 | 10 | 7000004211 | EP-GVB20X25KM, F-7421 FORGED STEELL GLOB | 2020-05-31 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11953957 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-12 | USNSB4 | 1 | EA | 0 | LO/TO Perform Isolations | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 110 | 7000002603 | 12" Flange Protectors for 12" JIS 10K Fl | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 4 | EA | 4 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
61131887 | 508 | Renew oil return sight glass. | S14 | HVAC | 2020-02-20 | 2020-06-23 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.HV.SPSG-108-505 | Refrig Comp 1B Oil Return Sight Glass | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-20 | 121058000000 | 10 | 10 | 7000000098 | Refrigeration compressor oil return sigh | 2020-02-20 | Received at Worksite | 2020-02-07 | 2020-01-10 | 2020-02-23 | U182 | 8201 | Stones Main | Issued | 12105756 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 20 |  | 2020-01-10 | USAMH7 | 1 | EA | 1 | Renew oil return sight glass. | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A1C 02/07/2020 CMR
60177919 | 508 | Mod 6 - vlv long bolts Diss metals | S04 | Gas Compress | 2020-06-01 | 2019-06-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VABL-771251 | Cooler Press Diff Transmitter Iso Valve | 2019-08-26 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-06-01 | 110146000000 | 10 | 50 | 1002316822 | GASW,CL150,316/316L,GPH,1.1/2in | 2020-06-01 | Ready for Shipment after Kitting | 2019-10-29 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB D3 | 11014637 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-26 | USNSB4 | 5 | EA | 5 | LO/TO Shutdown Down Process Train, De-In | REL ESTC CSER GMPS PRC SETC | EXEC EOM MAGN MAKD MANX WPOK | EXEC |  |  | PU WPT 11-25-19
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 310 | 7000003852 | MacWork 5-Piece Offset Ratcheting Spanne | 2020-12-07 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 31 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES11 |  |  | 2019-11-11 | USABCE | 2 | EA | 2 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
60737084 | 508 | Solenoid & VPI test fail 5S | S21 | Oil Treating | 2020-02-08 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-219 | Crude Oil to/from Fwd COT'S On/Off Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-08 | 116406000000 | 10 | 40 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-04-28 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-10 | U182 | 8201 | Stones Main | ST KB B6 | 11640589 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635S-219 | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60906380 | 508 | 6M Swivel Stack Maintenance | S19 | Marine Systems | 2020-02-25 | 2020-03-14 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-89801 | Swivel Drive System | 2019-08-28 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 3 Normal | 2020-02-25 | 118480000000 | 20 | 10 | 1002493892 | GREASE,LUBT,SHELL,GADUS S2 V100 2 | 2020-02-25 | Received at Worksite |  | 2020-01-11 |  | U182 | 8201 | Stones Main | ST KB A7 | 11847965 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2020-01-11 | USAMH7 | 2 | CS | 2 | 6M Swivel Stack Insp and Valve Exercise | REL CNF PRT GMPS PRC SETC | SCHD MAOK WPOK | EXEC |  |  | PU 02/16/20 AMW
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 50 | 7000004213 | KE35/8 SASAKURA KE35 P/N 8 ORIFICE FLANG | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 2 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 930 | 7000002591 | RIDGID 38048 Model 608 Heavy-Duty Pipe B | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 93 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60699172 | 508 | O/SI Valve XV-1122S-326 over rotating Ba | S19 | Marine Systems | 2020-04-08 | 2019-10-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.BB.XV-1122S-326 | WB Tank No. 1S Water Line Ballast Valve | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-09 | 115978000000 | 40 | 20 | 7000004211 | Repair Kit for Hydraulic Actuator Model | 2020-04-06 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11597808 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 2 | EA | 0 | Prep tank for entry | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 800 | 1000671260 | SUPER METAL,POLYMER,BELZONA,1111,Gry,1kg | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 80 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 1 | KG | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 650 | 1001676774 | SHT PLT SLD MET,4x4ft,3/4in,A572 GR.50 | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 65 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 210 | 1002316829 | GASW,CL300/600,316/316L,GPH,2in | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 117 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 3 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 510 | 1001267401 | CHANNEL,4in,5.4lb/ft,20ft | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 51 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 60 | FT | 60 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61070222 | 508 | Change out dryer #3 | S09 | Bldg & Qtrs | 2020-04-01 | 2019-12-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.BQ.ROOM-119 | Laundry Room | 2019-12-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2019-12-21 | 120352000000 | 10 | 10 | 1002582807 | TUMBLE DRYER,ELCTROLX,TD6-20,75mm | 2019-12-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12035227 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2019-12-03 | USAWJB | 1 | EA | 0 | Change out dryer #3 | REL ESTC CSER PRC SETC | APPR WPOK ZPMM | Deleted
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 60 | 1001676774 | SHT PLT SLD MET,4x4ft,3/4in,A572 GR.50 | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 1 | EA | 1 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 90 | 1001645336 | BLT HEX,A325,UNC,3in,3/4in | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 64 | EA | 64 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 70 | 7000000039 | YMD-8529 HOSE ASSEMBLY X31"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 260 | 7000002591 | 20Pack Abrasive Flap Wheel Sander，1" x 1 | 2020-02-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 26 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60548440 | 508 | Hose end valve blank | S21 | Oil Treating | 2020-02-04 | 2019-03-01 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.ZZZ-66450 | Cargo Offloading Primary Hose | 2019-08-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-04 | 114265000000 | 10 | 10 | 7000000098 | Aluminum Hose End Assemble Blanking Plat | 2020-02-04 | Received at Worksite | 2020-01-13 |  | 2020-01-25 | U182 | 8201 | Stones Main | Issued | 11426452 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 57 | USMSLN | 2019-03-12 | USRAR6 | 1 | EA | 1 | Hose end valve blank | TECO CNF ESTC GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU AARON W 01/24/20 GG
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 20 | 150 | 7000000068 | DK 1535-02120 DEKORON RTV HIGH TEMP END | 2019-12-08 | Received at Target Location |  | 2020-02-28 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11614811 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI64 | Name 2 | USNSB4 | 2019-11-05 | USSOLE | 1 | EA | 1 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5970 | 7000002662 | Pipe, 2", SMLS Class 700, 90/10 CuNi All | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 695 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 180 | FT | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1750 | 1001816212 | GASW,CL150,316,GPH,NPS1.1/2 | 2019-01-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 192 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01171901 | Name 2 | Name 2 | 2019-01-18 | USDSVB | 6 | EA | 6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5370 | 7000002644 | NEEDLE VALVE, 1/2" 6000 PSI MNPT X FNPT | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 598 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2900 | 7000002629 | Elbow, 3", 45, S/10S, BW, ASME B16.9, A | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 320 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 7 | EA | 7 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3740 | 1001271538 | ANGL MTL,EQ,CS,20ft,L4x4x1/4in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 404 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61175103 | 508 | Barrier Fluid HPU Sample Mod | S24 | Subsea Systems | 2020-03-03 | 2020-03-19 | O.US.STO.STO.002.724FP | 508ACR | US.WR508A.SE.OH.ZZZ-12865 | Barrier Fluid Hydraulic Power Unit | 2020-01-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-03 | 121557000000 | 10 | 20 | 7000003512 | 2507-T6-S-049-20-CP SAF 2507 TUBING WITH | 2020-03-03 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | Behind Kitting Box | 12155741 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-29 | USNSB4 | 20 | FT | 20 | Install Needle Valves & Fabricate Tubing | REL GMPS PRC SETC | SCHD EOM MAGN MAOK WPOK | EXEC |  |  | PU A WISTRAND 02/24/2020
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 120 | 7000004213 | KE35/15 SASAKURA KE35 P/N 16 COMPOUND GA | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 12 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2340 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 256 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 244 | EA | 275 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61102257 | 508 | P.Crane radiator fan shroud corroded | S40 | Cargo Handling | 2020-05-10 | 2020-06-10 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-10 | 120716000000 | 10 | 10 | 7000006081 | Fan Guard RS -7370FGSC | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12071582 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 2 | EA | 0 | P.Crane radiator fan shroud corroded | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6230 | 7000002644 | Ball Valve, 1/2", VBT-320MV A M x FNPT | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 721 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 30 | 7000002629 | Blind Flange, 500mm, JIS 5K, JIS B2220 ( | 2020-03-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E27 | 11477345 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05141901 | Entity 2 | USAWJB | 2019-05-14 | USSOLE | 2 | EA | 2 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
61175887 | 508 | LACT -Drain Valves Severely Corroded | S21 | Oil Treating | 2020-03-14 | 2020-03-25 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-24 | 121566000000 | 50 | 40 | 7000004751 | 1" 150 RF Flex Gaskets | 2020-03-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12156642 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-25 | USNSB4 | 38 | EA | 0 | Replace Defective Valves On LACT Skid | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4550 | 7000002629 | Flange, 3", 300#, RFWN, S/10S Bore, ASME | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 507 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 11 | EA | 11 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6890 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 937 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 90 | 7000003197 | Nylon Washer M20 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 2 | EA | 2 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 190 | 7000002644 | 4" 150# RF FP WKM Floating Ball | 2019-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 207 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN046 | Name 2 | Name 2 | 2019-01-25 | USSOLE | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60593001 | 508 | damaged pipe and check valve | S19 | Marine Systems | 2020-04-14 | 2019-08-02 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-04-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-21 | 114773000000 | 10 | 20 | 7000002629 | Flange, 500mm, JIS 5K, JIS B2220, SFVC1 | 2020-03-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E27 | 11477345 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05141901 | Entity 2 | USAWJB | 2019-05-14 | USSOLE | 2 | EA | 2 | R&R damaged pipe and check valve | REL PCNF ESTC CSER GMPS PPRT PRC SETC | APPR EOM MAGN WP | Approved
61208398 | 508 | UPS- blown fuses- Monitoring System | S03 | Elect. Systems | 2020-12-05 | 2021-02-10 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.CV.BMS-44502 | LER UPS Room Battery Monitoring System | 2020-02-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-12-05 | 121939000000 | 10 | 10 | 7000000090 | 0W2015 WIRE HARNESS 5A 600VDC FUSE | 2020-03-05 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12193856 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-17 | USAWJB | 40 | EA | 0 | UPS- blown fuses- Monitoring System | REL ESTC PRC SETC | APPR MAGN | Approved
60959173 | 508 | COP1 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-06 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PBE-66301A | Cargo Oil Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-12 | 119077000000 | 10 | 80 | 7000000038 | 3/8" fnpt SS wye strainer | 2020-03-06 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 11907749 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-17 | USRAR6 | 1 | EA | 1 | Add seal flush plan 12 to COP1 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
61023509 | 508 | Grating on green mile needs replacing. | S19 | Marine Systems | 2020-06-01 | 2019-12-25 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.HG | Handrails, Stairways, Grating | 2020-02-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-06-02 | 119822000000 | 10 | 70 | 1001723501 | WASHER,FLAT,F436,SERMAGAURD,1/2in | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G87 | 11982221 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02172001 | Name 4 | Name 60 | 2020-02-19 | USSOLE | 36 | EA | 36 | Grating on green mile needs replacing. | REL ESTC PRC SETC | APPR EOM MAGN MANX WPOK ZPMM | Approved
61089250 | 508 | Seawater Course Filter A Clogged | S18 | Water Systems | 2020-02-20 | 2020-06-02 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2020-01-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-21 | 120564000000 | 10 | 10 | 7000003684 | 5 GALLON QD-500 DESCALER, QTY:6 | 2020-02-20 | Received at Worksite | 2020-01-22 | 2020-02-01 | 2020-02-27 | U182 | 8201 | Stones Main | Chemical locker | 12056376 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 14 |  | 2019-12-13 | USMNF8 | 6 | EA | 6 | Clean Filters Pulled From B Unit | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO |  |  | ST1LD 01/29/20 GG
61074267 | 508 | O/SI SDV-66201-864 Needs Replacement | S22 | Prod Gathering | 2020-03-10 | 2020-01-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.SDV-66201-864 | Separator Crude Oil Outlet Shutdown Vlv | 2020-01-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-11 | 120397000000 | 10 | 10 | 1002404371 | PLUG+PLAY ASSY,N-2-RF3-R-UU-L-F-A,VIRGO | 2020-01-30 | Received at Worksite | 2020-01-02 | 2020-02-08 |  | U182 | 8201 | Stones Main | Module 14 | 12039685 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2019-11-30 | USAWJB | 1 | EA | 1 | LOTO and Deinventory 1 stage Separator | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | FRNTMOD.14 02/07/2020 CMR
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 250 | 7000002591 | 3/4" drive torque wrench. 120-600 ft-lb. | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0140 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60629360 | 508 | GT #1 Replace Air intake button plugs | S03 | Elect. Systems | 2020-03-15 | 2020-02-21 | O.US.STO.STO.005.724FP | GGTSSLTB | US.WR508A.ES.PG.LAN-11110 | Gas Turbine Power Generation Package 1 | 2019-07-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-15 | 115191000000 | 10 | 40 | 7000003739 | Conduit Plug PN 1739552 | 2020-03-15 | Received at Worksite |  | 2020-01-20 |  | U182 | 8201 | Stones Main | ST KB B7B | 11519116 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-24 | USAWJB | 2 | EA | 2 | GT #1 Replace Air intake button plugs | REL PRT GMPS PRC SETC | EXEC MAGN MAOK WPOK | EXEC |  |  | PU Aaron 01/19/2020
61219231 | 508 | GT #1 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113 | Generator #1 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 50 | 7000003763 | 2012 1-7/16 BUSHING | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206815 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #1 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
60902479 | 508 | Rusted door pin hinges on Sea Chest Blan | S19 | Marine Systems | 2020-02-18 | 2020-02-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.BB.VE112 | Ballast System | 2019-11-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-18 | 118434000000 | 10 | 10 | 7000000039 | 3/16" aluminum storage cabinet | 2020-02-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 11843432 | 1 | 4 | Non-Stock (Purchase Requisition) | N | [5 empty] | 2019-11-08 | USJDJW | 2 | EA | 0 | replace sea chest cabinet | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61065367 | 508 | Crude Transfer to Shuttle Tanker | S21 | Oil Treating | 2020-02-23 |  | O.US.STO.STO.005.71300 | 508COPER | US.WR508A.OT.SS.TS664-00000 | Upper Deck Cargo Offloading System | 2019-11-24 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 3 Low | 2020-02-24 | 120296000000 | 10 | 10 | 7000003852 | VideoSecu TV Wall Mount Articulating Arm | 2020-03-14 | Received at Worksite |  |  | 2020-02-29 | U182 | 8201 | Stones Main | STONES | 12029623 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0150 | CARGOSUP | USCRFI | 2020-02-19 | USCDP7 | 2 | EA | 2 | WK Crude Transfer to Shuttle Tanker | TECO CNF GMPS PPRT PRC SETC | XCNF XGI | TECO
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 20 | 1001676149 | NUT,A563-DH,HEXAGONAL,UNC,3/8,SERMAGARD | 2019-06-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Lower Turret Fire Extingu | 11545759 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A308 | Name 2 | Name 2 | 2019-06-03 | USSOLE | 40 | EA | 40 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 540 | 7000002591 | 4452K256 Straight Reducer, 3/4 x 1/4 NPT | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 54 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 130 | 7000002591 | 4548K175 1/2 NPT, 3" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61201257 | 508 | Slew gearbox 1 high ferrous oil sample | S40 | Cargo Handling | 2020-03-28 | 2020-04-08 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-29 | 121856000000 | 10 | 40 | 7000006081 | PB-304-100-050 1''X 1/2 BUSHINGS S/S | 2020-03-28 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12185593 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-13 | USAWJB | 4 | EA | 0 | Change and Flush Oil Slew gearbox 1 | REL ESTC PRC SETC | APPR MAGN MANX WPOK ZPMM | Approved
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 120 | 7000003852 | Simplistex - 3x1 HDMI Switcher/Selector | 2020-04-05 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | AJH021620 | Name 12 | USRRIG | 2020-02-19 | USCDP7 | 1 | EA | 1 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 20 | 7000002591 | Grainger 1-1/2 tailpiece #1PNY8 | 2020-01-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0005 | Name 8 | USCRFI | 2020-01-13 | USLFA4 | 3 | EA | 3 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
61049139 | 508 | HP/LP Piston Failure | S08 | Air Systems | 2020-02-12 | 2020-01-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11804A | Start Air Compressor No. 1 | 2020-02-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-14 | 120119000000 | 20 | 10 | 1002404741 | LP PISTON,3396MK,SPERRE | 2020-02-12 | Received at Worksite | 2020-02-13 | 2020-02-13 |  | U182 | 8201 | Stones Main | ST KB A3 | 12011865 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 1 | EA | 1 | Rebuild Start Compressor #1 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAKD MAXX RUSH WPOK | EXEC |  |  | ST1A3C 01/18/2020 CMR
60847987 | 508 | MOC GTG3 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-24000 | Gen #3 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 40 | 7000005901 | M20 Serrated Washer | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780940 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI78 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #3 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60884227 | 508 | Lagging for new 16 K Bellows | S17 | Steam/Hot H2O | 2020-03-03 | 2019-10-05 | O.US.STO.STO.005.724FP | GISNCANI | US.WR508A.GU.SW.VE115-41000 | 16K Steam System in Engine Room | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-03 | 118224000000 | 20 | 10 | 7000000132 | Fire blanket, 22" x 24" | 2020-03-03 | Received at Worksite | 2020-01-13 | 2020-01-24 |  | U182 | 8201 | Stones Main | Issued | 11822353 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-06 | USMNF8 | 1 | EA | 1 | Install Pipe insulation on flange | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 2/5/2020 JH GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5100 | 7000002629 | THREADOLET, 8 X 1/2" 3000LB ASTM A182 GR | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 571 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61165414 | 508 | Install Needle Valve on PG-33120-731 | S13 | Fire Protect | 2020-03-10 | 2020-03-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33120-731 | FW Lift Pump Outlet Pressure Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-10 | 121447000000 | 10 | 20 | 7000003196 | OA,US,SWAGELOK,FITTINGS,EA | 2020-03-10 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144699 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 1 | EA | 1 | Install Needle Valve on PG-33120-731 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3750 | 1001663814 | SHT PLT SLD MET,4x4ft,1/4in,A572-50 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 405 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7460 | 1002062555 | NUT,A563-DH,HEXAGONAL,UNC,7/8,SERMAGARD | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1004 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 28 | EA | 28 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60973122 | 508 | MGC-B 3rd Stg Bridle Removal | S04 | Gas Compress | 2020-04-18 | 2020-09-25 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-10000 | Main Gas Compression System Train B | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-19 | 119235000000 | 10 | 40 | 7000004751 | 7/8" X 9.5 Studs & Nuts | 2020-03-19 | Received at Worksite | 2020-01-06 | 2020-01-06 |  | U182 | 8201 | Stones Main | ST KB C7 | 11923512 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 59 | 2019-10-02 | USAWJB | 32 | EA | 32 | MGC-B 3rd Stg Bridle Removal MOC78183 | REL PRT GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU WPT AMW 11/30/19
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 50 | 1002309185 | SB2N,B8M CL2,8M,UNC,3/4in,4.25in | 2019-11-29 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | WP 194/ 198 SOLIDS | 11179936 | 536 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 2 | 2019-11-20 | USABCE | 28 | EA | 28 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 360 | 7000000086 | Model# 2711P-T15C22D9P AB Panel View | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 422 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
60665884 | 508 | O/SI Passing Valve SW.115-304V | S17 | Steam/Hot H2O | 2020-03-25 | 2019-09-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.115-304V | PCV Bypass Valve | 2019-11-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-26 | 115603000000 | 30 | 30 | 7000004211 | ham-hand-150 HAMMER HANDWHEEL | 2020-06-07 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11560290 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-25 | USNSB4 | 1 | EA | 0 | Replace 8" Control Valve SW.115-304V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7780 | 7000002662 | Pipe, 1", S/10S, ASME B16.19M, ASTM A312 | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1048 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 120 | FT | 123.9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 50 | 7000002591 | 3M Cold Shrink (3M 8425-8) | 2019-11-27 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI67 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 4 | EA | 5 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
60747149 | 508 | COT 2 STBD HC line Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127023 | COT 2 SB HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651961 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 30 | 7000002629 | Elbow, 2", LR 90, S/80S, BW, ASME B16.9 | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 99 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 100 | 7000003852 | MSA 10107602 ALTAIR 4X Gas Detector, Cha | 2021-03-01 | Received at Target Location |  | 2020-02-03 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOACR02BA | Name 18/Name 34 | USJRF5 | 2020-02-21 | USCDP7 | 3 | EA | 3 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60985335 | 508 | VABF-122009 Passing By | S18 | Water Systems | 2020-03-03 | 2019-11-30 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.VABF-122009 | Filter Backwash Water Outlet Valve | 2019-10-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-03 | 119372000000 | 20 | 10 | 7000004211 | 4IN150-CBFV-ISLIP | 2020-03-03 | Received at Worksite | 2019-11-13 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB D1 | 11937181 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 1 | USNSB4 | 2019-10-29 | USNSB4 | 1 | EA | 1 | Replace VABF-122009 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD WPOK | EXEC
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 20 | 7000003196 | SS-810-3-8TMT MALE RUN TEE | 2020-02-24 | Received at Worksite |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-09 | USNSB4 | 1 | EA | 1 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
61112406 | 508 | 2nd Stg Sep PST upgrade | S22 | Prod Gathering | 2020-04-11 | 2020-06-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.PST-66202-178 | 2nd Stg Separator Press Sfty Transmitter | 2019-12-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-11 | 120837000000 | 20 | 80 | 7000002644 | 1/2" Parker DBB valve | 2020-04-11 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 12083677 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-12 | USMNF8 | 10 | EA | 10 | Upgrade PST-66202-178 To Rosemount Trans | REL ESTC GMPS PPRT PRC SETC | APPR EOM MAGN MAOK RUSH WPOK ZPMM | Approved
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 30 | 7000004743 | 1- 500 gallon tote of Triethylene Glycol | 2020-01-20 | Received at Target Location |  | 2019-12-23 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200003A | Entity 6 | USRRIG | 2020-01-14 | USLFA4 | 500 | GLL | 500 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 130 | 7000003684 | UNCOATED COBALT STEEL DRILL BIT SET | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 13 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 80 | 7000005811 | 15# Loaner extinguishers CO2 | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 9 | EA | 0 | Send In/Replace Fire Ext Due Hydro | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60797147 | 508 | A/C Condenser Intermittent Operation | S40 | Cargo Handling | 2020-03-24 | 2019-08-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-07-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-27 | 117216000000 | 40 | 10 | 7000000040 | GEN 36 HOIST & LIFTING EQPT | 2019-08-27 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 11721562 | 3 | 4 | Non-Stock (Purchase Requisition) | N | [5 empty] | 2019-07-31 | USNSB4 | 1 | EA | 0 | Repair Service, Crane AC. | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM ZPVS | Deleted
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 600 | 1001991793 | PIPE MET,API 5L-X42,BARE,40,1.1/2in,SRL | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 60 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 273 | FT | 282.7 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61185292 | 508 | 6M Structural Support Function Tests | S19 | Marine Systems | 2020-05-05 | 2020-05-23 | O.US.STO.STO.005.724FP | 508OPER | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2020-02-12 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 1 Safety / TI Critical | 2020-05-05 | 121673000000 | 20 | 10 | 1002386543 | GREASE,LUBT,SHELL,GADUS S2 V220 2,18kg | 2020-05-05 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main |  | 12167268 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  |  |  | 2020-02-12 | USRAR6 | 2 | PAI | 2 | 6M Functional Test of Backup Release | REL ESTC GMPS ILNC PRC SETC | APPR MAOK | Approved |  |  | ST1A3A 02/14/2020 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 440 | 1001645338 | BLT HEX,A325,UNC,2.1/4in,3/4in | 2019-11-20 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 44 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06141901 | Name 2 | Name 59 | 2019-06-17 | USDKFB | 12 | EA | 12 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61109055 | 508 | Hilti clip installation engine room | S06 | General | 2020-10-05 | 2020-12-11 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GN.MI.HG | Handrails & Grating | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-10-06 | 120800000000 | 10 | 40 | 7000002583 | 10 EA 377079 Stepped drill bit TX-BT 4/7 | 2020-10-05 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12079993 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USMRRO | 2020-02-18 | USMRRO | 10 | EA | 0 | Hilti clip installation engine room | REL PPRT PRC SETC | APPR MAGN WPOK ZPMM | Approved
61142367 | 508 | SDTA Reprocess manifold Duplex Elbow | S26 | Water Treating | 2020-10-25 | 2020-12-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT | Water Treating Systems | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-10-25 | 121177000000 | 10 | 10 | 7000000113 | Gaskets for water treatment elbow | 2020-10-25 | Received at Worksite | 2020-01-17 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB D4 | 12117706 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-08 | USAMH7 | 2 | EA | 2 | SDTA Reprocess manifold Duplex Elbow | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A4D 02/3/20 GG
60847987 | 508 | MOC GTG3 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-24000 | Gen #3 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 30 | 7000005901 | M20 Nylon Washer | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780940 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI78 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #3 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60989313 | 508 | Erratic Speed Reading Steam Turbine #3 | S21 | Oil Treating | 2020-02-11 | 2020-04-04 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.OT.SS.CPI-66301C | Steam Turbine Control Panel | 2019-10-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-11 | 119417000000 | 20 | 50 | 7000005901 | 1/4-20 x 1" S/S HEX HEAD BOLTS & WASHERS | 2020-02-11 | Received at Worksite | 2019-11-21 | 2020-01-19 | 2020-02-19 | U182 | 8201 | Stones Main | ST1A5B | 11941691 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | 3.54 | 2019-10-24 | USNSB4 | 20 | EA | 20 | Replace Existing Cable With Shielded Cab | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD WPOK XGI | TECO |  |  | PU AMW ST1A5B
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 110 | 7000004211 | ANS200x150x350/PN-30 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 2 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 540 | 7000002629 | FULL FACE BLEED RING, 8", 300#, RF, 1.5" | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 70 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 150 | 7000002603 | Gasket, 12", JIS 10K, 1/8" THK, Garlock | 2020-01-17 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01152001 | Name 4 | Name 60 | 2020-01-16 | USSOLE | 4 | EA | 4 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2500 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2019-04-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 272 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04021905 | Name 2 | Name 2 | 2019-04-03 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60562362 | 508 | O/SI Passing Valve 3rd stage PST-330A MG | S04 | Gas Compress | 2020-03-10 | 2019-03-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VAMO-771031 | Pressure Transmitter Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 114424000000 | 30 | 80 | 7000002591 | PERMATEX 81724 SENSOR-SAFE ULTRA BLUE | 2020-03-10 | Received at Worksite |  | 2020-02-07 |  | U182 | 8201 | Stones Main | ST1A4C | 11442408 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-03 | USMNF8 | 2 | EA | 2 | Replace Defective Valve 3rd stage PST-33 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC |  |  | ST1A3C 02/3/20 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5270 | 1002360782 | SB2N,B7,2H,UNC,5/8in,4in,DOXSTEEL | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 588 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 80 | EA | 80 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4950 | 7000002629 | TEE, 4" SCH 40 BW ASTM A234 WPB | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 556 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 7 | EA | 7 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5400 | 7000002603 | GASKET, 4" 300LB, RF (Hydro Only) | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 601 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 9 | EA | 9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7610 | 7000002644 | Ball Valve, 3/4", VBT-602SS | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 1024 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6430 | 7000002629 | Flange, 2", 300#, RFWN, S/40S Bore, ASME | 2020-02-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 807 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01282001 | Name 4 | Name 4 | 2020-01-29 | USDKFB | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1870 | 7000002596 | STUD BOLTS, 1 1/8" DIA. X 7" LONG, W/ | 2019-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 205 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01241901 | Name 2 | Name 2 | 2019-01-24 | USSOLE | 54 | EA | 54 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 30 | 7000000052 | Orion Level Instrument | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2301 | 11340898 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN103 | ORION | ORION | 2019-11-19 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1000 | 7000003852 | Channellock, 818N, Adjustable Wrench, 18 | 2021-03-31 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 100 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST20CG0146 | MarineForman | USRRIG | 2020-02-20 | USCDP7 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60717786 | 508 | #3 latching dog cylinder bolts are broke | S19 | Marine Systems | 2020-02-18 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-21 | 116191000000 | 10 | 30 | 7000003852 | Precision Twist C29M40CO Cobalt Steel Sh | 2020-02-18 | Received at Worksite |  | 2019-10-27 | 2020-02-07 | U182 | 8201 | Stones Main | Issued | 11619069 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 14 |  | 2019-05-20 | USMNF8 | 1 | EA | 1 | Gather tools and equipment | TECO PRT GMCO GMPS PRC SETC | XCNF MAGN MAOK NCMP WPOK XGI | TECO |  |  | PU Aaron 06/11/2019 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 690 | 7000002596 | Bolt, 3/4" x 1 3/4" LG, ASTM F3125 Gr. A | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 69 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 10 | EA | 10 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 10 | 7000002596 | BLT+N A193B8MCL2 UNC 11in,1.1/2in | 2019-05-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E35 | 11545759 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05291902 | Name 2 | Name 2 | 2019-05-29 | USSOLE | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1250 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2020-05-07 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G04 | 11581207 | 125 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031901 | Name 4 | Name 59 | 2019-12-04 | USSOLE | 3 | EA | 3 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 480 | 7000002591 | 4452K174 Bushing Adapter, 1 Male x 3/8 F | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 48 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61089207 | 508 | Slip hazard inside GT1 enclosure | S03 | Elect. Systems | 2020-04-28 | 2020-06-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.LAN-11110 | Gas Turbine Power Generation Package 1 | 2019-12-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-28 | 120563000000 | 10 | 20 | 7000003852 | Tape King Anti Slip Traction Tape - 4 In | 2020-04-28 | Received at Worksite | 2019-12-17 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST1A6C | 12056334 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-11 | USMNF8 | 5 | EA | 5 | LOTO GT1 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A6C 01/19/2020 AMW
61104113 | 508 | EWS55001 Hard Drive #3 failed | S20 | Monitor & Ctrl | 2020-02-08 | 2020-12-08 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.MC.DC.FWD | Firewalls and Devices | 2019-12-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-02-11 | 120737000000 | 10 | 10 | 7000003852 | ORICO 2.5 to 3.5 Hard Drive Adapter HDD | 2020-02-08 | Received at Worksite | 2019-12-20 | 2020-01-19 | 2020-02-12 | U182 | 8201 | Stones Main | ST KB B7D | 12073690 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-15 | USMNF8 | 3 | EA | 3 | Configure Hard Drive #3 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
61209426 | 508 | Sub-Order To Purchase Magnets In Advance | S19 | Marine Systems | 2020-03-24 | 2020-04-15 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2020-02-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-24 | 121952000000 | 10 | 10 | 7000002591 | CERAMIC MAGNET W/UNTHREADED HOLE 1/4" TH | 2020-03-24 | Received at Worksite | 2020-02-26 |  |  | U182 | 8201 | Stones Main | Stones | 12195195 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-02-18 | USNSB4 | 48 | EA | 48 | Sub-Order To Purchase Magnets in advance | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 150 | 7000003852 | Logitech Spotlight Presentation Remote - | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | Stones | 12090697 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 34 |  | 2020-02-10 | USJRF5 | 1 | EA | 1 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61041516 | 508 | Replace Scott EEBDs With Ocenco EEBDs | S15 | Life Saving | 2020-02-11 | 2020-01-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.PP-EE | Emergency Escape Personal Prot Equipment | 2020-01-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-17 | 120021000000 | 10 | 10 | 7000005811 | Ocenco EEBD | 2020-02-14 | Received at Worksite | 2020-01-28 | 2020-02-10 |  | U182 | 8201 | Stones Main | STONES | 12002097 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 100 | EA | 100 | Replace Scott EEBDs With Ocenco EEBDs | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK RUSH WPOK | EXEC |  |  | PU FRANK D 02/07/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2600 | 1002309190 | STUD BOLTS, 7/8" DIA. X 5 1/2" LONG, AST | 2019-04-22 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 282 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04081901 | Name 2 | Name 2 | 2019-04-08 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7590 | 7000002603 | GASKET,GARLOCK,STRESS SAVER XP,4in | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 1021 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-16 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3640 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Stones Solids Tie-in | 11179936 | 394 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161902 | Name 4 | Name 4 | 2019-10-17 | USGBI5 | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3450 | 1000710324 | FTG_PIPE,PLUG,3/4",316 SS | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 375 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 260 | 7000003197 | MCT Frame, R 75B Ex AISI316/AISI316 (Rox | 2020-04-06 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 26 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI92 | Name 2 | USMCS1 | 2020-02-19 | USLFA4 | 2 | EA | 0 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6420 | 7000002629 | Flange, 3", 300#, RFWN, S/10S Bore, ASME | 2020-02-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 806 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01282001 | Name 4 | Name 4 | 2020-01-29 | USDKFB | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 770 | 7000002629 | Blind Flange, 2", 150#, RF, ASME B16.5, | 2020-03-02 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose |  | 11179936 | 1043 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-23 | USSOLE | 1 | EA | 1 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 260 | 7000000052 | GEN 43 SPARES PLANT ELEMENT/COMPON | 2019-10-09 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 310 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN092 | Name 23 | Name 23 | 2019-09-27 | USGBI5 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
61050323 | 508 | Hydraulic hose outer layer damaged | S21 | Oil Treating | 2020-03-06 | 2019-12-13 | O.US.STO.STO.005.724FP | 508DANOS | US.WR508A.OT.SS.ZZZ-66410 | Offloading Hose Reel | 2019-11-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 4 Complete by 4 Weeks | 2020-03-06 | 120124000000 | 20 | 40 | 7000000098 | Hose for offloading hose reel | 2020-03-06 | Received at Worksite |  | 2020-02-19 |  | U182 | 8201 | Stones Main | ST KB A6 | 12012401 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 55 |  | 2020-02-03 | USAMH7 | 1 | EA | 1 | Replace Hydraulic hose | REL PCNF PRT GMPS PRC SETC | SCHD MAGN MAOK WPOK | EXEC |  |  | PU 02/19/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1520 | 7000002629 | ELBOW, 6", LR 90, BW, SCH 10S, ASME B16. | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 168 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3370 | 1001774419 | RECB,WPB,80,NPS3x2 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 367 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7450 | 1002062554 | BLT HEX,A325,UNC,7/8in,2.1/2in,SERMAGARD | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1003 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-15 | USSOLE | 28 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 180 | 7000003739 | 442828 LOCKNUT,0.375-24UNJF-3B,HEX | 2020-02-24 | Received at Target Location |  |  | 2020-02-26 | U182 | 8201 | Stones Main | STONES | 12155706 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 40 | 7000000052 | Orion Level Instrument | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2301 | 11340898 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN103 | ORION | ORION | 2019-11-19 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60470624 | 508 | Turret Gantry Crane Out of Service | S40 | Cargo Handling | 2020-06-01 | 2019-11-19 | O.US.STO.STO.005.724FP | GHEMSPAR | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-06-01 | 113409000000 | 10 | 40 | 7000000040 | Mainhook Latch, Pin, Return Spring | 2020-06-01 | Received at Worksite |  | 2019-07-17 | 2020-01-02 | U182 | 8201 | Stones Main | ST KB B2 | 11340935 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-02-15 | USRAR6 | 1 | EA | 1 | Turret Gantry Crane Out of Service | TECO PCNF ESTC GMPS PPRT PRC SETC | XCNF NCMP WPOK XGI ZPVS | TECO |  |  | PU Marty S 05/07/2019 CR
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 110 | 1001210592 | VBT-1501 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 56 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 5 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 160 | 7000000103 | HK322U7G31433Z Hex Double Block and Blee | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN112 | Name 2 | Name 2 | 2020-01-21 | USSOLE | 4 | EA | 4 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 10 | 7000000052 | 35 Custom Orientation Wheels | 2019-06-28 | Not Shipped |  |  |  | U182 | 8290 | ENG AND CONST | Stones | 11545759 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 23 | Name 23 | 2019-06-13 | USGBI5 | 1 | EA | 0 | Engineered Equipment | REL SETC | APPR MAGN | Deleted
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 70 | 7000003458 | EMBR18527A.32B | 2020-02-26 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200013A | Name 3 | USRRIG | 2020-02-12 | USLFA4 | 1500 | GLL | 1500 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 200 | 7000002591 | 2” COUPLING THRD SCH 80S ASTM 182 GR 53 | 2019-10-18 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 44 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN091 | Name 2 | Name 2 | 2019-09-23 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 180 | 7000005901 | 8570-12-304 Plug, 110v,16Amp Series, Yel | 2020-03-03 | Not Shipped |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 18 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOELEC001 | Name 30 | USCRFI | 2020-02-04 | USLFA4 | 12 | EA | 0 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 140 | 7000003852 | DampRid FG37 Moisture Absorber, 7.5 lb, | 2020-03-01 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG014 | Name 52 | USCRFI | 2020-02-04 | USLFA4 | 4 | EA | 4 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 120 | 7000004213 | KE35/15 SASAKURA KE35 P/N 16 COMPOUND GA | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 12 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 10 | 60 | 7000000068 | DK 1548-30110 Power Connection Kit (RTPC | 2020-02-07 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | Issued | 11614811 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 7 | USNSB4 | 2019-09-28 | USAWJB | 1 | EA | 1 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5470 | 7000002629 | 8" 300 RFWN Flange Protectors | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 608 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2990 | 7000002603 | Gasket, 3", 300#, RF, Pikotek Insulating | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 329 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5490 | 7000002629 | 2" 300 RFWN Flange Protectors | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 610 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3350 | 7000002629 | Concentric Reducer, 12" x 10", STD x S/4 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 365 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 110 | 7000002596 | 1 1/8"x6 3/4" STUD BOLTs HH Nuts Super D | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 637 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 34 | EA | 34 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6710 | 7000002629 | Adapter Straight, 1/2", SWM x FNPT, 90/1 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 882 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6350 | 7000002629 | SOCKOLET, 12 X 1 1/2" 3000LB ASTM A182 G | 2020-01-17 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 743 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12271901 | Name 4 | Name 4 | 2019-12-30 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5210 | 7000002603 | GASKET, 1" 300LB, 1/8" THICK, RF SPIRAL | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 582 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2390 | 7000002591 | Fabreeka Pad 1/4" THK x 5 1/2" x 41 5/8 | 2019-04-08 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 261 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011905 | Name 2 | Name 2 | 2019-04-02 | USSOLE | 6 | EA | 6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 890 | 7000003197 | SSW612HBP S.S. 6IN 12W HOR BEND PLATE | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 920 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 10 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 130 | 7000003740 | Material Certificate of Conformance | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN110 | Name 2 | Name 2 | 2019-12-18 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60935785 | 508 | Foam Monitor doesn't Oscillate | S13 | Fire Protect | 2020-02-18 | 2019-11-03 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.M-F3106 | SB Cargo Deck Dry Foam FZ7 Foam Monitor | 2019-11-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 118802000000 | 10 | 10 | 7000004211 | CMU-28/40-A9-1/800-P-40x20 AS GEARBOX S. | 2020-02-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 11880241 | 1 | 4 | Non-Stock (Purchase Requisition) | N | [5 empty] | 2019-11-07 | USJDJW | 1 | EA | 0 | replace gearbox on MOV-33107A-351 | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60985335 | 508 | VABF-122009 Passing By | S18 | Water Systems | 2020-03-03 | 2019-11-30 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.VABF-122009 | Filter Backwash Water Outlet Valve | 2019-10-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-03 | 119372000000 | 20 | 20 | 7000004211 | PAINT-SHELL SHELL PAINT SPECIFICATIONS | 2020-03-03 | Received at Target Location | 2019-11-13 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB D1 | 11937181 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 1 | USNSB4 | 2019-10-29 | USNSB4 | 1 | EA | 1 | Replace VABF-122009 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD WPOK | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 960 | 7000002591 | Glarks 5Pcs Stainless Steel Screw Thread | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 96 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 2 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60832269 | 508 | O/SI #2 Feed Pump Suction Valve Passing | S17 | Steam/Hot H2O | 2020-04-11 | 2020-01-02 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-7V | Pump Suction Isolation Valve | 2019-12-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-11 | 117625000000 | 10 | 10 | 7000004211 | 5K 100MM F-700 JIS SERIES ANGLE VALVE | 2020-04-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11762541 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-19 | USMNF8 | 1 | EA | 0 | Replace passing valve 115-7V | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 750 | 1001630849 | BLT HEX,A325,UNC,3.1/4in,1/2in,CTD | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 75 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 22 | EA | 22 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60629525 | 508 | Butterfly Valves Leak Media Filter | S06 | General | 2021-03-01 | 2020-02-07 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.HC.MAJ-12512 | Heating Medium Duplex Filter | 2019-11-14 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2021-03-02 | 115194000000 | 10 | 10 | 7000000039 | 3" Lug Series 45 HPBFV, CS Body, SS Disc | 2021-03-01 | Received at Worksite | 2019-12-12 | 2019-12-28 |  | U182 | 8201 | Stones Main | ST KB A6 | 11519441 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-14 | USJDJW | 4 | EA | 4 | replace Butterfly Valves on Filter Pots | REL CSER GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU AMW 12/29/19
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 130 | 7000004213 | Customs IMPORT DUTIES/TAX/CUSTOMS BROKER | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 26 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 380 | 7000002591 | Hydramax HM06 ADPT KIT SUIT, 1-1/2IN, 8U | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 69 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 18 | EA | 18 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 310 | 7000002629 | 2" COUPLING THRD 3000# ASTM 182 GR 53 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 58 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A363 | Name 2 | Name 2 | 2019-10-21 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60881246 | 508 | Containment plugs on stern | S06 | General | 2020-02-04 | 2020-01-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.HB.PC | Process Containment Hardware Barriers | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-04 | 118192000000 | 10 | 20 | 7000003852 | Moeller Boat Deck and Baitwell Plug (7/8 | 2020-02-04 | Received at Target Location |  |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B6 | 11819160 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-08 | USAWJB | 5 | EA | 5 | Containment plugs on stern | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU 10/15/2019 AMW
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 10 | 50 | 7000000068 | DK 2256-27A99 | 2020-02-07 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | GRN Mile Mod 1 | 11614811 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-28 | USAWJB | 100 | EA | 100 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 270 | 7000002596 | M22" x 2" A193 B7 Cap Bolt, Xylan | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 27 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 10 | EA | 10 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60655411 | 508 | Discharge check valve passing | S08 | Air Systems | 2020-02-27 | 2019-09-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11805 | Top Up Start Air Compressor | 2019-11-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-27 | 115485000000 | 10 | 50 | 7000000034 | Valve Gasket, Type: Starting Air Compres | 2020-04-12 | Received at Worksite |  | 2020-02-16 | 2020-03-01 | U182 | 8201 | Stones Main | Issued | 11548488 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 13 | USNSB4 | 2019-11-26 | USNSB4 | 2 | EA | 2 | LO/TO Compressor #1, Single Isolation | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 02/16/20 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 270 | 1002149847 | CHANNEL,B-LINE,B22-120SS6,1.5/8in | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 819 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 120 | EA | 120 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 270 | 7000004461 | SDSS Anderson Greenwood PSV Model# 45310 | 2020-01-17 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 311 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN094 | Name 23 | Name 23 | 2019-10-04 | USLFA4 | 8 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 300 | 7000002596 | Square U-Bolt for SHS200x200 (See attach | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 730 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231901 | Name 4 | Name 4 | 2019-12-24 | USSOLE | 6 | EA | 6 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 680 | 7000003740 | Rosemount Product Drawing | 2020-02-21 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 860 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN117 | Name 2 | Name 2 | 2020-01-31 | USLFA4 | 2 | EA | 2 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7420 | 1001645331 | BLT HEX,A325,UNC,4in,3/4in,SERMAGARD | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1000 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-15 | USSOLE | 50 | EA | 19 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 440 | 7000003197 | Serrated Washer for 3/4" Connector | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 836 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 3 | EA | 3 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6860 | 7000000126 | Nitrogen Regulators | 2020-02-05 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 11179936 | 933 | 4 | Non-Stock (Purchase Requisition) | N | X |  | 203202001 | Name 25 | Name 25 | 2020-02-04 | USLFA4 | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 690 | 7000003197 | PL SSTW06HCC SS 6INW CHNL WRAP AROUND CV | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 900 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 45 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 610 | 7000006110 | SLING,WEB,TUFFY,EEF2901P-08,2PLY,1inx8ft | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 778 | 4 | Non-Stock (Purchase Requisition) | N |  |  | SWR551A388 | Name 2 | Name 2 | 2020-01-27 | USSOLE | 6 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 330 | 1002128206 | CABLE,ARMD,AMER-CBL,37-102-309-BS,8AWG | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 825 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 696 | FT | 696 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 580 | 1002058431 | NUT,A563-DH,HEXAGONAL,UNC,1/2,SERMAGARD | 2020-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 775 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A389 | Name 2 | Name 2 | 2020-01-27 | USSOLE | 220 | EA | 220 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 430 | 7000003197 | Nylon Washer for 3/4" Connector | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 835 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 3 | EA | 3 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 60 | 1002059414 | CBL ELEC ARM FIRE,600V,3,12AWG | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 400 | FT | 400 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3690 | 7000002603 | 4" Flange Protectors for Flange, 4", 150 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 399 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 6 | EA | 6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61050323 | 508 | Hydraulic hose outer layer damaged | S21 | Oil Treating | 2020-03-06 | 2019-12-13 | O.US.STO.STO.005.724FP | 508DANOS | US.WR508A.OT.SS.ZZZ-66410 | Offloading Hose Reel | 2019-11-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 4 Complete by 4 Weeks | 2020-03-06 | 120124000000 | 20 | 10 | 7000000098 | 1/2" X 5ft Hose, 4300 PSI | 2020-03-06 | Received at Worksite |  | 2019-12-21 |  | U182 | 8201 | Stones Main | Issued | 12012401 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 54 |  | 2019-11-15 | USMNF8 | 1 | EA | 1 | Replace Hydraulic hose | REL PCNF PRT GMPS PRC SETC | SCHD MAGN MAOK WPOK | EXEC |  |  | PU CLAUDIU
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 80 | 7000002596 | Stud, 1" x 8" LG., ASTM A193 Gr. B8M CLS | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 104 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 18 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1120 | 7000002591 | Description: SLA Smart-Ex 02 DZ1/21 | 2020-03-06 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 112 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STENG22520 | Name 44 | USRRIG | 2020-02-27 | USLFA4 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 450 | 7000002629 | 2" 600# RF Blind 1/2" NPT, ASTM A182 GR F3 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 90 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 2 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61163869 | 508 | MeOH Inj Limit Switch Swap MOC 69266 | S10 | Chem Injection | 2020-04-01 | 2020-03-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.CI.ZZZ-12870 | Turret Methanol Injection System | 2020-01-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-01 | 121427000000 | 10 | 20 | 7000000062 | Custom SS316 Brackets | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12142743 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-27 | USNSB4 | 14 | EA | 0 | Install TopWorx Limit Switch MeOH Inject | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61006507 | 508 | PSV test kits | S21 | Oil Treating | 2020-02-11 | 2020-10-15 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.VE663-00000 | Cargo Oil Pump Systems | 2020-01-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-17 | 119629000000 | 10 | 90 | 7000002603 | 8" Bleed ring | 2020-02-11 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-25 | U182 | 8201 | Stones Main | ST1A3A | 11962883 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 1 | EA | 1 | Install PSV Testt kits | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 10 | 7000003196 | SS-600-2-8 MALE ELBOW | 2020-02-24 | Received at Worksite |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-09 | USNSB4 | 1 | EA | 1 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 70 | 7000003768 | 2”x 6’ CEE2-92, 2 ply E & E nylon | 2020-01-25 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0002 | Name 17 | USJRF5 | 2020-01-08 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU ST1A4B 01/22/2020 CMR
60163073 | 508 | O/SI HCV-835 Stripped Out | S39 | Gas Treating | 2020-02-15 | 2018-07-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.HCV-77401-835 | Gas Export Pipeline HCV | 2018-08-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-15 | 109935000000 | 10 | 10 | 1002360858 | SB2N,B7,2H,UNC,7/8in,6.5in,DOXSTEEL | 2020-02-15 | Received at Worksite |  | 2019-05-08 | 2020-02-18 | U182 | 8201 | Stones Main | ST KB D1 | 10993478 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-08-06 | USNSB4 | 8 | EA | 8 | Replace HCV-835 Hand Choke Valve | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU Marty S 05/07/2019 CR
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 90 | 7000003739 | 901722090 LOCKWASHER,BEARING | 2020-01-19 | Received at Worksite |  | 2020-02-16 | 2020-02-26 | U182 | 8201 | Stones Main | ST KB B2 | 12155706 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-28 | USAWJB | 2 | EA | 2 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO |  |  | PU 02/16/20 AMW
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 100 | 1001208917 | VALVE,ANDRS-GR,H7HIS-44Q,SS316,1/2in | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 40 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 2 |  | 2020-02-17 | USSOLE | 5 | EA | 5 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
60737083 | 508 | Solenoid & VPI test fail 5P | S21 | Oil Treating | 2020-02-10 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635P-217 | Crude Oil to/from COT 5 On/Off PS Valve | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-10 | 116406000000 | 20 | 30 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-04-30 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B6 | 11640588 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635P-217 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60881246 | 508 | Containment plugs on stern | S06 | General | 2020-02-04 | 2020-01-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.HB.PC | Process Containment Hardware Barriers | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-04 | 118192000000 | 10 | 30 | 7000003852 | Seasense Drain Plug 1-1/4-Inch Snap, Bra | 2020-02-04 | Received at Target Location |  |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B6 | 11819160 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-13 | USAWJB | 6 | EA | 6 | Containment plugs on stern | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU 10/15/2019 AMW
60878862 | 508 | O/SI Expansion Bellows Replacement | S17 | Steam/Hot H2O | 2020-04-01 | 2019-10-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.VE115 | Vessel Steam/Tank Heating Systems | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-01 | 118164000000 | 10 | 10 | 7000000026 | BELLOW (20K 300A X 514L) | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11816364 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-08-06 | USAWJB | 1 | EA | 0 | Expansion Bellows Replacement | REL PCNF ESTC CSER GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 130 | 7000002629 | 1" 1500# Blind with 1/2" NPT TAP, RTJ, ASM | 2021-02-18 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Gas Riser Pressure Gauge | 11057838 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A190 | Entity 3 | USRRIG | 2018-08-16 | USSOLE | 1 | EA | 1 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1510 | 7000002629 | RED TEE,6" X 3", BW, SCH 10S, ASME B16.9 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 167 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60839364 | 508 | Check Valve VACH-331020 Passing by | S13 | Fire Protect | 2020-06-01 | 2020-01-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.VACH-331020 | SW Jockey Pump to Helideck Check Valve | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-01 | 117712000000 | 10 | 20 | 7000004212 | 3" Gasket for 8-hole flange | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11771154 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-15 | USNSB4 | 2 | EA | 0 | Replace Check Valve VACH-331020 | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5800 | 7000002603 | 3" Flange Protectors for Flange, 3", 300 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 674 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 30 | EA | 30 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60929009 | 508 | COPT#3 Gland Seal Pres Gauge Inaccurate | S21 | Oil Treating | 2020-02-19 | 2019-10-31 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.ZZZ-11501C | Steam Turbine | 2019-12-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-19 | 118744000000 | 10 | 10 | 7000000062 | WK 52902407 233.53.063 -1/+5 bar 2nd sca | 2020-02-19 | Received at Worksite | 2020-01-27 | 2020-02-07 | 2020-02-22 | U182 | 8201 | Stones Main | Issued | 11874368 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 20 | USNSB4 | 2019-12-16 | USNSB4 | 1 | EA | 1 | Replace Pressure Gauge COPT#3 Gland Seal | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK RUSH WPOK XGI | TECO |  |  | ST1A1C 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7640 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2020-02-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 1027 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-23 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60737089 | 508 | VPI test fail COT 5 STBD | S21 | Oil Treating | 2020-02-05 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-544 | Crude Oil to/from COT 5 On/Off SB Valve | 2019-09-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 116406000000 | 20 | 10 | 7000005901 | P.0244110037 AVC 02 CL1 A1 VPI MANIFOLD | 2020-04-25 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-09 | U182 | 8201 | Stones Main | ST KB B7F | 11640594 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-16 | USNSB4 | 1 | EA | 1 | Repair VPI XV-6635S-544 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 290 | 1001271538 | ANGL MTL,EQ,CS,20ft,L4x4x1/4in | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 729 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231901 | Name 4 | Name 4 | 2019-12-24 | USSOLE | 20 | FT | 20 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 480 | 7000000052 | Hex SDSS DBB Injection Quill | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 537 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN105 | Name 2 | Name 2 | 2019-11-22 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6800 | 7000002646 | Needle Valve, 1/2", VNT-2505 MON | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 891 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4620 | 1001816265 | GASW,CL300-600,316,GPH,NPS3 | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 514 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2670 | 7000002646 | 3/4" Ball Valve VBT-1502SD (See attached | 2019-06-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 290 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06041902 | Name 2 | Name 2 | 2019-06-04 | USDKFB | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 190 | 7000003197 | B-Line 9(SS6)-9034 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 19 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 7 | EA | 7 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 460 | 1001207642 | PIPE, 12", S/STD (0.375 WT), ASTM A106 A | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 62 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 21 | FT | 19.9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61006507 | 508 | PSV test kits | S21 | Oil Treating | 2020-02-11 | 2020-10-15 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.VE663-00000 | Cargo Oil Pump Systems | 2020-01-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-17 | 119629000000 | 10 | 30 | 7000002603 | OA,US,MRC,GASKET,PACKING,JOINTS, EA | 2020-02-11 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-25 | U182 | 8201 | Stones Main | ST1A3A | 11962883 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 9 | EA | 9 | Install PSV Testt kits | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
61057325 | 508 | Faulty level trans LT-77121A-917A MGC A | S04 | Gas Compress | 2020-06-02 | 2019-12-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.MBF-77121A | 2nd Stage Suction Scrubber | 2019-11-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Complete by 2 Weeks | 2020-06-04 | 120203000000 | 30 | 30 | 7000000065 | ZT4510.79 Level transmitter | 2020-06-02 | Received at Worksite |  | 2020-02-08 |  | U182 | 8201 | Stones Main | ST1FLOOR Pallet | 12020299 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-19 | USMNF8 | 2 | EA | 2 | Replace level trans LT-77121A-917A | REL PRT GMPS PRC SETC | APPR MAGN WPOK ZPMM | EXEC |  |  | ST1FLRPALLET 02/15/2020 CMR
60935789 | 508 | COP2 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-10 | 2019-10-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 118809000000 | 10 | 70 | 7000000038 | 3/8” fnpt SS needle valve | 2020-03-10 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11880945 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-26 | USAWJB | 2 | EA | 2 | Install mechanical seal flush plan 12 | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
60628343 | 508 | O/SI Leaking CI Hose coupling in Stab Pl | S19 | Marine Systems | 2020-04-25 | 2019-04-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-89001A | Umb Fluid #1 Upr Stabplate FL Connector | 2019-04-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-27 | 115180000000 | 10 | 10 | 7000003196 | BLKHD 9/16 MP FEM 20K | 2020-04-25 | Received at Worksite |  | 2019-09-22 |  | U182 | 8201 | Stones Main | ST KB B7B | 11517991 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-04-22 | USJDJW | 1 | EA | 1 | REPLACE LEAKING BULKHEAD FITTING | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU AARON 09/29/2019 CMR
60921250 | 508 | O/SI Steam Inlet Drain Valve Leaking | S17 | Steam/Hot H2O | 2020-03-11 | 2020-03-02 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.SW.VAGL-115552 | Steam Inlet Drain Valve | 2020-01-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 118651000000 | 20 | 80 | 1002407398 | GLOBE VALVE,1/2GL01-A,NEWAY | 2020-03-10 | Received at Worksite | 2020-02-05 |  |  | U182 | 8201 | Stones Main |  | 11865065 | 8 | 1 | Stocked Locally (Reservation) | L | X |  |  |  |  | 2020-02-05 | USMNF8 | 1 | EA | 1 | Shut down steam system | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK RUSH WP ZPMM | Kit Complete |  |  | ST1A1C 02/07/2020 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 470 | 7000002591 | Intrepid Industries UDG-32 Safety Gates | 2019-12-03 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 47 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06171901 | Name 2 | Name 59 | 2019-06-17 | USDKFB | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 150 | 7000002591 | 4548K177 1/2 NPT, 5" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000003458 | EMBR18527A.32B | 2021-01-22 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO190001A | Name 3 | USRRIG | 2020-01-06 | USLFA4 | 2000 | GLL | 2000 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 900 | 7000002662 | Pipe, 8 5/8" x 0.875 WT (XXS), ASTM A53 | 2020-02-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F13 | 11581207 | 90 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09191901 | Entity 3 | Name 59 | 2019-09-19 | USSOLE | 2 | FT | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1150 | 1001645336 | BLT HEX,A325,UNC,3in,3/4in | 2020-04-15 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F64 | 11581207 | 115 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111901 | Name 4 | Name 59 | 2019-11-12 | USSOLE | 38 | EA | 38 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118336 | 508 | 2020 Lube Oils / Grease - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 20 | 7000003946 | Shell Corena S4 R 46 Drums | 2021-01-20 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | CPORT | 12090693 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200002A | Entity 6 | JP832018 | 2020-01-13 | USLFA4 | 2 | DR | 2 | 2020 Lube Oils / Grease - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61041514 | 508 | SDTA Leaking Actuator XV-309 | S19 | Marine Systems | 2020-04-03 | 2020-05-06 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.BB.XV-1123P-309 | WB Tank No. 3P Suct/Disch Ballast Valve | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-06 | 120021000000 | 20 | 10 | 7000004212 | HAA-D10-RK HYD. ROTARY ACTUATOR - (DOUBL | 2020-04-03 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12002095 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-03-02 | USNSB4 | 1 | EA | 0 | Erect Scaffold Platform | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60739056 | 508 | COT 4 STBD netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127009 | COT 4 SB HC Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642932 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60315608 | 508 | Replace SC5 LVDT2 Sensor | S19 | Marine Systems | 2020-06-12 | 2019-02-26 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-88505 | Structural Connector No. 5 | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-12 | 111682000000 | 20 | 10 | 7000005901 | 011317340983-M LINEAR VARIABLE DIFFERENT | 2020-12-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11168230 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-10-14 | USNSB4 | 2 | EA | 0 | Replace SC#5 LVDT Sensor | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 20 | 120 | 7000000068 | DK 1548-30110 Power Connection Kit (PTPC | 2019-12-08 | Received at Target Location |  | 2020-02-28 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11614811 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI64 | Name 2 | USNSB4 | 2019-11-05 | USSOLE | 1 | EA | 1 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3060 | 7000002603 | Gaskets, 3", 300#, RF (for Hydro Only) | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 336 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60908998 | 508 | Passing SPSV 049 MAJ 12202A | S18 | Water Systems | 2020-02-20 | 2020-02-14 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PSV-12202A-902 | Filter Pressure Safety Valve | 2019-10-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-20 | 118510000000 | 20 | 40 | 7000002596 | 5/8 X 5-1/2 (5-1/4 FTF) DOX PLTD STUD BO | 2020-02-20 | Received at Worksite |  | 2020-02-08 | 2020-02-26 | U182 | 8201 | Stones Main | ST1A5B | 11851034 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-03 | USNSB4 | 16 | EA | 16 | Replace SPSV 049 MAJ 12202A | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | ST1A5B 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 320 | 1001764015 | SB2N,A193-B7,CTD,UNC,4in,3/4in | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 45 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 550 | 7000002629 | FULL FACE BLEED RING 12", 300#, RF | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 71 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 800 | 7000002629 | BLIND FLANGE, 3", 300#, RF, ASTM A105N, | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 96 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5250 | 7000002596 | STUD BOLT, 5/8" X 5" ASTM A193 GRADE B8M | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 586 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 32 | EA | 32 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 310 | 7000002596 | 4" Bondstrand U-Bolt (See attached DWG S | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 731 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231901 | Name 4 | Name 4 | 2019-12-24 | USSOLE | 10 | EA | 10 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 770 | 7000003463 | PC-KK9D3YP01M | 2020-03-18 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1068 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-26 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
61006507 | 508 | PSV test kits | S21 | Oil Treating | 2020-02-11 | 2020-10-15 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.VE663-00000 | Cargo Oil Pump Systems | 2020-01-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-17 | 119629000000 | 10 | 80 | 7000002603 | 8" 300# BLIND FLANGE | 2020-02-11 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-25 | U182 | 8201 | Stones Main | WHS Floor | 11962883 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 1 | EA | 1 | Install PSV Testt kits | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
60847991 | 508 | MOC GTG1 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-04000 | Gen #1 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117810000000 | 10 | 50 | 7000005901 | M20 Earth Tag | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780966 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI76 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #1 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60453584 | 508 | Turret Room Cleaning | S21 | Oil Treating | 2020-04-01 | 2019-01-09 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.OT.RL.MS113 | Turret Drain System | 2019-08-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-08 | 113217000000 | 10 | 10 | 7000003516 | 55 Gallon drum of Bio max 120 degreaser, | 2020-04-01 | Received at Target Location |  |  | 2020-02-01 | U182 | 8201 | Stones Main | Stones FSPO | 11321738 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | 60453584 | USAWJB | 2019-04-15 | USMNF8 | 1 | GLL | 1 | Turret Room Cleaning - Nacher | TECO GMPS PRC SETC | XCNF MAGN MAOK NCMP RUSH WPOK XGI ZPMM* | TECO |  |  | PU NOTIFIED MIKE NETTLES 8/29/2019
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 660 | 7000003852 | Proto J1304AVPS Antivibe Ball Pein Hamme | 2020-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 66 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0011 | Name 29 | USRRIG | 2020-02-18 | USLFA4 | 10 | EA | 10 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61006507 | 508 | PSV test kits | S21 | Oil Treating | 2020-02-11 | 2020-10-15 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.VE663-00000 | Cargo Oil Pump Systems | 2020-01-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-17 | 119629000000 | 10 | 50 | 7000002603 | 10" flex 150# spiral wound gasket | 2020-02-11 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-25 | U182 | 8201 | Stones Main | ST1A3A | 11962883 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 6 | EA | 6 | Install PSV Testt kits | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
60172772 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-03-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.95T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 110086000000 | 10 | 60 | 7000002596 | Stud, M16x85, ASTM A193 Gr. B7 w/(2) AST | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008581 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081901 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 18 | EA | 18 | MOC missing steam trap | REL PCNF ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 350 | 7000002591 | LaiShuo Zip Ties, 500 Pcs Adjustable Dur | 2020-02-25 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 35 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 1 | EA | 1 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60891772 | 508 | Hiller Deficiencies | S13 | Fire Protect | 2020-03-21 | 2020-02-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2019-08-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-21 | 118312000000 | 10 | 30 | 7000000108 | 15LB CO2 IMO Sign | 2020-03-04 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A1B | 11831177 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19CG112 | USFDY0 |  | 2019-08-19 | USABCE | 1 | EA | 1 | Hiller Deficiiencies | REL PRT GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved |  |  | PU AMW 12/29/19
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 20 | 30 | 7000004211 | MECHANICAL SEAL 42619064 21, 20078-256 | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11762536 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 1 | Replace pump cover on Jockey Pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved |  |  | ST1A2B 02/18/2020 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 270 | 1001707958 | HITCH PIN,WILSNMFG,SWL3600,3/8in,2.1/2in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 27 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 14 | EA | 14 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1100 | 7000002591 | 17100 rotaloc pilot | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 110 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 30 | EA | 30 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 70 | 7000003196 | SS-12-P | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 2 | EA | 2 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
60739071 | 508 | COT 3S IG Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127059 | COT 3 SB IG Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116430000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642967 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61219225 | 508 | GT #5 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-4 | Generator #5 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 40 | 7000003763 | 8MX-80S-12 SPKT | 2020-04-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206809 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #5 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
60796833 | 508 | Damaged pipe insultaion on COPT#3 Stm IS | S17 | Steam/Hot H2O | 2020-02-12 | 2019-08-07 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-340V | No. 3 COPT Steam Balance Line Iso Vlv | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-12 | 117212000000 | 10 | 10 | 7000000132 | Fire blanket, 12" x 20" | 2020-02-12 | Received at Worksite | 2020-01-13 | 2020-01-24 | 2020-03-01 | U182 | 8201 | Stones Main | ST KB A6 | 11721239 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-06 | USMNF8 | 1 | EA | 1 | Replace #3 COPT Stm valve insulation | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD WPOK XGI | TECO |  |  | PU AARON W 01/24/20 GG
60874068 | 508 | FRC inspection deficiencies | S15 | Life Saving | 2020-02-13 | 2020-03-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2019-08-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-03 | 118106000000 | 10 | 70 | 7000004662 | ARMS Lifeboat, Pin, Winch LL160 | 2020-02-13 | Not Shipped |  | 2020-02-13 |  | U182 | 8201 | Stones Main | POD- Questions | 11810577 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-08-04 | USAWJB | 1 | EA | 0 | FRC inspection deficiencies | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD MAGN WPOK | EXEC
60675075 | 508 | O/SI PV Bulkhead Main Steam Stop | S17 | Steam/Hot H2O | 2020-03-25 | 2019-09-24 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.115-331V | Steam to Separater Isolation Valve | 2019-12-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-26 | 115709000000 | 80 | 40 | 7000004211 | FLANGE PACK, flange pack to include all | 2020-06-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11570942 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-02 | USNSB4 | 1 | EA | 0 | De-Isolate | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7300 | 7000003344 | Plate, .5" x 48" x 48", API 2H Gr. 50 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 988 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1950 | 7000002596 | STUD BOLTS, 3/4" DIA. X 7 1/2" LONG, AST | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 217 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 480 | 7000002662 | PIPE, 1 1/2", S/40S (0.145 WT), ASTM A79 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 64 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 1 | FT | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5630 | 7000002629 | Elbow, 3", LR 90, S/10S, BW, ASME B16.9 | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 657 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 9 | EA | 9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4140 | 7000002596 | Bolt, 3/4" x 4 1/4" Lg., ASTM F3125 Gr. | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 464 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60847989 | 508 | MOC GTG5 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-44000 | Gen #5 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 80 | 7000005901 | Brady Part No. M21-187-C-342 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780944 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI80 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 1 | EA | 1 | SAEP LO/TO Isolate GTG #5 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
61163868 | 508 | CPI-55304 Lamp switch broken | S13 | Fire Protect | 2020-02-18 | 2021-01-14 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.GU.FP.CPI-55304 | Topsides Fire & Gas Local Control Panel | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-18 | 121427000000 | 10 | 10 | 1002408835 | DOOR SWITCH,Z15GQ,OMRON | 2020-02-18 | Received at Worksite |  | 2020-02-07 | 2020-02-20 | U182 | 8201 | Stones Main | Issued | 12142742 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 31 |  | 2020-01-23 | USRAR6 | 1 | EA | 1 | Replace Lamp Switch | TECO CNF PRT GMPS PRC SETC | XCNF MAOK WPOK XGI | TECO |  |  | ST1A1C 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6130 | 7000002629 | Reducing Insert, 2" x 1/2", SWM x SWF, 3 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 711 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 16 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 60 | 7000002596 | M12 EYE BOLTS WLL = 0.4T AXIAL DIN 580 | 2020-04-01 | Received at Worksite | 2019-12-19 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 12027172 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-01 | USAWJB | 4 | EA | 4 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 40 | 7000003197 | HWKE DIRECT ITEM HAWKE M20 SERRATED WASH | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11780965 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | Name 58 | 2019-10-29 | USNSB4 | 4 | EA | 0 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC PRC SETC | APPR EOM MAGN WP ZPMM | Deleted
60675080 | 508 | Cracked motor frame on Ejector pump #3 | S18 | Water Systems | 2020-12-24 | 2019-09-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PBE-12204C | No. 3 FW Generator Ejector Pump | 2019-12-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-12-24 | 115709000000 | 10 | 10 | 7000000037 | F020301100091 Motor frame S-MP 65-65-200 | 2020-12-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11570947 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-15 | USNSB4 | 1 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60879643 | 508 | 16000 HR service due #1 Air Compressor | S08 | Air Systems | 2020-02-04 | 2019-09-04 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11801A | No. 1 Air Compressor | 2019-09-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 4 Complete by 4 Weeks | 2020-02-05 | 118173000000 | 10 | 10 | 7000000083 | Service Kit # 3001500640 | 2020-02-04 | Ready for Shipment after Kitting |  | 2020-01-20 | 2020-02-04 | U182 | 8201 | Stones Main | ST1FLR1 | 11817325 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-09-05 | USRAR6 | 1 | EA | 1 | 16000 HR service due #1 Air Compressor | TECO CNF ESTC GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU 02/05/2020 JH GG
60871600 | 508 | O/SI TEG Stripping Gas Flow Meter-001 | S39 | Gas Treating | 2020-04-11 | 2020-01-29 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.FI-77211-001 | TEG Reboiler LP Fuel Gas Flow Indicator | 2019-08-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-11 | 118080000000 | 20 | 10 | 7000005901 | H250-RR VARIABLE AREA FLOW METER | 2020-04-11 | Received at Worksite | 2019-10-21 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB D7 | 11808019 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-16 | USNSB4 | 1 | EA | 1 | Replace Gas Flowmeter, TEG Stripping Gas | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU WPT AMW 11/30/19
60737086 | 508 | VPI test fail 5S | S21 | Oil Treating | 2020-02-08 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-223 | Crude Oil to/from COT 5 On/Off SB Valve | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-08 | 116406000000 | 20 | 20 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-04-28 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7F | 11640591 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-12 | USNSB4 | 1 | EA | 1 | Repair VPI XV-6635S-223 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 50 | 7000000052 | Orion Level Instrument | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2301 | 11340898 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN103 | ORION | ORION | 2019-11-19 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 450 | 7000002591 | .5M Hose w/ Couplers & Whip Check | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 76 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 32 | EA | 32 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
60973032 | 508 | MGC-A 3rd Stg Bridle Removal | S04 | Gas Compress | 2020-04-20 | 2020-09-26 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2019-10-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-20 | 119235000000 | 10 | 40 | 7000004751 | 2" 1500 RTJ RING GASKETS | 2020-03-21 | Received at Worksite | 2019-10-10 | 2019-11-30 |  | U182 | 8201 | Stones Main | ST KB C7 | 11923491 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-02 | USAWJB | 2 | EA | 2 | MGC-A 3rd Stg Bridle Removal MOC78183 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU WPT AMW 11/30/19
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 110 | 1001759241 | SB2N,A193B8MCL2,UNC,4.5in,5/8in | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 107 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 9 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 160 | 7000002591 | 4548K191 3/4 NPT, 1-3/8" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61026269 | 508 | Send In/Replace Fire Ext Due Hydro | S13 | Fire Protect | 2020-03-10 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-01-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-11 | 119851000000 | 10 | 100 | 7000005811 | CF N2 Cylinders Amerex | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11985114 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 9 | EA | 0 | Send In/Replace Fire Ext Due Hydro | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
60847987 | 508 | MOC GTG3 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-24000 | Gen #3 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 10 | 7000005903 | Amercable Part Number 37-102-308 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780940 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI78 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 120 | FT | 120 | SAEP LO/TO Isolate GTG #3 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1100 | 1002309186 | SB2N,B8M CL2,8M,UNC,3/4in,5.00in | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 126 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2890 | 7000002629 | Elbow, 3", LR 90, S/10S, BW, ASME B16.9 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 319 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 17 | EA | 17 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 240 | 7000000052 | AB Processor | 2019-10-09 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 308 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN092 | Name 23 | Name 23 | 2019-09-27 | USGBI5 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5960 | 7000002662 | Pipe, 3", SMLS Class 700, 90/10 CuNi All | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 694 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 140 | FT | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4660 | 7000002629 | Plug, 1/2", SC, Hex head, ASME B16.11, A | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 518 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 350 | 7000003198 | Amercable 37-102-310-BS | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 827 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 45 | FT | 45 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 150 | 7000002629 | 3" 300 # ASME B16.5 A 182 GR F51 1/2" TAPP | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 641 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 3 | EA | 3 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2280 | 7000002591 | Fabreeka Pad, 1/4" THK x 7" x 7" (See At | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 250 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4430 | 7000002591 | Neoprene Strips, 1/8 x 3 1/2 W x 11L | 2019-11-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 495 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141901 | Name 4 | Name 4 | 2019-11-14 | USSOLE | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61026238 | 508 | MGCB Pipe Support Bracket Installation | S04 | Gas Compress | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DANOS | US.WR508A.GC.GS.VADB-771017 | Inlet Gas Valve | 2019-11-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-01 | 119851000000 | 10 | 10 | 1000840366 | SHT PLT SLD MET,4X4ft,3/4in | 2020-03-27 | Received at Target Location |  | 2019-11-12 |  | U182 | 8201 | Stones Main | SHF9-F65 | 11985064 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111902 | Name 4 |  | 2019-11-12 | USLFA4 | 1 | EA | 1 | Install 4x A325 3/4 x 3-3/4 Bolts | REL PRT GMPS PRC SETC | APPR MAGN MAOK WP ZPMM | EXEC
60989317 | 508 | Port crane Emer load lowering hoses bad | S40 | Cargo Handling | 2020-02-18 | 2019-12-05 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-12-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 119417000000 | 10 | 20 | 7000000098 | 3/8 X 16FT. 6'' HYDRAULIC HOSE FJICEE FI | 2020-02-18 | Received at Worksite | 2019-12-26 | 2020-01-20 | 2020-02-18 | U182 | 8201 | Stones Main | ST KB C1 | 11941695 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-28 | USCMFR | 1 | EA | 1 | Port Crane Emer Load lowering hoses bad | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK RUSH WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60935789 | 508 | COP2 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-10 | 2019-10-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 118809000000 | 10 | 90 | 7000000100 | 40’…3/8” x .035 wall SS tubing | 2020-03-10 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11880945 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-01 | USAWJB | 1 | EA | 1 | Install mechanical seal flush plan 12 | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
61098380 | 508 | Biocide Chemical Inj for Cargos & Drains | S21 | Oil Treating | 2020-09-28 | 2020-11-27 | C.US.STO.FI.19.012.1230A | 508CI&E | US.WR508A.OT.SS.VE663-70000 | Cargo Tank Systems | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-09-28 | 120671000000 | 10 | 40 | 7000000052 | MM/75F/50F/FS/HL/NA | 2020-09-28 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 12067106 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI76 | Name 2 | Name 61 | 2019-12-23 | USSOLE | 14 | EA | 0 | Biocide Chemical Inj for Cargos & Drains | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60959173 | 508 | COP1 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-06 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PBE-66301A | Cargo Oil Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-12 | 119077000000 | 10 | 30 | 7000000038 | 1/2" mnpt x 3/8" tube SS fitting (for pu | 2020-03-06 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 11907749 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-10-17 | USRAR6 | 1 | EA | 1 | Add seal flush plan 12 to COP1 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 60 | 7000002603 | Gskt, 12" Garlock GraphLock Style 3125TC | 2020-01-03 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 7 | EA | 0 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
61098380 | 508 | Biocide Chemical Inj for Cargos & Drains | S21 | Oil Treating | 2020-09-28 | 2020-11-27 | C.US.STO.FI.19.012.1230A | 508CI&E | US.WR508A.OT.SS.VE663-70000 | Cargo Tank Systems | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-09-28 | 120671000000 | 10 | 80 | 7000003512 | ¾” x 0.065 Alloy 254 (6 Moly) Uncoated T | 2020-05-22 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 12067106 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI89 | Name 2 | Name 61 | 2020-02-12 | USSOLE | 1600 | FT | 0 | Biocide Chemical Inj for Cargos & Drains | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 380 | 7000002591 | 30mm ½” drive crowfoot socket. Part numb | 2020-03-01 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 38 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO20CG014 | Name 16 | USJRF5 | 2020-02-04 | USLFA4 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61112406 | 508 | 2nd Stg Sep PST upgrade | S22 | Prod Gathering | 2020-04-11 | 2020-06-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.PST-66202-178 | 2nd Stg Separator Press Sfty Transmitter | 2019-12-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-11 | 120837000000 | 20 | 70 | 1000709399 | PLUG,PIPE,1/4",SS,NPT,SS-4-P,SWAGELOK | 2020-04-11 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B3 | 12083677 | 8 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 | USNSB4 | 2019-12-28 | USNSB4 | 1 | EA | 1 | Upgrade PST-66202-178 To Rosemount Trans | REL ESTC GMPS PPRT PRC SETC | APPR EOM MAGN MAOK RUSH WPOK ZPMM | EXEC |  |  | ST1A3C 02/3/20 GG
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 760 | 7000002591 | DRILLFORCE (5Pcs) 11/32 in. x 4-3/4 in. | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 76 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 3 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 320 | 7000002591 | 41mm Ratcheting combination wrench. Part | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 32 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0140 | Name 16 | USCRFI | 2020-02-04 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU CARGO 2/24/2020 GG
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1340 | 1002062545 | BLT HEX,A325,UNC,5/8in,3in,SERMAGARD | 2019-12-27 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | Crane Access Platform | 11581207 | 134 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A380 | Name 2 | Name 59 | 2019-12-24 | USSOLE | 20 | EA | 20 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 60 | 1001642081 | STL SECT MAR,BEAM,7.995in,20ft,A992 | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 20 | FT | 20 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 180 | 7000002662 | Pipe 4 OD 0.318 WT, ASTM A53 Gr. B | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 21 | FT | 20.65 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 280 | 7000002629 | 1 1/2 ELB 90D THRD 3000# ASME B16.11 AST | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 55 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A363 | Name 2 | Name 2 | 2019-10-21 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60840044 | 508 | O/SI Slop S Steam Valve Leaking | S17 | Steam/Hot H2O | 2020-04-01 | 2020-01-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGA-115516 | Stbd Steam to Slop Tank Isolation Valve | 2020-01-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-02 | 117719000000 | 20 | 30 | 7000004211 | 4-GASKETS-GM 4" GRAPHITE FLAT METAL GASK | 2020-04-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11771882 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-07 | USNSB4 | 2 | EA | 0 | Replace Gate valve VAGA -115516 | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 210 | 1001210571 | VBT-1502 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 66 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 1 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 160 | 1002316829 | GASW,CL300/600,316/316L,GPH,2in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 61 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 6 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60797392 | 508 | A/C Condenser Coil Leak / Bad Motor | S14 | HVAC | 2020-03-25 | 2019-08-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.DAL-10813 | Emerg TER A/C Air Handling Unit | 2019-08-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-25 | 117218000000 | 70 | 10 | 7000000086 | TER Emergency Backup AC Unit (TAG: ZZZ-1 | 2020-03-25 | Received at Worksite | 2020-01-16 |  |  | U182 | 8201 | Stones Main | Warehouse floor | 11721803 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-14 | USNSB4 | 1 | EA | 1 | De-Isolate AC Unit & Function Check | REL PCNF PRT GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPVS | Kit Complete |  |  | ST1FLR 01/30/2020 GG
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 10 | 7000003343 | Flat Bar, 1/4" x 4", ASTM A36 | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 20 | FT | 20 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2460 | 1001645338 | BLT HEX,A325,UNC,2.1/4in,3/4in | 2019-04-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 268 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04021905 | Name 2 | Name 2 | 2019-04-03 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 520 | 7000002629 | 1-1/2" Flange Blind ASME B16.5, CL 300 R | 2020-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 766 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A382 | Name 2 | Name 2 | 2020-01-20 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5990 | 7000002629 | Tee, 3" x 3", BW, Class 700, ASME B16.9, | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 697 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 330 | 1001664310 | BLT HEX,A325,UNC,2.1/2in,3/4in,SERMAGARD | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 733 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231901 | Name 4 | Name 4 | 2019-12-24 | USSOLE | 32 | EA | 32 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60675075 | 508 | O/SI PV Bulkhead Main Steam Stop | S17 | Steam/Hot H2O | 2020-03-25 | 2019-09-24 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.115-331V | Steam to Separater Isolation Valve | 2019-12-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-26 | 115709000000 | 80 | 20 | 7000004211 | ham-hand-125 HAMMER HANDWHEEL | 2020-06-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11570942 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-02 | USNSB4 | 1 | EA | 0 | De-Isolate | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 30 | 7000003197 | Stahl Part Number 8570/21-306 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 1 | EA | 1 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4090 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 459 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 74 | EA | 74 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2350 | 7000002596 | Stud 5/8 x 3 1/2 A193/ 2 nuts SERMAGARD | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 257 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 70 | EA | 70 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6490 | 1002360784 | SB2N,B7,2H,UNC,5/8in,3.5in,DOXSTEEL | 2020-02-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 813 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01282001 | Name 4 | Name 4 | 2020-01-29 | USDKFB | 72 | EA | 72 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61041516 | 508 | Replace Scott EEBDs With Ocenco EEBDs | S15 | Life Saving | 2020-02-11 | 2020-01-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.PP-EE | Emergency Escape Personal Prot Equipment | 2020-01-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 8 User defined period | 2020-03-17 | 120021000000 | 60 | 20 | 7000005811 | Ocenco EEBD | 2020-03-12 | Not Shipped | 2020-02-18 |  |  | U182 | 8201 | Stones Main | STONES | 12002097 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-18 | USAWJB | 15 | EA | 0 | Replace Scott EEBDs With Ocenco EEBDs | REL PCNF ESTC GMPS PPRT PRC SETC | APPR MAGN MAKD RUSH WPOK ZPMM | Kit Complete
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 10 | 7000000103 | 12" Duplex Remington Floating Ball Valve | 2019-01-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN031 | Name 2 | Name 2 | 2018-11-06 | USSOLE | 4 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6760 | 1001646136 | GASKET,GARLOCK,36010-0006,CL150,2in | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 887 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 34 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60507054 | 508 | PBE12216B Suction Valve Actuator Failing | S18 | Water Systems | 2020-04-01 | 2019-02-05 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.122-8V | Pump Suction Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-01 | 113806000000 | 10 | 20 | 7000004212 | 14-150-DF-4131-GR | 2020-04-01 | Received at Worksite |  | 2019-12-22 |  | U182 | 8201 | Stones Main | Steering Gear/Wrong valve | 11380553 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | engn rm Entity 3 |  | 2019-09-03 | USAWJB | 1 | EA | 1 | Replace #2 COPT Pump Suction Valve | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK | EXEC
61187003 | 508 | Deficiencies found on IAC#3 Service | S08 | Air Systems | 2020-04-05 | 2021-01-28 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11801C | No. 3 Air Compressor | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-06 | 121692000000 | 10 | 30 | 7000000034 | Air system valve, 1623178680 | 2020-04-05 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12169170 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-04 | USMNF8 | 2 | EA | 0 | Fix Deficiencies found on IAC#3 Service | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 980 | 7000002591 | Campbell Hausfeld 25' Air Hose (PA117701 | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 98 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 4 | EA | 4 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 230 | 7000003852 | Pro-Lift C-2036D Grey 36" Z-Creeper Seat | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
61089158 | 508 | O/SI BGCA Discharge Valve Passing | S04 | Gas Compress | 2020-02-15 | 2020-01-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.VABL-771085 | Compressor SDV Isolation Valve | 2019-12-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 8 User defined period | 2020-02-15 | 120564000000 | 10 | 10 | 7000004753 | 8" 300 RF Full Port, GVI G4 Trunnion, 31 | 2020-02-15 | Received at Worksite | 2020-01-13 | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | Stones | 12056365 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-24 | USAWJB | 1 | EA | 1 | Replace VABL-771085 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 100 | 7000004213 | KE35/13 SASAKURA KE35 P/N 13 LONG NIPPLE | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 23 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 910 | 7000002591 | Neiko Pro 10230B 1/2” Shank Silver and D | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 91 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 220 | 1001210592 | VBT-1501 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 67 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 5 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 50 | 1002316829 | GASW,CL300/600,316/316L,GPH,2in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 50 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 6 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 200 | 7000002591 | 4548K197 3/4 NPT, 5" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61218667 | 508 | Replace Lifeboat Rations & Water | S15 | Life Saving | 2020-12-10 | 2021-02-17 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.LB | Lifeboats | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-12-11 | 122061000000 | 10 | 30 | 7000004662 | Datrex Emergency Food Ration, 2400kcal | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12206109 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-25 | USAWJB | 80 | EA | 0 | Replace Lifeboat Rations & Water | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60739054 | 508 | 6S HC Netherlock Not Locking Open/Close | S06 | General | 2020-04-01 | 2019-11-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127005 | COT 6 SB HC Main Isolation Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642930 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61209426 | 508 | Sub-Order To Purchase Magnets In Advance | S19 | Marine Systems | 2020-03-24 | 2020-04-15 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2020-02-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-24 | 121952000000 | 10 | 30 | 7000003517 | 316 STAINLESS STEEL WASHER FOR M6 SCREW | 2020-03-24 | Received at Worksite | 2020-02-26 |  |  | U182 | 8201 | Stones Main | Stones | 12195195 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-02-18 | USNSB4 | 1 | PK | 1 | Sub-Order To Purchase Magnets in advance | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3270 | 7000002596 | BLT HEX,A325,UNC,5.1/8n,3/4in,HDG | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 357 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 6 | EA | 6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 810 | 7000003197 | SCHNEIDER ELECTRIC MULTI 9 - C60N - MCB | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1087 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-28 | USLFA4 | 2 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3040 | 7000002603 | 3" Flange Protectors , 3", 300 RFWN | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 334 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 38 | EA | 38 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60973122 | 508 | MGC-B 3rd Stg Bridle Removal | S04 | Gas Compress | 2020-04-18 | 2020-09-25 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-10000 | Main Gas Compression System Train B | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-19 | 119235000000 | 10 | 10 | 7000004751 | 2" 1500 RTJ ASME B16.5 Blind Flanges Sim | 2020-03-19 | Received at Worksite | 2020-01-06 | 2020-01-06 |  | U182 | 8201 | Stones Main | ST KB C7 | 11923512 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | Name 59 | 2019-10-02 | USAWJB | 4 | EA | 4 | MGC-B 3rd Stg Bridle Removal MOC78183 | REL PRT GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU WPT AMW 11/30/19
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 100 | 7000003196 | Swagelok SS-810-1-8 | 2019-11-20 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI68 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 6 | EA | 6 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
60986290 | 508 | OSI Passing steam valve VAGL-115617 | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-05 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGL-115617 | Steam Inlet Drain Valve | 2020-01-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-01 | 119384000000 | 10 | 10 | 1001816213 | GASW,CL150,316,GPH,NPS1 | 2020-06-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A1B | 11938370 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-01 | USNSB4 | 2 | EA | 2 | Replace COT5S Steam Inlet Drain Valve VA | REL ESTC GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved |  |  | ST1A1B 02/18/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 230 | 7000002596 | Bolt, 3/4" x 2 1/2" Lg., ASTM F3125 Gr. | 2019-12-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 649 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12121902 | Name 4 | Name 4 | 2019-12-13 | USSOLE | 28 | EA | 28 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2740 | 7000002629 | Flange, 3", 300#, RFWN, S/40S Bore, ASME | 2019-09-19 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 298 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09051902 | Entity 3 | Entity 3 | 2019-09-06 | USSOLE | 90 | EA | 90 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7850 | 1000721634 | U-BOLT,GALV,3/8x1in,ARMORCOAT,W/4NUT | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G96 | 11179936 | 1055 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-24 | USSOLE | 13 | EA | 13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1500 | 7000002662 | PIPE, 6", SCH 10S ASME B36.19M, ASTM A79 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 166 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 21 | FT | 21 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60935789 | 508 | COP2 Seal Flush Plan 12 | S21 | Oil Treating | 2020-03-10 | 2019-10-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 118809000000 | 10 | 30 | 7000000038 | 1/2” mnpt x 3/8” tube SS fitting (for pu | 2020-03-10 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | MMR738 - 2/12 | 11880945 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-26 | USAWJB | 1 | EA | 1 | Install mechanical seal flush plan 12 | REL PRT GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | Approved
61023509 | 508 | Grating on green mile needs replacing. | S19 | Marine Systems | 2020-06-01 | 2019-12-25 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.HG | Handrails, Stairways, Grating | 2020-02-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-06-02 | 119822000000 | 10 | 30 | 1001642069 | BAR FL,1/4in,1.1/2in | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G87 | 11982221 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02172001 | Name 4 | Name 60 | 2020-02-19 | USSOLE | 20 | FT | 20 | Grating on green mile needs replacing. | REL ESTC PRC SETC | APPR EOM MAGN MANX WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1010 | 7000002591 | 7/8''- #17128, Rotaloc Cutter. M430910-2 | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 101 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 6 | EA | 6 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 280 | 7000002591 | ¾” drive ratchet wrench 20” Proto Part n | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 28 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0140 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 340 | 7000002596 | 1 1/4" x 9 3/4" A193 B7 Teflon stud | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 79 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 10 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 170 | 7000000103 | Hydro Test | 2020-02-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN112 | Name 2 | Name 2 | 2020-01-21 | USSOLE | 8 | EA | 8 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1240 | 1001687020 | BLT HEX,A325,UNC,3.1/4in,5/8in | 2020-05-07 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G04 | 11581207 | 124 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031901 | Name 4 | Name 59 | 2019-12-04 | USSOLE | 3 | EA | 3 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 20 | 7000004754 | 1/2" x 0.049 317L SMLS Coated Tubing | 2020-03-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 28 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI86 | Name 2 | Name 2 | 2020-02-07 | USSOLE | 260 | FT | 0 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 60 | 7000003852 | Lion Post Consumer Recycled Plastic Clip | 2020-02-01 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO200006 | Name 10 | USRRIG | 2020-01-19 | USLFA4 | 2 | EA | 0 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | Deleted |  |  | PU DOYLE
61165403 | 508 | Install Needle Valve on PG-33110-733 | S13 | Fire Protect | 2020-04-01 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33110-733 | Seawater Booster Pump Outlet Press Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-01 | 121447000000 | 10 | 20 | 7000003196 | Stainless Steel Integral Bonnet Needle V | 2020-04-01 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144687 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 1 | EA | 1 | Install Needle Valve on PG-33110-733 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60704788 | 508 | SB Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983-1 | SB Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 100 | 7000000039 | 6400-16-16-O-SS STR. THREAD O-RING CONNE | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604174 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 4 | EA | 0 | assist Replace STBD Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 680 | 7000002591 | 4452K238 Cap, 1/2 NPT | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 68 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 430 | 7000002591 | 4452K166 Bushing Adapter, 1/2 Male x 3/8 | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 43 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 180 | 7000002591 | 4548K195 3/4 NPT, 3" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 650 | 7000002591 | 2"x 4' Kevlar nylon strap protector | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 922 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A396 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 6 | EA | 6 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6340 | 7000002644 | BALL VALVE, 1/2" FULL PORT 3705 PSI MNPT | 2020-01-17 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 742 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12271901 | Name 4 | Name 4 | 2019-12-30 | USSOLE | 7 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5140 | 7000002629 | PLUG, 1/2" SOLID HEX THRD, ASTM A182 GRA | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 575 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 22 | EA | 22 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1490 | 1001759324 | SB2N,A193B8MCL2,UNC,4.5in,3/4in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 165 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 44 | EA | 44 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 140 | 1000882464 | SUPPORT KIT,TUBE,3/4,304S3PP12T,SWAGELOK | 2020-03-24 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI63 | Name 2 | Name 58 | 2019-11-05 | USSOLE | 15 | KIT | 15 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3510 | 1001210571 | VBT-1502SS | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 381 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60935864 | 508 | SWOS-Certify Offload Hose Tethers | S21 | Oil Treating | 2020-02-18 | 2019-11-01 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.ZZZ-66410 | Offloading Hose Reel | 2019-10-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 118810000000 | 20 | 10 | 7000000041 | Proof load 26MM tethers, 5000-00010 | 2020-02-18 | Not Shipped |  | 2019-10-18 | 2020-02-13 | U182 | 8201 | Stones Main | Stones/Turitella | 11881041 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-10-18 | USMNF8 | 2 | EA | 0 | Reinstall Offload Hose Tethers | TECO ESTC PRC SETC | XCNF MAGN NCMP WPOK XGI ZPMM | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3320 | 1000718546 | PIPE MET,A106-B,BARE,40,4.1/2in | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 362 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 120 | FT | 126 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3240 | 7000002596 | BLT HEX,A325,UNC,4.75in,3/4in,HDG | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 354 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 6 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 220 | 7000002603 | 3/4" 300# Flex Gasket 316 spiral wound, FG | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 8 | EA | 8 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60737058 | 508 | O/SI Actuator Seal Test Fail 4 STBD | S21 | Oil Treating | 2020-03-24 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6634S-250 | Crude Oil to/from COT 4 SB Valve | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-24 | 116406000000 | 20 | 10 | 7000004212 | HAA-D10-RK HYD. ROTARY ACTUATOR - (DOUBL | 2020-03-24 | Received at Worksite | 2019-10-24 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB B8 | 11640563 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-03 | USNSB4 | 2 | EA | 2 | Repair Hydraulic Actuator 4 STBD. | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 220 | 1001816210 | GASW,316/316L,GPH,CL150,NPS3 | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 210 | 1001768457 | ELB BW,WPB,90DEG,LR,40,NPS2 | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 7 | EA | 7 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 530 | 1000817951 | ANGL MTL,UNEQ,CS,20ft,4X3X3/8in | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 53 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 100 | FT | 100 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 100 | 7000002596 | Stud, 1 ½” x 15” Lg., ASTM A320 Gr. L7 ( | 2020-01-28 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G40 | 11545759 | 90 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01142002 | Name 2 | Name 2 | 2020-01-15 | USSOLE | 17 | EA | 17 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
61221684 | 508 | Steam Expansion Bellows critical spare | S17 | Steam/Hot H2O | 2020-06-01 | 2020-04-22 | P.US.STO.NF.20.015.7240A | 508ERENG | US.WR508A.GU.SW.VE115-32000 | Boiler System Steam Distribution | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-06-02 | 122096000000 | 10 | 30 | 7000003323 | Expansion Joint EJ-540583 | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12209639 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAMH7 | 2020-03-02 | USRAR6 | 1 | EA | 0 | Shut down steam system | CRTD PRC | INIT RUSH WP | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 290 | 7000002644 | Model# 320F-23-CGF-23 WKM 2" 600# Floati | 2020-08-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 33 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-16 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 220 | 7000002596 | 1/2 “x 2-3/4” Stud Bolt ASTM A193 GR B8M | 2019-10-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | STONES | 11545759 | 48 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 15 | Name 15 | 2019-10-18 | USABCE | 8 | EA | 8 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 100 | 7000003739 | 24813R1 RING,RETAINING,SPIRAL | 2020-01-19 | Received at Worksite |  | 2020-02-16 | 2020-02-26 | U182 | 8201 | Stones Main | ST KB B2 | 12155706 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-28 | USAWJB | 2 | EA | 2 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO |  |  | PU 02/16/20 AMW
61042035 | 508 | Install Fall protection for IG platform | S06 | General | 2020-02-09 | 2020-01-03 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.IG | Inert Gas/Vent Systems | 2020-01-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-09 | 120026000000 | 20 | 30 | 7000002596 | "3/8" Lag Bolts | 2020-02-09 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-09 | U182 | 8201 | Stones Main | WHSE FLOOR | 12002575 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-09 | USMNF8 | 4 | EA | 4 | Install Fall protection for IG platform | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3C 01/29/20 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 180 | 7000002644 | 1-1/2" 150# RF FP WKM Floating Ball Valv | 2019-01-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 206 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN046 | Name 2 | Name 2 | 2019-01-25 | USSOLE | 2 | EA | 2 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3800 | 1001708318 | NUT,A563-DH,HEXAGONAL,UNC,3/4in,GALV | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 410 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 28 | EA | 28 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1820 | 7000002629 | FLANGE, 8", 300#, RF, WN, SCH 40S, ASTM | 2019-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 200 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01241901 | Name 2 | Name 2 | 2019-01-24 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 510 | 7000003197 | TNB Catalog Number F2034 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 843 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 500 | EA | 500 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 790 | 7000003197 | PL SSW612HCC STAINLESS STEEL ACCESSORIES | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 910 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 90 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3960 | 1001267672 | PCM-0.23) | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 446 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 210 | 7000002591 | 2" x 27' U-Hook Ratchet Strap (including | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 4 | EA | 4 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 50 | 7000002629 | Flange, 12", JIS 10K Slip-on | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 4 | EA | 4 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 70 | 7000003852 | Loboo Waterproof Bag Expedition Dry Duff | 2021-05-26 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main | STONES | 11419724 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19BBSM1 | Name 11 | USKHU3 | 2019-10-15 | USLFA4 | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/01/19 J WELBOURN
61023509 | 508 | Grating on green mile needs replacing. | S19 | Marine Systems | 2020-06-01 | 2019-12-25 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.HG | Handrails, Stairways, Grating | 2020-02-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-06-02 | 119822000000 | 10 | 50 | 1001676309 | BLT HEX,A325,2in,1/2in | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G87 | 11982221 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02172001 | Name 4 | Name 60 | 2020-02-19 | USSOLE | 36 | EA | 36 | Grating on green mile needs replacing. | REL ESTC PRC SETC | APPR EOM MAGN MANX WPOK ZPMM | Approved
61219229 | 508 | GT #4 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-3 | Generator #4 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-21 | 122068000000 | 10 | 60 | 7000003763 | 14325 3/8 X 12 SQ KEYSTOCK | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206813 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #4 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61006511 | 508 | SUP R&R COP mech seal | S21 | Oil Treating | 2020-03-28 | 2020-04-18 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.OT.SS.PBE-66301B | Cargo Oil Pump No. 2 | 2019-12-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-28 | 119629000000 | 10 | 10 | 1002409049 | MECH SEAL,AZT00798SSV01-A+,AESSEAL | 2020-03-28 | Not Shipped |  |  | 2020-01-18 | U182 | 8201 | Stones Main |  | 11962907 | 1 | 1 | Stocked Locally (Reservation) | L | [5 empty] | 2019-10-22 | USMNF8 | 1 | EA | 0 | Repair and replace COP mech seal | TECO CNF ESTC GMCO PRC SETC | XCNF XGI | TECO
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 870 | 7000002591 | JET JAT-620 Pneumatic R12 Composite Rev | 2020-02-25 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 87 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USRRIG | 2020-02-19 | USLFA4 | 2 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 70 | 80 | 7000004213 | KE35/11 SASAKURA KE35 P/N 11 GLOBE VALVE | 2020-05-18 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | Replace FW Gen Pump 3 Inlet Spool | REL ESTC GMCO PRC SETC | APPR EOM WPOK ZPMM | Deleted
61178974 | 508 | Fire extinguishers expiring March 2020 | S13 | Fire Protect | 2020-03-13 | 2020-03-26 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2020-02-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-13 | 121602000000 | 10 | 20 | 7000005811 | 23 CUFT N2 Cylinders | 2020-03-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12160189 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-27 | USMNF8 | 8 | EA | 0 | Fire extinguishers expiring March 2020 | REL ESTC PRC SETC | APPR MAGN RUSH WP | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 380 | 7000002596 | 1" x 9" A193 B8M Class 2 S&N | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 83 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 14 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60959401 | 508 | MOC Replace SeaSafe with CargoMax | S20 | Monitor & Ctrl | 2020-03-24 | 2020-03-15 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.MC.PL.PF552-00000 | PSS Panels | 2019-09-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-24 | 119079000000 | 10 | 10 | 7000001232 | Seasafe Computer and Software | 2020-03-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 02/26 | 11907923 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAWJB | 2019-10-01 | USRAR6 | 1 | EA | 0 | MOC Replace SeaSafe with CargoMax | REL ESTC PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 130 | 7000002629 | 2" Flange Blind 600# RF ASME B16.5, 3/4" N | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 58 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 2 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 190 | 7000002591 | 2” NIPPLE SCH 80S TBE 4" LONG ASTM 182 G | 2019-10-18 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 43 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN091 | Name 2 | Name 2 | 2019-09-23 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60832264 | 508 | Replace pump cover on Jockey Pump B | S13 | Fire Protect | 2020-04-01 | 2020-01-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.FP.PBE-33151B | Seawater Jockey Pump | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-02 | 117625000000 | 20 | 80 | 7000004211 | NILOS GREASE SEAL 149, 20074-001 | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A2B | 11762536 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-05 | USMNF8 | 1 | EA | 1 | Replace pump cover on Jockey Pump B | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WPOK ZPMM | Approved |  |  | ST1A2B 02/18/2020 CMR
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 220 | 7000002591 | 1 LOT: Two (2) Hilti MI/MQ Modular Platf | 2020-04-10 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | JOB NO: 2333 | 11545759 | 89 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN093 | Name 2 | Name 2 | 2019-12-12 | USABCE | 1 | EA | 0 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 70 | 1002309185 | SB2N,B8M CL2,8M,UNC,3/4in,4.25in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 52 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 64 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 890 | 1001816265 | GASW,CL300-600,316,GPH,NPS3 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 105 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3180 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-10-22 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 348 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151903 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 150 | 7000003852 | PhysiciansCare by First Aid Only 24-000 | 2020-03-01 | Received at Worksite |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0148 | Entity 7 | USCRFI | 2020-02-12 | USLFA4 | 4 | EA | 4 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU CARGO 2/24/2020
60661352 | 508 | O/SI Steam Inlet is Passing | S17 | Steam/Hot H2O | 2020-03-10 | 2019-09-07 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-410V | Steam to No. COW Pump Isolation Valve | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 115550000000 | 30 | 20 | 7000004211 | 10K50A-GLV-F.P. FLANGE PACKS. DOXSTEEL F | 2020-05-09 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11555032 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-21 | USNSB4 | 2 | EA | 0 | Replace Valve 115-410V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 740 | 7000002603 | Gaskets 8" 300# FR 1/8" THK SPIRAL WOUND | 2020-02-13 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 962 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A398 | Name 2 | Name 2 | 2020-02-11 | USSOLE | 6 | EA | 6 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 500 | 7000002591 | Pilot for mag drill bit | 2020-01-20 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 763 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A383 | Name 2 | Name 2 | 2020-01-18 | USSOLE | 20 | EA | 20 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 810 | 7000002603 | GASKET, 8", 150#, FF, 1/8" THICK, GARLOC | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 97 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60737088 | 508 | VPI test fail COT 5 STBD | S21 | Oil Treating | 2020-02-05 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635S-241 | Crude Oil to/from Fwd COTs On/Off Valve | 2019-09-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 116406000000 | 20 | 10 | 7000005901 | P.0244110037 AVC 02 CL1 A1 VPI MANIFOLD | 2020-04-25 | Received at Worksite | 2019-12-10 | 2020-01-19 | 2020-02-09 | U182 | 8201 | Stones Main | ST KB B7F | 11640593 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-16 | USNSB4 | 1 | EA | 1 | Repair VPI XV-6635S-241 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7370 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 995 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 50 | EA | 50 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61049139 | 508 | HP/LP Piston Failure | S08 | Air Systems | 2020-02-12 | 2020-01-08 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.AS.CAE-11804A | Start Air Compressor No. 1 | 2020-02-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-14 | 120119000000 | 10 | 60 | 7000005901 | 7746 THERMO SWITCH AIR 80DEGC STOP | 2020-02-12 | Received at Worksite | 2020-02-13 | 2020-02-13 |  | U182 | 8201 | Stones Main | ST KB A3 | 12011865 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-13 | USMNF8 | 1 | EA | 1 | Rebuild Start Compressor #1 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAKD MAXX RUSH WPOK | EXEC |  |  | ST1A1C 02/07/2020 CMR
60271479 | 508 | Annual station #45 valve leaking | S13 | Fire Protect | 2020-02-18 | 2019-02-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PF331-10000 | FPSO Foam Systems | 2019-03-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-18 | 111200000000 | 10 | 20 | 7000004211 | 1-1/2-NPN-GSK-105, 1 1/2" ANSI 150 Neopr | 2020-02-18 | Received at Worksite |  | 2019-07-25 |  | U182 | 8201 | Stones Main | issued to 1 Tom honeycutt | 11119960 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-03-04 | USNSB4 | 10 | EA | 10 | Replace Annual Station #45 Valve PF331-1 | REL PRT GMCO GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | EXEC |  |  | PU Tommy Honeycutt 07/31/2019 CMR
60177919 | 508 | Mod 6 - vlv long bolts Diss metals | S04 | Gas Compress | 2020-06-01 | 2019-06-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VABL-771251 | Cooler Press Diff Transmitter Iso Valve | 2019-08-26 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-06-01 | 110146000000 | 10 | 20 | 7000002596 | 5/8-11 X 2-1/2 STUD BOLT A193 B8M SS | 2020-06-01 | Ready for Shipment after Kitting | 2019-10-29 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB D3 | 11014637 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-26 | USNSB4 | 4 | EA | 4 | LO/TO Shutdown Down Process Train, De-In | REL ESTC CSER GMPS PRC SETC | EXEC EOM MAGN MAKD MANX WPOK | EXEC |  |  | PU WPT 11-25-19
60739047 | 508 | Repair Welding Rod Oven | S06 | General | 2020-02-11 | 2019-10-31 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GN | General | 2019-06-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-11 | 116427000000 | 10 | 10 | 7000003196 | PHX1200200 OVEN ELECTRODE STABILISATION | 2019-09-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642663 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-06-24 | USNSB4 | 1 | EA | 0 | Replace Welding Rod Oven. Assemble & Fu | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Deleted
60352956 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-10 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33320 | No. 1 Starboard Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-11 | 112105000000 | 10 | 50 | 7000000133 | Marine Packing PN 400-RUDD0010 | 2020-02-10 | Received at Worksite |  | 2019-10-20 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210548 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-07-17 | USRAR6 | 1 | EA | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
60888917 | 508 | Faulty Temp Probe on Swivel | S19 | Marine Systems | 2020-04-11 | 2020-02-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89650 | Electrical Power & Signal Swivel | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-11 | 118279000000 | 20 | 10 | 7000005901 | DGPT2-HP/IB/PA/PT/X TRANSFORMER PROTECTI | 2020-04-18 | Received at Worksite | 2019-12-09 | 2019-12-21 |  | U182 | 8201 | Stones Main | ST KB B4 | 11827852 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-17 | USNSB4 | 1 | EA | 1 | Replace Temperature Safety Transmitter O | REL ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MAKD RUSH WPOK | EXEC |  |  | PU WPT ST KB B4
61155246 | 508 | Install Barring Device on MGCA | S04 | Gas Compress | 2020-03-03 | 2020-07-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-00000 | Main Gas Compression System Train A | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-03 | 121329000000 | 10 | 100 | 7000003517 | 92620A718 (1/2" x 1-3/4" grade 8 bolts) | 2019-11-01 | Received at Worksite |  | 2020-02-16 |  | U182 | 8201 | Stones Main | ST1A6C | 12132852 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0006 | Name 17 | JP832018 | 2020-01-27 | USLFA4 | 1 | PK | 1 | Install Barring Device on MGCA | REL PCNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC |  |  | ST1A6C 02/16/20 AMW
61118371 | 508 | 2020 Lab Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 30 | 7000003852 | Belkin 12-Outlet Power Strip Surge Prote | 2021-03-11 | Received at Target Location |  | 2020-01-11 |  | U182 | 8201 | Stones Main | STONES | 12090728 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20OP001 | Name 27 | USRRIG | 2020-02-27 | USCDP7 | 1 | EA | 1 | 2020 Lab Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61015474 | 508 | MGC B-TT-77100B-365B need to be replaced | S04 | Gas Compress | 2020-04-07 | 2020-04-21 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.TT-77100B-365B | DE Lube Oil Return Temp Transmitter | 2019-11-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-07 | 119725000000 | 20 | 10 | 1002407400 | TRTE,YOKOGAWA,YTA610-JA1C-4DJ/N4/SU2 | 2020-04-07 | Received at Worksite | 2020-02-04 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB A5 | 11972502 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 | USNSB4 | 2019-11-20 | USNSB4 | 1 | EA | 1 | Replace Yokogawa Transmitter & Temperatu | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK RUSH WPOK | EXEC |  |  | PU 02/19/20 AMW
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 530 | 7000003852 | Kingston 64GB USB 3.0 Black DataTraveler | 2021-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 53 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN012620A | Name 3 | USRRIG | 2020-02-12 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61077544 | 508 | PG-33110-731 broken | S13 | Fire Protect | 2020-03-05 | 2020-05-29 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33110-731 | Firewater Lift Pump Outlet Press Gauge | 2019-12-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-05 | 120431000000 | 10 | 10 | 7000002629 | 4" panel mount gauges | 2020-03-05 | Received at Worksite | 2020-01-17 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB C3 | 12043118 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-13 | USAMH7 | 3 | EA | 3 | Replace PG-33110-731 | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A3C 02/3/20 GG
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 470 | 7000002591 | ADA, 90 DEG Swivel, 1/4 IN Male x 1/4 IN | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 78 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 60 | EA | 60 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1370 | 7000002591 | 2" THICK X 10" WIDE X 54-1/4" LONG BLACK | 2019-12-27 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | Crane Access Platform | 11581207 | 137 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A380 | Name 2 | Name 59 | 2019-12-24 | USSOLE | 2 | EA | 2 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1220 | 7000002629 | Pipe Nipple, 1 1/4" x S/10 x 12" LG, (1. | 2020-05-07 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G04 | 11581207 | 122 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031901 | Name 4 | Name 59 | 2019-12-04 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 100 | 7000003852 | Power Strip with USB, AUOPRO Grounded Su | 2020-04-05 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | AJH021620 | Name 12 | USRRIG | 2020-02-19 | USCDP7 | 1 | EA | 1 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60352955 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-09 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33310 | No. 1 Port Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-10 | 112105000000 | 10 | 20 | 1001618990 | FUEL FILTER,359-BUKH0201,ALXR-RYN | 2020-02-09 | Received at Worksite |  | 2019-10-20 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210547 | 2 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 | USAWJB | 2019-07-17 | USRAR6 | 1 | EA | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
60507050 | 508 | STB Vent N2 snuffing system rusting | S06 | General | 2020-03-10 | 2019-02-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.ZZZ-12707 | Cargo Vent Stacks N2 Stuffing System | 2019-06-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-11 | 113805000000 | 20 | 60 | 1000716034 | GASW,316L,GPH,CL150,2in | 2020-03-10 | Received at Worksite |  | 2019-06-07 |  | U182 | 8201 | Stones Main | ST KB B3 | 11380546 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-04-19 | USNSB4 | 1 | EA | 1 | Replace Rusted Components Starboard Vent | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MAOK WPOK ZPMM | EXEC
60848038 | 508 | Torque Meter Incorrect Reading | S19 | Marine Systems | 2020-02-05 | 2020-07-08 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.MA.PR.VE109-07000 | Main Engine Control System | 2019-07-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-25 | 117810000000 | 20 | 10 | 7000003852 | MEAN WELL RS-25-12 AC to DC Power Supply | 2020-04-25 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B7C | 11781017 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-02-06 | USMNF8 | 1 | EA | 1 | Replace Torque Meter Signal Conditioner | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MAKD WPOK | EXEC
61054608 | 508 | 3M Breathing Air Compressor Output Test | S08 | Air Systems | 2020-02-25 | 2020-02-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.VE118-50000 | Fwd TR Breathing Air System | 2019-11-17 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 1 Safety / TI Critical | 2020-02-25 | 120173000000 | 20 | 20 | 7000002591 | P/N:ROUTINE ANALYSIS RA01 | 2020-02-25 | Received at Target Location |  | 2020-02-07 |  | U182 | 8201 | Stones Main | WPT Desk | 12017311 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-02-07 | GW982959 | 4 | EA | 4 | 3M Breathing Air Compressor Output Test | REL CNF PRT GMPS PRC SETC | SCHD MAGN WPOK | EXEC
60665886 | 508 | GS #1 Pump Discharge Valves Passing | S19 | Marine Systems | 2020-03-24 | 2019-09-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.BB.PBE-12301A | Bilge/Ballast/General Service Pump No. 1 | 2019-11-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-26 | 115603000000 | 10 | 20 | 7000004211 | FLANGE PACK 10K 200A) flange pack to inc | 2020-06-06 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11560292 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-26 | USNSB4 | 2 | EA | 0 | Rigging Services & Assist Replacement 8" | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 30 | 7000003196 | SS-8-HCG HEX COUPLING | 2021-03-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB C7 | 11057838 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO182KDC | Name 37 | USRRIG | 2018-07-24 | USLFA4 | 4 | EA | 4 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved |  |  | PU MOD22 1st FLR 09/04/2018 MP
60748463 | 508 | Feed Water Pipe on FWG #1 leaking | S18 | Water Systems | 2020-06-01 | 2019-11-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.ZAN-12101 | No. 1 Fresh Water Generator | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-06-02 | 116535000000 | 10 | 50 | 7000004213 | KE35/8 SASAKURA KE35 P/N 8 ORIFICE FLANG | 2020-07-16 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11653517 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-05 | USNSB4 | 2 | EA | 0 | Shut Down Affected Train | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3330 | 7000002629 | Pipe Nipple, 3" x 12" LG, S/80, ASME B36 | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 363 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1330 | 7000002662 | PIPE, 3", SCH 10S ASME B36.19M, ASTM A79 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 149 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 21 | FT | 20.8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 550 | 1001573305 | LUG,COMP,BURNDY,YA2CL4BOX,2AWG,2.06in | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 847 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 50 | EA | 50 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4680 | 1002301610 | SB2N,B8M CL2,8M,UNC,5/8in,3.50in | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 520 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7240 | 7000003344 | Plate, .1875" x 24" x 24", ASTM A36 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 982 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 180 | 7000002591 | Flat Washer, 3/8", SS | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 8 | EA | 8 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4670 | 7000002644 | Ball Valve, 3/4", VBT-1502D (See Attache | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 519 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 3 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 290 | 7000000052 | Topworx Limit Switch | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 415 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN099 | Name 2 | Name 2 | 2019-10-29 | USLFA4 | 2 | EA | 2 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3840 | 1001676333 | BLT HEX,A325,UNC,2.1/4in,5/8in | 2019-11-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 434 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10311902 | Name 2 | Name 2 | 2019-10-31 | USSOLE | 74 | EA | 74 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4240 | 1001807386 | FLWN,A105,CL150,80,NPS2 | 2019-11-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 476 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11121901 | Name 4 | Name 4 | 2019-11-12 | USLFA4 | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4710 | 7000002596 | Bolt, 1/2" x 1 1/2" LG, ASTM F3125 Gr. | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 523 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 118 | EA | 118 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60989313 | 508 | Erratic Speed Reading Steam Turbine #3 | S21 | Oil Treating | 2020-02-11 | 2020-04-04 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.OT.SS.CPI-66301C | Steam Turbine Control Panel | 2019-10-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-11 | 119417000000 | 20 | 30 | 7000005901 | BEAM CLAMP WITH 1/4-20 TAPPED HOLE | 2020-02-11 | Received at Worksite | 2019-11-21 | 2020-01-19 | 2020-02-19 | U182 | 8201 | Stones Main | ST1A5B | 11941691 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | 3.54 | 2019-10-24 | USNSB4 | 20 | EA | 20 | Replace Existing Cable With Shielded Cab | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD WPOK XGI | TECO |  |  | PU AMW ST1A5B
61118367 | 508 | 2020 Catering - Material | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 20 | 7000003454 | Pkg of 12, R-R Textile 13X13 Cotton Wash | 2020-02-28 | Not Shipped |  | 2020-01-15 |  | U182 | 8201 | Stones Main | STONES | 12090704 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOR11620A | Camp Boss | USJRF5 | 2020-01-16 | USLFA4 | 15 | PK | 0 | 2020 Catering - Material | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60756604 | 508 | Vacuum Condenser Heat Exchanger | S17 | Steam/Hot H2O | 2020-04-01 | 2019-06-16 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.HBG-11508 | COPT Vacuum Condenser Heat Exchanger | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-01 | 116627000000 | 10 | 70 | 7000002596 | SNB7 M22 X 120MM: STUDS AND NUTS. B7 tef | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST1A2C | 11662728 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | GW982959 | 2020-01-16 | GW982959 | 60 | EA | 60 | Main condenser tubes leaking | REL ESTC GMPS PRC SETC | APPR MAGN RUSH WP ZPMM ZPVS | Approved |  |  | ST1A3B 02/18/2020 CMR
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 90 | 7000002596 | 5/8 X 4-1/2 (4-1/4 FTF) DOX PLTD STUD | 2020-04-01 | Received at Worksite | 2019-12-19 | 2020-01-19 |  | U182 | 8201 | Stones Main | ST KB A3 | 12027172 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-01 | USAWJB | 4 | EA | 4 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU 01/19/2020 AMW
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 60 | 7000003458 | BIOC16298A.32B | 2021-02-19 | Received at Target Location |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200012A | Name 3 | USRRIG | 2020-02-05 | USLFA4 | 500 | GLL | 492 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60828492 | 508 | Mechanical seal leaking on PBE-12201B se | S18 | Water Systems | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12201B | No. 2 Sea Water Lift Pump | 2019-12-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-10 | 117588000000 | 80 | 10 | 1002404891 | MECHANICAL SEAL,MSA2001442,CLYUNION | 2020-03-10 | Received at Worksite |  | 2020-01-29 |  | U182 | 8201 | Stones Main | ST KB B3 | 11758822 | 1 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2019-12-11 | USCWJG | 1 | EA | 1 | Remove and Replace Mechanical Seal | REL ESTC GMPS PRC SETC | EXEC MAOK WPOK | EXEC |  |  | ST1A3C 01/18/2020 CMR
61021143 | 508 | Replace Dryer filters 1B Acom HVAC comp | S14 | HVAC | 2020-04-07 | 2020-04-22 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.HV.VE108-00000 | Accommodation HVAC | 2020-01-30 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-07 | 119795000000 | 20 | 20 | 7000000047 | filter dryer, Castle model : 4423/21A | 2020-04-07 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11979462 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-30 | USMNF8 | 6 | EA | 0 | Replace Dryer filters 1B Acom HVAC unit | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60847988 | 508 | MOC GTG4 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-34000 | Gen #4 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 20 | 7000005901 | Hawke Part Number 121 / A / M20 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780943 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI79 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #4 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS2 | 20 | 7000003196 | Swagelok SS-1210-1-12 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Seawater Eductor | 11545759 | 65 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI59 | Name 2 | Name 2 | 2019-10-23 | USSOLE | 12 | EA | 12 | Shop Order Sheets - I&E Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
61131894 | 508 | PBM-12405A Floatation Cell Recl Pmp Brgs | S26 | Water Treating | 2020-05-02 | 2020-06-15 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.WT.FL.PBM-12405A | Flotation Cell Recycle Pump A | 2020-01-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-04 | 121058000000 | 10 | 30 | 7000004211 | ANS200x150x350/PN-12 | 2020-05-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12105764 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-25 | USAWJB | 1 | EA | 0 | PBM-12405A Floatation Cell Recl Pmp Brgs | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 30 | 7000002591 | Five Star Spiral Notebook, 5 Subject, Co | 2020-02-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200006 | Name 10 | USRRIG | 2020-01-19 | USLFA4 | 10 | EA | 10 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU DOYLE
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 30 | 7000002591 | 4548K135 1/4 NPT, 3" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60544614 | 508 | Mechanical seal is leaking | S18 | Water Systems | 2020-06-02 | 2019-07-01 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.PBE-12216A | No. 1 Main/COPT Condenser Cooling Pump | 2019-12-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-02 | 114224000000 | 10 | 70 | 7000004211 | Mechanical seal, set, SVS350M-MS-SET-PN5 | 2020-06-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11422404 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-12-15 | USMNF8 | 1 | EA | 0 | Mechanical seal is leaking | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4750 | 1001676781 | SHT PLT SLD MET,4x4ft,1/2in,A572 GR.50 | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 527 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118366 | 508 | 2020 Safety Equipment / Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 110 | 7000000133 | RKI ES-037RM-h2s Sensor hydrogen sulf | 2020-02-28 | Received at Target Location |  | 2020-01-10 |  | U182 | 8201 | Stones Main | STONES | 12090702 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG144 | Entity 7 | USKHU3 | 2020-02-05 | USLFA4 | 1 | EA | 1 | 2020 Safety Equipment / Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2440 | 7000002591 | Fabreeka Pad 1/4" THK x 5 1/2" x 28 5/8" | 2019-04-09 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 266 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04021905 | Name 2 | Name 2 | 2019-04-03 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 870 | 7000002591 | 9'' Saw-Zaw Blades (Milwaukee Torch Bime | 2020-03-03 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia |  | 11179936 | 1077 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-28 | USLFA4 | 100 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
60696550 | 508 | Spare parts for MGC's | S04 | Gas Compress | 2020-02-09 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GC | Gas Compression | 2020-02-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-02-09 | 115950000000 | 10 | 70 | 7000000033 | Nut D-R Part No: 38A4K10 | 2020-02-09 | Received at Worksite |  |  | 2020-02-10 | U182 | 8201 | Stones Main | ST1A2B | 11595045 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-04-11 | USRAR6 | 24 | EA | 24 | Check in spare compressor parts | TECO ESTC GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO |  |  | PU MIKE N 2/8/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7120 | 1001622964 | STL SECT MAR,BEAM,6in,5.990in,20ft | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 970 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 80 | FT | 80 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4010 | 1001663814 | (PCM-0.23) | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 451 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1020 | 7000002596 | STUD BOLTS, 5/8" DIA. X 3 1/2" LONG, AS | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 118 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3890 | 1002309190 | SB2N,B8M CL2,8M,UNC,7/8in,5.50in | 2019-11-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 439 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10311902 | Name 2 | Name 2 | 2019-10-31 | USSOLE | 15 | EA | 15 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6700 | 7000002629 | Reducing Insert, 2" x 1/2", SWM x SWF, 3 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 881 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7410 | 1001645338 | BLT HEX,A325,UNC,2.1/4in,3/4in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 999 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 36 | EA | 36 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60599729 | 508 | HPU Skid Cooling Fan Motor Failure | S19 | Marine Systems | 2020-02-18 | 2019-08-06 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.MA.PS.ZZZ-89021 | Turret Centralised Hydraulic Power Unit | 2019-08-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-25 | 114852000000 | 10 | 10 | 7000000084 | HPU fan electric motor ZM-87410 M3KP 80 | 2020-05-18 | Received at Target Location |  | 2020-02-07 | 2020-02-27 | U182 | 8201 | Stones Main | WHS Floor | 11485163 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-06-17 | USNSB4 | 1 | EA | 1 | LOTO-HPU Cooling Fan Motor | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU JUHO 11-23-19
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6780 | 7000002596 | Stud Bolt, 5/8" x 3 1/2", Aluminum Bronz | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 889 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 72 | EA | 72 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5910 | 7000002596 | Bolt, 3/4" x 3" LG, ASTM F3125 Gr. A325T | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 685 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 26 | EA | 26 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60915161 | 508 | Ess Generator 1 Overspeed Test failure | S03 | Elect. Systems | 2020-04-28 | 2019-10-26 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.ES.PG.ZZZ-11101A | Essential Generator No. 1 Engine | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-28 | 118572000000 | 20 | 20 | 7000005901 | Overspeed trip device | 2020-06-27 | Received at Worksite | 2020-01-28 |  |  | U182 | 8201 | Stones Main | Stones | 11857150 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-11 | USNSB4 | 1 | EA | 1 | Replace Overspeed Trip, Generator 1 Over | REL ESTC GMCO GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete |  |  | ST1A1B 02/07/2020 CMR
60921249 | 508 | O/SI Isolation Valve Packing Leak | S17 | Steam/Hot H2O | 2020-04-02 | 2020-03-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGA-115514 | Stbd Steam to COT 6 Isolation Valve | 2020-01-16 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-03 | 118650000000 | 60 | 30 | 7000004211 | 4-GASKETS-GM, 4" GRAPHITE FLAT METAL GAS | 2020-04-02 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11864984 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-01-16 | USNSB4 | 2 | EA | 0 | Replace Valve VAGA-115514 | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 50 | 7000003768 | 2”x 3’ CEE2-92, 2 ply E & E nylon | 2020-01-25 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0002 | Name 17 | USJRF5 | 2020-01-08 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU ST1A4B 01/22/2020 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1380 | 7000003344 | PS Doors LSG-36-PCY Ladder Safety Gate P | 2019-12-27 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | Crane Access Platform | 11581207 | 138 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A380 | Name 2 | Name 59 | 2019-12-24 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 90 | 7000004213 | KE35/12 SASAKURA KE35 P/N 12 UNION JOINT | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 22 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 510 | 1001723501 | WASHER,FLAT,F436,SERMAGAURD,1/2in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 96 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 4 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | ENEQ | 240 | 7000003740 | Rosemount Documentation, Certifications | 2020-03-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2301 | 11340898 | 24 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN118 | Name 2 | Name 2 | 2020-01-31 | USLFA4 | 1 | EA | 0 | Engineered Equipment | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 190 | 1002301610 | SB2N,B8M CL2,8M,UNC,5/8in,3.50in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 64 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 48 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 650 | 7000003852 | Wilton 11110 B.A.S.H Ball Pein HammerKit | 2020-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 65 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0011 | Name 29 | USRRIG | 2020-02-18 | USLFA4 | 8 | EA | 8 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 40 | 7000004213 | KE35/7 SASAKURA KE35 P/N 7 NIPPLE | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 17 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 200 | 1001723500 | WASHER,LOCK,F436,SERMAGAURD,1/2in | 2020-02-18 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E83 | 11581210 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09111901 | Entity 3 | Name 60 | 2019-09-11 | USSOLE | 15 | EA | 15 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60445278 | 508 | Corrosion blisters on HP flare lines | S03 | Elect. Systems | 2020-02-18 | 2019-11-10 | O.US.STO.STO.005.724FP | MI_PAINT | US.WR508A.ES.PG.TS111-25100 | Gen #3 Gas Turbine Fuel Gas System | 2018-11-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-02-18 | 113123000000 | 10 | 20 | 1001210773 | EYE ROD,U-BOLT,3/8x1,INODO1 | 2020-02-18 | Received at Worksite |  | 2019-10-09 |  | U182 | 8201 | Stones Main | 6 of 23 ST1A2C | 11312272 | 2 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 |  | 2019-10-09 | USAWJB | 23 | EA | 23 | Corrosion blisters on HP flare lines | REL PRT GMPS PRC SETC | EXEC MAOK WPOK | EXEC |  |  | ST 1A2C 6EA 10/18/2019 CMR
60683741 | 508 | Damaged Hyd return hose SC#6 | S19 | Marine Systems | 2020-03-10 | 2019-09-25 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-88506 | Structural Connector No. 6 | 2019-07-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-10 | 115806000000 | 10 | 10 | 7000002629 | 2.25MTR HYD RETURN HOSE | 2020-03-10 | Received at Worksite | 2019-11-20 | 2019-12-07 |  | U182 | 8201 | Stones Main | ST KB C1 | 11580635 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-07-23 | USJDJW | 1 | EA | 1 | Replace Damaged Hyd Return Hose SC#6 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WP WPOK | EXEC |  |  | PU WPT AMW 11/30/19
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1050 | 7000002591 | 1'' #17132, Rotaloc Cutter. Pilot M41796 | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 105 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 6 | EA | 6 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 30 | 1002119302 | WASHER,FLAT,F436,SERMAGARD,0.083in,3/8in | 2019-06-07 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Lower Turret Fire Extingu | 11545759 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A308 | Name 2 | Name 2 | 2019-06-03 | USSOLE | 30 | EA | 30 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60661354 | 508 | O/SI Steam Inlet is Passing | S17 | Steam/Hot H2O | 2020-03-10 | 2019-09-07 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-337V | Steam to No. 2 COPT Isolation Valve | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 115550000000 | 30 | 20 | 7000004211 | 10K50A-GLV-F.P. FLANGE PACKS. DOXSTEEL F | 2020-03-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11555034 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-21 | USNSB4 | 2 | EA | 0 | Replace Valve 115-337V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60739065 | 508 | COT 4S Vent netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127049 | IG Vent COT 4 SB Manual Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642941 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
29504908 | 508 | XV-66702-655 Hot Oil Valve Passing | S21 | Oil Treating | 2020-03-31 | 2019-02-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-66702-655 | Heater/Cooler Actuated Inlet Valve | 2019-11-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-02 | 107451000000 | 30 | 40 | 7000004751 | 4" 150 RF Flex Gaskets | 2020-03-31 | Received at Worksite | 2020-02-12 | 2020-02-24 |  | U182 | 8201 | Stones Main | Staged | 10745081 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-13 | USNSB4 | 2 | EA | 2 | Replace XV-66702-655 Valve, Actuator, & | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | ST LAYDOWN 02/24/2020
61102085 | 508 | FRC Lifeline discrepancies | S15 | Life Saving | 2020-03-05 | 2020-06-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2020-01-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-05 | 120714000000 | 10 | 10 | 7000004662 | Snubber for door, HR-7 | 2020-03-05 | Received at Worksite | 2020-02-17 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B2 | 12071420 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-17 | USMNF8 | 2 | EA | 2 | FRC Lifeline discrepancies | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
60874068 | 508 | FRC inspection deficiencies | S15 | Life Saving | 2020-02-13 | 2020-03-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2019-08-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-03 | 118106000000 | 10 | 10 | 7000004662 | ARMS Lifeboat, Bilge Pump, Automatic-(-, | 2020-02-13 | Received at Worksite |  | 2020-02-13 |  | U182 | 8201 | Stones Main | ST KB C7 | 11810577 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-08-04 | USAWJB | 1 | EA | 1 | FRC inspection deficiencies | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD MAGN WPOK | EXEC |  |  | PU 02/16/20 AMW
60847989 | 508 | MOC GTG5 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-44000 | Gen #5 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 10 | 7000005903 | Amercable Part Number 37-102-308 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780944 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI80 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 120 | FT | 120 | SAEP LO/TO Isolate GTG #5 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60847989 | 508 | MOC GTG5 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-44000 | Gen #5 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 40 | 7000005901 | M20 Serrated Washer | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780944 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI80 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #5 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3020 | 7000002629 | Blind Flanges, 3", 300#, RF, ASME B16.5, | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 332 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1290 | 7000002603 | 12" FLG PROTECTOR (FLANGE, 12",150#, RF | 2019-12-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 145 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12101801 | Name 2 | Name 2 | 2018-12-11 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 300 | 7000003852 | Ergodyne N-Ferno 6823 Winter Ski Mask .. | 2020-12-07 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 30 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES11 |  |  | 2019-11-11 | USABCE | 2 | EA | 2 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2970 | 1002316830 | GASW,CL300/600,316/316L,GPH,3in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 327 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5450 | 7000002603 | GASKET, 4" 150LB, RF (Hydro Only) | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 606 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 11 | EA | 11 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3900 | 7000002591 | 12" FLANGE PROTECTOR FOR (FLANGE, 12", 3 | 2019-11-04 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 440 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11011901 | Name 2 | Name 2 | 2019-11-01 | USSOLE | 22 | EA | 22 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1980 | 7000002596 | 4" NEOPRENE COATED U-BOLT W/ TRIPLE NUT | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 220 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7170 | 1001267674 | BAR FL,1/4in,4in,20ft | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 975 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 320 | 1000709105 | CHASSIS,1756A10,ALLENB | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 418 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6750 | 1001646140 | GASKET,GARLOCK,36010-0008,CL150,3in | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 886 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 15 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 240 | 1001759242 | SB2N,A193B8MCL2,UNC,4in,5/8in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 69 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 18 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 490 | 7000002596 | BLT HEX,A325,UNC,4in,1/2in SERMAGARD | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 94 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 4 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61015474 | 508 | MGC B-TT-77100B-365B need to be replaced | S04 | Gas Compress | 2020-04-07 | 2020-04-21 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.TT-77100B-365B | DE Lube Oil Return Temp Transmitter | 2019-11-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-07 | 119725000000 | 20 | 20 | 7000000062 | Mfr: WIKA INSTRUMENT CORP Mfr pn: WK M | 2020-04-07 | Received at Worksite | 2020-02-04 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB A5 | 11972502 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-20 | USNSB4 | 1 | EA | 1 | Replace Yokogawa Transmitter & Temperatu | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK RUSH WPOK | EXEC |  |  | PU 02/19/20 AMW
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 20 | 7000003739 | 905715C1 BEARING,BALL,RADIAL,1.5748 ID | 2020-01-19 | Received at Worksite |  | 2020-02-16 | 2020-02-26 | U182 | 8201 | Stones Main | ST KB B2 | 12155706 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-28 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO |  |  | PU 02/16/20 AMW
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 100 | 7000003458 | EMBR18527A.32B | 2020-03-04 | Not Shipped |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO200012A | Name 3 | USRRIG | 2020-02-19 | USLFA4 | 2000 | GLL | 0 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 740 | 7000002591 | DRILLFORCE (5 Pcs) 15/16 in. x 4-1/2 in. | 2020-02-25 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 74 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOERT0119 | Name 5 | USHBE9 | 2020-02-19 | USLFA4 | 3 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60636179 | 508 | MGC-B Replace all inspection door bolts | S04 | Gas Compress | 2020-04-04 | 2020-02-25 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.TS771-11000 | Compressor Package B | 2020-03-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-04 | 115265000000 | 10 | 30 | 7000002596 | 1/2 Lock washer, yellow zinc | 2020-04-04 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11526529 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-15 | USMNF8 | 500 | EA | 0 | Replace inspection cover bolts | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 240 | 1000727769 | STUD,GRATING,HILTI,377074,SS,15mm | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 24 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 1 | BX | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61060944 | 508 | Air chokes not resetting without problem | S13 | Fire Protect | 2020-02-06 | 2020-05-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.ZZZ-33110 | Aft Firewater Pump Package | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-06 | 120246000000 | 10 | 10 | 7000005901 | 0986AH0603 MAIN CURRENT RELAY | 2020-03-07 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7E | 12024587 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-22 | USNSB4 | 10 | EA | 10 | Replace Defective Relays On Air Chokes | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU AARON W 01/24/2020 GG
61218667 | 508 | Replace Lifeboat Rations & Water | S15 | Life Saving | 2020-12-10 | 2021-02-17 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.LB | Lifeboats | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-12-11 | 122061000000 | 10 | 60 | 7000004662 | Datrex Water, DX1000W<(>,<)> 4oz (125ml) | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12206109 | 6 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-25 | USAWJB | 960 | EA | 0 | Replace Lifeboat Rations & Water | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 20 | 7000003852 | Pluqis Thermal Laminating Pouches 5 mil, | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | Stones | 12090697 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 32 | USRRIG | 2020-01-18 | USAWJB | 2 | EA | 2 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A1C 02/07/2020 CMR
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 50 | 7000000101 | 1" Pipe Plug Stainless Steel 304 | 2020-04-29 | Received at Worksite | 2019-11-27 | 2020-01-29 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772908 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 5 | EA | 5 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO |  |  | ST1A1C 01/22/2020 CMR
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 40 | 7000002591 | Pentel Champ Pencil, Automatic Pencil, 0 | 2020-02-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200006 | Name 10 | USRRIG | 2020-01-19 | USLFA4 | 2 | EA | 2 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU DOYLE
60920252 | 508 | Ballast Pump 1 Bellows Leaking | S19 | Marine Systems | 2020-02-16 | 2019-10-27 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.BB.PBE-11201A | Ballast Pump No. 1 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-17 | 118636000000 | 10 | 20 | 7000000038 | P/N:435 BELLOWS | 2020-02-02 | Received at Worksite | 2020-01-07 | 2020-01-20 | 2020-02-25 | U182 | 8201 | Stones Main | GRN MILE MOD 22 | 11863639 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-09-03 | USAWJB | 2 | EA | 2 | Replace Ballast Pump 1 Bellows | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD RUSH WPOK XGI | TECO |  |  | PU Aaron GRN MILE MOD 22
60908998 | 508 | Passing SPSV 049 MAJ 12202A | S18 | Water Systems | 2020-02-20 | 2020-02-14 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PSV-12202A-902 | Filter Pressure Safety Valve | 2019-10-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-20 | 118510000000 | 20 | 30 | 1001816127 | GASW,CL300-600,316,GPH,NPS2 | 2020-05-20 | Received at Worksite |  | 2020-02-08 | 2020-02-26 | U182 | 8201 | Stones Main | ST1A5B | 11851034 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-03 | USNSB4 | 1 | EA | 1 | Replace SPSV 049 MAJ 12202A | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | ST1A5B 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3820 | 7000002629 | Bolted Shoe Type Support for 3" Pipe, Pe | 2019-11-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 413 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST10241901 | Name 4 | Name 4 | 2019-10-25 | USSOLE | 52 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7650 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2020-02-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 1028 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-23 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4450 | 7000003344 | Plate, 3/8" x 24" x 24", ASTM A572 Gr. 5 | 2019-11-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 497 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11141903 | Name 4 | Name 4 | 2019-11-14 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2660 | 7000002629 | FLANGE, 12", 300#, RF, WN, ASTM A182 GR | 2019-06-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 289 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05291901 | Name 2 | Name 2 | 2019-05-29 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 670 | 7000003740 | Rosemount Documentation, Certifications | 2020-02-21 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 859 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN117 | Name 2 | Name 2 | 2020-01-31 | USLFA4 | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6590 | 7000002629 | Concentric Reducer, 3" x 2", .095 x .083 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 870 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60344326 | 508 | VABL-777050 Ext Stm Leak | S05 | Gas Dist | 2021-04-30 | 2019-03-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GD.FG.VABL-777050 | Superheater PCV Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2021-04-30 | 112007000000 | 20 | 20 | 1002360705 | SB2N,B7,2H,UNC,3/4in,5in,DOXSTEEL | 2021-04-30 | Received at Worksite | 2019-02-21 | 2019-03-06 |  | U182 | 8201 | Stones Main | ST KB D3 | 11200701 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-01-30 | USNSB4 | 12 | EA | 12 | Repair Valve VABL-777050 | REL PRT CSER GMPS PRC SETC | EXEC EOM MAKD MAOK WPOK | EXEC |  |  | PU WPT 03/05/2019 AJ
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 230 | 7000003197 | IDEAL Part Number 2007 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 23 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 100 | EA | 100 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3000 | 1001759324 | SB2N,A193B8MCL2,UNC,4.5in,3/4in | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 330 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 160 | EA | 160 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 610 | 7000000103 | 2" Duplex Remington Floating Ball Valve | 2020-03-01 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 759 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN111 | Name 2 | Name 2 | 2020-01-16 | USSOLE | 4 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1680 | 7000002603 | 3" 300# RFWN FLANGE PROTECTOR | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 184 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 1010 | 7000003197 | APPLETON ERMB42CCLBUNGW2 | 2020-03-11 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 1088 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-29 | USSOLE | 8 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 10 | 20 | 7000003852 | COMOK Silver Tone 45 Degree Stainless St | 2020-05-16 | Ready for Shipment after Kitting |  | 2020-01-19 |  | U182 | 8201 | Stones Main | Issued | 11783572 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 14 | USNSB4 | 2019-08-10 | USMNF8 | 4 | EA | 4 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC |  |  | PU KIM C
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 70 | 7000002603 | Gaskets 8" 300# FR 1/8" THK SPIRAL WOUND | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 633 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 420 | 1001676774 | SHT PLT SLD MET,4x4ft,3/4in,A572 GR.50 | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 55 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5440 | 7000002603 | GASKET, 2" 150LB, RF (Hydro Only) | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 605 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 27 | EA | 27 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60629360 | 508 | GT #1 Replace Air intake button plugs | S03 | Elect. Systems | 2020-03-15 | 2020-02-21 | O.US.STO.STO.005.724FP | GGTSSLTB | US.WR508A.ES.PG.LAN-11110 | Gas Turbine Power Generation Package 1 | 2019-07-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-15 | 115191000000 | 10 | 20 | 7000003739 | Conduit Plug PN 1739552 | 2020-03-15 | Received at Target Location |  | 2019-09-11 |  | U182 | 8201 | Stones Main | Dist to Solar Tech | 11519116 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 48 | USAWJB | 2019-07-17 | USRAR6 | 2 | EA | 2 | GT #1 Replace Air intake button plugs | REL PRT GMPS PRC SETC | EXEC MAGN MAOK WPOK | EXEC |  |  | PU WPT STKB B7
60699172 | 508 | O/SI Valve XV-1122S-326 over rotating Ba | S19 | Marine Systems | 2020-04-08 | 2019-10-08 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.MA.BB.XV-1122S-326 | WB Tank No. 1S Water Line Ballast Valve | 2020-01-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-09 | 115978000000 | 50 | 100 | 7000004211 | Hydraulic Actuator Model HAA-D12 | 2020-04-08 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11597808 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-08 | USMNF8 | 1 | EA | 0 | Valve over rotating | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61179242 | 508 | Modified code for ESD station MOC 76924 | S20 | Monitor & Ctrl | 2020-06-06 |  | O.US.STO.STO.005.71300 | 508ET | US.WR508A.MC.SH.ESD | Emergency Shutdown Stations | 2020-02-28 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-16 | 121605000000 | 10 | 10 | 7000000132 | Reverse Engraved Nametag (Vendor alread | 2020-06-06 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12160545 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2020-02-28 | USNSB4 | 56 | EA | 0 | Replace ESD stations name plates | REL ESTC PRC SETC | APPR EOM WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 360 | 7000002591 | 26mm ½” drive crowfoot socket Part numbe | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 36 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20CG014 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
29504908 | 508 | XV-66702-655 Hot Oil Valve Passing | S21 | Oil Treating | 2020-03-31 | 2019-02-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-66702-655 | Heater/Cooler Actuated Inlet Valve | 2019-11-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-02 | 107451000000 | 30 | 20 | 7000004751 | 3-COAT PAINT RAL1023 STONES YELLOW | 2020-03-31 | Received at Worksite | 2020-02-12 | 2020-02-24 |  | U182 | 8201 | Stones Main | Staged | 10745081 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-11-13 | USNSB4 | 1 | EA | 1 | Replace XV-66702-655 Valve, Actuator, & | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | ST LAYDOWN 02/24/2020
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 70 | 7000002591 | Grainger Crescent wrench #1NYB4 | 2020-01-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0005 | Name 8 | USCRFI | 2020-01-13 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
61170198 | 508 | Faulty Press Trans LACT Skid | S21 | Oil Treating | 2020-04-25 | 2021-01-20 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-25 | 121499000000 | 10 | 10 | 1000711628 | VALVE,BALL,SWAGELOK,SS-45F8,1/2in,S316 | 2020-04-25 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 12149917 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-26 | USAWJB | 1 | EA | 1 | MOC 79792 Faulty Press Trans LACT Skid | REL ESTC GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 70 | 7000003852 | 2-Pack Pocket Notebook Journal Notepad S | 2020-03-31 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | CAOA021320 | Name 12 | USRRIG | 2020-02-19 | USLFA4 | 4 | EA | 4 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60737083 | 508 | Solenoid & VPI test fail 5P | S21 | Oil Treating | 2020-02-10 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6635P-217 | Crude Oil to/from COT 5 On/Off PS Valve | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-10 | 116406000000 | 20 | 20 | 7000005901 | P.0244110028 AVC 02 CL1 A1 VPI MANIFOLD | 2020-04-30 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B6 | 11640588 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 1 | Rebuild Bifold Solenoid XV-6635P-217 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 120 | 7000002591 | Plate, 1/4" x 48" x 96", ASTM A36 | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 1 | EA | 1 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 30 | 7000002591 | Flange, 20", JIS 5K, FF, ASME B16.5, AST | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 7 | EA | 7 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
61152125 | 508 | SUB order to replace GT2 oil scavenger p | S03 | Elect. Systems | 2020-07-01 | 2020-07-11 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.ES.PG.M-3500-1 | Turbine Scavenge Pump A Motor | 2020-01-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-07-02 | 121291000000 | 10 | 10 | 7000000035 | GT2 oil scavenger pump | 2020-07-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12129125 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-01-13 | USAMH7 | 1 | EA | 0 | Perform Electrical Isolation To Replace | REL PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5020 | 7000002629 | 45 DEG ELBOW, 12" SCH 10S LR BW CLASS WP | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 563 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60747149 | 508 | COT 2 STBD HC line Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127023 | COT 2 SB HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651961 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 470 | 7000002662 | PIPE, 12", S/10S (0.180 WT), ASTM A790 U | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 63 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 84 | FT | 79.6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 650 | 7000002629 | ELBOW, 12, S/10S (0.180 WT), LR, 90 DEG. | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 81 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7570 | 7000002629 | Blind Flange, 4", 150#, RF, ASME B16.5, | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 1019 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 90 | 1000720246 | ADIMC,SWAGELOK,SS8TA18,1/2x1/2NPT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 787 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 4 | EA | 4 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 220 | 7000003852 | Timex Men's T5H591 Ironman Classic 30 .. | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 620 | 7000000052 | Det-Tronics Flame Detector | 2020-02-26 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 769 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN114 | Name 2 | Name 2 | 2020-01-23 | USSOLE | 1 | EA | 1 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7400 | 1001664310 | BLT HEX,A325,UNC,2.1/2in,3/4in,SERMAGARD | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 998 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-15 | USSOLE | 14 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 160 | 1001665228 | PLIC,SWAGELOK,SS6FTA160,3/8x1/4in | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 794 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 50 | EA | 50 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 270 | 7000003852 | Armor All 18574 Premier Car Care Kit, 94 | 2020-12-07 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 27 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES11 |  |  | 2019-11-11 | USABCE | 2 | EA | 2 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5750 | 1002301610 | SB2N,B8M CL2,8M,UNC,5/8in,3.50in | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 669 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3290 | 7000002646 | Needle Valve, 1/2, VNT-2505D (See Attach | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 359 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161903 | Name 4 | Name 4 | 2019-10-16 | USLFA4 | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 340 | 1002128206 | CABLE,ARMD,AMER-CBL,37-102-309-BS,8AWG | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 826 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 681 | FT | 681 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60470624 | 508 | Turret Gantry Crane Out of Service | S40 | Cargo Handling | 2020-06-01 | 2019-11-19 | O.US.STO.STO.005.724FP | GHEMSPAR | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-06-01 | 113409000000 | 10 | 90 | 7000000040 | Lube for Main Hoist | 2020-06-01 | Received at Worksite |  | 2019-07-17 | 2020-01-02 | U182 | 8201 | Stones Main | ST KB B2 | 11340935 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-02-15 | USRAR6 | 2 | EA | 2 | Turret Gantry Crane Out of Service | TECO PCNF ESTC GMPS PPRT PRC SETC | XCNF NCMP WPOK XGI ZPVS | TECO |  |  | PU Marty S 05/07/2019 CR
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1080 | 7000003852 | Channellock 2 Piece Tongue and Groove Pl | 2021-03-31 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 108 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST20CG0146 | MarineForman | USRRIG | 2020-02-20 | USCDP7 | 12 | EA | 12 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60470624 | 508 | Turret Gantry Crane Out of Service | S40 | Cargo Handling | 2020-06-01 | 2019-11-19 | O.US.STO.STO.005.724FP | GHEMSPAR | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-06-01 | 113409000000 | 10 | 60 | 7000000040 | Parking Brake Chain Pull Handle | 2020-06-01 | Received at Worksite |  | 2019-07-17 | 2020-01-02 | U182 | 8201 | Stones Main | ST KB B2 | 11340935 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-02-15 | USRAR6 | 1 | EA | 1 | Turret Gantry Crane Out of Service | TECO PCNF ESTC GMPS PPRT PRC SETC | XCNF NCMP WPOK XGI ZPVS | TECO |  |  | PU Marty S 05/07/2019 CR
60739057 | 508 | COT 4 Port HC line Netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127010 | COT 4 PS HC Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642933 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 290 | 1002316830 | GASW,CL300/600,316/316L,GPH,3in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 74 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 3 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 100 | 7000002629 | 0002 560Z-XXXX 00000 SHELL PAINT ON BL | 2020-02-24 | Received at Target Location |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  |  | USNSB4 | 2019-07-15 | USNSB4 | 2 | EA | 2 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 200 | 1002316830 | GASW,CL300/600,316/316L,GPH,3in | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 116 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 3 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 120 | 7000002662 | Pipe, 8", S/60, ASME B36.10M, ASTM A312 | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 108 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 20 | FT | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 20 | 20 | 7000003196 | SS-45F8 BALL VALVE | 2020-02-04 | Received at Worksite |  |  | 2020-02-14 | U182 | 8201 | Stones Main | ST1A1B | 11882270 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-29 | USNSB4 | 4 | EA | 4 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 110 | 7000000039 | 6801-16-16-NW0-SS STR. THREAD ELBOW | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 6 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 40 | 1001267674 | BAR FL,1/4in,4in,20ft | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 20 | FT | 20 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 330 | 7000002629 | 200-DC-SS 2" Camlock DC Female | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 60 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A363 | Name 2 | Name 2 | 2019-10-21 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60737094 | 508 | Solenoid Valve test fail Slop STBD | S21 | Oil Treating | 2020-03-17 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-663SS-231 | Crude Oil to/frm Slop Tank On/Off SB Vlv | 2019-08-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-17 | 116406000000 | 20 | 20 | 7000000070 | BiFold FP02/S0A/C3/43/SC/S/RK-04 Repair | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | ETA 10/23 | 11640599 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-08-27 | USNSB4 | 1 | EA | 0 | Repair Solenoid Valve Slop STBD | REL PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 20 | 7000003196 | SS-8-HLN-3.00 HEX LONG NIPPLE | 2021-03-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB C7 | 11057838 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO182KDC | Name 37 | USRRIG | 2018-07-24 | USLFA4 | 4 | EA | 4 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved |  |  | PU MOD22 1st FLR 09/04/2018 MP
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 220 | 7000003197 | IDEAL Part Number 2006S | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 100 | EA | 100 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 410 | 7000002591 | 2''x20'x2Ply Nylon Straps | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 750 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A384 | Name 2 | Name 2 | 2020-01-11 | USSOLE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1590 | 1002150255 | SHT PLT SLD MET,4x4ft,3/8in,A572-50 | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 175 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118331 | 508 | 2020 Chemical Order - Engine Room | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical |  | 2020-12-31 | 120907000000 | 10 | 30 | 7000003458 | BIOC16298A.32B | 2020-01-29 | Received at Target Location |  | 2020-01-10 |  | U182 | 8201 | Stones Main | CPORT | 12090688 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200004A | Name 40 | USRRIG | 2020-01-16 | USLFA4 | 500 | GLL | 492 | 2020 Chemical Order - Engine Room | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60850124 | 508 | Grease caps filled with water | S19 | Marine Systems | 2020-05-16 | 2019-09-11 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.MS885-00000 | Turret Structural Connectors | 2019-09-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-05-16 | 117836000000 | 10 | 80 | 7000005901 | 737M42x2 SEALING SCREW PLUG W/ O-RING 10 | 2020-05-16 | Received at Worksite |  | 2020-01-19 |  | U182 | 8201 | Stones Main | Kim Case | 11783572 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-21 | USNSB4 | 100 | EA | 100 | Remove old grease zerks | REL PCNF PRT GMPS PRC SETC | EXEC MAGN WPOK | EXEC |  |  | PU AARON W 01/19/2020
60696550 | 508 | Spare parts for MGC's | S04 | Gas Compress | 2020-02-09 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GC | Gas Compression | 2020-02-10 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-02-09 | 115950000000 | 10 | 60 | 7000000033 | Stud D-R Part No: R89158JX08052 | 2020-02-09 | Received at Worksite |  |  | 2020-02-10 | U182 | 8201 | Stones Main | ST1A2B | 11595045 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAWJB | 2019-04-11 | USRAR6 | 48 | EA | 48 | Check in spare compressor parts | TECO ESTC GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO |  |  | PU MIKE N 2/8/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5520 | 7000002629 | 4" 150 RFWN Flange Protectors | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 613 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 21 | EA | 21 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 170 | 7000002629 | Reducing Tee, 3" x 2", S/10S x S/80, ASM | 2019-09-08 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04221901 | Entity 2 | Name 60 | 2019-04-22 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 310 | 1001583867 | GSKT RJ,CS,OCTAL,R46 | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 76 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 2 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61210834 | 508 | PDT-66501-130 Needs to be Replaced | S21 | Oil Treating | 2020-04-20 | 2021-02-13 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.PDT-66501-130 | Run 3 Strainer Pressure Diff Transmitter | 2020-02-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-20 | 121971000000 | 10 | 10 | 1002404510 | TRDP,EMER-PM,3051CD2A22A1KS2M5B4K7D4P1Q+ | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12197071 | 1 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-02-20 | USAWJB | 1 | EA | 0 | PDT-66501-130 Needs to be Replaced | REL ESTC PRC SETC | APPR MAOK WPOK ZPMM | Approved
60352956 | 508 | YR Lifeboat Launch and Run Test | S15 | Life Saving | 2020-02-10 | 2020-05-31 | O.US.STO.STO.005.724FP | MI_LFSAV | US.WR508A.GU.LS.ZZZ-33320 | No. 1 Starboard Side Lifeboat | 2018-09-23 | WO | U100 | 72FP | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 0 Statutory / Legislat | 2020-02-11 | 112105000000 | 10 | 60 | 1001726076 | ALTERNATOR BELT,400-BELT0001,ALXR-RYN | 2020-02-10 | Received at Worksite |  | 2020-01-19 | 2020-02-13 | U182 | 8201 | Stones Main | ST1A3B | 11210548 | 6 | 1 | Stocked Locally (Reservation) | L | X |  |  | Name 3 | USAWJB | 2019-11-29 | USAWJB | 1 | EA | 1 | YR Lifeboat Launch and Run Test | TECO CNF PRT GMPS ILAS PRC SETC | XCNF MAGN MAOK WPOK XGI | TECO |  |  | PU 01/30/2020 JH
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 30 | 7000003768 | 1”x 4’ CEE2-91, 2 ply E & E nylon | 2020-01-25 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0002 | Name 17 | USJRF5 | 2020-01-08 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU ST1A4B 01/22/2020 CMR
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 290 | 1001645338 | BLT HEX,A325,UNC,2.1/4in,3/4in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 18 | EA | 18 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60975188 | 508 | XV-12202A-912 Fails to Open | S18 | Water Systems | 2020-02-06 | 2019-10-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.XV-12202A-912 | Filter Backwash On/Off Control Valve | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-02-06 | 119260000000 | 10 | 40 | 7000000104 | Set of drawings for valve | 2020-02-06 | Not Shipped |  | 2019-12-28 | 2020-02-10 | U182 | 8201 | Stones Main | Stones | 11925969 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 1 | USAWJB | 2019-10-31 | USRAR6 | 1 | EA | 0 | LOTO System - Confirm Isolation | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1190 | 1001991793 | PIPE MET,API 5L-X42,BARE,40,1.1/2in,SRL | 2020-05-07 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G04 | 11581207 | 119 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031901 | Name 4 | Name 59 | 2019-12-04 | USSOLE | 21 | FT | 21 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 910 | 1001573042 | SHT PLT SLD MET,4x4in,1/2in | 2020-02-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F13 | 11581207 | 91 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09191901 | Entity 3 | Name 59 | 2019-09-19 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60739056 | 508 | COT 4 STBD netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127009 | COT 4 SB HC Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642932 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60985336 | 508 | PBE-10907A High vibration at 6X | S19 | Marine Systems | 2020-06-01 | 2020-03-29 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.MA.PR.PBE-10907A | Steering Gear No. 1 Pump | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-06-04 | 119372000000 | 20 | 20 | 7000000103 | O-rings for Hydraulic pump | 2020-06-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11937182 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-03-02 | USMNF8 | 1 | EA | 0 | Install rigging | REL ESTC PRC SETC | APPR MAGN RUSH WP | Approved
60989313 | 508 | Erratic Speed Reading Steam Turbine #3 | S21 | Oil Treating | 2020-02-11 | 2020-04-04 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.OT.SS.CPI-66301C | Steam Turbine Control Panel | 2019-10-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-11 | 119417000000 | 10 | 60 | 7000002591 | 1/4" x 1" 316SS bolt w/1 washer | 2026-10-11 | Received at Worksite | 2019-12-05 | 2020-01-19 | 2020-02-19 | U182 | 8201 | Stones Main | Stones | 11941691 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-05 | USAWJB | 30 | EA | 30 | Shut Down Affected Unit & LO/TO Steam Tu | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD WPOK XGI | TECO |  |  | ST1A5B 01/19/2020 AMW
61200672 | 508 | Stones Small Civil Projects 2020 |  |  | 2020-12-31 |  | P.US.STO.NF.20.009.7240A | GENERIC |  |  | 2020-02-11 | WO | U100 | GEN | US01 | P16 | [5 empty] | 3 Low | 2020-12-31 | 121848000000 | 10 | 20 | 7000002603 | Gasket, 3/4", Flat Ring, Compressed Inor | 2020-02-28 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G97 | 12184838 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST02242002 | Name 4 | Name 60 | 2020-02-27 | USSOLE | 3 | EA | 0 | Stones Small Civil Projects 2020 | REL ESTC PRC SETC | APPR | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 280 | 7000002596 | 5/16" x 1" 316 SS Cap Bolt AND Nut | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 28 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 200 | EA | 200 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 500 | 7000002629 | PLUG, 1/2", SC, HEX HEAD, ASTM A182 GR F | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 66 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 240 | 7000003196 | Swagelok SS-TBP12 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 802 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 100 | EA | 100 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
61118338 | 508 | 2020 Waste Disposal | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 10 | 7000002591 | E-Waste container | 2020-04-01 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090695 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO020320B | Name 41 | USKHU3 | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Waste Disposal | REL ESTC PRC SETC | EXEC STDG | EXEC
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 150 | 1000715365 | SEALANT,THREAD,SWAGELOK,MS-PTS-50 | 2019-11-20 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 15 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI68 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 1 | EA | 1 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
60055275 | 508 | O/SI Incorrect material on gauge LG-7715 | S04 | Gas Compress | 2020-04-11 | 2019-03-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GC.GS.LG-77151A-231A | 1st Stage Suction Scrubber Level Gauge | 2019-02-13 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-04-11 | 108488000000 | 10 | 30 | 7000002603 | 00000 VCS0.75150 3/4" 150# VCS FLANGE IN | 2020-04-11 | Ready for Shipment after Kitting | 2019-02-25 | 2019-03-27 |  | U182 | 8201 | Stones Main | ST KB C7 | 10848765 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-02-12 | USJDJW | 4 | EA | 4 | LG-7715 change bolting/gaskets | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 520 | 7000003197 | TNB Catalog Number F2040 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 844 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 200 | EA | 200 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 220 | 7000002603 | FLAT RING GASKET, 14", 150#, RF, FLEXIBL | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 35 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 5 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 40 | 1000720054 | TEIC,SWAGELOK,2507-1210-3,3/4in | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 782 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 5 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
29423230 | 508 | Isolation valves for main gas compressor | S01 | Platform | 2020-06-01 |  | O.US.STO.STO.002.724FP | GENERIC | US.WR508A | Stones FPSO | 2017-12-28 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-06-01 | 106230000000 | 10 | 10 | 7000000113 | 3M Gasket Adhesive | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8201 | Stones Main | Stones | 10623043 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USMSLN | 2019-07-03 | USRAR6 | 1 | EA | 1 | Isolation valves for main gas compressor | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60172772 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-03-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.95T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 110086000000 | 10 | 10 | 7000002591 | Blind Flange, 40mm, FF, JIS 16K, JIS B22 | 2020-02-04 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008581 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10111901 | Place 1 | Name 60 | 2019-10-11 | USLFA4 | 2 | EA | 2 | MOC missing steam trap | REL PCNF ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5220 | 7000002603 | GASKET, 2" 150LB, 1/8" THICK, RF SPIRAL | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 583 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 27 | EA | 27 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61114758 | 508 | O/SI SDV-77163A-904A Passing By | S04 | Gas Compress | 2020-02-15 | 2020-06-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.SDV-77163A-904 | 2nd Stg Compressor Out Gas Shutdown Vlv | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-15 | 120863000000 | 10 | 50 | 7000002591 | GearWrench-P95-525-POP-Flange-Spreader/d | 2020-02-04 | Received at Target Location | 2020-01-27 | 2020-02-07 | 2020-02-18 | U182 | 8201 | Stones Main | SDV-77163A-904A | 12086293 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A385 | Name 2 | Name 59 | 2020-01-27 | USSOLE | 2 | EA | 2 | Replace SDV-77163A-904A | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO
61098380 | 508 | Biocide Chemical Inj for Cargos & Drains | S21 | Oil Treating | 2020-09-28 | 2020-11-27 | C.US.STO.FI.19.012.1230A | 508CI&E | US.WR508A.OT.SS.VE663-70000 | Cargo Tank Systems | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-09-28 | 120671000000 | 10 | 70 | 7000003512 | 1” x 0.065 Alloy 254 (6 Moly) Uncoated T | 2020-05-22 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 12067106 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI89 | Name 2 | Name 61 | 2020-02-12 | USSOLE | 660 | FT | 0 | Biocide Chemical Inj for Cargos & Drains | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 90 | 7000002629 | 0001 1705-1059 00000 3/4 (3-7/8 OD) X | 2020-02-24 | Received at Target Location |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-15 | USNSB4 | 2 | EA | 2 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 40 | 7000002583 | "10 X 3/4 SS SELF TAP SCREW PAN HEAD | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 500 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60725219 | 508 | Replace Suction and Discharge Gauges | S18 | Water Systems | 2020-02-09 | 2020-04-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PG-12110A-102 | Pump Suction Pressure Gauge | 2019-12-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-09 | 116277000000 | 10 | 10 | 7000000062 | WK 52900716 233.54 2.5 10BAR/PSI 1/4 L R | 2020-02-09 | Received at Worksite | 2020-01-13 | 2020-01-29 |  | U182 | 8201 | Stones Main | ST KB A6 | 11627685 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 2 | Replace Suction and Discharge Gauges | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 2/5/2020 JH GG
60683738 | 508 | O/SI SDV-66202-870 Failed to Close | S22 | Prod Gathering | 2020-04-02 | 2019-05-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.SDV-66202-870 | 2nd Stg Separator Prod Wtr Shutdown Vlv | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-02 | 115806000000 | 30 | 30 | 1002360783 | SB2N,B7,2H,UNC,5/8in,3.75in,DOXSTEEL | 2020-04-02 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | ST KB D3 | 11580631 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-04-19 | USNSB4 | 4 | EA | 4 | Replace SDV-66202-870 | REL ESTC GMCO GMPS PPRT PRC SETC | APPR EOM MAGN MAOK WP | EXEC |  |  | PU Aaron 07/08/2019
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 160 | 7000003739 | 918966C1 LOCKNUT,0.875-14UNJF-3B,LIGHT | 2020-02-24 | Received at Target Location |  |  | 2020-02-26 | U182 | 8201 | Stones Main | STONES | 12155706 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 150 | 7000003739 | 951504C1 WASHER,FLAT,0.875 IN,1.845 OD | 2020-02-24 | Received at Target Location |  |  | 2020-02-26 | U182 | 8201 | Stones Main | STONES | 12155706 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO
61175887 | 508 | LACT -Drain Valves Severely Corroded | S21 | Oil Treating | 2020-03-14 | 2020-03-25 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.ZAU-66501 | Metering Unit | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-24 | 121566000000 | 50 | 30 | 7000004751 | 3-COAT PAINT STONES RAL-1023 YELLOW | 2020-03-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main |  | 12156642 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  |  | USNSB4 | 2020-02-25 | USNSB4 | 19 | EA | 0 | Replace Defective Valves On LACT Skid | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60708311 | 508 | Faulty check valve on FW Gen # 3 | S18 | Water Systems | 2020-04-22 | 2019-10-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.VACH-122504 | Pump Discharge Check Valve | 2020-01-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-22 | 116082000000 | 10 | 10 | 7000005901 | P/N: G52-24-A02-6 6" GLOBE VALVE ANGLE P | 2020-04-22 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones WPT | 11608239 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | GW982959 | 2020-01-23 | GW982959 | 1 | EA | 0 | LOTO- Electric motor FW#3 | REL ESTC GMPS PRC SETC | APPR MAGN WP ZPMM | Approved
60629364 | 508 | GT-5 Replace air inlet button plugs | S03 | Elect. Systems | 2020-03-15 | 2020-02-21 | O.US.STO.STO.005.724FP | GGTSSLTB | US.WR508A.ES.PG.LAN-11150 | Gas Turbine Power Generation Package 5 | 2019-07-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-15 | 115191000000 | 10 | 20 | 7000003739 | Conduit Plug PN 1739552 | 2020-03-15 | Received at Target Location |  | 2019-10-15 |  | U182 | 8201 | Stones Main | Dist to Solar Tech | 11519120 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 48 | USAWJB | 2019-07-17 | USRAR6 | 2 | EA | 2 | GT-5 Replace air inlet button plugs | REL PRT GMPS PRC SETC | EXEC MAGN MAOK WPOK | EXEC |  |  | PU AARON 09/29/2019 CMR
60739058 | 508 | COT 3 Stbd HC Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127013 | COT 3 SB HC Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116429000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642934 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3530 | 7000002603 | 12" Flange Protectors 12", 150#, RF | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 383 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 1020 | 7000003197 | APPLETON ERMB42CCLBUHGW2 | 2020-03-11 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 1089 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-29 | USSOLE | 6 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7360 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 994 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 50 | EA | 50 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5740 | 1001759324 | SB2N,A193B8MCL2,UNC,4.5in,3/4in | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 668 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 256 | EA | 256 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1790 | 7000002603 | GASKET, 12", 300#, RF, 1/8" THICK, SPIRA | 2019-01-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 196 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01171902 | Name 2 | Name 2 | 2019-01-18 | USDSVB | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 200 | 7000000052 | eProcess Model WSD10-300-T wellstream de | 2019-08-22 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 208 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN045 | Name 2 | Name 2 | 2019-01-25 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7050 | 7000003343 | Angle, L2 X 2 X .3125, ASTM A36 | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 963 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61229190 | 508 | Blackwater plumbing restricted in Qtrs. | S09 | Bldg & Qtrs | 2020-04-15 | 2020-04-27 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.BQ.F1 | Main Deck Accomodations | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-15 | 122182000000 | 10 | 10 | 7000002583 | Uriclean Concentrate, 25 liters | 2020-04-15 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12218218 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-03-02 | USMNF8 | 2 | EA | 0 | Apply Vecom Uriclean in urinals | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3010 | 1002360784 | SB2N,B7,2H,UNC,5/8in,3.5in,DOXSTEEL | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 331 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10151902 | Entity 3 | Entity 3 | 2019-10-16 | USSOLE | 9 | EA | 9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 100 | 1000720145 | COIMC,SWAGELOK,SS81014,1/2x1/4NPT | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 788 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 4 | EA | 4 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 170 | 1002316830 | GASW,CL300/600,316/316L,GPH,3in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 62 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 8 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 80 | 7000003684 | BUCKING BAR 6-3/8 OAL 1924N11 | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 1 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61179018 | 508 | FRC Engine Turbo Exhaust piping corroded | S15 | Life Saving | 2020-04-25 | 2020-07-27 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.LS.ZZZ-33330 | Fast Rescue Boat | 2020-02-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-25 | 121603000000 | 10 | 20 | 7000005811 | Exhaust Clamp | 2020-04-25 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12160259 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-03 | USMNF8 | 1 | EA | 0 | Replace FRC Engine Turbo Exhaust piping | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
60888917 | 508 | Faulty Temp Probe on Swivel | S19 | Marine Systems | 2020-04-11 | 2020-02-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89650 | Electrical Power & Signal Swivel | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-11 | 118279000000 | 20 | 40 | 7000005901 | PL513 COMPLETE 1 REED CONTACT | 2020-06-10 | Received at Worksite | 2019-12-09 | 2019-12-21 |  | U182 | 8201 | Stones Main | ST KB B4 | 11827852 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-23 | USNSB4 | 1 | EA | 1 | Replace Temperature Safety Transmitter O | REL ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MAKD RUSH WPOK | EXEC |  |  | PU WPT ST KB B4
60739057 | 508 | COT 4 Port HC line Netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127010 | COT 4 PS HC Main Manual Valve | 2019-05-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116429000000 | 10 | 10 | 7000000060 | MRL-02-14 MRL Valve Interlock, Dual Key, | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642933 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61219230 | 508 | GT #3 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-2 | Generator #3 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 60 | 7000003763 | 14325 3/8 X 12 SQ KEYSTOCK | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206814 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #3 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 390 | 7000002596 | Plate Washer, 3/4" ID x 2" OD x 5/16" TH | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 39 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 5 | EA | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61037587 | 508 | Compressor Bleed Blind Installation | S04 | Gas Compress | 2020-02-18 |  | O.US.STO.STO.005.71300 | 508DANOS | US.WR508A.GC.GS | Gas Sales | 2019-11-30 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-02-18 | 119969000000 | 10 | 10 | 7000002591 | 2" 300# Hydro/Paddle Blind, CS 516 Gr-70 | 2020-01-29 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 11996884 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STO011720A | Name 8 | TK821001 | 2020-01-21 | USLFA4 | 1 | EA | 0 | Compressor Bleed Blind Installation | REL ESTC PRC SETC | APPR | Approved
61219230 | 508 | GT #3 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113-2 | Generator #3 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 40 | 7000003763 | 8MX-80S-12 SPKT | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206814 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #3 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61175084 | 508 | Nitrogen Comp. B has low output | S19 | Marine Systems | 2020-03-13 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87409B | Turret Centralised HPU N2 Intensifer B | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-15 | 121557000000 | 10 | 10 | 7000000047 | N2 Intensifier Piston Ring Kit | 2020-03-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 12155722 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USAWJB | 2020-01-28 | USRAR6 | 1 | EA | 0 | Nitrogen Comp. B has low output | REL ESTC PRC SETC | APPR MAGN WP | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 860 | 1001664239 | WASHER,FLAT,F436,SERMAGARD,5/8in | 2020-01-12 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 86 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08051901 | Entity 3 | Name 59 | 2019-08-05 | USDKFB | 148 | EA | 148 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 430 | 7000002591 | FRL Filter Regulator Lubricator ASSY | 2019-10-28 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STONES | 11545759 | 74 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TDRTNSNR81 | Name 14 | Name 14 | 2019-10-28 | USABCE | 1 | EA | 1 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved |  |  | PU BUBBA 2/9/2020
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 800 | 7000003463 | PC-KL9D3YV01M | 2020-03-18 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | Job No: 2309 | 11179936 | 1071 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-02-26 | USSOLE | 1 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 720 | 7000003198 | 6 Strand Fiber / 8.3um, Fiber Optic, Sin | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 934 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI85 | Name 2 | Name 2 | 2020-02-05 | USLFA4 | 300 | FT | 300 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
61042037 | 508 | End Stops OOC - Collar Deck - ZZZ-887106 | S40 | Cargo Handling | 2020-02-09 | 2020-06-30 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-11-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-03-21 | 120026000000 | 10 | 40 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2020-01-18 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | Trolley End Stops | 12002579 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A393 | Name 2 | Name 59 | 2020-02-01 | USSOLE | 48 | EA | 48 | Fabricate End Stops | REL PCNF ESTC GMCO GMPS PPRT PRC SETC | EXEC MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 460 | 7000002591 | 1500138 - Python Long Safe Bucket 120 in | 2020-01-20 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 755 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A373 | Name 2 | Name 2 | 2020-01-14 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6120 | 7000002629 | FNPT Boss, 3" x 1/2", 3000#, ASME B16.11 | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 710 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 4 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2430 | 1002058432 | NUT,A563-DH,HEXAGONAL,UNC,5/8,SERMAGARD | 2019-04-08 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 265 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011905 | Name 2 | Name 2 | 2019-04-02 | USSOLE | 124 | EA | 124 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4850 | 7000002662 | PIPE 12" SCH 10S B.E., ASME B36.19M, AST | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 546 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 60 | FT | 59.5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 560 | 1001816278 | GASW,CL300,316,GPH,NPS6 | 2020-01-30 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids | 11179936 | 773 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A389 | Name 2 | Name 2 | 2020-01-27 | USSOLE | 4 | EA | 4 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1050 | 1002360782 | SB2N,B7,2H,UNC,5/8in,4in,DOXSTEEL | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 121 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61184263 | 508 | busted diaphragm on suction damper 12878 | S10 | Chem Injection | 2020-06-20 | 2021-01-26 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.CI.MBL-12878 | D Pump Suction Pulsation Damper | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-06-20 | 121654000000 | 10 | 10 | 7000000103 | PAR CPD100-0-0304, Parker Pulsation Damp | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12165419 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-11 | USMNF8 | 2 | EA | 0 | Replace diaphragm on suction damper | REL ESTC PRC SETC | APPR MAGN WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4630 | 1001816127 | GASW,CL300-600,316,GPH,NPS2 | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 515 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6810 | 7000002603 | Flange Protectors 4", SO, 150#, FF | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 892 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 300 | 7000002591 | 3/4 “drive 12 piece metric impact socket | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 30 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0140 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 290 | 7000002603 | Flange Protectors 3", 600#, RF | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 125 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60828048 | 508 | Emergency Kits for Lifeboats STONES | S15 | Life Saving | 2020-06-01 |  | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.LS.LB | Lifeboats | 2019-07-04 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 117583000000 | 10 | 10 | 7000002591 | First Alert Marine Fire Extinguisher 10 | 2020-06-01 | Received at Target Location |  |  | 2020-01-31 | U182 | 8201 | Stones Main | ST1A5B | 11758304 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-07-04 | USDHIE | 5 | EA | 5 | Stage all kits as directed by Leadership | TECO ESTC CSER GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO |  |  | ST1A4B 10/25/19 GG
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 10 | 7000000039 | AMD-2421 HYDRAULIC OIL COOLER ASSEMBLY | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 170 | 7000000039 | 247 110v, 16amp Straight Connector | 2020-03-03 | Not Shipped |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 17 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOELEC001 | Name 30 | JP832018 | 2020-02-04 | USLFA4 | 12 | EA | 0 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | Deleted
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 780 | 1001201050 | HITCH PIN/WIRE LOCK PIN,WILSNMFG,SWL2600 | 2019-12-24 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E69 | 11581207 | 78 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST07181901 | Entity 3 | Name 59 | 2019-07-19 | USSOLE | 9 | EA | 9 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 80 | 1000584317 | REIC,SWAGELOK,SS810R12,3/4x1/2in | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 3 | EA | 3 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 40 | 1000720080 | TEE,UNION,SWAGELOK,SS-1210-3,3/4in | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 9 | EA | 9 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
60661352 | 508 | O/SI Steam Inlet is Passing | S17 | Steam/Hot H2O | 2020-03-10 | 2019-09-07 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.SW.115-410V | Steam to No. COW Pump Isolation Valve | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 115550000000 | 30 | 10 | 7000004211 | 125-20K-F7314-CSxBT 125mm JIS 20K CS Ang | 2020-05-09 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11555032 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-21 | USNSB4 | 1 | EA | 0 | Replace Valve 115-410V | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6250 | 7000002603 | Flange Protectors, 3", SO, 150#, FF | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 723 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 18 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
60758330 | 508 | O/SI Leaking Steam Flange In Pumproom | S17 | Steam/Hot H2O | 2020-03-10 | 2020-03-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.VE115-52000 | Tank Heating System | 2020-01-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-15 | 116748000000 | 10 | 140 | 7000002629 | Blind Flange, 12", JIS 10K, w/1/2" NPT O | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G33 | 11674758 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12231902 | Name 4 | Name 60 | 2019-12-30 | USSOLE | 2 | EA | 2 | Shut down Steam system / LOTO | REL ESTC GMPS PRC SETC | APPR MAGN MANX WP | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5040 | 7000002629 | REDUCER CONC, 8" X 4" SCH 10S BW CLASS W | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 565 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 200 | 7000003852 | Travel Wallet RFID Blocking Bifold Slim | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1240 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 140 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061802 | Name 2 | Name 2 | 2018-12-07 | USSOLE | 156 | EA | 156 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1890 | 1000712038 | VALVE,NEEDLE,1/2in,SS,H1RDS44Q,ANDRS-GR | 2019-02-12 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 211 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02081901 | Name 2 | Name 2 | 2019-02-08 | USDSVB | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 950 | 1001816275 | GASW,CL300,316,GPH,NPS12 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 111 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 12 | EA | 12 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2640 | 7000002629 | FLANGE, 12", 300#, RF, WN, ASTM A182 GR | 2019-05-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 287 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04301901 | Name 2 | Name 2 | 2019-05-01 | USSOLE | 5 | EA | 6 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5940 | 1002058423 | WASHER,LOCK,F436,SERMAGARD,3/4in | 2019-12-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G29 | 11179936 | 688 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12161901 | Name 4 | Name 4 | 2019-12-17 | USSOLE | 26 | EA | 26 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61063352 | 508 | Service Coarse Filter MAJ-12202A | S18 | Water Systems | 2020-04-01 | 2019-12-16 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.WS.TS122-00000 | Sea Water Coarse Filters | 2019-11-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 120272000000 | 10 | 120 | 1000789893 | ACID,DESCALER,WATERMKR,QD-500-L,5gal | 2020-04-01 | Not Shipped | 2020-01-24 |  |  | U182 | 8201 | Stones Main | STONES | 12027172 | 12 | 1 | Stocked Locally (Reservation) | L |  |  |  | Name 3 |  | 2020-01-24 | USAWJB | 6 | PAI | 0 | Motor Terminations MAJ-12202B Motor | REL ESTC GMPS PRC SETC | APPR MAGN MAKD MAOK WPOK ZPMM | Kit Complete
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 130 | 1001645366 | WASHER,FLAT,SS316,5/8in | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 28 | EA | 28 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 40 | 7000003196 | SS-8-TA-1-8 MALE ADAPTER | 2020-02-24 | Received at Worksite |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-09 | USNSB4 | 1 | EA | 1 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 110 | 7000002596 | Stud Bolts, 5/8" x 4" LG., ASTM A320 Gr. | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 5 | EA | 5 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
61112406 | 508 | 2nd Stg Sep PST upgrade | S22 | Prod Gathering | 2020-04-11 | 2020-06-16 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.PST-66202-178 | 2nd Stg Separator Press Sfty Transmitter | 2019-12-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-04-11 | 120837000000 | 20 | 20 | 1001816210 | GASW,316/316L,GPH,CL150,NPS3 | 2020-04-11 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB B3 | 12083677 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-12-23 | USNSB4 | 2 | EA | 2 | Upgrade PST-66202-178 To Rosemount Trans | REL ESTC GMPS PPRT PRC SETC | APPR EOM MAGN MAOK RUSH WPOK ZPMM | EXEC |  |  | ST1A3C 02/3/20 GG
60985464 | 508 | FW Gen Pump 3 Inlet Spool leak | S18 | Water Systems | 2020-03-17 | 2020-04-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.VE121-01001 | FW Generators and Hot Water Loop System | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-18 | 119373000000 | 10 | 120 | 7000004213 | KE35/15 SASAKURA KE35 P/N 16 COMPOUND GA | 2020-05-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11937331 | 25 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-11-27 | USNSB4 | 1 | EA | 0 | LO/TO PBE-12204A, Bump Test | REL PRT GMCO PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 50 | 7000002629 | Flange, 2", 300#, RFWN, S/80S Bore, ASME | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 101 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 70 | 1000709964 | UNIC,SWAGELOK,SS8106,1/2in | 2019-11-19 | Received at Target Location |  |  | 2020-02-14 | U182 | 8270 | Danos - Amelia | Onsite Danos Has | 11882270 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI66 | Name 15 | Name 58 | 2019-11-06 | USABCE | 2 | EA | 2 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60975188 | 508 | XV-12202A-912 Fails to Open | S18 | Water Systems | 2020-02-06 | 2019-10-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.XV-12202A-912 | Filter Backwash On/Off Control Valve | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-02-06 | 119260000000 | 10 | 10 | 7000003464 | 4-150-BA02B SHIPHAM 4-150-BA02B 4" 150# | 2020-02-06 | Received at Worksite |  | 2019-12-28 | 2020-02-10 | U182 | 8201 | Stones Main | STAGED | 11925969 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 1 | USAWJB | 2019-10-04 | USAWJB | 1 | EA | 1 | LOTO System - Confirm Isolation | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU AMW 12/29/19
60739069 | 508 | COT 5 P IG netherlock | S06 | General | 2020-05-21 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127053 | COT 5 PS IG Vent Line Valve | 2019-05-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-05-21 | 116430000000 | 10 | 30 | 7000000060 | Documentation Packing Handling | 2020-06-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642965 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 1 | EA | 0 | Repair NetherLocks Device | REL ESTC CSER PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60794547 | 508 | Modify 1st Stg Sep Bridles | S22 | Prod Gathering | 2020-03-21 | 2019-12-09 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.PS.MBD-66201 | 1st Stage Separator | 2019-10-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-28 | 117187000000 | 10 | 180 | 7000002662 | 3/4" x 0.065 317L SMLS Uncoated Tubing | 2020-03-21 | Received at Target Location |  | 2020-02-17 |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11718694 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI69 | Name 2 |  | 2019-11-07 | USSOLE | 240 | FT | 240 | Modify 1st Stg Sep Bridles MOC72153 | REL ESTC GMCO GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC
60959171 | 508 | Replace No.2 Ejector Pump Impeller | S18 | Water Systems | 2020-04-01 | 2020-04-06 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PBE-12204B | No. 2 FW Generator Ejector Pump | 2019-12-18 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 4 Complete by 4 Weeks | 2020-04-02 | 119077000000 | 10 | 10 | 7000000036 | SONDEX-MP-80-80-220 SERIAL NO. SMP001408 | 2020-06-30 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11907747 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-18 | USNSB4 | 1 | EA | 0 | Replace Impeller No.2 Ejector Pump | REL ESTC PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2550 | 7000002629 | FULL FACE BLEED RING, 8", 300#, RF, 1.5" | 2019-04-22 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 277 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04081901 | Name 2 | Name 2 | 2019-04-08 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2400 | 7000002591 | Fabreeka #700 Epoxy Adhesive (Gallon) | 2019-04-08 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 262 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011905 | Name 2 | Name 2 | 2019-04-02 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60684131 | 508 | Port side crane access improvement | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-04-03 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 10 | 7000000108 | Web Devices, 30' SRL, Triple Locking Car | 2020-06-13 | Received at Worksite |  | 2019-12-17 |  | U182 | 8201 | Stones Main | STONES | 11581208 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES0612 | USMABH | USKHU3 | 2019-06-12 | USABCE | 10 | EA | 10 | Port side crane access improvement | REL PCNF GMPS PRC SETC | EXEC | EXEC |  |  | PU JOHN GASTIAN 07012019 AJ
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 130 | 7000003852 | Bluetooth Beanie,Stereo Knit Music Hat w | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 13 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 20 | 7000002591 | Tubes of marine Grade silicone sealant 3 | 2019-11-15 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Skids | 11179936 | 475 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSW551A367 | Name 2 | Name 2 | 2019-11-11 | USLFA4 | 40 | EA | 40 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7490 | 7000002596 | Washer, 5/8", SS Bonded Rubber | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1007 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-15 | USSOLE | 200 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6770 | 7000002596 | Stud Bolt, 5/8" x 4", Aluminum Bronze, A | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 888 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 50 | EA | 50 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60909046 | 508 | REPLACE DAMAGED AIR OIL REGULATOR | S08 | Air Systems | 2020-02-20 | 2020-08-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.AS.VE118-30000 | Service Air System | 2020-01-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-20 | 118510000000 | 10 | 20 | 7000000034 | 3/4 NPT LUBRICATOR | 2020-02-20 | Received at Worksite | 2020-01-27 | 2020-02-07 | 2020-02-21 | U182 | 8201 | Stones Main | Issued | 11851043 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 20 | USNSB4 | 2020-01-03 | USNSB4 | 1 | EA | 1 | Replace Air/Oil Regulator | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A1B 02/07/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1540 | 1002316832 | GASW,CL300,316/316L,GPH,6in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 170 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1480 | 1002309186 | SB2N,B8M CL2,8M,UNC,3/4in,5.00in | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 164 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 30 | 1000720064 | UNIC,SWAGELOK,250712106,3/4in | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 781 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 35 | EA | 35 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 190 | 7000003196 | Swagelok 316-S3-WPE | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 797 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 180 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 280 | 1002128203 | NUT,SPRING,COOP-BLI,N224SS6,1/4in,316 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 820 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 200 | EA | 200 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7680 | 7000002629 | Threadolet, 2" x 3/4", 3000#, FS MSS-SP- | 2020-03-02 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 1031 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-02-23 | USSOLE | 1 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60367921 | 508 | CARGO-Dummy Spade Replace COT 5S IG Line | S06 | General | 2020-03-20 | 2018-11-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127046 | COT 5 SB IG Main Manual Valve | 2019-05-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-22 | 112273000000 | 10 | 10 | 7000000102 | WHALE TUFNOL SLIDING SPECTACLE BLIND TO | 2020-04-19 | Received at Worksite |  | 2020-02-03 |  | U182 | 8201 | Stones Main | Warehouse floor | 11227253 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-05-15 | USNSB4 | 4 | EA | 4 | CARGO-Dummy Spade Replace COT 5S IG Line | REL PRT GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | ST1FLR 2/3/20 GG
60756605 | 508 | SUP HMI for AUS - Monitor connections | S21 | Oil Treating | 2020-05-01 | 2020-05-12 | O.US.STO.STO.005.724FP | 508ET | US.WR508A.OT.SS.ZZZ-66318 | Control Panel | 2019-08-12 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-05-01 | 116627000000 | 10 | 10 | 7000000062 | New HMI, Automatic Unloading Control Sys | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11662729 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-08-12 | USNSB4 | 1 | EA | 0 | Replace HMI for Automatic Unloading Syst | REL ESTC CSER PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 170 | 7000000039 | One(1) Det-tronics Laser Battery 3V Lith | 2020-02-28 | Received at Target Location |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20ACR00 | Name 9 | USCRFI | 2020-01-28 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60847991 | 508 | MOC GTG1 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-04000 | Gen #1 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117810000000 | 10 | 70 | 7000005901 | MLTFC4H-LP316 50 PER PACK | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780966 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI76 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 1 | EA | 1 | SAEP LO/TO Isolate GTG #1 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
61023509 | 508 | Grating on green mile needs replacing. | S19 | Marine Systems | 2020-06-01 | 2019-12-25 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.HG | Handrails, Stairways, Grating | 2020-02-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-06-02 | 119822000000 | 10 | 20 | 1001582225 | BAR FL,3/8in,3in | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G87 | 11982221 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02172001 | Name 4 | Name 60 | 2020-02-19 | USSOLE | 20 | FT | 20 | Grating on green mile needs replacing. | REL ESTC PRC SETC | APPR EOM MAGN MANX WPOK ZPMM | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 270 | 7000002603 | 3" Flange Protector 3", 150#, RF | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 27 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
61060939 | 508 | O/SI CAIR3399 CAT2 corrosoin to flange | S08 | Air Systems | 2020-04-01 | 2020-05-19 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.AS.TS118-00000 | Nitrogen Generation & Distribution | 2020-01-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 120244000000 | 20 | 10 | 7000002629 | Reducing Flange(4-1/4 OD) X 1/2 150# T31 | 2020-04-01 | Received at Worksite | 2020-01-21 | 2020-02-03 |  | U182 | 8201 | Stones Main | ST KB D3 | 12024358 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-07 | USMNF8 | 1 | EA | 1 | Replace Corroded Flange | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | ST1A5A 02/3/20 GG
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 30 | 7000000039 | YMD-8529 HOSE ASSEMBLY X45"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60881246 | 508 | Containment plugs on stern | S06 | General | 2020-02-04 | 2020-01-31 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.HB.PC | Process Containment Hardware Barriers | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-04 | 118192000000 | 10 | 10 | 7000003852 | Five Oceans Marine Rubber Drain Plug, Sn | 2020-02-04 | Not Shipped |  |  | 2020-02-11 | U182 | 8201 | Stones Main | PO Cancelled | 11819160 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-08-08 | USAWJB | 8 | EA | 0 | Containment plugs on stern | TECO CNF PRT GMPS PRC SETC | XCNF MAGN WPOK XGI | TECO |  |  | PU PO CANCELLED
60828048 | 508 | Emergency Kits for Lifeboats STONES | S15 | Life Saving | 2020-06-01 |  | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.LS.LB | Lifeboats | 2019-07-04 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 117583000000 | 10 | 30 | 7000002591 | Cyclops REVO 1100 LED Rechargeable Hand- | 2020-06-01 | Received at Target Location |  |  | 2020-01-31 | U182 | 8201 | Stones Main | Issued | 11758304 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Entity 5 |  | 2019-07-04 | USDHIE | 5 | EA | 5 | Stage all kits as directed by Leadership | TECO ESTC CSER GMPS PRC SETC | XCNF WPOK XGI ZPMM | TECO
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 10 | 7000004754 | 1/2" x 0.065 317L SMLS Coated Tubing | 2020-03-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 27 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI86 | Name 2 | Name 2 | 2020-02-07 | USSOLE | 320 | FT | 0 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
60989313 | 508 | Erratic Speed Reading Steam Turbine #3 | S21 | Oil Treating | 2020-02-11 | 2020-04-04 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.OT.SS.CPI-66301C | Steam Turbine Control Panel | 2019-10-24 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-11 | 119417000000 | 20 | 20 | 7000005901 | SST3816 316SS 12" CABLE TIES | 2020-02-11 | Received at Worksite | 2019-11-21 | 2020-01-19 | 2020-02-19 | U182 | 8201 | Stones Main | ST1A5B | 11941691 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | 3.54 | 2019-10-24 | USNSB4 | 2 | EA | 2 | Replace Existing Cable With Shielded Cab | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD WPOK XGI | TECO |  |  | PU AMW ST1A5B
60714280 | 508 | Upgrade AT-77202-342 Dewpoint Analyzer | S39 | Gas Treating | 2020-02-07 | 2020-04-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.AT-77202-342 | TEG Contactor Dewpoint Analyser | 2020-02-19 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-07 | 116148000000 | 20 | 20 | 7000003512 | 317L 1/4"X .035 SMLS 1/4" x .035 SMLS TU | 2019-12-08 | Received at Worksite |  | 2020-02-28 |  | U182 | 8201 | Stones Main | Issued | 11614811 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 7 | USNSB4 | 2019-06-20 | USNSB4 | 80 | FT | 80 | Upgrade AT-77202-342 | REL PCNF ESTC GMPS PPRT PRC SETC | SCHD EOM MAGN RUSH WPOK | EXEC
60184795 | 508 | Repair HCV-77202-842 | S39 | Gas Treating | 2021-03-01 | 2019-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.HCV-77202-842 | TEG Contactor Choke Valve | 2018-08-22 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2021-03-01 | 110226000000 | 10 | 20 | 7000000104 | WEIR 50x25x50 mm (2"x1"x2") Class 600 BV | 2021-03-01 | Received at Worksite |  | 2019-05-09 |  | U182 | 8201 | Stones Main | ST KB D1 | 11022591 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-08-07 | USNSB4 | 1 | EA | 1 | Repair HCV-77202-842 | REL PRT CSER GMCO GMPS PRC SETC | EXEC MAGN MAOK WPOK | EXEC |  |  | PU Aaron W. 5/18/19
60747152 | 508 | COT 2 STBD IG Netherlock | S06 | General | 2020-04-01 | 2019-11-04 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.IG.VABF-127055 | COT 2 SB IG Main Manual Valve | 2019-05-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-01 | 116520000000 | 10 | 20 | 7000000060 | Single Standard Key | 2020-05-01 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11651964 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-03 | USNSB4 | 2 | EA | 0 | Repair NetherLocks Device | REL ESTC PPRT PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60014436 | 508 | Non OEM Valve PUPD-10903-MIS003 | S19 | Marine Systems | 2020-02-25 | 2019-02-20 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PR.PUPD-10903-MIS | Cylinder No. 1 HP Fuel Oil Pump | 2019-01-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 107753000000 | 10 | 10 | 7000000103 | Ball Valve, 7223G8YDXV-1/2" SAE TUBE END | 2020-02-25 | Received at Worksite |  | 2019-04-23 |  | U182 | 8201 | Stones Main | delv wrong-see po atachmt | 10775349 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-01-09 | USNSB4 | 2 | EA | 2 | Replace Non-OEM Valve PUPD-10903-MIS003 | REL CNF PRT GMPS PRC SETC | SCHD EOM MAGN MAOK WPOK | EXEC |  |  | PU AARON 04/20/2019
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6840 | 7000000126 | Nitrogen Regulators | 2020-02-05 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | STONES | 11179936 | 926 | 4 | Non-Stock (Purchase Requisition) | N |  |  | 203202001 | Name 25 | Name 25 | 2020-02-03 | USLFA4 | 2 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6820 | 7000002603 | Flange Protectors 3", SO, 150#, FF | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 893 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 16 | EA | 16 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1430 | 7000002629 | BLIND FLANGE, 3" 300, RF, ASME B16.5, AS | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 159 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5290 | 7000002596 | STUD BOLT, 3/4" X 4" ASTM A193 GRADE B8M | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 590 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 4 | EA | 4 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5190 | 7000002603 | GASKET, 2" 300LB, 1/8" THICK, RF SPIRAL | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 580 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 9 | EA | 9 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6560 | 7000002629 | Tee, 2" x 2", SW, 400 PSIG WOG, ASME B16 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 867 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 12 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4730 | 1001723501 | WASHER,FLAT,F436,SERMAGAURD,1/2in | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 525 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 118 | EA | 118 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6690 | 7000002629 | FNPT Boss, 3" x 1/2", 3000#, ASME B16.11 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 880 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3780 | 1001663813 | SHT PLT SLD MET,4x4ft,1in,A572-50 | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 408 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161904 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
61026238 | 508 | MGCB Pipe Support Bracket Installation | S04 | Gas Compress | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DANOS | US.WR508A.GC.GS.VADB-771017 | Inlet Gas Valve | 2019-11-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-04-01 | 119851000000 | 10 | 30 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2020-03-27 | Received at Target Location |  | 2019-11-12 |  | U182 | 8201 | Stones Main | SHF9-F65 | 11985064 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11111902 | Name 4 |  | 2019-11-12 | USLFA4 | 10 | EA | 10 | Install 4x A325 3/4 x 3-3/4 Bolts | REL PRT GMPS PRC SETC | APPR MAGN MAOK WP ZPMM | EXEC
60942275 | 508 | Replace Chain Bucket - Hoist ZZZ-874139 | S40 | Cargo Handling | 2020-04-18 | 2020-06-30 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.PF874-00000 | Trollies and Monorails | 2019-11-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-04-18 | 118880000000 | 10 | 10 | 7000000040 | Stainless steel Chain Bucket | 2020-04-18 | Received at Worksite | 2020-02-20 |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 11887983 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-04 | USCMFR | 1 | EA | 1 | Install S.S Chain Bucket ZZZ-874139 | REL GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPMM | Kit Complete
60989317 | 508 | Port crane Emer load lowering hoses bad | S40 | Cargo Handling | 2020-02-18 | 2019-12-05 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2019-12-10 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 119417000000 | 10 | 30 | 7000000098 | 3/8 MJIC PLUGS PLASTIC | 2020-02-18 | Received at Worksite | 2019-12-26 | 2020-01-20 | 2020-02-18 | U182 | 8201 | Stones Main | ST KB C1 | 11941695 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-28 | USCMFR | 4 | EA | 4 | Port Crane Emer Load lowering hoses bad | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK RUSH WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 80 | 7000003196 | PTFE Tape Pipe Thread Sealant (MS-STR-4) | 2019-11-19 | Received at Target Location |  |  | 2020-02-14 | U182 | 8270 | Danos - Amelia | Onsite Danos Has | 11882270 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI66 | Name 15 | Name 58 | 2019-11-06 | USABCE | 1 | EA | 1 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60970408 | 508 | CRN Boom Tip Platform Grating Deficiency | S06 | General | 2020-02-20 | 2020-03-26 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GN.MI.HG | Handrails & Grating | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-21 | 119205000000 | 10 | 30 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-10-04 | Received at Target Location |  |  | 2020-02-13 | U182 | 8256 | Danos - Larose | SHF9-F21 | 11920544 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09301902 | Name 4 | USMCS1 | 2019-10-01 | USSOLE | 2 | EA | 2 | CRN Boom Tip Platform Grating Deficiency | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WP XGI | TECO
61118336 | 508 | 2020 Lube Oils / Grease - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 40 | 7000003946 | 55 gal. drums of (Shell Morlina S3 BA 15 | 2020-02-22 | Received at Target Location |  | 2020-01-08 |  | U182 | 8201 | Stones Main | CPORT | 12090693 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0010 | Name 17 | JP832018 | 2020-02-03 | USLFA4 | 2 | DR | 2 | 2020 Lube Oils / Grease - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 120 | 1000710324 | FTG_PIPE,PLUG,3/4",316 SS | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 57 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 3 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 110 | 7000003323 | Part# 200-DC-SS | 2019-09-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 34 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN082 | Name 2 | Name 2 | 2019-08-19 | USGBI5 | 2 | EA | 2 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 10 | 1001271537 | ANGL MTL,EQ,CS,20ft,L3x3x1/4in | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 80 | FT | 80 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118361 | 508 | 2020 IT / Communications / Bandwidth | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 20 | 7000003852 | Fiber Optic Adaptor, SC Male to LC Femal | 2021-03-01 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090698 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO20O0112 | Name 12 | USRRIG | 2020-01-13 | USLFA4 | 4 | EA | 4 | 2020 IT / Communications / Bandwidth | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | DLVD 2/2/2020 GG
61076060 | 508 | Install Drink & Ice Cream Machine | S09 | Bldg & Qtrs | 2020-03-17 |  | O.US.STO.STO.005.71300 | 508MECH | US.WR508A.GU.BQ.ROOM-213 | Galley | 2019-12-01 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-03-17 | 120415000000 | 10 | 20 | 7000000129 | SODA ICE & BEVERAGE DISPENSER | 2019-12-17 | Received at Worksite |  | 2020-02-21 |  | U182 | 8201 | Stones Main | Stones | 12041473 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-02 | USAWJB | 1 | EA | 1 | Install Drink & Ice Cream Machine | REL PRT GMPS PRC SETC | SCHD WPOK | EXEC |  |  | PU ARCHIE MOD22 02/15/2020
60985331 | 508 | O/SI Steam Valve VAGL-115635 corrosion | S17 | Steam/Hot H2O | 2020-03-24 | 2020-04-05 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.VAGL-115635 | Steam to Coil 1 Isolation Valve | 2020-02-05 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-24 | 119372000000 | 10 | 10 | 1001816213 | GASW,CL150,316,GPH,NPS1 | 2020-03-24 | Received at Worksite | 2020-02-18 |  |  | U182 | 8201 | Stones Main | MMR773 2-27-2020 | 11937177 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-03 | USNSB4 | 2 | EA | 2 | Replace steam valve VAGL-115635 | REL ESTC GMPS PRC SETC | APPR EOM MAKD MAOK WPOK ZPMM | Kit Complete
61118360 | 508 | 2020 Office Supplies | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 170 | 7000003852 | Space Heater Fan with Timer and Remote,. | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090697 | 17 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 32 |  | 2020-02-21 | USAWJB | 1 | EA | 1 | 2020 Office Supplies | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60440621 | 508 | Replace Laydown Timber - MODs 15, 17, 19 | S40 | Cargo Handling | 2020-03-10 | 2020-06-30 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.CH.LS | Loading Stations | 2019-08-06 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-11 | 113072000000 | 10 | 100 | 7000002583 | 4IN X 8IN X 8FT MARINE GRADE .6 PRESSURE | 2020-03-10 | Received at Worksite |  | 2019-12-28 |  | U182 | 8201 | Stones Main | Starboard laydown | 11307214 | 11 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-11-04 | USAWJB | 32 | EA | 32 | Replace Laydown Timbers - MOD 15 | REL ESTC GMPS PPRT PRC SETC | EXEC MAGN MAOK RUSH WPOK | EXEC
61020440 | 508 | MOC Subsea CI/SI Air Eliminator | S10 | Chem Injection | 2020-04-01 | 2019-12-24 | O.US.STO.STO.005.724FP | 508DINST | US.WR508A.GU.CI.MS128 | Turret Chemical Injection System | 2019-11-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-02 | 119786000000 | 10 | 120 | 1000709964 | UNIC,SWAGELOK,SS8106,1/2in | 2020-04-01 | Received at Target Location |  | 2020-02-18 | 2020-02-19 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11978555 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI75 | Name 2 | Name 58 | 2019-12-05 | USSOLE | 6 | EA | 6 | Install CI/SI Air Eliminators | TECO CNF ESTC GMCO GMPS PRC SETC | XCNF MAGN MAOK RUSH WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5150 | 7000002629 | PLUG, 1/2" SOLID HEX THRD, ASTM A182 GRA | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 576 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 21 | EA | 21 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 920 | 7000004754 | 3/8" x 0.049 317L SMLS SS Coated Tubing | 2020-03-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 931 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI84 | Name 2 | Name 2 | 2020-02-04 | USSOLE | 300 | FT | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4260 | 1002360784 | SB2N,B7,2H,UNC,5/8in,3.5in,DOXSTEEL | 2019-11-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 478 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11121901 | Name 4 | Name 4 | 2019-11-12 | USLFA4 | 5 | EA | 5 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60562362 | 508 | O/SI Passing Valve 3rd stage PST-330A MG | S04 | Gas Compress | 2020-03-10 | 2019-03-08 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GC.GS.VAMO-771031 | Pressure Transmitter Isolation Valve | 2019-02-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-10 | 114424000000 | 30 | 70 | 7000002591 | ELRING CURIL T LIQUID GASKET NON-HARDENI | 2020-03-10 | Received at Worksite |  | 2020-02-07 |  | U182 | 8201 | Stones Main | ST1A4C | 11442408 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2020-01-03 | USMNF8 | 2 | EA | 2 | Replace Defective Valve 3rd stage PST-33 | REL PRT GMPS PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC |  |  | ST1A3C 02/3/20 GG
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 20 | 7000003197 | 2-Pole, 20A Tumbler Switch EDSC175-F2 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 1 | EA | 1 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1170 | 7000003343 | W6 X 15, BEAM, ASTM A992/A992M | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 133 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061802 | Name 2 | Name 2 | 2018-12-07 | USSOLE | 60 | FT | 60 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7560 | 1000710324 | FTG_PIPE,PLUG,3/4",316 SS | 2020-02-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F32 | 11179936 | 1018 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-16 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 80 | 1001842231 | FLBL,A105,RF,CL150,NPS3 | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 140 | 7000002596 | 0006 2421-XXXX 00000 1/4-20 X 1/2" SS | 2020-02-24 | Received at Target Location |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-15 | USNSB4 | 25 | EA | 25 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
60739085 | 508 | 663UD-XV-299 Actuator & VPI test fail | S21 | Oil Treating | 2020-03-26 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-663UD-299 | Crude Oil O/O to COT 2 PS Valve | 2019-09-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-29 | 116430000000 | 111 | 20 | 7000005901 | P.0244110028 AVC 02 CL1 A1 VPI MANIFOLD | 2020-06-14 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11642981 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-09-17 | USNSB4 | 1 | EA | 0 | Repair Hydraulic Actuator Cargo Valve XV | REL GMPS PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
60154871 | 508 | PV Passing cargo valves - COT 3S -STRIP | S21 | Oil Treating | 2022-01-01 | 2018-07-18 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6633S-269 | Crude Oil to/from COT 3 SB Valve | 2018-06-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2022-01-01 | 109843000000 | 10 | 10 | 7000000105 | REPAIR KIT 18" NAKAKITA VALVE (10K-450A, | 2022-01-01 | Received at Worksite |  | 2018-10-17 |  | U182 | 8201 | Stones Main | ST KB D5 | 10984273 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-06-25 | USNSB4 | 1 | EA | 1 | Replace Soft Goods COT-3S XV-6633S-269 - | REL ESTC CSER GMPS PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU Aaron 10/03/2018
60888917 | 508 | Faulty Temp Probe on Swivel | S19 | Marine Systems | 2020-04-11 | 2020-02-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.MA.PS.ZZZ-89650 | Electrical Power & Signal Swivel | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-11 | 118279000000 | 20 | 30 | 7000005901 | AC101 FLAT SEAL FOR FLANGE | 2020-06-10 | Received at Worksite | 2019-12-09 | 2019-12-21 |  | U182 | 8201 | Stones Main | ST KB B4 | 11827852 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-23 | USNSB4 | 1 | EA | 1 | Replace Temperature Safety Transmitter O | REL ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MAKD RUSH WPOK | EXEC |  |  | PU WPT ST KB B4
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 20 | 7000002662 | Pipe, 2", S/80S, ASME B36.19M, ASTM A790 | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 98 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 20 | FT | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 890 | 7000002591 | PS Doors Split Gate Model LSGDBL-12-PCY/ | 2020-02-02 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-E05 | 11581207 | 89 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08261903 | Entity 3 | Name 59 | 2019-08-27 | USSOLE | 1 | EA | 1 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | ENEQ | 90 | 7000003323 | Part# 200-AL-SS | 2019-09-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Stones | 11545759 | 32 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STN082 | Name 2 | Name 2 | 2019-08-19 | USGBI5 | 4 | EA | 4 | Engineered Equipment | ACAS MANC PRC PREL | INIT | Approved
60847991 | 508 | MOC GTG1 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-04000 | Gen #1 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117810000000 | 10 | 40 | 7000005901 | M20 Serrated Washer | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780966 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI76 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 4 | EA | 4 | SAEP LO/TO Isolate GTG #1 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 30 | 7000002591 | 3/16 X 2 ALUMINUM FLAT BAR X 10FT | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 6 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 160 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 16 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 2 | EA | 2 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 1050 | 7000003852 | Olympia Tools 64-410 48-inch Gorilla Bar | 2021-03-31 | Not Shipped |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 105 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST20CG0146 | MarineForman | USCRFI | 2020-02-20 | USCDP7 | 1 | EA | 0 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 30 | 7000002629 | 1 1/2" Flange Blind 300# RF ASME B16.5, | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77111B | 11340898 | 48 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 1 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 280 | 7000002596 | 3/4" x 6" A193 L7 B&N, Dox stud | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 73 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 10 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60847988 | 508 | MOC GTG4 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-34000 | Gen #4 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-19 | 117809000000 | 10 | 80 | 7000005901 | Brady Part No. M21-187-C-342 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11780943 | 18 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI79 | Name 2 | Name 58 | 2020-01-16 | USSOLE | 1 | EA | 1 | SAEP LO/TO Isolate GTG #4 MOC-71695 | REL ESTC GMPS PRC SETC | APPR EOM MAGN WP ZPMM | Approved
60035839 | 508 | Emergency switchboard water ingress | S03 | Elect. Systems | 2020-03-03 | 2018-05-05 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.ES.PD.SGR-44201 | Emergency Switchboard | 2020-01-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-04 | 107990000000 | 10 | 70 | 7000002596 | Studs, 1/2" x 3" Lg., ASTM A193 w/(2) AS | 2020-02-05 | Received at Target Location |  | 2020-02-18 |  | U182 | 8256 | Danos - Larose | SHF9-F93 | 10799002 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221903 | Name 4 |  | 2019-11-22 | USLFA4 | 9 | EA | 9 | Sponsor / Supervise Actvities | REL GMPS PRC SETC | SCHD EOM MAGN WPOK | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 250 | 7000002591 | Shark 12248 Wrap around pipe template | 2020-02-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 25 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0117 | Name 5 | USCRFI | 2020-02-19 | USLFA4 | 3 | EA | 3 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 260 | 1001664288 | BLT HEX,A325,UNC,2in,5/8in,SERMAGARD | 2020-04-23 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-F90 | 11581210 | 26 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11201901 | Name 4 | Name 60 | 2019-11-20 | USABCE | 3 | EA | 3 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 120 | 7000002591 | ROD, BRASS 360 ¾ DIA x 3 Ft L,, | 2020-02-10 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO115EREN | Name 33 | USCRFI | 2020-02-03 | USLFA4 | 3 | EA | 3 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU ENG RM 2/24/2020 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 860 | 1001816275 | GASW,CL300,316,GPH,NPS12 | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 102 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 20 | EA | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4790 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2019-11-27 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 531 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11191903 | Name 4 | Name 4 | 2019-11-19 | USABCE | 82 | EA | 82 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 10 | 7000000066 | Yokogawa Differential Pressure Transmitt | 2020-02-05 | Received at Worksite |  |  | 2020-02-17 | U182 | 8201 | Stones Main | ST KB A3 | 11882563 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-24 | USNSB4 | 1 | EA | 1 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO |  |  | PU 01/19/2020 AMW
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 180 | 7000002646 | 6,000 psig minimum CWP, 1/2" MNPT x 1/2" FNP | 2019-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | Solids Handling | 11179936 | 644 | 4 | Non-Stock (Purchase Requisition) | N |  |  | SWR551A371 | Name 2 | Name 2 | 2019-12-13 | USSOLE | 10 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 880 | 7000003197 | SS DROP OUT 12INW | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 919 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 5 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 90 | 7000002591 | Stud, M22 x 4", ASTM A193 Gr. B7 w/ASTM | 2020-03-22 | Received at Target Location |  | 2019-12-03 |  | U182 | 8256 | Danos - Larose | JOB NO: SHF9-E95 | 11739629 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08291901 | USMMSW | Name 59 | 2019-08-30 | USABCE | 22 | EA | 22 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | ENEQ | 430 | 1002196197 | POWER SUPPLY,ALLENB,1756-PB72/C.24Vdc | 2019-11-19 | Received at Target Location |  |  |  | U182 | 8290 | ENG AND CONST | Job No: 2309 | 11179936 | 429 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STN101 | Entity 4 | Entity 4 | 2019-10-31 | USSOLE | 2 | EA | 0 | Engineered Equipment | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7010 | 1001573336 | PAD,DELRIN,BLACK,3x1/8in | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 949 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052001 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 13 | EA | 13 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5070 | 7000002629 | BLEED RING, 1" , FULL FACE 300LB w/ (2) | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 568 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60627382 | 508 | Drain Tubing-Heating Medium Filter Pot | S06 | General | 2020-02-24 | 2020-02-07 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.HC.VABL-125100 | Filter Drain Valve | 2019-07-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-25 | 115169000000 | 10 | 50 | 7000003196 | SS-63TS8 BALL VALVE | 2020-02-24 | Received at Worksite |  | 2019-09-16 | 2020-03-02 | U182 | 8201 | Stones Main | ST KB B6 | 11516913 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-07-09 | USNSB4 | 2 | EA | 2 | Danos Stage and Erect Scaffolding | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK WPOK XGI | TECO |  |  | PU 10/30/2019 AMW
60737097 | 508 | VPI test fail COT 5 Port | S21 | Oil Treating | 2020-02-10 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-663UD-293 | Crude Oil To COT 5 PS O/O Valve | 2020-02-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-10 | 116406000000 | 20 | 20 | 7000005901 | B.0140969001 SEAL KIT FOR INDICATOR, VC | 2020-04-30 | Received at Worksite | 2020-02-11 |  | 2020-02-11 | U182 | 8201 | Stones Main | ST KB B7F | 11640602 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-09-13 | USNSB4 | 1 | EA | 1 | Repair VPI XV-663UD-293 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAKD MAOK WPOK XGI | TECO |  |  | PU Aaron ST1A1B 01/19/2020 C
60172772 | 508 | O/SI Missing Steam Trap | S17 | Steam/Hot H2O | 2020-03-10 | 2019-05-29 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GU.SW.95T | Boiler Water Drum Condensate Trap | 2019-10-09 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 110086000000 | 10 | 80 | 7000002591 | 2" x 27' U-Hook Ratchet Strap | 2020-01-31 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | Issued | 11008581 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10081901 | Place 1 | Name 60 | 2019-10-14 | USSOLE | 2 | EA | 2 | MOC missing steam trap | REL PCNF ESTC GMPS PRC SETC | APPR EOM MAGN WP | Approved
60874368 | 508 | Refurbish 2 each MMR 1002409049 | S21 | Chem Injection | 2020-04-01 |  |  | EXTCO |  |  | 2019-08-04 | WO | U100 | 72XR | US01 | P16 | [5 empty] | 2 Medium | 2020-04-01 | 118107000000 | 10 | 0 | 1002409049 | MECH SEAL,AZT00798SSV01-A+,AESSEAL | 2020-04-01 | Not Shipped |  |  | 2020-02-19 | U182 | 8201 | Stones Main |  | 11810720 | 1 | 1 | Stocked Locally (Reservation) | L | [5 empty] | 2019-08-04 | USAWJB | 2 | EA | 0 | Refurbish 2 each MMR 1002409049 | TECO PCNF ESTC GMPS PRC SETC | XCNF XGI | TECO |  |  | PU and add to stock 1002409049
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 100 | 1002316823 | GASW,CL150,316/316L,GPH,2in | 2019-08-21 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | MD-01 Mid-Level | 10754707 | 10 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011904 | Entity 2 | Name 60 | 2019-04-01 | USSOLE | 4 | EA | 4 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 1020 | 7000002591 | 11/16''#17122, Rotaloc Cutter. M508140-1 | 2020-04-17 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | VFD Storage | 11581207 | 102 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SSWR551A36 | Name 2 | Name 59 | 2019-10-31 | USABCE | 6 | EA | 6 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | SOS1 | 230 | 7000002596 | Stud, 1 1/8" x 9 1/4" LG., ASTM A193 Gr. | 2020-03-24 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H05 | 11340898 | 119 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 4 |  | 2020-03-03 | USSOLE | 14 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PRC PREL | INIT | Approved
60704787 | 508 | Port Crane Hydraulic Oil Cooler corroded | S40 | Cargo Handling | 2020-04-20 | 2020-12-31 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.DMD-3983 | PS Crane Hydraulic Oil Reservoir HPU | 2019-06-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-21 | 116042000000 | 10 | 80 | 7000000039 | YMD-8524 HOSE ASSEMBLY X27"LG | 2020-04-20 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | stones | 11604173 | 8 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2019-06-26 | USJDJW | 1 | EA | 0 | ASSIST Replace Port Crane Hyd Oil Cooler | REL PRC SETC | APPR EOM MAGN RUSH WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 610 | 7000003852 | ABN Dead Blow Hammer 3-Piece Set – 1, 2, | 2020-03-06 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 61 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0011 | Name 29 | USRRIG | 2020-02-18 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | SOS1 | 40 | 7000002603 | Gasket, 1/8” Neoprene, Cut to Match 8” A | 2019-05-31 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-E35 | 11545759 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05291902 | Name 2 | Name 2 | 2019-05-29 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS MANC PRC PREL | INIT | Approved
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 200 | 7000002629 | Flange, 1 1/2", 150#, S/80, RFWN, ASME B | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 20 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
29513209 | 508 | O/SI LCV-66202-866 Passing | S22 | Prod Gathering | 2020-02-16 | 2018-08-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.LCV-66202-866 | Separator Prod Water Level Control Valve | 2019-03-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-18 | 107547000000 | 10 | 290 | 7000002603 | 1 1/2" Flange Protector 1 1/2", 150#, RF | 2020-02-16 | Received at Target Location |  | 2020-02-20 | 2020-02-21 | U182 | 8270 | Danos - Amelia | SHF9-D88 | 10754707 | 29 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01222001 | Name 2 | Name 60 | 2020-01-23 | USSOLE | 1 | EA | 1 | Replace LCV-866 & Spool Piece | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WPOK XGI | TECO
61219231 | 508 | GT #1 Put poly/chain system on fan | S03 | Elect. Systems | 2020-07-20 | 2020-08-22 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.HZZ-11113 | Generator #1 Lube Oil Cooler | 2020-02-26 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-07-20 | 122068000000 | 10 | 20 | 7000003763 | 8MX-31S-12 1210 GT2SPKT | 2020-07-20 | Received at Target Location | 2020-03-03 |  |  | U182 | 8201 | Stones Main | STONES | 12206815 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-02-26 | USAWJB | 1 | EA | 1 | GT #1 Put poly/chain system on fan | REL ESTC GMPS PRC SETC | APPR MAGN MAKD WPOK ZPMM | Kit Complete
61057585 | 508 | Filter Brackets collapsed in AHU B | S14 | HVAC | 2020-04-13 | 2020-05-17 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.ACCU-B-108412 | ACCU B Air Handling Unit | 2020-02-21 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-04-15 | 120208000000 | 10 | 20 | 7000002591 | 10 FT LENGTH 1-1/2X2 ALUMINUM ANLGE | 2020-04-13 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12020785 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-21 | USAWJB | 2 | EA | 0 | Rebuild/Repair Filter Brackets in AHU | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 220 | 7000002591 | Item # 6PFK8 (hand siphon pump) | 2020-02-21 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 22 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0008 | Name 17 | USHBE9 | 2020-01-30 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A6C 02/18/2020 CMR
61074267 | 508 | O/SI SDV-66201-864 Needs Replacement | S22 | Prod Gathering | 2020-03-10 | 2020-01-23 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.PS.SDV-66201-864 | Separator Crude Oil Outlet Shutdown Vlv | 2020-01-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-11 | 120397000000 | 10 | 30 | 7000002603 | 8 FLEX CGI 150# SP WND GSKT GRF FLR | 2020-03-10 | Received at Worksite | 2020-01-02 | 2020-02-08 |  | U182 | 8201 | Stones Main | ST1A4B | 12039685 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-10 | USMNF8 | 2 | EA | 2 | LOTO and Deinventory 1 stage Separator | REL PRT GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC |  |  | PU AMW ST1A4B
61165412 | 508 | Install Needle Valve on PG-33110-732 | S13 | Fire Protect | 2020-03-07 | 2020-03-19 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33110-732 | Seawater Booster Pump Inlet Press Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-07 | 121447000000 | 10 | 10 | 1000719976 | COIMC,SWAGELOK,SS60016,3/8x3/8NPT | 2020-03-07 | Received at Worksite | 2020-02-14 | 2020-02-28 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144697 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 2 | EA | 2 | Install Needle Valve on PG-33110-732 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 120 | 7000003196 | MS-MHSU-U-E-FKIT-M-B | 2020-12-31 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 9 | USCRFI | 2020-01-27 | USAWJB | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU S SAMHA 2/24/2020 GG
61165403 | 508 | Install Needle Valve on PG-33110-733 | S13 | Fire Protect | 2020-04-01 | 2020-03-17 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PG-33110-733 | Seawater Booster Pump Outlet Press Gauge | 2020-02-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-04-01 | 121447000000 | 10 | 10 | 1000719976 | COIMC,SWAGELOK,SS60016,3/8x3/8NPT | 2020-04-01 | Received at Worksite | 2020-02-14 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST KB B7D | 12144687 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USAMH7 | 2020-02-04 | USRAR6 | 2 | EA | 2 | Install Needle Valve on PG-33110-733 | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD MAOK WPOK | EXEC
61102257 | 508 | P.Crane radiator fan shroud corroded | S40 | Cargo Handling | 2020-05-10 | 2020-06-10 | O.US.STO.STO.005.724FP | 508L&H | US.WR508A.GU.CH.ZZZ-87401 | Port Side Pedestal Crane | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-10 | 120716000000 | 10 | 100 | 7000006081 | Paint all components per shell spec | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12071582 | 10 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-07 | USMNF8 | 1 | EA | 0 | P.Crane radiator fan shroud corroded | REL ESTC PRC SETC | APPR MAGN RUSH WP ZPMM | Approved
61118339 | 508 | 2020 GEN MAT - Rope, Soap, & Dope | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 90 | 7000002591 | Grainger channel lock pliers #5LJ49 | 2020-01-25 | Received at Worksite |  | 2020-01-08 |  | U182 | 8201 | Stones Main | STONES | 12090696 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0005 | Name 8 | USCRFI | 2020-01-13 | USLFA4 | 2 | EA | 2 | 2020 GEN MAT - Rope, Soap, & Dope | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU 2/25/2020 GG
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7440 | 1002125060 | WASHER,FLAT,F436,13/16in,3/4in,0.122in | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1002 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 160 | EA | 160 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1040 | 1002360864 | SB2N,B7,2H,UNC,7/8in,5in,DOXSTEEL | 2019-12-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 120 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12061801 | Name 2 | Name 2 | 2018-12-06 | USSOLE | 26 | EA | 26 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5430 | 7000002603 | GASKET, 1" 300LB, RF (Hydro Only) | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 604 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 18 | EA | 18 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60271479 | 508 | Annual station #45 valve leaking | S13 | Fire Protect | 2020-02-18 | 2019-02-02 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.FP.PF331-10000 | FPSO Foam Systems | 2019-03-04 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-02-18 | 111200000000 | 20 | 10 | 7000004211 | D001220E Bib NoseHydrant Reducing valve | 2020-02-18 | Received at Worksite |  | 2019-07-25 |  | U182 | 8201 | Stones Main | issued to 1 Tom honeycutt | 11119960 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-02-26 | USNSB4 | 10 | EA | 10 | Replace Annual Station #45 Valve PF331-1 | REL PRT GMCO GMPS PRC SETC | APPR MAGN MAOK WPOK ZPMM | EXEC |  |  | PU Tommy H/ M. Payton 07/31/2019
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6170 | 1001119606 | SHEET,GASKET, CL150,6in,SF 3300,FLEXITAL | 2020-01-03 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 715 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST12181901 | Name 4 | Name 4 | 2019-12-19 | USSOLE | 5 | EA | 0 | Shop Order Sheets - Mech Mat. for Fab. | REL SETC | APPR MAGN MANX | Deleted
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6940 | 7000003344 | Plate, 1/4" x 24" x 24", ASTM A572 Gr. 5 | 2020-02-07 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-C56 | 11179936 | 942 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02052002 | Name 4 | Name 4 | 2020-02-07 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS1 | 240 | 1001645390 | NUT,A563-DH,HEXAGONAL,UNC,3/4,SERMAGARD | 2019-12-20 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F34 | 11179936 | 650 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12121902 | Name 4 | Name 4 | 2019-12-13 | USSOLE | 28 | EA | 28 | Field Order Sheets -Mech. Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7140 | 1001690904 | CHNL,1.920in,0.200in,20ft | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 972 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 850 | 7000003197 | TB ABWNSP EXPANSION PAD | 2020-02-11 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 916 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI83 | Name 2 | Name 2 | 2020-02-03 | USSOLE | 50 | EA | 0 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1340 | 7000002629 | ELBOLET, 12" X 3", SCH. STD X SCH 40, BW | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 150 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 2 | EA | 2 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60937468 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-05 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202B-923 | Filter Pressure Differential Transmitter | 2020-02-07 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-05 | 118826000000 | 40 | 120 | 1000709357 | PLUG,PIPE,THREADED,1/2in,SS-8-P,SWAGELOK | 2019-11-20 | Received at Target Location |  |  | 2020-02-17 | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11882563 | 12 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI68 | Name 2 | USNSB4 | 2019-11-06 | USSOLE | 2 | EA | 2 | Remove & Install PDT-12202B-923 | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK MOC WPOK XGI | TECO
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 260 | 7000003196 | Swagelok SS-TBP6 | 2020-02-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 804 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI81 | Name 2 | Name 2 | 2020-01-28 | USSOLE | 200 | EA | 200 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
60881904 | 508 | Stones Mechanic Connex Power Addition | S03 | Elect. Systems | 2020-06-02 |  | O.US.STO.STO.005.71300 | 508CI&E | US.WR508A.ES.LI.LFN | Normal Power Light Fixtures/Receptacles | 2019-10-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 2 Medium | 2020-06-09 | 118199000000 | 10 | 50 | 7000003197 | RM 30 EX EXRM00100301000 | 2020-03-19 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11819908 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI56 | Name 2 | USMCS1 | 2019-09-23 | USSOLE | 4 | EA | 4 | Stones Mechanic Connex Power Addition | REL ESTC GMPS PRC SETC | APPR EOM WP ZPMM | Approved
60592977 | 508 | MeOH A Pump passing valve VADB-128103 | S10 | Chem Injection | 2020-03-10 | 2020-01-28 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.CI.VADB-128103 | A Pump Discharge Isolation Valve | 2019-07-03 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-10 | 114773000000 | 10 | 10 | 1002401747 | VALVE,CHECK,BIFOLD,MPCV-20-16-1 | 2020-03-10 | Received at Worksite |  | 2019-09-22 |  | U182 | 8201 | Stones Main | ST KB B7A | 11477341 | 1 | 19 | Modified SP1 - w/o STR & STO / item ctg | L | X |  |  | Name 3 |  | 2019-04-13 | USMNF8 | 2 | EA | 2 | LO/TO Perform Isolations To Replace Valv | REL ESTC GMPS PPRT PRC SETC | APPR EOM MANX WPOK ZPMM | EXEC |  |  | PU WPT
61023509 | 508 | Grating on green mile needs replacing. | S19 | Marine Systems | 2020-06-01 | 2019-12-25 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.HG | Handrails, Stairways, Grating | 2020-02-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-06-02 | 119822000000 | 10 | 40 | 7000003343 | DIAMOND PLATE TREAD NOSING FOR 1 1/2" Gr | 2020-02-25 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G87 | 11982221 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST02172001 | Name 4 | Name 60 | 2020-02-19 | USSOLE | 40 | FT | 40 | Grating on green mile needs replacing. | REL ESTC PRC SETC | APPR EOM MAGN MANX WPOK ZPMM | Approved
60739045 | 508 | ESS GEN 1 level switch fuel leakage fail | S03 | Elect. Systems | 2020-04-28 | 2019-11-03 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.ES.PG.ZZZ-11101A | Essential Generator No. 1 Engine | 2019-10-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-28 | 116427000000 | 10 | 10 | 7000005901 | DK3319011-9 FUEL OIL LEAGAGE ALARM | 2021-01-13 | Received at Worksite | 2020-02-06 | 2020-02-20 |  | U182 | 8201 | Stones Main | ST KB B3 | 11642661 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-10-11 | USNSB4 | 1 | EA | 1 | Replace GEN#1 Fuel Level Switch | REL ESTC GMPS PRC SETC | EXEC EOM MAGN MAKD MAOK WPOK | EXEC |  |  | PU 02/19/20 AMW
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 60 | 7000003768 | 2”x 4’ CEE2-92, 2 ply E & E nylon | 2020-01-25 | Received at Worksite |  | 2019-12-23 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0002 | Name 17 | USJRF5 | 2020-01-08 | USLFA4 | 2 | EA | 2 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | PU ST1A4B 01/22/2020 CMR
61118372 | 508 | 2020 Chemical Order - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 80 | 7000003458 | HSCV19021A.32B | 2020-02-26 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | CPORT | 12090729 | 9 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO200013A | Name 3 | USAAN5 | 2020-02-12 | USLFA4 | 500 | GLL | 500 | 2020 Chemical Order - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 50 | 7000003197 | HWKE DIRECT ITEM HAWKE M20 EARTH TAG Pn: | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11780965 | 5 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | Name 58 | 2019-10-29 | USNSB4 | 4 | EA | 0 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC PRC SETC | APPR EOM MAGN WP ZPMM | Deleted
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 60 | 7000002591 | 600 ½” Manilla Rope | 2020-02-04 | Received at Worksite |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | DIISTO1927 | Entity 1 | USJRF5 | 2020-01-28 | USLFA4 | 3 | EA | 3 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 250 | 1001763845 | SB2N,A193-B7,CTD,UNC,4.5in,5/8in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 70 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 10 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
60891772 | 508 | Hiller Deficiencies | S13 | Fire Protect | 2020-03-21 | 2020-02-13 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF332 | Portable Fire Extinguishers | 2019-08-17 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-03-21 | 118312000000 | 10 | 40 | 7000000108 | AMEREX 125LB Wheel Unit Refurb | 2020-03-04 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | STBD Laydown | 11831177 | 4 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STO19CG112 | USFDY0 |  | 2019-08-19 | USABCE | 1 | EA | 1 | Hiller Deficiiencies | REL PRT GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS2 | 30 | 7000004754 | 3/8" x 0.049 317L SMLS Coated Tubing | 2020-03-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11340898 | 29 | 4 | Non-Stock (Purchase Requisition) | N |  |  | WR551AEI86 | Name 2 | Name 2 | 2020-02-07 | USSOLE | 400 | FT | 0 | Field Order Sheets -E&I Field Material | ACAS PRC PREL | INIT | Approved
61074272 | 508 | Centralized HPU Motor A bad relay. | S19 | Marine Systems | 2020-04-22 | 2020-05-27 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.MA.PS.PBE-89021A | Turret Centralized HPU Pump 1/A | 2019-12-20 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-22 | 120397000000 | 10 | 10 | 7000005901 | 3RN1011-1CK00 MOTOR EVALUATION UNIT | 2020-04-22 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Stones | 12039690 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-12-20 | USAWJB | 1 | EA | 1 | Centralized HPU Motor A bad relay. | REL ESTC CSER GMPS PRC SETC | APPR MAGN WPOK ZPMM | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 340 | 7000002596 | J-Bolt, 3/4" x 3" Long (Sermaguard ) | 2020-06-01 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 34 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST05031901 | Entity 2 | Name 59 | 2019-05-04 | USSOLE | 5 | EA | 5 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
60675078 | 508 | O/SI PV Bulkhead Main Steam Stop Bypass | S17 | Steam/Hot H2O | 2020-04-25 | 2019-09-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.SW.115-332V | Isolation Valve Bypass Valve | 2019-12-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-25 | 115709000000 | 30 | 10 | 7000004211 | EP-GVB20X25KM, F-7421 FORGED STEELL GLOB | 2020-07-09 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11570945 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-02 | USNSB4 | 1 | EA | 0 | Job Lead, Replace 1" Globe Valve SW.115- | REL ESTC PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60970408 | 508 | CRN Boom Tip Platform Grating Deficiency | S06 | General | 2020-02-20 | 2020-03-26 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.GN.MI.HG | Handrails & Grating | 2019-10-01 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-21 | 119205000000 | 10 | 20 | 1001642069 | BAR FL,1/4in,1.1/2in | 2019-10-04 | Received at Target Location |  |  | 2020-02-13 | U182 | 8256 | Danos - Larose | SHF9-F21 | 11920544 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST09301902 | Name 4 | USMCS1 | 2019-10-01 | USSOLE | 20 | FT | 20 | CRN Boom Tip Platform Grating Deficiency | TECO CNF ESTC GMPS PRC SETC | XCNF EOM MAGN MANX WP XGI | TECO
61021343 | 508 | O/SI Passing Valve VABL-661044 on PST104 | S22 | Prod Gathering | 2020-02-15 | 2020-01-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.FM.VABL-661044 | Pressure Transmitter Isolation Valve | 2019-10-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-16 | 119797000000 | 10 | 30 | 7000002596 | 7/8” X 9 ½” Stud Bolts with 2 Heavy Hex | 2020-01-16 | Received at Target Location |  | 2020-02-11 | 2020-02-20 | U182 | 8270 | Danos - Amelia | VABL-661044 | 11979727 | 3 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A386 | Name 2 | Name 59 | 2020-01-28 | USSOLE | 12 | EA | 12 | Replace VABL-661044 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN RUSH WPOK XGI | TECO
60797150 | 508 | A/C Unit - Multiple Failures | S14 | HVAC | 2020-03-24 | 2019-08-09 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.HV.DAL-10842 | Normal TER Air Handling Unit | 2019-08-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-03-25 | 117216000000 | 10 | 10 | 7000000086 | TER Normal Operation AC Unit (TAG: ZZZ-1 | 2020-04-23 | Received at Worksite | 2020-01-16 |  |  | U182 | 8201 | Stones Main | Warehouse floor | 11721605 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-08-13 | USNSB4 | 1 | EA | 1 | LO/TO & Hot Work Permit | REL PCNF PRT GMPS PRC SETC | APPR EOM MAGN MAKD MAOK WPOK ZPVS | Kit Complete
60701397 | 508 | Leaking Globe/Check Valve on Hydrophore | S18 | Water Systems | 2020-04-11 | 2019-10-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.121-20V | Tank Outlet Check Valve | 2020-01-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-04-11 | 116003000000 | 20 | 30 | 7000004211 | 5/8-DXST, 5/8" X 3" (2-3/4" FTF) DOX PLT | 2020-04-11 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Never Received- Not need | 11600310 | 3 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-05-19 | USNSB4 | 8 | EA | 0 | Drain Hydrophore Tank | REL ESTC GMPS PPRT PRC SETC | APPR MAGN MANX WPOK ZPMM | EXEC
61218667 | 508 | Replace Lifeboat Rations & Water | S15 | Life Saving | 2020-12-10 | 2021-02-17 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.GU.LS.LB | Lifeboats | 2020-02-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-12-11 | 122061000000 | 10 | 70 | 7000004662 | Datrex Emergency Food Ration, 2400kcal | 2020-05-10 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | STONES | 12206109 | 7 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 |  | 2020-02-25 | USAWJB | 40 | EA | 0 | Replace Lifeboat Rations & Water | REL ESTC PRC SETC | APPR MAGN WPOK ZPMM | Approved
61021343 | 508 | O/SI Passing Valve VABL-661044 on PST104 | S22 | Prod Gathering | 2020-02-15 | 2020-01-31 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.PG.FM.VABL-661044 | Pressure Transmitter Isolation Valve | 2019-10-31 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 5 Complete by 8 Weeks | 2020-02-16 | 119797000000 | 10 | 10 | 7000002603 | Octagonal ASME B16.20 CL1500 RTJ TYPE R- | 2020-01-16 | Received at Target Location |  | 2020-02-11 | 2020-02-20 | U182 | 8270 | Danos - Amelia | VABL-661044 | 11979727 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A386 | Name 2 | Name 59 | 2020-01-28 | USSOLE | 4 | EA | 4 | Replace VABL-661044 | TECO CNF PRT GMPS PRC SETC | XCNF MAGN RUSH WPOK XGI | TECO
60695904 | 508 | on/off switch is missing | S13 | Fire Protect | 2020-04-01 | 2020-03-30 | O.US.STO.STO.005.724FP | 508ELEC | US.WR508A.GU.FP.BAT-33120A | Diesel Engine Starting Battery | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 7 Complete by 12 Mths | 2020-04-01 | 115942000000 | 10 | 20 | 7000005901 | ASLW20 ILLUMINATED SELECTOR SWITCH | 2020-04-01 | Received at Worksite |  |  |  | U182 | 8201 | Stones Main | Stones | 11594235 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2019-06-21 | USNSB4 | 10 | EA | 10 | Replace Missing On/Off Switch | REL ESTC GMPS PRC SETC | APPR EOM MAGN WPOK ZPMM | Approved
60717786 | 508 | #3 latching dog cylinder bolts are broke | S19 | Marine Systems | 2020-02-18 | 2020-01-31 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.MA.PS.ZZZ-87412B | Bell/Stinger Latching Mechanism | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-21 | 116191000000 | 10 | 20 | 7000003852 | Stanley Proto J9500B Proto 10-Piece Scre | 2020-02-18 | Received at Worksite |  | 2019-10-27 | 2020-02-07 | U182 | 8201 | Stones Main | Issued | 11619069 | 2 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 14 |  | 2019-05-20 | USMNF8 | 1 | EA | 1 | Gather tools and equipment | TECO PRT GMCO GMPS PRC SETC | XCNF MAGN MAOK NCMP WPOK XGI | TECO |  |  | PU Aaron 06/11/2019 CMR
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 140 | 7000002591 | 4548K176 1/2 NPT, 4" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60684133 | 508 | Vacuum Condenser Monorail | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-23 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-19 | 115812000000 | 10 | 360 | 7000002591 | 2" x 27' U-Hook Ratchet Strap (including | 2020-05-13 | Received at Target Location |  | 2019-12-17 |  | U182 | 8256 | Danos - Larose | SHF9-G14 | 11581210 | 36 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12091901 | Name 4 | Name 60 | 2019-12-09 | USSOLE | 2 | EA | 2 | Vacuum Condenser Monorail | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3460 | 1000710996 | FTG_PIPE,PLG,1/2",SS | 2019-10-23 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F33 | 11179936 | 376 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST10161901 | Name 4 | Name 4 | 2019-10-17 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 350 | 7000002596 | STUD BOLTS, 3/4" DIA. X 11" LONG, ASTM A | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 48 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 14 | EA | 14 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | FOS2 | 490 | 7000003197 | Brady Part No. M21-187-C-342 | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | 102673.011.03 | 11179936 | 841 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI82 | Name 2 | Name 2 | 2020-01-31 | USSOLE | 10 | EA | 10 | Field Order Sheets -E&I Field Material | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2190 | 7000003343 | HSS Tubing, TS 8 X 8 X 3/8, ASTM A500 | 2019-04-05 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 241 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST04011902 | Name 2 | Name 2 | 2019-04-01 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 4870 | 7000002629 | FLANGE, 12" 300 LB RFWN SCH 10S ASME B16 | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 548 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 10 | EA | 10 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 2690 | 7000002629 | FULL FACE BLEED RING, 8", 300#, RF, 1.5" | 2019-09-24 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 292 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST08271902 | Name 2 | Name 2 | 2019-08-28 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 7510 | 7000003515 | Chain, 3/16" Proof Coil, Galv. | 2020-02-18 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G59 | 11179936 | 1009 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 4 |  | 2020-02-15 | USSOLE | 20 | FT | 20 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60542134 | 508 | 2019 BBSM / Awards / Recognition | S01 | Platform | 2020-11-07 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-01-02 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2021-11-07 | 114197000000 | 10 | 140 | 7000003852 | DOSS SoundBox Touch Wireless Bluetooth V | 2020-11-27 | Received at Worksite |  | 2019-04-04 | 2020-02-29 | U182 | 8201 | Stones Main |  | 11419724 | 14 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STONES1111 |  |  | 2019-11-11 | USABCE | 1 | EA | 1 | 2019 BBSM / Awards / Recognition | TECO ESTC GMPS PRC SETC | XCNF STDG XGI | TECO |  |  | PU 11/27/19 J WELBOURN
60871421 | 508 | O/SI TEG Reboiler Stripping Gas PCV-001 | S39 | Gas Treating | 2020-03-10 | 2020-01-29 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.DE.PCV-77211-001 | TEG Reboiler Pressure Control Valve | 2019-09-23 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-03-10 | 118080000000 | 20 | 20 | 7000002646 | FISHER 1"300RF MR95H WCC STEEL BODY, 15- | 2019-12-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11807985 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-09-23 | USNSB4 | 1 | EA | 0 | Replace 1" Fisher Valve TEG Reboiler Str | REL ESTC PRC SETC | APPR EOM MAGN MANX WPOK ZPMM | Deleted
61134552 | 508 | Helideck foam monitor upgrade MOC 80280 | S13 | Fire Protect | 2020-05-27 | 2020-07-01 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.FP.PF331-12100 | FiFi Helideck Foam System | 2020-03-02 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-05-27 | 121087000000 | 10 | 10 | 7000002629 | Eccentric Reducer, 3" x 6", .095 x .134 | 2020-03-06 | Not Shipped |  |  |  | U182 | 8256 | Danos - Larose | SHF9-H04 | 12108694 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  | ST03022001 | Name 4 | Name 60 | 2020-03-03 | USSOLE | 2 | EA | 0 | Helideck foam monitor upgrade MOC 80280 | REL ESTC PRC SETC | APPR MAGN MANX WP | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 410 | 1001768461 | ELB BW,WPB,90DEG,LR,40,NPS1.1/2 | 2019-11-20 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 41 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06141901 | Name 2 | Name 59 | 2019-06-17 | USDKFB | 9 | EA | 9 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 150 | 1002316828 | GASW,CL300/600,316/316L,GPH,1.1/2in | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-272 MGC B 77121B | 11340898 | 60 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-02 | USSOLE | 1 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved
61118336 | 508 | 2020 Lube Oils / Grease - Topsides | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2020-01-08 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 90 | 7000003946 | 55 gal. drums of (Shell Corena S4 R46 oi | 2020-03-27 | Not Shipped |  | 2020-01-08 |  | U182 | 8201 | Stones Main | CPORT | 12090693 | 9 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOMEC0015 | Name 17 | JP832018 | 2020-03-02 | USLFA4 | 4 | DR | 0 | 2020 Lube Oils / Grease - Topsides | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 110 | 7000003852 | MSA 10110030 Front Housing with Integrat | 2021-03-01 | Received at Target Location |  | 2020-02-03 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 11 | 4 | Non-Stock (Purchase Requisition) | N |  |  | STOACR02BA | Name 18/Name 34 | USJRF5 | 2020-02-21 | USCDP7 | 3 | EA | 0 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
30300429 | P09 | 2019 TDR Improvements |  |  | 2020-02-26 |  | C.US.STO.FI.19.004.1230A |  |  |  | 2019-10-21 | NWO | U100 | NT01 | US01 | P16 | [6 empty] | 2020-04-30 | 115458000000 | FOS1 | 260 | 7000002629 | 1 1/2 ASME CL 150 THRD FLANGE B16.5 ASTM | 2019-10-25 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | TDR Improvements | 11545759 | 53 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A363 | Name 2 | Name 2 | 2019-10-21 | USSOLE | 2 | EA | 2 | Field Order Sheets -Mech. Field Material | ACAS MANC PRC PREL | INIT | Approved
60684130 | 508 | Crane Maintenance Platform | S19 | Marine Systems | 2020-06-01 |  | P.US.STO.NF.19.006.7240A | 508MECH | US.WR508A.MA.ST | Structure | 2019-05-09 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 3 Low | 2020-06-01 | 115812000000 | 10 | 420 | 1001768460 | ELB BW,WPB,90DEG,LR,80,NPS1.1/2 | 2019-11-20 | Received at Target Location |  | 2019-12-17 |  | U182 | 8270 | Danos - Amelia | SHF9-E05 | 11581207 | 42 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST06141901 | Name 2 | Name 59 | 2019-06-17 | USDKFB | 3 | EA | 3 | Stones Small Civil Projects | REL PCNF ESTC GMPS PRC SETC | EXEC | EXEC
61154995 | 508 | 2020 Stones YR General Maintenance Paint | S01 | Platform | 2020-12-31 |  | P.US.STO.NF.20.003.7240A | GENERIC | US.WR508A | Stones FPSO | 2020-01-16 | WO | U100 | GEN | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 121326000000 | 10 | 80 | 7000002591 | #16 Ga. Bailing Wire (Tie Wire) | 2020-02-04 | Received at Target Location |  | 2020-01-16 |  | U182 | 8201 | Stones Main | STONES | 12132576 | 8 | 4 | Non-Stock (Purchase Requisition) | N | X |  | DIISTO1927 | Entity 1 | USJRF5 | 2020-01-28 | USLFA4 | 2 | EA | 2 | 2020 YR General Maintenance Painting | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
61168078 | 508 | Elbow prior to flowmeter weeping | S18 | Water Systems | 2020-03-03 | 2021-01-17 | O.US.STO.STO.005.724FP | 508ERENG | US.WR508A.GU.WS.ZZZ-12203 | Sea Water Lift Hypochlorite Unit | 2020-01-25 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-03-04 | 121477000000 | 10 | 210 | 7000002591 | 4548K221 1 NPT, 1-1/2" Long | 2019-12-19 | Received at Worksite | 2020-02-06 | 2020-02-24 |  | U182 | 8201 | Stones Main | ST1A5B | 12147679 | 21 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOERT0102 | Name 5 | USHBE9 | 2020-01-27 | USLFA4 | 12 | EA | 12 | Elbow prior to flowmeter weeping | REL ESTC GMPS PRC SETC | EXEC MAGN MAKD WPOK | EXEC |  |  | PU 02/25/2020 GG
60079803 | 508 | O/SI XV-6636P-211 6P main suction | S21 | Oil Treating | 2020-03-30 | 2018-06-01 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.OT.SS.XV-6636P-211 | Crude Oil to/from COT 6 On/Off PS Valve | 2018-05-29 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 5 Complete by 8 Weeks | 2020-03-31 | 108902000000 | 310 | 10 | 7000000105 | REPAIR KIT 18" NAKAKITA VALVE (10K-450A, | 2020-03-30 | Received at Worksite |  | 2018-10-17 |  | U182 | 8201 | Stones Main | CR Request 9/25 | 10890165 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 | USNSB4 | 2018-05-29 | USNSB4 | 1 | EA | 1 | Replace Soft Goods XV-6636P-211 | REL ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MAOK WPOK | EXEC |  |  | PU Aaron 10/03/2018
60841320 | 508 | Relocate STBD CRN Slew Gearbox Drain | S40 | Cargo Handling | 2020-04-29 | 2020-07-06 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.GU.CH.ZZZ-87402 | Stbd Side Pedestal Crane | 2019-11-11 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 7 Complete by 12 Mths | 2020-04-29 | 117729000000 | 10 | 10 | 7000000103 | 1" Stainless Steel Ball Valve | 2020-04-29 | Received at Worksite | 2019-11-27 | 2020-01-29 | 2020-02-22 | U182 | 8201 | Stones Main | ST KB B3 | 11772908 | 1 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2019-10-29 | USCMFR | 5 | EA | 5 | Relocate Crane Slew Gearbox Drain | TECO ESTC GMCO GMPS PRC SETC | XCNF MAGN MAKD NCMP WPOK XGI ZPMM | TECO |  |  | ST1A1C 01/22/2020 CMR
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 1400 | 7000002629 | FLANGE, 3" 300, RFWN, SCH 10S, ASME B16. | 2018-12-28 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 156 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12181801 | Name 2 | Name 2 | 2018-12-19 | USSOLE | 3 | EA | 3 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 190 | 7000002629 | PLUG, 1/2", SC, HEX HEAD, ASTM A182 GR. | 2018-12-06 | Received at Target Location |  |  |  | U182 | 8270 | Danos - Amelia | SHF9-C56 | 11179936 | 32 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST12031801 | Name 2 | Name 2 | 2018-12-05 | USSOLE | 1 | EA | 1 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3970 | 1001622964 | (PCM-0.23) | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F49 | 11179936 | 447 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11041901 | Name 4 | Name 4 | 2019-11-04 | USSOLE | 160 | FT | 160 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 6660 | 7000002629 | Flange, 2", SW, 150#, FF, Min Wall .083, | 2020-02-14 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-G15 | 11179936 | 877 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST01312001 | Name 4 | Name 4 | 2020-02-01 | USSOLE | 32 | EA | 32 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 3940 | 1001723501 | WASHER,FLAT,F436,SERMAGAURD,1/2in | 2019-11-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F05 | 11179936 | 444 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11011902 | Name 4 | Name 4 | 2019-11-01 | USSOLE | 232 | EA | 232 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60216111 | 508 | SDTA/2021 BSDV-840 passing | S39 | Gas Treating | 2021-03-01 | 2018-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GT.GM.BSDV-77401-840 | Gas Export Pipeline Shutdown Valve | 2018-08-06 | WO | U100 | 72FC | US01 | P16 | 30305553 | WR508 | WR 508 Stones | A | SCE | 2 Complete by 1 Week | 2021-03-01 | 110578000000 | 10 | 70 | 7000002629 | 1" 1500# Blind with 1/2" NPT TAP, RTJ, ASM | 2021-03-01 | Received at Target Location |  |  |  | U182 | 8201 | Stones Main | Gas Riser Pressure Gauge | 11057838 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A176 | Entity 3 | USRRIG | 2018-08-06 | USSOLE | 1 | EA | 1 | BSDV-840 passing | REL ESTC CSER GMPS PRC SETC | APPR MAGN MANX | Approved
60812727 | 508 | Ballast pump #2 spool piece replacement. | S19 | Marine Systems | 2020-06-01 | 2019-12-21 | O.US.STO.STO.005.724FP | 508CNST | US.WR508A.MA.BB.PBE-11201B | Ballast Pump No. 2 | 2019-10-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-06-01 | 117396000000 | 10 | 300 | 7000002596 | 3/8" x 1" 316 SS Cap Bolt AND Nut | 2020-04-19 | Received at Target Location |  | 2019-12-03 |  | U182 | 8270 | Danos - Amelia | STONES | 11739629 | 30 | 4 | Non-Stock (Purchase Requisition) | N | X |  | SWR551A348 | Name 2 | Name 59 | 2019-09-25 | USSOLE | 12 | EA | 12 | Ballast pump #2 spool piece replacement. | REL PCNF ESTC GMPS PPRT PRC SETC | EXEC EOM MAGN MANX WPOK | EXEC
30289818 | 508 | Turritella Solids Handling Equipment |  |  | 2020-02-25 |  | C.US.STO.FI.18.012.1230A |  |  |  | 2020-01-17 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2020-01-01 | 111799000000 | SOS1 | 5030 | 7000002629 | REDUCER CONC, 4" X 2", SCH 40 X SCH 80, | 2019-12-06 | Received at Target Location |  |  |  | U182 | 8256 | Danos - Larose | SHF9-F73 | 11179936 | 564 | 4 | Non-Stock (Purchase Requisition) | N | X |  | ST11221904 | Name 4 | Name 4 | 2019-11-25 | USABCE | 8 | EA | 8 | Shop Order Sheets - Mech Mat. for Fab. | ACAS PCNF PRC PREL | INIT | Approved
60675080 | 508 | Cracked motor frame on Ejector pump #3 | S18 | Water Systems | 2020-12-24 | 2019-09-25 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PBE-12204C | No. 3 FW Generator Ejector Pump | 2019-12-27 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-12-24 | 115709000000 | 40 | 10 | 7000000037 | SONDEX-MP-80-80-220 SERIAL NO. SMP001408 | 2021-03-24 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11570947 | 1 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | USNSB4 | 2019-12-27 | USNSB4 | 1 | EA | 0 | Replace Cracked Motor Frame PBE-12204C | REL ESTC PRC SETC | APPR EOM RUSH WPOK ZPMM | Deleted
61006507 | 508 | PSV test kits | S21 | Oil Treating | 2020-02-11 | 2020-10-15 | O.US.STO.STO.005.724FP | 508COPER | US.WR508A.OT.SS.VE663-00000 | Cargo Oil Pump Systems | 2020-01-22 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 7 Complete by 12 Mths | 2020-02-17 | 119629000000 | 10 | 70 | 7000002603 | 10" 300# BLIND FLANGE | 2020-02-11 | Received at Worksite | 2020-01-22 | 2020-02-03 | 2020-02-25 | U182 | 8201 | Stones Main | WHS Floor | 11962883 | 7 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-14 | USMNF8 | 1 | EA | 1 | Install PSV Testt kits | TECO CNF PRT GMPS PRC SETC | XCNF MAGN MAKD MAOK WPOK XGI | TECO |  |  | ST1A3B 02/3/20 GG
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 240 | 7000000133 | Item # 00740069 (8MGT-1120-12 Gates Poly | 2020-02-22 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 24 | 4 | Non-Stock (Purchase Requisition) | N | X |  | STOMEC0009 | Name 17 | USHBE9 | 2020-02-03 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC |  |  | ST1A6C 02/18/2020 CMR
60557093 | 508 | O/SI Passing Valve VABL-661050 | S22 | Prod Gathering | 2020-02-15 | 2019-07-10 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.PG.FM.VABL-661050 | Test Fluids Manual Isolation Valve | 2019-10-14 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | B | Production Critical | 6 Complete by 6 Months | 2020-02-15 | 114365000000 | 20 | 40 | 7000004211 | SHELL PAINT | 2020-02-15 | Not Shipped |  | 2020-02-11 | 2020-02-20 | U182 | 8201 | Stones Main | ETA 8/10 | 11436470 | 4 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  |  | USNSB4 | 2019-05-29 | USNSB4 | 1 | EA | 0 | Confirm VABL-661050 Replacement | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MAOK RUSH WPOK XGI | TECO
61118370 | 508 | 2020 Tools | S01 | Platform | 2020-12-31 |  | O.US.STO.STO.005.71300 | GENERIC | US.WR508A | Stones FPSO | 2019-12-23 | WO | U100 | 71PO | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 3 Low | 2020-12-31 | 120907000000 | 10 | 330 | 7000002591 | 20mm ½” drive crowfoot socket Part numbe | 2020-03-01 | Received at Worksite |  | 2020-01-14 |  | U182 | 8201 | Stones Main | STONES | 12090727 | 33 | 4 | Non-Stock (Purchase Requisition) | N | X |  | TO20CG0140 | Name 16 | USRRIG | 2020-02-04 | USLFA4 | 1 | EA | 1 | 2020 Tools | REL ESTC GMPS PRC SETC | EXEC STDG | EXEC
60937059 | 508 | Seawater Coarse Filter dP Gauge | S18 | Water Systems | 2020-02-04 | 2020-03-09 | O.US.STO.STO.005.724FP | 508ACR | US.WR508A.GU.WS.PDT-12202A-911 | Filter Pressure Differential Transmitter | 2020-02-08 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | C | Non Critical | 6 Complete by 6 Months | 2020-02-07 | 118823000000 | 10 | 60 | 1000709357 | PLUG,PIPE,THREADED,1/2in,SS-8-P,SWAGELOK | 2019-11-19 | Received at Target Location |  |  | 2020-02-14 | U182 | 8270 | Danos - Amelia | Onsite Danos Has | 11882270 | 6 | 4 | Non-Stock (Purchase Requisition) | N | X |  | WR551AEI66 | Name 15 | Name 58 | 2019-11-06 | USABCE | 2 | EA | 2 | LOTO System | TECO CNF PRT GMPS PRC SETC | XCNF EOM MAGN MANX RUSH WPOK XGI | TECO
60847990 | 508 | MOC GTG2 Vent Fans CT Addition | S03 | Elect. Systems | 2020-03-17 | 2020-01-12 | O.US.STO.STO.005.724FP | 508CI&E | US.WR508A.ES.PG.TS111-14000 | Gen #2 Gas Turbine Enclosure System | 2020-01-15 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 6 Complete by 6 Months | 2020-03-20 | 117810000000 | 10 | 20 | 7000003197 | HWKE DIRECT ITEM, HAWKE 121/A/M20 HAWKE | 2020-03-17 | Not Shipped |  |  |  | U182 | 8201 | Stones Main | Stones | 11780965 | 2 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 3 | Name 58 | 2019-10-29 | USNSB4 | 4 | EA | 0 | SAEP LO/TO Isolate GTG #2 MOC-71695 | REL ESTC PRC SETC | APPR EOM MAGN WP ZPMM | Deleted
61175050 | 508 | GT4 Clutch Not Disengaging | S03 | Elect. Systems | 2020-02-18 | 2020-03-23 | O.US.STO.STO.005.724FP | 508MECH | US.WR508A.ES.PG.ZAE-11140 | Power Generation Package 4 Turbine | 2020-01-28 | WO | U100 | 72FC | US01 | P16 |  | WR508 | WR 508 Stones | A | SCE | 5 Complete by 8 Weeks | 2020-02-18 | 121557000000 | 10 | 40 | 7000003739 | 909103C1 SPACER,GEARBOX,CLUTCH | 2020-01-19 | Received at Worksite |  | 2020-02-16 | 2020-02-26 | U182 | 8201 | Stones Main | ST KB B2 | 12155706 | 5 | 4 | Non-Stock (Purchase Requisition) | N | X |  |  | Name 3 |  | 2020-01-28 | USAWJB | 1 | EA | 1 | Replace GT#4 Starter Adaptor | TECO CNF ESTC GMPS PPRT PRC SETC | XCNF MAGN WPOK XGI ZPMM | TECO |  |  | PU 02/16/20 AMW
30294248 | 508 | Turritella MGC Scrubber Replacement |  |  | 2020-02-09 |  | C.US.STO.FI.18.014.1230A |  |  |  | 2020-01-07 | NWO | U182 | NT01 | US01 | P16 | [6 empty] | 2019-10-02 | 113409000000 | FOS1 | 500 | 1002058431 | NUT,A563-DH,HEXAGONAL,UNC,1/2,SERMAGARD | 2020-03-13 | Not Shipped |  |  |  | U182 | 8270 | Danos - Amelia | WP-265 MGC B | 11340898 | 95 | 4 | Non-Stock (Purchase Requisition) | N |  |  |  | Name 2 |  | 2020-03-03 | USSOLE | 8 | EA | 0 | Field Order Sheets -Mech. Field Material | ACAS PRC PREL | INIT | Approved